## CriticalPath (2)
Id | Parent | Type | Summary | Planned For | Status | Story Points (numeric) | Blocks
1024146 |  | Story | Develop DSN GW Obs Test, Verification, and Validation Artifacts [16.4] | PI 16 | New | 5
1024145 |  | Story | Develop DSN GW Obs Test, Verification, and Validation Artifacts [16.3] | PI 16 | New | 5
1024144 |  | Story | Develop DSN GW Obs Test, Verification, and Validation Artifacts [16.2] | Unassigned | New | 2
1024116 | #1024104 | Story | WinOBS: 2-FA Capability Design Document Development (part 4) | PI 17 | New | 8
1024115 | #1024104 | Story | WinOBS: 2-FA Capability Design Document Development (part 3) | PI 17 | New | 20 | #1024116
1024114 | #1024104 | Story | WinOBS: 2-FA Capability Design Document Development (part 2) | PI 17 | New | 40 | #1024115
1024113 | #1024104 | Story | WinOBS: 2-FA Capability Design Document Development (part 1) | PI 16 | New | 40 | #1024114
1024105 |  | Feature | Lab - Maintain Labs for Integration, Testing and Test Events with minimal down time (PI-17) | PI 17 | Draft
1024098 | #1023615 | Story | Mobility Study Systems Support | EA 16.2 | New | 1
1024096 | #1023615 | Story | Mobility Study Systems Support | EA 16.2 | New | 3
1024095 | #1023615 | Story | Mobility Study Systems Support | EA 16.1 | New | 3
1024094 | #1023615 | Story | Mobility Study Systems Support | EA 16.1 | New | 1
1024092 | #1023615 | Story | Mobility Study Lab Support | EA 16.1 | New | 1
1024091 | #1023615 | Story | Mobility Study Lab Support | EA 16.2 | New | 1
1024089 | #1023615 | Story | Mobility Study WF SME Support | EA 16.2 | New | 1
1024088 | #1023615 | Story | Mobility Study WF SME Support | EA 16.1 | New | 1
1024084 | #383165 | Task | Feature 383165 PDO Release of IDP (red lines Hardware drawings submitted(red lines Hardware drawings submitted), needed 120 days prior to FRCB; | PI 16 | New
1024083 | #383165 | Story | Feature 383165 Update and Release IDP (red lines Hardware drawings submitted(red lines Hardware drawings submitted), needed 120 days prior to FRCB; | PI 16 | New | 2 | #1024084
1024066 |  | Problem | Need to determine what events trigger a move to the next cell on a MAMA 2 Response list. | Unassigned | Triage
1024052 | #1018285 | Story | Feature 1018285: fix problem 329774: IETM: Update CRL instructions to clarify how to copy files | PI 16 | New | 1
1024051 | #1008506 | Problem | Fix Problem 1010043: IETM Style Guide update for "Splunk Enterprise - Account Administration - Normal Operation Procedure" | PI 16 | Triage
1024050 | #1008506 | Story | Fix Problem 1010039: IETM Style Guide update for "Accounting Management Troubleshooting - Normal Operation Procedure" | PI 16 | New | 2
1024046 |  | Problem | GOVT: WF hangs after SIB read timeout and OOS not triggered | Unassigned | Triage
1024045 |  | Problem | Govt: WF is not functional after exiting EMCON | Unassigned | Triage
1024044 |  | Problem | GOVT: Deactivating service during pre-emption results in state machine failure | Unassigned | Triage
1024043 |  | Problem | GOVT: pTMSI not saved to LKS (MIL-STD_01_003 Transmit Unique ID ) | Unassigned | Triage
1024040 |  | Problem | GOVT: WF stuck during Exit EMCON, Teardown takes > 4 min | Unassigned | Triage
1024037 |  | Problem | GOVT: WF does not download the first SAFP when several selected. | Unassigned | Triage
1024035 |  | Problem | GOVT: WF fails group join, WF recovers after Authentication failure | Unassigned | Triage
1024034 |  | Problem | GOVT: WF Fails to complete mobility when serving cell is locked | Unassigned | Triage
1024033 |  | Problem | GOVT: Failure to enter EMCON after k key compromise | Unassigned | Triage
1024031 |  | Problem | GOVT: WF not responsive when bad SAFP selected when in EMCON | Unassigned | Triage
1024028 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of SOW for RINCON | EA 15.4 | Done
1024027 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of SOW for AMS | EA 15.4 | Done
1024020 | #1020704 | Story | Feature 1020704: Support TO9 Vendors (AMS & RINCON) | EA 16.4 | New | 5
1024018 | #1020704 | Story | Feature 1020704: Support TO9 Vendors (AMS & RINCON) | EA 16.3 | New | 5
1024017 | #1020704 | Story | Feature 1020704: Support TO9 Vendors (AMS & RINCON) | EA 16.2 | New | 5
1024013 |  | Problem | GOVT: SIP:200 (OK) Gracefully | Unassigned | Triage
1024008 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V012 ET ASSEMBLY, Parts List | EA 15.5 | New
1024007 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V011 ET ASSEMBLY, Parts List | EA 15.5 | New
1024006 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V010 ET ASSEMBLY, Parts List | EA 15.5 | New
1024005 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V009 ET ASSEMBLY, Parts List | EA 15.5 | New
1024004 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V008 ET ASSEMBLY, Parts List | EA 15.5 | New
1024003 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V007 ET ASSEMBLY, Parts List | EA 15.5 | New
1024002 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V006 ET ASSEMBLY, Parts List | EA 15.5 | New
1024001 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V005 ET ASSEMBLY, Parts List | EA 15.5 | New
1024000 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V004 ET ASSEMBLY, Parts List | EA 15.5 | New
1023999 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V003 ET ASSEMBLY, Parts List | EA 15.5 | New
1023998 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V002 ET ASSEMBLY, Parts List | EA 15.5 | New
1023997 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V001 ET ASSEMBLY, Parts List | EA 15.5 | New
1023996 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P58844V ET ASSEMBLY Document | EA 15.5 | New
1023994 | #1023618 | Story | TO-6 Feasibility of Load Balancer - Cisco ITD Engineering Study | PI 16 | New | 3
1023993 | #1023618 | Story | TO-6 Feasibility of Load Balancer - Cisco ITD Engineering Study | PI 16 | New | 5
1023963 | #379001 | Task | Re-apply Problem 370782 Task for Deployment : Add additional SCS telemetry values to Splunk index | Unassigned | New
1023962 | #311386 | Story | Rebase and Test Problem 370782 Story : Add additional SCS telemetry values to Splunk index | Unassigned | New | 2
1023956 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: PDR | EA 16.5 | New | 1
1023952 | #1021037 | Task | Feature 1021037 EAD-18: PDO release for GGSN or GIS (depending on which device we made the updates) | EA 16.5 | New
1023950 | #1021037 | Story | Feature 1021037 EAD-18: Demo | EA 16.5 | New | 1
1023949 | #1021037 | Story | Feature 1021037 EAD-18: update and prepare to close PWIs associated with this feature | EA 16.5 | New | 1
1023948 | #1021037 | Story | Feature 1021037 EAD-18: complete review and build of GGSN or GIS | EA 16.4 | New | 2
1023947 | #1021037 | Story | Feature 1021037 EAD-18: complete clearcase edits to the GGSN or GIS | EA 16.3 | New | 3
1023946 | #1021037 | Story | Feature 1021037 EAD-18: STCD development | EA 16.3 | New | 2
1023945 | #1023752 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.5 | New | 2
1023943 | #1023752 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.4 | New | 2
1023938 | #1023752 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support (PI 17) | PI 17 | New | 5
1023935 |  | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (16.5) | EA 16.5 | New | 2
1023930 |  | Problem | EAD-15 Deployment: Redlines for SQL Server Instructions | Unassigned | Triage
1023927 | #1021037 | Task | Feature 1021037 EAD-18: Decision point | EA 16.3 | New
1023925 | #1021037 | Story | Feature 1021037 EAD-18: Capture statistics for OSPF SPF calculations on whiassir1/2 after hard coding the APNs or turning parameters | EA 16.3 | New | 2
1023923 | #1021037 | Story | Feature 1021037 EAD-18: Support Radio testing in VLAB to validate calls still work after hard coding APN in network | EA 16.2 | New | 0
1023922 | #1021037 | Story | Feature 1021037 EAD-18: Radio testing in VLAB to validate calls still work after hard coding APN in network | EA 16.2 | New | 1
1023921 | #1021037 | Story | Feature 1021037 EAD-18: Test hard coding APN networks or tuning parameters in the GGSN or RAF IR routers | EA 16.2 | New | 2
1023920 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support (PI 17) | PI 17 | New | 40
1023919 | #1021037 | Story | Feature 1021037 EAD-18: Determine most optimal and possible place to hard code the APNs or OSPF tuning parameters without affecting redundancy or route behavior | PI 16 - Candidate | New | 3
1023918 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.5 | New | 5
1023917 | #1021037 | Story | Feature 1021037 EAD-18: capture statistics for OSPF SPF calculations on whiassir1/2 before statically coding APNs | PI 16 - Candidate | New | 1
1023916 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.5 | New | 2
1023915 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.4 | New | 3
1023914 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.5 | New | 8
1023910 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: WWTS WF SME Support | EA 16.5 | New | 1
1023905 | #1022300 | Story | Feature 1022300: Need test support for making DSN calls | PI 16 | New | 2
1023904 | #1022300 | Story | Feature 1022300: Support the transition of moving the signaling from the Spectra2 to the REDCOM. | EA 16.3 | New | 3
1023903 | #1022300 | Story | Feature 1022300: Need full feature support, from start to finish, to help determine the plan, lab mapping and impacts; configurations of the DSN GW, Spectra2, and REDCOM; implementation; testing; knowledge sharing | PI 16 | New | 8
1023902 | #1022300 | Story | Feature 1022300: Need full feature support, from start to finish, to help determine the plan, lab mapping and impacts; configurations of the DSN GW, Spectra2, and REDCOM; implementation; testing; knowledge sharing. | PI 16 | New | 13
1023901 | #1022300 | Story | Feature 1022300: Need feature support to collaborate on how to configure and test REDCOM to support signalling channels. | EA 16.2 | New | 3
1023900 | #1022300 | Story | Feature 1022300: Need early feature support to help understand existing REDCOM configuration and Spectra2 configuration | EA 16.1 | New | 1
1023899 | #1022300 | Story | Feature 1022300: Need early feature support to determine any changes in lab DSN GW configuration | EA 16.1 | New | 1
1023898 | #1022300 | Story | Feature 1022300: need to connect those T1s into the REDCOM. And have the lab mapping changed. | EA 16.3 | New | 1
1023897 | #1022300 | Story | Feature 1022300: Need to know how the T1 cables map/route from the DSN GW in H1125N to the Spectra2 and to REDCOM in H1125B . | EA 16.1 | New | 1
1023896 | #1020703 | Story | Feature 1020703: ETISP FPGA for ULX - Design and test development | PI 16 | New | 8
1023887 | #1022398 | Task | Feature 1022398: Procurement Verification and Approvals for PPA Implement Web Frameword | PI 16 | New
1023883 | #1020704 | Story | Support Venders | PI 17 | New | 20
1023882 | #1020704 | Story | Feature 1020704: Support TO9 Vendors (AMS & RINCON) | EA 16.1 | New | 5
1023866 | #1023839 | Story | Develop Capability Specification for Replacement ERS (2) | PI 16 | New | 8
1023865 | #1023839 | Story | Develop Capability Specification for Replacement ERS (1) | PI 16 | New | 20
1023864 | #1023839 | Story | Support Capability Specification for Replacement ERS | PI 16 | New | 3
1023863 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (Appendix - Preprocessor ICD) | EA 15.4 | Done
1023862 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (Appendix - RF Processor ICD) | EA 15.4 | Done
1023861 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (Appendix - ULX Manager) | EA 15.4 | Done
1023860 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (Appendix - Channel Processor) | EA 15.4 | Done
1023859 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (Appendix - Monitor & Control) | EA 15.4 | Done
1023858 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (RVM) | EA 15.4 | Done
1023855 | #1014595 | Task | Feature 1014595: ULX DD - CM Delivery of CDRL54 Design Specification (CDD) | EA 15.4 | Done
1023853 | #1022146 | Story | KPI and Metrics - Analyze and report on KPIs and metrics defined in PI 13 - PI 15 | PI 16 | New | 5
1023852 | #1022146 | Story | KPI and Metrics - Implement KPI and metrics and associated changes defined in PI 15 | PI 16 | New | 8
1023851 | #1022146 | Story | KPI and Metrics - Definition of KPIs and metrics | PI 16 | New | 5
1023850 | #1023794 | Story | Cyber Support Develop Capability Design Document | PI 17 | New | 8
1023849 | #1023794 | Story | Cyber Support Develop Capability Design Document | PI 16 | New | 5
1023848 | #1023794 | Story | Develop Capability Design Document | PI 17 | New | 40
1023847 | #1023794 | Story | Develop Capability Design Document | PI 16 | New | 40
1023845 |  | Story | Feature 1013961: Develop ETISP Capabilities Specification (40 pts, 2nd) | Unassigned | Invalid | 0
1023844 |  | Story | Feature 1013961: Develop ETISP Capabilities Specification (2) | Unassigned | Invalid | 0
1023843 | #1013961 | Story | Feature 1013961: Develop ETISP Capabilities Specification (2) | Unassigned | New | 13
1023841 |  | Feature | TO-5: Develop Capability Design Document for Replacement ERS | PI 17 | Draft
1023840 |  | Problem | RNC - MGB not handle situation when eic is down | Unassigned | Triage
1023839 |  | Feature | TO-5: Develop Capability Specification for Replacement ERS | PI 16 - Candidate | Analyzing
1023835 | #1022398 | Task | Feature 1022398: Hardware/Software Procurement Request for PPA Implement Web Framework | PI 16 | New
1023834 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New
1023833 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New | 2
1023832 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New | 2
1023824 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New
1023823 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New | 2
1023810 |  | Task | Feature XXXXX: Submit PDO for 99-P61628A – Engineering Management Plan (EMP) | PI 16 | Done
1023809 | #1023808 | Feature | TO-5: Support Vendor Development, Test, and Reviews | Unassigned | Analyzing
1023805 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | New
1023792 | #1023806 | Feature | TO-5: Design Redundant ERS (Capability Specification and Capability Design Document) | Unassigned | Analyzing
1023791 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - SCB3 (ROJ 119 2108/4) | EA 15.4 | Done | 1
1023762 | #1014162 | Story | Feature 1014162: Cyber Support ETISP Vender Requirements and Specification | EA 16.4 | New | 1
1023761 | #1014162 | Story | Feature 1014162: Cyber Support ETISP Vender Requirements and Specification | EA 16.3 | New | 1
1023760 | #1014162 | Story | Feature 1014162: Cyber Support ETISP Vender Requirements and Specification | EA 16.2 | New | 1
1023756 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.3 | New | 2
1023755 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.2 | New | 3
1023754 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.1 | New | 2
1023750 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.4 | New | 5
1023749 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.4 | New | 5
1023748 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.3 | New | 5
1023747 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.3 | New | 5
1023746 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.2 | New | 5
1023745 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.2 | New | 5
1023744 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.1 | New | 5
1023743 | #1020703 | Story | Feature 1020703: ETISP FPGA for ULX - Verification in MUOS VLAB | EA 16.4 | New | 8
1023742 | #1020703 | Story | Feature 1020703: ETISP FPGA for ULX - Verification in MUOS VLAB | EA 16.3 | New | 5
1023741 | #1020703 | Story | Feature 1020703: ETISP FPGA for ULX - Implement and Unit Test FPGA | EA 16.2 | New | 13
1023740 | #1020703 | Story | Feature 1020703: ETISP FPGA for ULX - Prototype Design (1) | EA 16.1 | New | 13
1023733 | #1020702 | Story | Feature 1020702: ULX MGR- Develop ULX Manager UI & L2/L3 Tests | EA 16.4 | New | 8
1023732 | #1020702 | Story | Feature 1020702: ULX MGR- Develop ULX Manager UI & L2/L3 Tests | EA 16.3 | New | 8
1023731 | #1020702 | Story | Feature 1020702: ULX MGR- Develop ULX Manager UI & L2/L3 Tests | EA 16.2 | New | 8
1023730 | #1020701 | Story | Feature 1020701: ULX MC - Develop Monitor & Control Framework & Services | EA 16.4 | New | 8
1023729 | #1020701 | Story | Feature 1020701: ULX MC - Develop Monitor & Control Framework & Services | EA 16.3 | New | 8
1023728 | #1020701 | Story | Feature 1020701: ULX MC - Develop Monitor & Control Framework & Services | EA 16.2 | New | 8
1023727 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.4 | New | 8
1023726 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.4 | New | 5
1023725 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.3 | New | 8
1023724 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.3 | New | 8
1023723 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.2 | New | 5
1023722 | #1020700 | Story | Feature 1020700: ULX CP - Develop Full Implementation of CP uServices for ULX | EA 16.2 | New | 5
1023721 | #1020700 | Story | Feature 1020700 ULX CP - MBSE Support | EA 16.4 | New | 2
1023720 | #1020700 | Story | Feature 1020700 ULX CP - MBSE Support | EA 16.3 | New | 2
1023719 | #1020700 | Story | Feature 1020700 ULX CP - MBSE Support | EA 16.2 | New | 3
1023699 | #272509 | Story | Determine IETM impacts for PPA UI Cleanup | PI 16 | New | 1
1023698 | #272509 | Story | Review/Validate PPA UI Cleanup with Stakeholders & Users | PI 16 | New | 1
1023696 | #272509 | Story | Create Mockups for PPA Views, Reports, & Screens negatively impacted by the lack of CDRs/PM/FM data | PI 16 | New | 2
1023693 | #272509 | Story | Create Updated Information Architecture for PPA UI Cleanup | PI 16 | New | 2
1023686 |  | Problem | SGSN Operational Verification Missing Additional Verification Commands | Unassigned | Triage
1023685 | #332951 | Story | Feature 332951: IETM Cross Training for RBS Alarm Recovery Procedures (15.4) | EA 15.4 | Implementing | 1
1023683 | #1019513 | Story | Feature 1019513: Create Terminal Profiles for PRC-155 / WDE | PI 16 | New | 3
1023682 | #1019513 | Story | Feature 1019513: Integration test updated WF code | PI 16 | New | 13
1023666 |  | Problem | PM__1000 Alarm Recovery did not resolve Failure | Unassigned | Triage
1023663 | #1022870 | Story | TO-10 IA: Support NSA Discussions (PI16) | PI 16 - Candidate | New | 20
1023662 |  | Problem | RNC MAMA processing: does not exclude all cells that not provisioned for a group when the cell's beam has provisioned cells | Unassigned | Triage
1023661 | #1019513 | Story | Feature 1019513: Perform OTA-FT when the WF when the last known state flag is set to true | PI 16 | New | 20
1023660 | #1019513 | Story | Feature 1019513: Modify WF to always include all objects in the terminal profile in OTA-FT Request | PI 16 | New | 8
1023659 | #1019513 | Story | Feature 1019513: Design approach and document in SDD | PI 16 | New | 5
1023658 | #297335 | Story | RDE BuildForge - Fix External Delivery | EA 16.4 | New | 3
1023656 | #297335 | Story | RDE BuildForge - Fix Release Verification & Packaging | EA 15.4 | Implementing | 3
1023655 | #297335 | Story | RDE BuildForge - Fix UE & Cell | EA 16.4 | New | 3
1023653 | #297335 | Story | RDE BuildForge - Fix RNC Compiles Part 2 (12 modules) | EA 16.3 | New | 2
1023652 | #297335 | Story | RDE BuildForge - Fix RNC Compiles Part 1 (12 modules) | EA 16.3 | New | 2
1023650 | #297335 | Story | RDE BuildForge - Fix Cross Project Rebase | EA 16.2 | New | 3
1023649 | #297335 | Story | RDE BuildForge - Fix Cross Project Deliver | EA 16.1 | New | 3
1023647 |  | Problem | GGSN Health Check Procedure Redlines from I-Level 5/20 | Unassigned | Triage
1023646 | #1022872 | Story | WDE Development PI 16 (Part 2) | PI 16 | New | 13
1023624 | #1015005 | Story | Develop Capability Design Doc for ActiveMQ Replacement | EA 16.4 | New | 2
1023621 | #1015005 | Story | Develop Capability Design Doc for ActiveMQ Replacement | EA 16.4 | New | 5
1023620 | #1013279 | Feature | TO-6 NMF Software Engineering Study | PI 17 - Candidate | Ready for PO Sync Approval
1023618 | #1013279 | Feature | TO-6 Feasibility of Load Balancer - Cisco ITD Engineering Study | PI 16 - Candidate | Approved
1023617 | #1013279 | Feature | TO-6 System Service Life Extension Engineering Study | PI 16 - Candidate | Approved
1023615 | #1013279 | Feature | TO-6 Mobility Engineering Study | PI 16 - Candidate | Approved
1023604 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 16.2 | EA 16.2 | New | 5
1023603 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 16.1 | EA 16.1 | New | 5
1023602 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 16.2 | EA 16.2 | New | 3
1023601 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 16.1 | EA 16.1 | New | 3
1023572 | #1013452 | Task | Feature 1013452: Submit PDO for 99-P57050M – NMS – NM – PKI | PI 16 | New
1023567 | #1022616 | Story | Feature 1022616: Implement 'Chain of Command' move Node | PI 16 - Candidate | Invalid | 0
1023565 | #1022616 | Story | Feature 1022616: Implement 'Chain of Command' view/edit page and operations | PI 16 - Candidate | New | 5
1023563 |  | Problem | During overnight NMS Automation load runs, PPA becomes not responsive. Pages take minutes to load (if it loads at all). This propblem is also being encountered by testers using PPA in the lab. This issue is not unique to automation. | Unassigned | Triage
1023562 | #376446 | Story | Feature 376446: MultiHAL Support | EA 15.4 | New | 3
1023561 | #1002381 | Story | Feature 1002381: Update SOVT from review | EA 15.4 | Implementing | 2
1023560 | #380808 | Story | Feature 380808: Incorporate review comments in 99-P59435M_NM_HW_SW_Mapping.doc for Nutanix Hardware | EA 15.4 | Ready for Acceptance | 2
1023557 | #380808 | Story | Feature 380808: Complete CoCo Review & build RHEL SVD | EA 15.5 | New | 5
1023555 | #380808 | Story | Feature 380808: Tectia PCR verification | EA 15.5 | New | 2
1023554 | #380808 | Story | Feature 380808: (IA) IA evaluation of Cisco Switch & give feedback to developer | EA 15.4 | Implementing | 3
1023553 |  | Problem | RNC board 18 core dumps | Unassigned | Triage
1023552 | #380808 | Story | Feature 380808: (IA) IA evaluation of RHEL 7.8 image & give feedback to developer | EA 15.4 | Implementing | 2
1023550 | #385442 | Story | Feature 385442:Capabilities Specification Documentation - Support Internal Peer Review document | EA 15.4 | New | 2
1023544 | #1015565 | Story | Developer support for IETM Updates | PI 16 | New | 40
1023540 | #1007900 | Story | Feature 1007900: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 2
1023539 | #1015565 | Story | UX/ILS Support for RBS Alarm Recovery Procedures | PI 16 | New | 20
1023538 | #1015565 | Story | Lab Support of RBS IETM Updates | PI 16 | New | 5
1023535 | #1007900 | Story | Feature 1007900: Continued Developer Support of STCD Testing of SVD and IETM procedures | EA 16.1 | New | 5
1023533 | #1007900 | Story | Feature 1007900: Developer Support Prep For Demo – Customer Demo Event | PI 16 | New | 5
1023532 | #1007900 | Story | Feature 1007900: Continued STCD Testing of SVD and IETM procedures | EA 16.1 | New | 8
1023524 | #1004171 | Story | Feature 1004171: Perform IA Posture Assessment | EA 15.4 | New | 2
1023523 | #216662 | Feature | OBS DSN Gateway Test and SBC Configuration Artifacts | PI 16 | Analyzing
1023521 | #1023518 | Feature | OBS- HAIPE D Upgrades | PI 16 | Analyzing
1023517 |  | Feature | OBS- Windows OS: Database Servers Upgrade (MS SQL) Capability Spec | Unassigned | Rejected
1023514 | #1023515 | Feature | WinOBS: KMS Capability Design Specification | PI 16 | Ready for PO Sync Approval
1023512 | #1019754 | Story | Feature 1019754: Analyze IBTEV3 (INTERFACE BOARD 4XT1/E1 VERSION 3), PN = ROJ 208 132/1, SN = A063602280 for SR 1125477 / G3256. | PI 16 | New | 1
1023511 | #1019754 | Story | Feature 1019754: Analyze IBTEV3 (INTERFACE BOARD 4XT1/E1 VERSION 3), PN = ROJ 208 132/1, SN = A063602281 for SR 1125478 / G3255. | PI 16 | New | 1
1023510 | #1019754 | Story | Feature 1019754: Analyze IBTEV3 (INTERFACE BOARD 4XT1/E1 VERSION 3), PN = ROJ 208 132/1, SN = A063602282 for SR 1125476 / G3254 | PI 16 | New | 1
1023509 | #1019754 | Story | Feature 1019754: Analyze IBS7V3 (INTERFACE BOARD SS7 VERSION 3), PN = ROJ 208 132/9, SN = A063481058 for SR 1125475 / G3253 | PI 16 | New | 1
1023508 | #1019754 | Story | Feature 1019754: Analyze IBASV3B (INTERFACE BOARD ATM SMF VERSION 3B), PN = ROJ 208 132/10 , SN = A063602918 for SR 1125474 / G3252. | PI 16 | New | 1
1023507 | #1023503 | Feature | OBS- Transec Controller (MTC) | PI 16 | Analyzing
1023506 | #1019754 | Story | Feature 1019754: Analyze IBASV3B (INTERFACE BOARD ATM SMF VERSION 3B), PN = ROJ 208 132/10 , SN = A063602910 for SR 1125472 / G3251. | PI 16 | New | 1
1023505 | #1019754 | Story | Feature 1019754: Analyze IBASV3B (INTERFACE BOARD ATM SMF VERSION 3B), PN = ROJ 208 132/10, SN = A063602920 for SR 1125469 / G3250 | PI 16 | New | 1
1023504 | #1019754 | Story | Feature 1019754: Analyze IBASV3B (INTERFACE BOARD ATM SMF VERSION 3B), PN = ROJ 208 132/10, SN = A063602909 for SR 1125473 / G3249 | PI 16 | New | 1
1023502 | #1019754 | Story | Feature 1019754: Analyze IBASV3B (INTERFACE BOARD ATM SMF VERSION 3B), PN = ROJ 208 132/10, SN = A063602911 for SR 1125471 / G3248. | PI 16 | New | 1
1023501 | #1019754 | Story | Feature 1019754: Evaluation and Testing of 1536_ MHZ_ CLOCK_ DISTRIBUTION_ CARD, PN = WS/CSYNC-0/0, SN = 1000056 | PI 16 | New | 2
1023499 | #1023462 | Feature | OBS: Anti Jam Modem- Establish Plan, Subcontract and Migration Approach | PI 16 | Analyzing
1023488 | #245573 | Feature | WF PWI Burn down (PI 16) | PI 16 - Candidate | Approved
1023486 | #1022872 | Story | WDE Development PI 17 | PI 17 | New | 40
1023484 | #1022872 | Story | WDE Development PI 16 | PI 16 | New | 40
1023478 | #1008506 | Story | Feature 1008506: Dry run troubleshooting procedure 4- Recover from DB Connect going down | EA 15.4 | New | 1
1023473 | #354871 | Story | Feature 354871: Deployment Notes and Operator Impacts for OA Workstation Related to EAD 17 | EA 15.4 | Implementing | 1
1023463 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (15.4) | EA 15.4 | Implementing | 1
1023461 | #1009453 | Story | Feature 1009453: Reproduce B2U Power Spike for Log Analysis - Chad | EA 15.4 | New | 2
1023460 | #1009453 | Story | Feature 1009453: Reproduce B2U Power Spike for Log Analysis - Sang | EA 15.4 | New | 3
1023459 | #1006376 | Story | Feature 1006376: Complete test execution | EA 15.4 | New | 3
1023458 | #1004171 | Story | Feature 1004171: Complete the execution of the STCD against the RNC build for final verification | EA 15.4 | New | 3
1023455 | #1013452 | Story | Feature 1013452: Support update of SIPRNet workstation for Ephemeris (for Windows) | EA 15.4 | Done | 1
1023454 | #387446 | Story | Mobility Call Flow Updates | EA 15.3 | Done | 1
1023453 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.3 | Done | 1
1023452 | #388053 | Story | Design PPA Replacement | EA 15.4 | Implementing | 1
1023451 | #1013452 | Story | Feature 1013452: Test SIPRNet workstation for Ephemeris (for Windows) | EA 15.4 | Done | 2
1023450 | #1004171 | Story | Feature 1004171: SME support of EAD15 installation of RNC with Group traces | EA 15.4 | New | 1
1023447 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.5 | EA 16.5 | New | 1
1023446 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.4 | EA 16.4 | New | 1
1023445 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.3 | EA 16.3 | New | 1
1023444 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.2 | EA 16.2 | New | 1
1023443 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.1 | EA 16.1 | New | 1
1023441 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.5 | EA 16.5 | New | 1
1023440 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.4 | EA 16.4 | New | 1
1023439 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.3 | EA 16.3 | New | 1
1023438 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.2 | EA 16.2 | New | 1
1023437 | #1021439 | Story | Feature 1021439: ET/ETI PWI triage/assessment support 16.1 | EA 16.1 | New | 1
1023434 | #342054 | Story | Fix Problem 1007246: AWARE - EAD14 Deployment - Common Group Key update caused AWARE failure (Part 2) | EA 15.4 | Implementing | 2
1023427 | #1023424 | Story | Complete the Exam - Person A | PI 17 | New | 1
1023426 | #1023424 | Story | Attend Online Training - Person A | PI 17 | New | 5
1023425 | #1023424 | Story | Self-Study for the Exam - Person A | PI 17 | New | 8
1023424 | #1022688 | Feature | 1023424: IAT Security Compliance Execution - PI 17 | PI 17 | Draft
1023422 | #376446 | Story | Feature 376446: Install and Configure AWARE Architecture on Second Server & Remaining VMs | PI 16 | New | 3
1023421 | #396669 | Story | Feature 396669: Update RCG Alarms Procedure | EA 15.3 | Done | 1
1023420 | #1007900 | Story | Feature 384136: Update MUOS_IG_GS_NMS_NM_Security_GSKey_SVD_98-P59414M003 to update epo201 to add second certificate for SQL | PI 16 | New | 3
1023371 |  | Problem | [MAINT] SCIP call failed 100% after mobility completed | Unassigned | Triage
1023368 | #1022616 | Story | Feature 1022616: Update "Account Management" Eggplant Regression Tests | PI 16 - Candidate | New | 2
1023322 | #1021904 | Task | Feature 1021904: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1023321 | #1022319 | Story | Complete the Exam - Aidan Spies | PI 16 | New | 1
1023320 | #1022319 | Story | Complete the Exam - Bob Baumgartner | PI 16 | New | 1
1023319 |  | Story | Complete the Exam - Rich Nadolski | Unassigned | New | 1
1023317 | #1022319 | Story | Attend Online Training - Aidan Spies | PI 16 | New | 5
1023316 | #1022319 | Story | Attend Online Training - Bob Baumgartner | PI 16 | New | 5
1023315 |  | Story | Attend Online Training - Rich Nadolski | Unassigned | New | 5
1023314 | #1022319 | Story | Self-Study for the Exam - Aidan Spies | PI 16 | New | 8
1023313 | #1022319 | Story | Self-Study for the Exam - Bob Baumgartner | PI 16 | New | 8
1023312 |  | Story | Self-Study for the Exam - Person A | Unassigned | Invalid | 0
1023311 | #1022319 | Story | Complete the Exam - Michael Valverde | PI 16 | New | 1
1023310 | #1022319 | Story | Attend Online Training - Michael Valverde | PI 16 | New | 5
1023309 | #1022319 | Story | Self-Study for the Exam - Michael Valverde | PI 16 | New | 8
1023295 | #1020412 | Task | Feature 1020412: Team Kickoff for NW RF Alignment | EA 16.1 | New
1023240 | #1008506 | Story | Feature 1008506: Developer perform recovery procedure dry-runs (Part 3) | EA 15.4 | New | 1
1023237 | #1015153 | Story | Justification for Demo by Analysis | EA 15.4 | Ready for Acceptance | 1
1023201 | #1022616 | Story | Feature 1022398: SE Support | PI 16 - Candidate | New | 3
1023189 | #1022398 | Story | Feature 1022398: Integrate PPA with Fault Notifier (Part 2) | PI 16 - Candidate | New | 2
1023183 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: IA and COMSEC | EA 16.4 | New | 1
1023182 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.4 | New | 3
1023181 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: Author and SME support | EA 16.4 | New | 8
1023180 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering Tech Lead | EA 16.4 | New | 5
1023178 | #1023751 | Story | TO-8 Unclass GDS Capability Design Document: WWTS WF SME Support | EA 16.4 | New | 1
1023177 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: IA and COMSEC | EA 16.3 | New | 3
1023176 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.3 | New | 5
1023170 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.3 | New | 8
1023158 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering Tech Lead | EA 16.3 | New | 5
1023157 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: WWTS WF SME Support | EA 16.3 | New | 2
1023155 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: IA and COMSEC | EA 16.2 | New | 3
1023149 | #1012540 | Story | Feature 1012540: Provide MTBF Values for HP/HLR Subcomponents as Part of CDRL A004 | PI 16 | New | 2
1023144 | #1022763 | Story | TO-10 Systems: SDD Chapter 4 and WDS App O&P Updates - Part 2 (PI16) | PI 16 | New | 20
1023141 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.2 | New | 5
1023140 | #1023326 | Story | TO-10 SE: Complete Capability Design Document Part 2 (PI16) | PI 16 | New | 13
1023139 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.2 | New | 8
1023138 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering Tech Lead | EA 16.2 | New | 5
1023106 | #378964 | Task | Mark Sederstrom PTO (EA 15.3 (5/14)) | EA 15.3 | Done
1023082 |  | Problem | Update training material with MPC EAD 15.6 polatis alignment requirements | Unassigned | Triage
1023075 | #1022398 | Story | Feature 1022398: SE Support | PI 16 - Candidate | New | 5
1023074 | #1021169 | Task | Feature 1021169: Submit PDO for 99-P53449E - ILS - IETM | EA 16.5 | New
1023069 | #380808 | Story | Feature 380808: Add IA Inputs to the Nutanix Capabilitty Design Document | EA 15.4 | Implementing | 2
1023066 | #378964 | Task | Marcus Ray PTO (EA 15.4 (5/22)) | EA 15.4 | Done
1023055 | #1022133 | Story | TEST ONLY - PLEASE IGNORE | Unassigned | Implementing | 13
1023033 | #380808 | Story | Feature 380808: MIgrate V-Lab Nutanix cluster to DX360 hardware | EA 15.4 | Implementing | 3
1023004 | #1022769 | Story | TO-10 Systems: Crypto Spec (PI17) | PI 17 | New | 13
1023003 | #1022769 | Story | TO-10 Systems: RSS API & Supplement (PI17) | PI 17 | New | 20
1022999 | #1022769 | Story | TO-10 Systems: RSS API & Supplement, Crypto Spec Updates (PI16) | PI 16 | New | 20
1022996 | #1022768 | Story | TO-10 Systems: CAI Addm 19 and 21 Updates (PI 17) | PI 17 | New | 13
1022995 | #1022768 | Story | TO-10 Systems: CAI Addm 19 and 21 Updates (PI 16) | PI 16 | New | 20
1022993 | #1022763 | Story | TO-10 Systems: SDD Chapter 4 and WDS App O&P Updates (PI17) | PI 17 | New | 13
1022992 | #1022763 | Story | TO-10 Systems: SDD Chapter 4 and WDS App O&P Updates - Part 1 (PI16) | PI 16 | New | 40
1022989 | #1023326 | Story | TO-10 SE: Complete Capability Design Document (PI17) | PI 17 | New | 8
1022988 | #1023326 | Story | TO-10 SE: Complete Capability Design Document Part 1 (PI16) | PI 16 | New | 20
1022987 | #1022758 | Story | TO-10 SE: Complete Capability Spec | PI 16 | New | 20
1022912 | #387452 | Story | Text Updates for Call Flows Document | EA 16.4 | New | 2
1022911 | #387452 | Story | Text Updates for Call Flows Document | EA 16.3 | New | 2
1022910 | #387452 | Story | Text Updates for Call Flows Document | EA 16.2 | New | 2
1022909 | #387452 | Story | Text Updates for Call Flows Document | EA 16.1 | New | 2
1022908 | #387452 | Story | SME and Lab Support for Mobility Call Flow Updates | PI 16 | New | 1
1022907 | #387452 | Story | SME and Lab Support for Mobility Call Flow Updates | PI 16 | New | 1
1022906 | #387452 | Story | SME and Lab Support for Mobility Call Flow Updates | PI 16 | New | 1
1022905 | #387452 | Story | SME and Lab Support for Mobility Call Flow Updates | PI 16 | New | 1
1022904 | #387452 | Story | SME Support for Mobility Call Flow Updates | PI 16 | New | 2
1022903 | #387452 | Story | SME Support for Mobility Call Flow Updates | PI 16 | New | 2
1022902 | #387452 | Story | SME Support for Mobility Call Flow Updates | PI 16 | New | 2
1022901 | #387452 | Story | SME Support for Mobility Call Flow Updates | PI 16 | New | 2
1022900 | #387452 | Story | Mobility Call Flow Updates | EA 16.4 | New | 2
1022899 | #387452 | Story | Mobility Call Flow Updates | EA 16.3 | New | 2
1022898 | #387452 | Story | Mobility Call Flow Updates | EA 16.2 | New | 2
1022897 | #387452 | Story | Mobility Call Flow Updates | EA 16.1 | New | 2
1022891 | #1022616 | Story | Feature 1022616: Update "Login" Eggplant Regression Tests | PI 16 - Candidate | New | 2
1022870 | #1022362 | Feature | TO-10 IA: Support NSA Discussions (PI16) | PI 16 - Candidate | Approved
1022857 | #380808 | Story | Feature 380808: Create CoCo Review for the Power Cables for Nutanix | EA 15.3 | Done | 1 | #1019109 #1019105
1022856 | #380808 | Story | Feature 380808: Update the Power Cables for Nutanix | EA 15.3 | Done | 1 | #1022857
1022848 | #1008506 | Story | Feature 1008506: Write recovery Procedure Power-up/Power Down | EA 15.4 | Implementing | 1
1022846 | #383958 | Story | Feature 383958 Bulk SAR: Generate, Submit Build and Verify | EA 15.4 | New | 1
1022838 | #1012540 | Story | Feature 1012540: Update the Spares Plan for HLR/Auc | PI 16 | New | 1
1022804 | #1013234 | Story | Feature 1013234: Prototype interface for Spring MVC to SQL DB (Part 2) | EA 15.5 | Implementing | 3
1022801 | #1022398 | Story | Feature 1022398: Implement Server Error Pages | PI 16 - Candidate | New | 5
1022800 | #1022398 | Story | Feature 1022398: SIC SME Support | PI 16 - Candidate | New | 3
1022778 | #384084 | Story | Create build of FM for HBSS Regression Testing | EA 15.5 | New | 2
1022777 | #384084 | Story | Create build of FM for Splunk Regression Testing | EA 15.3 | Done | 3
1022776 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.4 | EA 15.4 | Implementing | 3
1022762 | #395688 | Story | Investigate and test Solaris 10 patches for July deployment. | EA 15.4 | New | 2
1022758 | #1022359 | Feature | TO-10 SE: Capability Spec | PI 16 - Candidate | Approved
1022725 |  | Task | Unit testing excelInvoker service | EA 15.3 | Done
1022724 |  | Task | Muos Metrics handover | EA 15.3 | Done
1022720 | #1022398 | Story | Feature 1022398: Integrate PPA with Fault Notifier (Part 1) | PI 16 - Candidate | New | 8
1022718 | #380808 | Story | Feature 380808: Complete remaining CI work for Router & ExtremeSwitch CIs after cleanup migration script completion | EA 15.3 | Done | 1
1022701 | #378964 | Task | Billy Cetroute PTO (EA 15.4 (5/26 - 5/29)) | EA 15.4 | Done
1022700 | #342163 | Task | Feature 342163: Submit PDO for 01-P53574E001 - NMS - NMO ASSEMBLY Drawing | EA 15.4 | Invalid
1022695 | #1022616 | Story | Feature 1022616: Document detailed design to start Implementation (SE) | PI 16 - Candidate | Invalid | 0
1022685 | #1022398 | Story | Feature 1022398: Determine if notifications/messages are to be removed. | PI 16 - Candidate | New | 1
1022684 | #1022398 | Story | Feature 1022398: Implement page layout, home page, and login page | PI 16 - Candidate | New | 5
1022683 | #1022398 | Story | Feature 1022398: Implement Login Authentication services to support login operations | PI 16 - Candidate | New | 8
1022681 | #1022398 | Story | Feature 1022398: Implement Login Authentication Persistence Layer | PI 16 - Candidate | New | 5
1022680 | #1022398 | Story | Feature 1022398: Implement PPA Web Framework | PI 16 - Candidate | New | 13
1022661 | #1022616 | Story | Feature 1022616: Implement 'Chain of Command' persistence objects | PI 16 - Candidate | New | 5
1022660 | #1022616 | Story | Feature 1022616: Implement 'Chain of Command' management page and operations | PI 16 - Candidate | New | 5
1022659 | #395114 | Story | Feature 395114: Update and Maintain MUOS GTS RBD | EA 15.4 | Implementing | 1
1022658 | #1022616 | Story | Feature 1022616: Implement 'Operator Roles' page and operations | PI 16 - Candidate | New | 13
1022657 | #1022616 | Story | Feature 1022616: Implement 'Operator Accounts' page and operations | PI 16 - Candidate | New | 0
1022656 | #354871 | Story | Feature 354871: Provide Cyber Support for NAVSOC OA Workstation upgrade | EA 15.4 | Implementing | 2
1022653 | #380808 | Task | Feature 380808: Submit PDO for 01-P59882M - SEIT - HPE Server DX360 Virtual Platform, SCD | EA 15.3 | Done
1022636 | #1020753 | Story | Feature 1020753: Procurement Tasks for all Features | PI 16 | New | 0
1022631 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (15.3) | EA 15.3 | Done | 1
1022630 | #1022616 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 16 - Candidate | Invalid | 0
1022629 | #1022616 | Story | Feature 1022616: Prep and Perform Interim Demo in SWIT | PI 16 - Candidate | New | 2 | #1022630
1022628 | #1022616 | Story | Feature 1022616: Review the Site Functional Test Plan within STCD | PI 16 - Candidate | New | 2 | #1022629
1022627 | #1022616 | Story | Feature 1022616: Execute STCD Feature Integration and testing including STCD updates identified in SWIT | PI 16 - Candidate | New | 2 | #1022629
1022626 | #1022616 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 16 - Candidate | Invalid | 0 | #1022629
1022625 | #1022616 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 16 - Candidate | Invalid | 0
1022624 | #1022616 | Story | Feature 1022616: UX Update CoC Wireframes | PI 16 - Candidate | New | 3
1022623 | #1022616 | Story | Feature 1022616: Develop IETM Redlines and Perform Development Testing | PI 16 - Candidate | Invalid | 0 | #1022629
1022622 | #1022616 | Story | Feature 1022616: Update Cybersecurity Assessment | PI 16 - Candidate | New | 2 | #1022629
1022621 | #1022616 | Story | Feature 1022616: Implement 'my account' and sub pages | PI 16 - Candidate | New | 5 | #1022629
1022620 | #1022616 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 16 - Candidate | Invalid | 0 | #1022629
1022619 | #1022616 | Story | Feature 1022616: Create STCD | PI 16 - Candidate | New | 3 | #1022628 #1022621 #1022627 #1022629
1022618 | #1022616 | Story | Feature 1022616: Document detailed design to start Implementation (SIC SME) | PI 16 - Candidate | New | 2 | #1022621 #1022619
1022617 | #1022616 | Task | Feature 1022616: Hold Feature Review with SMEs | PI 16 - Candidate | New
1022616 | #1022224 | Feature | WinOBS: PPA Web Implement Administration Menu Items | PI 16 - Candidate | Approved
1022613 | #1019464 | Story | Canada FMS Capability Spec v1: FCAPS high level design | EA 16.4 | New | 1
1022612 | #1019464 | Story | Canada FMS Capability Spec v1: FCAPS high level design | EA 16.2 | New | 1
1022607 | #1019464 | Story | Canada FMS Capability Spec v1: ILS | EA 16.4 | New | 1
1022606 | #1019464 | Story | Canada FMS Capability Spec v1: ILS | EA 16.2 | New | 1
1022602 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.5 | New | 1
1022601 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.4 | New | 1
1022600 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.3 | New | 1
1022599 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.2 | New | 1
1022596 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.4 | New | 1
1022595 | #1019464 | Story | Canada FMS Capability Spec v1: IA and COMSEC | EA 16.2 | New | 1
1022591 | #1019464 | Story | Canada FMS Capability Spec v1: Situational Awareness high level design | EA 16.5 | New | 1
1022590 | #1019464 | Story | Canada FMS Capability Spec v1: Situational Awareness high level design | EA 16.4 | New | 1
1022589 | #1019464 | Story | Canada FMS Capability Spec v1: Situational Awareness high level design | EA 16.3 | New | 1
1022588 | #1019464 | Story | Canada FMS Capability Spec v1: Situational Awareness high level design | EA 16.2 | New | 1
1022584 | #1019464 | Story | Canada FMS Capability Spec v1: GDS design deltas from UGDS | EA 16.5 | New | 1
1022583 | #1019464 | Story | Canada FMS Capability Spec v1: GDS design deltas from UGDS | EA 16.4 | New | 1
1022582 | #1019464 | Story | Canada FMS Capability Spec v1: GDS design deltas from UGDS | EA 16.3 | New | 1
1022581 | #1019464 | Story | Canada FMS Capability Spec v1: GDS design deltas from UGDS | EA 16.2 | New | 1
1022577 | #1019464 | Story | Canada FMS Capability Spec v1: Engineering Tech Lead for version 1 document | EA 16.5 | New | 1
1022576 | #1019464 | Story | Canada FMS Capability Spec v1: Engineering Tech Lead for version 1 document | EA 16.4 | New | 1
1022575 | #1019464 | Story | Canada FMS Capability Spec v1: Engineering Tech Lead for version 1 document | EA 16.3 | New | 1
1022574 | #1019464 | Story | Canada FMS Capability Spec v1: Engineering Tech Lead for version 1 document | EA 16.2 | New | 1
1022570 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.5 | New | 1
1022569 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.4 | New | 1
1022568 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.3 | New | 1
1022567 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.2 | New | 1
1022563 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.5 | New | 1
1022562 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.4 | New | 1
1022560 | #378964 | Task | Sonia Montalvo-Johnson PTO (EA 15.5 (6/16)) | EA 15.5 | New
1022559 | #378964 | Task | Sonia Montalvo-Johnson PTO (EA 16.1 (6/22 - 6/25)) | EA 16.1 | New
1022558 | #379175 | Task | Sonia Montalvo-Johnson PTO (EA 16.1 (6/22 - 6/25)) | EA 16.1 | New
1022557 | #379175 | Task | Sonia Montalvo-Johnson PTO (EA 15.5 (6/15)) | EA 15.5 | New
1022553 | #1022246 | Story | [Feature 1022246] Configure BuildForge Management Console | EA 16.4 | New | 2
1022552 | #1022246 | Story | [Feature 1022246] Install BuildForge Management Console on New BuildForge Server | EA 16.3 | New | 2 | #1022553 #1022555
1022550 | #1022246 | Story | [Feature 1022246] Configure BuildForge Database Server and Database | EA 16.2 | New | 3 | #1022552
1022547 | #1019473 | Story | Canada FMS Capability Design Doc: IETM support for Canada detailed design | EA 16.5 | New | 1
1022546 | #1019473 | Story | Canada FMS Capability Design Doc: IETM support for Canada detailed design | EA 16.4 | New | 1
1022545 | #1019473 | Story | Canada FMS Capability Design Doc: IETM support for Canada detailed design | EA 16.3 | New | 1
1022544 | #1019473 | Story | Canada FMS Capability Design Doc: IETM support for Canada detailed design | EA 16.2 | New | 1
1022541 | #1019473 | Story | Canada FMS Capability Design Doc: UX support for SA/Splunk design | EA 16.5 | New | 2
1022540 | #1019473 | Story | Canada FMS Capability Design Doc: UX support for SA/Splunk design | EA 16.4 | New | 2
1022539 | #1019473 | Story | Canada FMS Capability Design Doc: UX support for SA/Splunk design | EA 16.3 | New | 2
1022538 | #1019473 | Story | Canada FMS Capability Design Doc: UX support for SA/Splunk design | EA 16.2 | New | 2
1022534 | #1019473 | Story | Canada FMS Capability Design Doc: FCAPS detailed design | EA 16.5 | New | 3
1022533 | #1019473 | Story | Canada FMS Capability Design Doc: FCAPS detailed design | EA 16.4 | New | 2
1022532 | #1019473 | Story | Canada FMS Capability Design Doc: FCAPS detailed design | EA 16.3 | New | 2
1022531 | #1019473 | Story | Canada FMS Capability Design Doc: FCAPS detailed design | EA 16.2 | New | 2
1022527 | #1019473 | Story | Canada FMS Capability Design Doc: WWTS WF SME support, UE SDD/WDS | EA 16.5 | New | 1
1022526 | #1019473 | Story | Canada FMS Capability Design Doc: WWTS WF SME support, UE SDD/WDS | EA 16.4 | New | 1
1022525 | #1019473 | Story | Canada FMS Capability Design Doc: WWTS WF SME support, UE SDD/WDS | EA 16.3 | New | 1
1022524 | #1019473 | Story | Canada FMS Capability Design Doc: WWTS WF SME support, UE SDD/WDS | EA 16.2 | New | 1
1022521 | #1019473 | Story | Canada FMS Capability Design Doc: SA and Splunk support | EA 16.5 | New | 1
1022520 | #1019473 | Story | Canada FMS Capability Design Doc: SA and Splunk support | EA 16.4 | New | 1
1022519 | #1019473 | Story | Canada FMS Capability Design Doc: SA and Splunk support | EA 16.3 | New | 1
1022518 | #1019473 | Story | Canada FMS Capability Design Doc: SA and Splunk support | EA 16.2 | New | 1
1022515 | #1019473 | Story | Canada FMS Capability Design Doc: ILS | EA 16.5 | New | 2
1022514 | #1019473 | Story | Canada FMS Capability Design Doc: ILS | EA 16.4 | New | 2
1022513 | #1019473 | Story | Canada FMS Capability Design Doc: ILS | EA 16.3 | New | 2
1022512 | #1019473 | Story | Canada FMS Capability Design Doc: ILS | EA 16.2 | New | 2
1022508 | #1019473 | Story | Canada FMS Capability Design Doc: Testing Strategy and Lab | EA 16.5 | New | 1
1022507 | #1019473 | Story | Canada FMS Capability Design Doc: Testing Strategy and Lab | EA 16.4 | New | 1
1022506 | #1019473 | Story | Canada FMS Capability Design Doc: Testing Strategy and Lab | EA 16.3 | New | 1
1022505 | #1019473 | Story | Canada FMS Capability Design Doc: Testing Strategy and Lab | EA 16.2 | New | 1
1022501 | #1019473 | Story | Canada FMS Capability Design Doc: ICD Updates | EA 16.5 | New | 2
1022500 | #1019473 | Story | Canada FMS Capability Design Doc: ICD Updates | EA 16.4 | New | 2
1022499 | #1019473 | Story | Canada FMS Capability Design Doc: ICD Updates | EA 16.3 | New | 2
1022498 | #1019473 | Story | Canada FMS Capability Design Doc: ICD Updates | EA 16.2 | New | 2
1022496 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.5 | New | 2
1022495 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.4 | New | 2
1022494 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.3 | New | 2
1022493 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.2 | New | 1
1022489 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.5 | New | 1
1022488 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.4 | New | 1
1022487 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.3 | New | 1
1022486 | #1019473 | Story | Canada FMS Capability Design Doc: IA and COMSEC | EA 16.2 | New | 1
1022481 | #1019473 | Story | Canada FMS Capability Design Doc: Situational Awareness detailed design | EA 16.5 | New | 2
1022480 | #1019473 | Story | Canada FMS Capability Design Doc: Situational Awareness detailed design | EA 16.5 | New | 2
1022479 | #1019473 | Story | Canada FMS Capability Design Doc: Situational Awareness detailed design | EA 16.4 | New | 3
1022478 | #1019473 | Story | Canada FMS Capability Design Doc: Situational Awareness detailed design | EA 16.3 | New | 3
1022477 | #1019473 | Story | Canada FMS Capability Design Doc: Situational Awareness detailed design | EA 16.2 | New | 3
1022475 | #1019473 | Story | Canada FMS Capability Design Doc: NMF & PPA SME support | EA 16.4 | New | 1
1022474 | #1019473 | Story | Canada FMS Capability Design Doc: NMF & PPA SME support | EA 16.2 | New | 1
1022471 | #1019473 | Story | Canada FMS Capability Design Doc: Network and Nutanix SME support | EA 16.5 | New | 1
1022470 | #1019473 | Story | Canada FMS Capability Design Doc: Network and Nutanix SME support | EA 16.4 | New | 1
1022469 | #1019473 | Story | Canada FMS Capability Design Doc: Network and Nutanix SME support | EA 16.3 | New | 1
1022468 | #1019473 | Story | Canada FMS Capability Design Doc: Network and Nutanix SME support | EA 16.2 | New | 1
1022464 | #1019473 | Story | Canada FMS Capability Design Doc: GDS design deltas from UGDS | EA 16.5 | New | 2
1022463 | #1019473 | Story | Canada FMS Capability Design Doc: GDS design deltas from UGDS | EA 16.4 | New | 1
1022462 | #1019473 | Story | Canada FMS Capability Design Doc: GDS design deltas from UGDS | EA 16.3 | New | 1
1022461 | #1019473 | Story | Canada FMS Capability Design Doc: GDS design deltas from UGDS | EA 16.2 | New | 1
1022458 | #1019473 | Story | Canada FMS Capability Design Doc: TACLANE SME support | EA 16.5 | New | 1
1022457 | #1019473 | Story | Canada FMS Capability Design Doc: TACLANE SME support | EA 16.4 | New | 1
1022456 | #1019473 | Story | Canada FMS Capability Design Doc: TACLANE SME support | EA 16.3 | New | 1
1022455 | #1019473 | Story | Canada FMS Capability Design Doc: TACLANE SME support | EA 16.2 | New | 1
1022451 | #1019473 | Story | Canada FMS Capability Design Doc: Engineering Tech Lead for Draft document | EA 16.5 | New | 5
1022450 | #1019473 | Story | Canada FMS Capability Design Doc: Engineering Tech Lead for Draft document | EA 16.4 | New | 5
1022449 | #1019473 | Story | Canada FMS Capability Design Doc: Engineering Tech Lead for Draft document | EA 16.3 | New | 5
1022448 | #1019473 | Story | Canada FMS Capability Design Doc: Engineering Tech Lead for Draft document | EA 16.2 | New | 5
1022444 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.5 | New | 2
1022443 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.4 | New | 2
1022442 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.3 | New | 2
1022441 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.2 | New | 2
1022437 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.5 | New | 2
1022436 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.4 | New | 2
1022435 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.3 | New | 2
1022434 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.2 | New | 2
1022430 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.5 | New | 3
1022429 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.4 | New | 3
1022428 | #1022246 | Story | [Feature 1022246] Commission and Configure New BuildForge Servers (console and DB) | EA 16.1 | New | 2 | #1022550
1022417 | #1022398 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 16 - Candidate | Invalid | 0
1022416 | #1022398 | Story | Feature 1022398: Prep and Perform Interim Demo | PI 16 - Candidate | New | 2 | #1022417
1022415 | #1022398 | Story | Feature 1022398: Review the Site Functional Test Plan within STCD | PI 16 - Candidate | Invalid | 0 | #1022416
1022414 | #1022398 | Story | Feature 1022398: Execute STCD Feature Integration and testing including STCD updates identified in SWIT | PI 16 - Candidate | New | 2 | #1022416
1022413 | #1022398 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 16 - Candidate | Invalid | 0 | #1022416
1022412 | #1022398 | Story | Feature 1022398: MFR 3 – CSE Updates CAP | PI 16 - Candidate | New | 2 | #1022416
1022411 | #1022398 | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 16 - Candidate | Invalid | 0 | #1022416 #1022412
1022410 | #1022398 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 16 - Candidate | Invalid | 0
1022409 | #1022398 | Story | Feature 1022398: UX Support | PI 16 - Candidate | New | 2
1022408 | #1022398 | Story | Feature 1022398: IETM Redlines and Perform Development Testing | PI 16 - Candidate | Invalid | 0 | #1022416
1022407 | #1022398 | Story | Feature 1022398: MFR 3 – Dev Team Resolves STIG Findings | PI 16 - Candidate | New | 2 | #1022411
1022406 | #1022398 | Story | Feature 1022398: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | PI 16 - Candidate | New | 1 | #1022407
1022405 | #1022398 | Story | Feature 1022398: MFR 3 – CSE Performs initial Cybersecurity Assessment | PI 16 - Candidate | New | 5 | #1022406
1022404 | #1022398 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 16 - Candidate | Invalid | 0 | #1022416 #1022405
1022403 | #1022398 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 16 - Candidate | Invalid | 0 | #1022416
1022402 | #1022398 | Story | Feature 1022398: Create STCD | PI 16 - Candidate | New | 3 | #1022415 #1022414 #1022416 #1022404
1022401 | #1022398 | Story | Feature 1022398: Document Initial detailed design to start Implementation (SIC SME) | PI 16 - Candidate | New | 2 | #1022402 #1022403 #1022404
1022400 | #1022398 | Task | Feature 1022398: Hold Feature Review with SMEs | PI 16 - Candidate | New
1022399 | #369754 | Story | Feature 369754: Design File Transfer | PI 17 | New | 5
1022398 | #1022224 | Feature | WinOBS: PPA Implement Web Framework | PI 16 - Candidate | Approved |  | #1022616
1022395 | #1022389 | Task | Support system demo | Unassigned | Invalid
1022393 | #1022389 | Task | Team demo | Unassigned | Invalid
1022392 | #1022389 | Task | Executing and tracking | Unassigned | Invalid
1022391 | #1022389 | Task | Iteration planning | Unassigned | Invalid
1022390 | #1022389 | Task | Team backlog refinement | Unassigned | Invalid
1022389 |  | Task | Development Iteration | Unassigned | Invalid
1022370 | #1011070 | Task | Feature 1011070: Assess Problem 329711 - EA 15.3 (Valverde) | EA 15.3 | Done
1022369 | #1011070 | Task | Feature 1011070: Assess Problem 336421 - EA 15.3 (Anil) | EA 15.3 | Done
1022368 | #1013452 | Story | Feature 1013452: Perform initial IA Assessment of current design with CURL (Ephemeris push) | EA 15.3 | Done | 2
1022367 | #1013452 | Story | Feature 1013452: Complete CURL testing in CentOs | EA 15.3 | Done | 1
1022366 | #1011150 | Task | Feature 1011150: MAGIC TT Support - EA 15.2 (Glen) | EA 15.2 | Done
1022365 | #1013534 | Story | Lab - Maintain Labs - DSN GW SME Support - Glen L. (15.2) | EA 15.2 | Done | 1
1022335 | #354680 | Task | Feature 354680: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | Done |  | #393686
1022334 |  | Task | Improve error handling for metrics automation VB script | Unassigned | In Development
1022322 | #1022319 | Story | Complete the Exam - Anil Boddapati | PI 16 | New | 1
1022321 | #1022319 | Story | Attend Online Training - Anil Boddapati | PI 16 | New | 5
1022320 | #1022319 | Story | Self-Study for the Exam - Anil Boddapati | PI 16 | New | 8
1022319 | #1022688 | Feature | 1022319: IAT Security Compliance Execution - PI 16 | PI 16 - Candidate | Approved
1022314 | #1022300 | Story | Feature 1022300: Initiate CM PDO Processing for all CI's | EA 16.5 | New | 0
1022313 | #1022300 | Story | Feature 1022300- Prep and Perform Feature Demo – Customer Demo Event | EA 16.5 | New | 0 | #1022314
1022312 | #1022300 | Story | Feature 1022300: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 16.5 | New | 0 | #1022313
1022311 | #1022300 | Story | Feature 1022300: Execute STCD Feature Integration and testing including STCD updates identified | EA 16.5 | New | 0 | #1022313
1022310 | #1022300 | Story | Feature 1022300: Provide Development inputs to common documents | EA 16.5 | New | 0 | #1022313
1022309 | #1022300 | Story | Feature 1022300: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | EA 16.5 | New | 0
1022308 | #1022300 | Story | Feature 1022300 UX Research and Design Support (Change back to UX Team) | EA 16.5 | New | 0
1022307 | #1022300 | Story | Feature 1022300: Develop IETMs and Perform Development Testing | EA 16.5 | New | 0 | #1022313
1022306 | #1022300 | Story | Feature 1022300: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 16.5 | New | 0 | #1022313
1022305 | #1022300 | Story | Feature 1022300: Perform Iterative Implementation, Integration, development Testing including updating design | EA 16.5 | New | 0 | #1022313
1022304 | #1022300 | Story | Feature 1022300: Provide Deployment Notes and Operator Impact Inputs | EA 16.5 | New | 0 | #1022313
1022303 | #1022300 | Story | Feature 1022300: Create STCD and review with stakeholders | EA 16.5 | New | 0 | #1022313 #1022311 #1022312 #1022305
1022302 | #1022300 | Story | Feature 1022300 Document Initial capability specification and detailed design to start Implementation | EA 16.5 | New | 0 | #1022303 #1022305
1022301 | #1022300 | Task | Feature 1022300 Hold Feature Review with SMEs | EA 16.1 | New
1022300 | #1023991 | Feature | Lab - DSN Emulator - Spectra2 STP Risk Mitigation | EA 16.5 | Approved
1022298 | #1007900 | Task | Feature 1007900 Submit PDO for HBSS Test Report | PI 16 | New |  | #1021611
1022297 | #1007900 | Task | Feature 1007900: Submit PDO for HBSS SOVT | PI 16 | New |  | #1021608
1022281 | #380808 | Task | Feature 380808: Submit PDO for 98-P59813M MUOS_IG_GS_NMS_NM_Common_Tectia_SVD | PI 16 | New |  | #1010512
1022268 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - RFIF | EA 15.3 | Done | 1
1022267 | #1013452 | Story | Feature 1013452: Get stakeholder concurrence on Ephemeris design approach | EA 15.4 | New | 1
1022263 |  | Feature | OBS - PPA Web Implement Mapping Server | PI 16 - Candidate | Rejected
1022261 | #1006191 | Story | Assist with Lab Activities for SBC Prototype Phase II | EA 15.3 | Done | 1
1022255 |  | Feature | OBS - PPA Web Implement Administration Menu Items | PI 16 - Candidate | Rejected
1022254 |  | Feature | OBS - PPA Implement Web Framework | PI 16 - Candidate | Rejected
1022249 | #1022138 | Story | Feature 1022138: Design build flow for PPA | PI 16 - Candidate | New | 3
1022245 | #1022138 | Story | Feature 1022138: Configure CM/ClearCase management for PPA | PI 16 - Candidate | New | 3
1022216 | #1022138 | Story | Feature 1022138: Add new PPA VM to DNS Server in SWIT | PI 16 - Candidate | New | 1
1022215 | #1022138 | Story | Feature 1022138: Configure connectivity for PPA VM | PI 16 - Candidate | New | 2
1022214 | #1022138 | Story | Feature 1022138: Nutanix Support for Okapi2 | PI 16 - Candidate | Implementing | 1
1022213 | #1022138 | Story | Feature 1022138: Create VM in SWIT for PPA Web Application | EA 16.1 | New | 5
1022212 | #1022138 | Story | Feature 1022138: Configure Build/Release management for PPA | PI 16 - Candidate | New | 5
1022209 | #367689 | Task | Feature 367689: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | New
1022208 |  | Task | Feature 354680: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | New
1022207 | #384084 | Task | Feature 384084: Submit PDO for 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD | PI 16 | New
1022206 | #1016383 | Task | Feature 1016383: Submit PDO for 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD | PI 16 | New
1022205 | #392058 | Task | Feature 392058: Submit PDO for 99-P53449E - ILS - IETM | EA 16.1 | New
1022202 | #367689 | Task | Feature 367689: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1022201 | #1020303 | Task | Feature 1020303: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1022200 | #1008506 | Task | Feature 1008506: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1022199 | #1008506 | Task | Feature 1008506: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1022198 | #1002345 | Task | Feature 1002345: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1022197 | #1002345 | Task | Feature 1002345: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1022195 | #1013452 | Task | Feature 1013452: Submit PDO for 99-P53198T – NMS – NM – NEDB | PI 16 | New
1022194 | #1013452 | Task | Feature 1013452: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1022193 | #1013452 | Task | Feature 1013452: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1022192 | #1013452 | Task | Feature 1013452: Submit PDO for 98-P55509M – Network – Router – SVD | PI 16 | New
1022191 |  | Task | Feature 1013452: Submit PDO for 98-P55464M MUOS_IG_GS_Network_LB_SVD | Unassigned | Invalid
1022184 |  | Problem | Board 12 crashed with “Out of space in user signal pool” errors | Unassigned | Assessing
1022150 | #1020849 | Task | Feature 1020849: Hardware/Software Procurement Request for Release Regression | PI 16 | New
1022149 | #1020797 | Task | Feature 1020797: Procurement Verification and Approvals for Release Regression | PI 16 | New
1022148 | #1020849 | Task | Feature 1020849: Hardware/Software Procurement Request for Lab - Maintain Labs | PI 16 | New
1022147 | #1020849 | Task | Feature 1020849: Procurement Verification and Approvals for Lab - Maintain Labs | PI 16 | New
1022146 | #1014021 | Feature | Identify/define additional metrics for WCDMA services, implement Retainability metrics defined in PI 15, track, analyze and report implemented metrics, investigate CSSR anamoly | PI 16 - Candidate | Approved
1022145 |  | Task | Feature 1021044: Hardware/Software Procurement Request for ETI - Polatis 6000 Switch Updates | PI 16 | New
1022143 | #1021044 | Task | Feature 1021044: Procurement Verification and Approvals for ETI - Polatis 6000 Switch Updates | PI 17 | New
1022138 | #1022224 | Feature | WinOBS: PPA Build, Release, and Dev Environment Setup | PI 16 - Candidate | Approved |  | #1022398 #1022616
1022134 | #1016900 | Story | Feature 1016900: Prototype new Login Authentication Solution | EA 16.1 | New | 8
1022133 |  | Feature | TEST ONLY - PLEASE IGNORE | Unassigned | Analyzing
1022122 | #1013452 | Story | Feature 1013452: OS Patching Support for Geo EAD 18 | EA 15.3 | Invalid | 0
1022118 | #385438 | Feature | OBS - NET: Develop Capability Design Document for the MUOS Ground System | PI 16 | Analyzing
1022110 | #1022133 | Story | TEST ONLY - PLEASE IGNORE | Unassigned | Done | 100
1022084 | #1002345 | Story | Fix problems 1015855 and 1013114 | PI 16 | New | 1
1022074 | #1021886 | Story | Lab - SWIT Revitalize - CDR Collector restore implementation | EA 16.3 | New | 2
1022072 | #1021886 | Story | Lab - SWIT Revitalize - Drawing updates | EA 16.4 | New | 8
1022071 | #1021886 | Story | Lab - SWIT Revitalize - Infrastructure restore (ATM, RANI, RCG) implementation | EA 16.3 | New | 8
1022070 | #1021886 | Story | Lab - SWIT Revitalize - Corben simulator hardware and wiring documentation and config update implementation | EA 16.2 | New | 8
1022069 | #1021886 | Story | Lab - SWIT Revitalize - tools support for RDE environment | EA 16.2 | New | 1
1022068 | #1007900 | Story | Feature 1007900: Create CoCo Review of NME 14 and NME 15 servers | EA 16.1 | New | 1
1022066 | #1021886 | Story | Lab - SWIT Revitalize - tools support for RDE environment | EA 16.1 | New | 1
1022065 | #1021886 | Story | Lab - SWIT Revitalize - Corben simulator hardware and wiring documentation and config update implementation | EA 16.1 | New | 5
1022064 | #1021886 | Story | Lab - SWIT Revitalize - RNC upgrades implementation | EA 16.1 | New | 3
1022063 | #1007900 | Story | Feature 1007900: Remove HBSS from NME 14 and NME 15 servers | EA 15.3 | Done | 1
1022059 | #385442 | Story | Feature 385442: Prepare and Hold Final Review of Capability Spec | EA 15.5 | Implementing | 3
1022058 | #385442 | Story | Feature 385442: Prepare and Hold Final Review of Capability Spec | EA 15.5 | New | 3
1022055 | #1022118 | Story | Feature 385442: Create rules and- route spreadsheet from Juniper Routers[PI 16] | PI 16 | New | 5
1022054 | #395897 | Story | Feature 395897 :Develop Version2 of the Cybersecurity Assessment Guidance Document | EA 15.4 | Implementing | 3
1022049 | #1022118 | Story | Feature 385442: Create - rules spreadsheetand from McAfee Firewalls [PI 16] | PI 16 | New | 5
1022044 | #1013452 | Story | Feature 1013452: Update SIPRNet workstation for Ephemeris (for Windows) | EA 15.3 | Done | 3
1022042 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.3 | EA 15.3 | Done | 5
1022029 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support | EA 15.4 | Implementing | 1
1022028 | #387446 | Story | Mobility Call Flow Updates | EA 15.2 | Done | 1
1022027 | #1006191 | Story | Feature 1006191 Review all CAT 1 and CAT 2 findings and provide estimate to address | EA 15.3 | Done | 1
1022026 | #1006191 | Story | Feature 1006191 Assist in the low level design effort, including DSN GW Prototype work, for DSN GW Obs effort | EA 15.2 | Done | 1
1022025 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.2 | Done | 2
1022021 | #384084 | Story | Feature 384084: Investigate updates to the FM Netcool topology to better reflect Nutanix hardware | EA 15.4 | Implementing | 2
1022019 | #1007900 | Story | Feature 1007900: Continued STCD Testing of IETM procedures | EA 15.3 | Done | 2
1022003 | #1013136 | Problem | Vendor: PTP IP IKE exchange fails when SCIP and HAIPE FFV keys are both loaded | EA 16.1 | Implementing
1022002 | #380808 | Task | Feature 380808: Submit PDO for PL30-P59588E001 - SEIT - CABLE KIT - SF/ NMF, WAHIAWA, PARTS LIST | PI 16 | New
1021988 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P54107T – GEO – AMS-GS SVD | PI 16 | New
1021987 | #1007900 | Task | Feature 1007900: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1021986 | #1007900 | Task | Feature 1007900: Submit PDO for 99-P59435M – NMS – NM – Common – HW-SW Map | PI 16 | New
1021985 | #1007900 | Task | Feature 1007900: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1021984 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P54188T - NMS -NM - Security -AAA - SVD | PI 16 | New
1021983 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P55755M - Firewall - Network - SVD | PI 16 | New
1021978 | #1007900 | Task | Feature 1007900: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | New
1021974 | #1007900 | Task | Feature 1007900: Submit PDO for 99-P53198T – NMS – NM – NEDB | PI 16 | New
1021973 | #1003390 | Task | Feature 1003390: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1021972 | #1003390 | Task | Feature 1003390: Submit PDO for 99-P53198T – NMS – NM – NEDB | PI 16 | New
1021970 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P59428M - NMS - NM - Security - SIEM - SVD | PI 16 | New
1021967 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P54199T - NMS - NM - Security - AntiVirusHIDS - SVD | PI 16 | New
1021966 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD | PI 16 | New
1021965 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P54188T - NMS -NM - Security -AAA - SVD | PI 16 | New
1021961 | #388053 | Story | Design FCAPS Replacement | EA 15.4 | Implementing | 2
1021960 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.2 | Done | 1
1021957 | #1009453 | Story | Feature 1009453: Investigate the tracing for the AIU boards | EA 15.3 | Done | 1
1021956 | #1009453 | Story | Feature 1009453: Investigate the tracing for the TRX boards | EA 15.3 | Done | 1
1021955 | #1009453 | Story | Feature 1009453: Investigate the tracing for the TX boards | EA 15.3 | Done | 1
1021954 | #1021904 | Story | <Feature 1021904>: Provide Deployment Notes and Operator Impact Inputs | EA 16.5 | New | 1
1021953 | #1021904 | Story | <Feature 1021904>- Prep and Perform Feature Demo  Customer Demo Event | EA 16.5 | New | 1
1021952 | #1021904 | Story | <Feature 1021904>: Initiate CM PDO Processing for all CI's | EA 16.5 | New | 1
1021951 | #1021904 | Story | Feature 1021904: Incorporation of IETM Updates and Integration Support for ETI - ACU Backup Procedure | EA 16.4 | New | 1
1021950 | #1021904 | Story | <Feature 1021904>: Provide Development inputs to common documents | EA 16.4 | New | 2
1021949 | #1021904 | Story | <Feature 1021904>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 16.4 | New | 2
1021948 | #1021904 | Story | <Feature 1021904>: Execute STCD Feature Integration and testing including STCD updates identified (Part 2 of 2) | EA 16.4 | New | 2
1021947 | #1021904 | Story | <Feature 1021904>: MFR 1  Dev Team Performs Cybersecurity Assessment | EA 16.3 | New | 1
1021946 | #1021904 | Story | <Feature 1021904>: Develop IETMs and Perform Development Testing | EA 16.3 | New | 3
1021945 | #1021904 | Story | Feature 1021904: Review ACU Backup and SW Configuration Procedure for Style Guide Compliance and Dry Runs | EA 16.3 | New | 3
1021944 | #1021904 | Story | <Feature 1021904>: Execute STCD Feature Integration and testing including STCD updates identified (Part 1 of 2) | EA 16.3 | New | 5
1021943 | #1021904 | Story | <Feature 1021904>: Perform Iterative Implementation, Integration, development Testing including updating design (Part 2 of 2) | EA 16.2 | New | 8
1021942 | #1021904 | Task | <Feature 1021904> Hold Feature Review with SMEs | EA 16.1 | New
1021941 | #1021904 | Story | <Feature 1021904> Document Initial capability specification and detailed design to start Implementation | EA 16.1 | New | 3
1021940 | #1021904 | Story | <Feature 1021904>: Create STCD and review with stakeholders | EA 16.1 | New | 3
1021939 | #1021904 | Story | <Feature 1021904>: Perform Iterative Implementation, Integration, development Testing including updating design (Part 1 of 2) | EA 16.1 | New | 1
1021909 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (part 4 of 4) | EA 15.4 | Implementing | 3
1021907 |  | Problem | ExtremeSwitch SVD missing instructions to update OSPF MD5 authentication on switch to match firewalls | Unassigned | Triage
1021906 |  | Problem | AMP missing instructions to update OSPF MD5 authentication on switch to match firewalls | Unassigned | Triage
1021904 | #1022632 | Feature | ETI - ACU backup procedure, IETM updates and ET SVD updates required | PI 16 | Approved
1021903 | #383958 | Story | Feature 383958 Bulk SAR: Complete testing of importing | EA 15.3 | Invalid | 0
1021902 | #383958 | Story | Feature 383958 Bulk SAR: Update design materials and complete testing | EA 15.3 | Done | 2
1021897 | #1002345 | Story | Fix Problem 375419: Signaling Link Unavailable alarm includes specifics in "Summary" such that O-Level could not find this specific alarm and perform recovery procedure. | EA 15.3 | Done | 2
1021894 | #1011295 | Story | Feature 1011295: Update Drawings for GEO Removal Problem 392388 | EA 15.5 | New | 5
1021893 | #1011295 | Story | Feature 1011295: Update Drawings for GEO Removal Problem 392388 | EA 15.5 | New | 2
1021891 | #1014387 | Story | Feature 1014387: ETISP SW/SVD Review Completion | EA 15.3 | Done | 2
1021886 | #1012099 | Feature | Lab - SWIT Revitalize - RAN SWIT Implementation (2nd of 3 Features) | PI 16 - Candidate | Approved
1021885 | #332951 | Story | Feature 332951: SME Support of RBS IETM Updates (15.3) | EA 15.3 | Done | 2
1021874 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Leslie | EA 15.3 | Done | 1
1021869 | #1013234 | Story | Feature 1013234: Test/validate compatibility of TomeEE JMS / ActiveMQ - part 3 | EA 15.3 | Done | 3
1021868 | #387448 | Story | Update P2P Communication Call Flows | EA 15.4 | New | 1
1021859 | #1011150 | Story | Feature 1011150: Incorporate IETM finding into NetCool IETM for recovery of alarms due to password changes | EA 15.3 | Done | 1
1021858 | #1011150 | Story | Update NetCool IETM for recovery of alarms due to password changes | EA 15.3 | Done | 3
1021856 | #377437 | Task | Feature 377437: IETM Development and Integration Updates for Gen 2 ETT Laptops | EA 15.3 | Done
1021848 | #1008506 | Story | Investigate Severity Change to Major for Netcool password changes | PI 16 | New | 3
1021841 | #1009453 | Story | Feature 1009453: Execute tests for DL power spike investigation (Lab team) | EA 15.3 | Done | 2
1021840 | #1013452 | Story | Feature 1013452: EAD 18 rebase story for MPC EAD14.43/MPC EA16.x | PI 16 | New | 1
1021832 | #1020744 | Story | Implement SWIT MUOS Domain Changes to Support first.last User ID Migration | PI 16 | New | 5
1021829 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.1 | New | 1
1021822 | #1021044 | Story | Polatis Switch Update - Initiate CM PDO Processing for SVD updates for Power supply replacement procedure and all other Cis | PI 17 | New | 2
1021821 | #1021044 | Story | Lab - Polatis Switch Update - MFR 3  CSE Completes Final CAP (Change back to Cyber Security Engineering) - Part 3b | EA 16.4 | Invalid | 0
1021820 | #1021044 | Story | Polatis Switch Update - Create Coco Review for Power supply replacement procedure | PI 17 | New | 1
1021819 | #1021044 | Story | Feature Demo  Customer Demo Event - Lab - Polatis Switch Update - Prep and Hold Feature Demo | PI 17 | New | 5
1021818 | #1021044 | Story | Feature Demo  Customer Demo Event - Lab - Polatis Switch Update - Prep and Hold Feature Demo | PI 17 | New | 5
1021817 | #1021044 | Story | Feature 1021044: Lab - Polatis Switch Update - Update to the IETM for Polatis | PI 17 | New | 1
1021816 | #1021044 | Story | Lab - Polatis Switch Update - MFR 3  CSE Completes Final CAP (Change back to Cyber Security Engineering) | PI 17 | New | 3
1021815 | #1021044 | Story | Lab - Polatis Switch Update - Perform lab integration and test (Tom) | PI 17 | New | 5
1021814 | #1021044 | Story | Lab - Polatis Switch Update - Run the SVD in the Lab (Tom) | PI 17 | New | 1
1021813 | #1021044 | Story | Lab - Polatis Switch Update - Run the SVD in the Lab (Glen) | PI 17 | New | 1
1021812 | #1021044 | Story | Lab - Polatis Switch Update - Create Deployment Notes, Operator Impact Inputs, and provide input on training | PI 17 | New | 1
1021811 | #1021044 | Story | Lab - Polatis Switch Update - SVD updates for Power supply replacement procedure | PI 17 | New | 2
1021810 | #1021044 | Story | Lab - Polatis Switch Update - SVD Updates and site test/check | PI 17 | New | 2
1021809 | #1021044 | Story | Lab - Polatis Switch Update - Add power supply alarms to whitelist | PI 17 | New | 3
1021808 | #1021044 | Story | Feature 1021044: Polatis Switch Update - Provide inputs for SVD Updates | PI 17 | New | 2
1021807 | #1021044 | Story | Lab - Polatis Switch Update - Management Interface support (if needed) | PI 17 | New | 2
1021806 | #1021044 | Story | Lab - Polatis Switch Update - MFR 3  CSE Completes initial CAP (Change back to Cyber Security Engineering) - Part 2 | PI 17 | New | 2
1021805 | #1021044 | Story | Feature 366348: Polatis Switch Update - Add to PDM Link and Update Cabinet Drawing | PI 17 | New | 1
1021804 | #1021044 | Story | Feature 366348: Polatis Switch Update - Create SCD drawing | PI 17 | New | 1
1021803 | #1021044 | Story | Feature 366348: Polatis Switch Update - Create Coco Review for Parts Lists and Drawings | PI 17 | New | 1
1021802 | #1021044 | Story | Lab - Polatis Switch Update - Perform lab integration and test (Tom) | PI 17 | New | 5
1021801 | #1021044 | Story | Lab - Polatis Switch Update - Create/Update Polatis Switch IETM Documentation (redlines to ILS) | PI 17 | New | 3
1021800 | #1021044 | Story | Lab - Polatis Switch Update - Create and Test Functional Site Test (Glen) | PI 17 | New | 2
1021799 | #1021044 | Story | Lab - Polatis Switch Update - Perform lab integration and test (Glen) | PI 17 | New | 2
1021798 | #1021044 | Story | Lab - Polatis Switch Update - IA Posture Assessment | PI 17 | New | 2
1021797 | #1021044 | Story | Feature 1021044: Lab - Polatis Switch Update - Complete Review of the PDM Link | PI 17 | New | 1
1021796 | #1021044 | Story | Feature 1021044: Polatis Switch Update - Alternate Parts List due to software upgrade? | PI 17 | New | 1
1021795 | #1021044 | Story | Lab - Polatis Switch Update - Load new s/w on lab swithch | PI 17 | New | 3
1021794 | #1021044 | Story | Lab - Polatis Switch Update - Procure s/w from Polatis, check with CM | PI 17 | New | 1
1021793 | #1021044 | Story | Lab - Polatis Switch Update - Create STCD and review with stakeholders | PI 17 | New | 2
1021792 | #1021044 | Story | Lab - Polatis Switch Update - Document Initial capability specification and detailed design to start implementation | PI 17 | New | 3
1021791 | #380808 | Task | Feature 380808: Submit PDO for 63-P53199T - ILS - Functional Block Diagram MUOS Ground System | PI 16 | New
1021788 | #380808 | Task | Feature 380808: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1021787 | #380808 | Task | Feature 380808: Submit PDO for 98-P59414M – NMS – NM – Security – GSKey – SVD (GSKM) | PI 16 | New
1021786 | #380808 | Task | Feature 380808: Submit PDO for 98-P54188T - NMS -NM - Security -AAA - SVD | PI 16 | New
1021785 | #380808 | Task | Feature 380808: Submit PDO for 98-P55755M - Firewall - Network - SVD | PI 16 | New
1021784 | #380808 | Task | Feature 380808: Submit PDO for 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD | PI 16 | New
1021783 | #380808 | Task | Feature 380808: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1021782 | #1021499 | Story | Feature 1021499: Create VA to reapply fix for Problem 1021441 (MPC EAD TBD) in EAD 16 | EA 16.1 | New | 2
1021781 | #1021499 | Story | Feature 1021499: Re-apply changes in EAD 16 for Problem 1021441 (MPC EAD TBD) | EA 16.1 | New | 2
1021780 | #380808 | Task | Feature 380808: Submit PDO for 99-P53198T – NMS – NM – NEDB | PI 16 | New
1021779 | #342054 | Task | Feature 342054: Submit PDO for 98-P59856M - Network - ExtremeSwitch - SVD | PI 16 | New
1021778 | #342054 | Task | Feature 342054: Submit PDO for 98-P59414M – NMS – NM – Security – GSKey – SVD (GSKM) | PI 16 | New
1021777 | #342054 | Task | Feature 342054: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | New
1021767 | #342054 | Task | Feature 342054: Submit PDO for 98-P59428M - NMS - NM - Security - SIEM - SVD | PI 16 | New
1021748 | #272399 | Task | Feature 272399: Submit PDO for 99-P53449E - ILS - IETM | PI 16 | New
1021747 | #272399 | Task | Feature 272399: Submit PDO for 98-P59422M – NMS – NM – SecretAppServer – SVD | PI 16 | New
1021741 | #1020849 | Story | Lab - Maintain Labs - OBS - Integration and Test Network - Initial Discovery and DMSMS | EA 16.5 | New | 3
1021740 | #1020849 | Story | Lab - Maintain Labs - OBS - Integration and Test Network - Initial Discovery and DMSMS | EA 16.5 | New | 3
1021735 | #1020849 | Story | Lab - Maintain Labs - OBS - Lab Support Workstations - Initial Discovery and DMSMS | EA 16.5 | New | 3
1021731 | #1020849 | Story | Lab - Maintain Labs - OBS - RF Fiber Transceiver - Initial Discovery and DMSMS | EA 16.5 | New | 3
1021730 | #1020849 | Story | Lab - Maintain Labs - OBS - IULAN - Initial Discovery and DMSMS | EA 16.5 | New | 5
1021728 | #1015153 | Story | Feature 1015153: Verify that a disc burned by the Okapi team is bootable (Load Balancer is the target hardware) | EA 15.3 | Done | 1
1021726 | #1020849 | Story | Lab - Maintain Labs - OBS - WILMA - Initial Discovery and DMSMS | EA 16.5 | New | 5
1021719 |  | Problem | ePO Established Large Number of unneeded connections to DB starving other processes of resources. | Unassigned | Triage
1021704 | #383958 | Story | Feature 383958: Complete Unit Tests for Bulk SAR PPA Implementation, Integration, development Testing - part 4R | EA 15.3 | Done | 2
1021685 | #1013234 | Story | Feature 1013234: Complete proof of concept library using JDBC for DB communication alternative to hibernate | EA 15.3 | Done | 2
1021661 | #1020011 | Task | Submit PDO for 98-P55616M – IA - SVD | EA 16.1 | New
1021634 |  | Task | Michael will be OOP (PTO) 11-15 May. | EA 15.3 | Done
1021628 | #1021626 | Story | Canada FMS: PI 17 Deliverables placeholder | PI 17 | Invalid | 0
1021627 | #1021626 | Story | Canada FMS: PI 16 Deliverables placeholder | PI 16 | Invalid | 0
1021611 | #383165 | Task | Feature 383165 Submit PDO for Test Report for Nutanix Release to LM needed 9/9/20 | EA 16.5 | New
1021609 | #272509 | Story | Sys Eng Review of PPA UI Cleanup Design | PI 16 | New | 1
1021608 | #383165 | Task | Feature 383165 Submit PDO for SOVT for Nutanix Release to LM needed 7/28/20 | EA 16.3 | New
1021598 | #383165 | Task | Feature 383165 Submit PDO for BESEP for Nutanix Release to LM needed 6/26/20 | EA 16.1 | New
1021596 | #383165 | Task | Feature 383165 Submit PDO for IDP for Nutanix Release to LMm needed 6/26/20 | EA 16.1 | New
1021595 | #1011150 | Task | Feature 1011150: Submit VA for 98-P54107T – GEO – AMS-GS SVD (MPC EAD 14.43) | EA 15.2 | Done
1021594 | #1011150 | Story | Feature 1011150: Create VA for Problem 1021441 (MPC EAD14.43) for EAD 14 | EA 15.2 | Done | 2
1021592 | #1011150 | Story | Feature 1011150: Fix Problem 1021441 (MPC EAD14.43) for EAD 14 | EA 15.2 | Done | 2
1021590 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.5 | EA 16.5 | New | 1
1021589 | #1021499 | Story | Feature 1021499: WWTS Waveform Analysis and Issue Support (5) | EA 16.5 | New | 1
1021588 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.5 | EA 16.5 | New | 3
1021587 | #1021499 | Task | Feature 1021499: SIC LOE TT Support - EA 16.5 | EA 16.5 | New
1021586 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.5 | EA 16.5 | New | 2
1021585 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.5 | EA 16.5 | New | 2
1021584 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.5 | New | 1
1021583 | #1021499 | Story | Feature 1021499: Labradors Trouble Ticket Support - 16.5 | EA 16.5 | New | 1
1021582 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.5 | Invalid | 0
1021581 | #1021499 | Story | Feature 1021499: PI 15 SA TT Support - EA 16.5 | EA 16.5 | New | 1
1021580 | #1021499 | Story | Feature 1021499: SIC LOE - FRB Support - EA 16.5 | EA 16.5 | New | 1
1021579 | #1021499 | Story | Feature 1021499: SIC LOE - MPC Support - EA 16.5 | EA 16.5 | New | 1
1021578 | #1021499 | Story | Feature 1021499: SIC LOE - Site Support and PWI generation - EA 16.5 | EA 16.5 | New | 1
1021577 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.5 | EA 16.5 | New | 1
1021576 | #1021499 | Story | Feature 1021499: MAGIC TT Support - EA 16.5 | EA 16.5 | New | 1
1021575 | #1021499 | Story | Feature 1021499: Alicorn Trouble Ticket Support - 16.4 | EA 16.4 | New | 1
1021574 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.4 | EA 16.4 | New | 1
1021573 | #1021499 | Story | Feature 1021499: WWTS Waveform Analysis and Issue Support (4) | EA 16.4 | New | 1
1021572 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.4 | EA 16.4 | New | 1
1021571 | #1021499 | Task | Feature 1021499: SIC LOE TT Support - EA 16.4 | EA 16.4 | New
1021570 | #1021499 | Task | Feature 1021499: SIC LOE - TT Support - EA 16.4 | EA 16.4 | New
1021569 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.4 | EA 16.4 | New | 1
1021568 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.4 | New | 1
1021567 | #1021499 | Story | Feature 1021499: Labradors Trouble Ticket Support - 16.4 | EA 16.4 | New | 1
1021566 | #1021499 | Story | Feature 1021499: Okapi Trouble Ticket Support - 16.4 | EA 16.4 | New | 1
1021565 | #1021499 | Story | Feature 1021499: PI 15 SA TT Support - EA 16.4 | EA 16.4 | New | 2
1021564 | #1021499 | Story | Feature 1021499: SIC LOE - FRB Support - EA 16.4 | EA 16.4 | New | 1
1021563 | #1021499 | Story | Feature 1021499: SIC LOE - MPC Support - EA 16.4 | EA 16.4 | New | 1
1021562 | #1021499 | Story | Feature 1021499: SIC LOE - Site Support and PWI generation - EA 16.4 | EA 16.4 | New | 1
1021561 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.4 | EA 16.4 | New | 3
1021560 | #1021499 | Story | Feature 1021499: MAGIC TT Support - EA 16.4 | EA 16.4 | New | 1
1021559 | #1021499 | Story | Feature 1021499: Alicorn Trouble Ticket Support - 16.3 | EA 16.3 | New | 1
1021558 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.3 | EA 16.3 | New | 1
1021557 | #1021499 | Story | Feature 1021499: WWTS Waveform Analysis and Issue Support (3) | EA 16.3 | New | 1
1021556 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.3 | EA 16.3 | New | 1
1021555 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.3 | EA 16.3 | New | 5
1021554 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.3 | EA 16.3 | New | 1
1021553 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.3 | New | 1
1021552 | #1021499 | Story | Feature 1021499: Labradors Trouble Ticket Support - 16.3 | EA 16.3 | New | 1
1021551 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.3 | Invalid | 0
1021550 | #1021499 | Story | Feature 1021499: PI 15 SA TT Support - EA 16.3 | EA 16.3 | New | 1
1021549 | #1021499 | Story | Feature 1021499: Okapi Trouble Ticket Support - 16.3 | EA 16.3 | New | 1
1021548 | #1021499 | Story | Feature 1021499: PI 15 SA TT Support - EA 16.3 | EA 16.3 | New | 2
1021547 | #1021499 | Story | Feature 1021499: SIC LOE - FRB Support - EA 16.3 | EA 16.3 | New | 1
1021546 | #1021499 | Story | Feature 1021499: SIC LOE - MPC Support - EA 16.3 | EA 16.3 | New | 1
1021545 | #1021499 | Story | Feature 1021499: SIC LOE - Site Support and PWI generation - EA 16.3 | EA 16.3 | New | 1
1021544 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.3 | EA 16.3 | New | 1
1021543 | #1021499 | Story | Feature 1021499: MAGIC TT Support - EA 16.3 | EA 16.3 | New | 1
1021542 | #1021499 | Story | Feature 1021499: Alicorn Trouble Ticket Support - 16.2 | EA 16.2 | New | 1
1021541 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.2 | EA 16.2 | New | 1
1021540 | #1021499 | Story | Feature 1021499: WWTS Waveform Analysis and Issue Support (2) | EA 16.2 | New | 1
1021539 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.2 | EA 16.2 | New | 1
1021538 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.2 | EA 16.2 | New | 1
1021537 | #1021499 | Story | Feature 1021499: Okapi Trouble Ticket Support - 16.2 | EA 16.2 | New | 1
1021536 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.2 | EA 16.2 | New | 2
1021535 | #1021499 | Story | Feature 1021499: Labradors TT Support - EA 16.2 | EA 16.2 | New | 2
1021534 | #1021499 | Story | Feature 1021499: Laptops Trouble Ticket Support - 16.2 | EA 16.2 | Invalid | 0
1021533 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.2 | New | 1
1021532 | #1021499 | Story | Feature 1021499: PI 16 SA TT Support - EA 16.2 | EA 16.2 | New | 1
1021531 | #1021499 | Story | Feature 1021499: SIC LOE - FRB Support - EA 16.2 | EA 16.2 | New | 2
1021530 | #1021499 | Story | Feature 1021499: SIC LOE - MPC Support - EA 16.2 | EA 16.2 | New | 2
1021529 | #1021499 | Story | Feature 1021499: SIC LOE - Site Support and PWI generation - EA 16.2 | EA 16.2 | New | 1
1021528 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.2 | EA 16.2 | New | 3
1021527 | #1021499 | Story | Feature 1021499: MAGIC TT Support - EA 16.2 | EA 16.2 | New | 1
1021526 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.1 | EA 16.1 | New | 1
1021525 | #1021499 | Story | Feature 1021499: Alicorn Trouble Ticket Support - 16.1 | EA 16.1 | New | 1
1021524 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.1 | EA 16.1 | New | 1
1021523 | #1021499 | Story | Feature 1021499: WWTS Waveform Analysis and Issue Support (1) | EA 16.1 | New | 1
1021522 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.1 | EA 16.1 | New | 1
1021521 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.1 | EA 16.1 | New | 5
1021520 | #1021499 | Task | Feature 1021499: SIC LOE - TT Support - EA 16.1 | EA 16.1 | New
1021519 | #1021499 | Story | Feature 1021499: SIC LOE TT Support - EA 16.1 | EA 16.1 | New | 3
1021518 | #1021499 | Story | Feature 1021499: PI 16 SA TT Support - EA 16.1 | EA 16.1 | New | 1
1021517 | #1021499 | Story | Feature 1021499: Labradors TT Support - EA 16.1 | EA 16.1 | New | 2
1021516 | #1021499 | Story | Feature 1021499: Laptops Trouble Ticket Support - 16.1 | EA 16.1 | Invalid | 0
1021515 | #1021499 | Story | Feature 1021499: Okapi Trouble Ticket Support - 16.1 | EA 16.1 | New | 1
1021514 | #1021499 | Story | Feature 1021499: WWTS Trouble Ticket Support | EA 16.1 | Invalid | 0
1021513 | #1021499 | Story | Feature 1021499: MAGIC TT Support - EA 16.1 | EA 16.1 | New | 1
1021512 | #1021499 | Story | Feature 1021499: PI 15 SA TT Support - EA 16.1 | EA 16.1 | New | 2
1021511 | #1021499 | Story | Feature 1021499: SIC LOE - FRB Support - EA 16.1 | EA 16.1 | New | 2
1021510 | #1021499 | Story | Feature 1021499: SIC LOE - MPC Support - EA 16.1 | EA 16.1 | New | 1
1021509 | #1021499 | Story | Feature 1021499: SIC LOE - Site Support and PWI generation - EA 16.1 | EA 16.1 | New | 1
1021508 | #1021499 | Story | Feature 1021499: SIC LOE - TT Support - EA 16.1 | EA 16.1 | New | 3
1021499 | #245568 | Feature | TT support; ID, report, prioritize, and resolve incidents (recurring) - PI 16 | PI 16 - Candidate | Approved
1021497 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.5 | EA 16.5 | New | 1
1021496 | #1021439 | Story | Feature 1021439: Octopi PWI Triage/Assessment Support EA 16.5 | EA 16.5 | New | 1
1021495 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.5 | New | 1
1021494 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.5 | New | 1
1021493 | #1021439 | Story | Feature 1021439: SIC PWI triage/assessment support 16.5 | EA 16.5 | New | 1
1021492 | #1021439 | Story | Feature 1021439: Falcons PWI Triage/Assessment Support EA 16.5 | EA 16.5 | New | 1
1021491 | #1021439 | Story | Feature 1021439: Cyber PWI Triage/Assessment Support - 16.5 | EA 16.5 | New | 1
1021490 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.5 | EA 16.5 | New | 1
1021489 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.4 | EA 16.4 | New | 2
1021488 | #1021439 | Story | Feature 1021439: Octopi PWI Triage/Assessment Support EA 16.4 | EA 16.4 | New | 1
1021487 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.4 | New | 1
1021486 | #1021439 | Story | Feature 1021439: PWI Triage/Assessment Support EA 16.4 (LOE) | EA 16.4 | New | 1
1021485 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.4 | New | 1
1021484 | #1021439 | Story | Feature 1021439: SIC PWI triage/assessment support 16.4 | EA 16.4 | New | 1
1021483 | #1021439 | Story | Feature 1021439: Okapi PWI Triage/Assessment Support EA 16.4 | EA 16.4 | New | 1
1021482 | #1021439 | Story | Feature 1021439: Falcons PWI Triage/Assessment Support EA 16.4 | EA 16.4 | New | 1
1021481 | #1021439 | Story | Feature 1021439: Cyber PWI Triage/Assessment Support - 16.4 | EA 16.4 | New | 1
1021480 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.4 | EA 16.4 | New | 1
1021479 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.3 | EA 16.3 | New | 2
1021478 | #1021439 | Story | Feature 1021439: Octopi PWI Triage/Assessment Support EA 16.3 | EA 16.3 | New | 1
1021477 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.3 | New | 1
1021476 | #1021439 | Story | Feature 1021439: PWI Triage/Assessment Support EA 16.3 (LOE) | EA 16.3 | New | 1
1021475 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.3 | New | 1
1021474 | #1021439 | Story | Feature 1021439: Cyber PWI Triage/Assessment Support - 16.3 | EA 16.3 | New | 1
1021473 | #1021439 | Story | Feature 1021439: SIC PWI triage/assessment support 16.3 | EA 16.3 | New | 1
1021472 | #1021439 | Story | Feature 1021439: Okapi PWI Triage/Assessment Support EA 16.3 | EA 16.3 | New | 1
1021471 | #1021439 | Story | Feature 1021439: Falcons PWI Triage/Assessment Support EA 16.3 | EA 16.3 | New | 1
1021470 | #1021439 | Story | Feature 1021439: CSE PWI Triage/Assessment Support | EA 16.4 | New | 1
1021469 | #1021439 | Story | Feature 1021439: CSE PWI Triage/Assessment Support | EA 16.3 | New | 1
1021468 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.3 | EA 16.3 | New | 1
1021467 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.2 | EA 16.2 | New | 2
1021466 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.2 (Valverde) | EA 16.2 | New | 1
1021465 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.2 (Aidan) | EA 16.2 | New | 1
1021464 | #1021439 | Story | Feature 1021439: Octopi PWI Triage/Assessment Support EA 16.2 | EA 16.2 | New | 1
1021463 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.2 | New | 1
1021462 | #1021439 | Story | Feature 1021439: PWI Triage/Assessment Support EA 16.2 (LOE) | EA 16.2 | New | 1
1021461 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.2 | New | 1
1021460 | #1021439 | Story | Feature 1021439: SIC PWI triage/assessment support 16.2 | EA 16.2 | New | 1
1021459 | #1021439 | Story | Feature 1021439: Okapi PWI Triage/Assessment Support EA 16.2 | EA 16.2 | New | 1
1021458 | #1021439 | Story | Feature 1021439: Falcons PWI Triage/Assessment Support EA 16.2 | EA 16.2 | New | 1
1021457 | #1021439 | Story | Feature 1021439: CSE PWI Triage/Assessment Support | EA 16.2 | New | 1
1021456 | #1021439 | Story | Feature 1021439: Cyber PWI Triage/Assessment Support - 16.2 | EA 16.2 | New | 1
1021455 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.2 (Anil) | EA 16.2 | New | 1
1021454 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.1 | EA 16.1 | New | 5
1021453 | #1021439 | Story | Feature 1021439: SA PWI Support - EA 16.1 | EA 16.1 | Invalid | 0
1021452 | #1021439 | Story | Feature 1021439: Octopi PWI Triage/Assessment Support EA 16.1 | EA 16.1 | New | 1
1021451 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.1 | New | 1
1021450 | #1021439 | Story | Feature 1021439: PWI Triage/Assessment Support EA 16.1 (LOE) | EA 16.1 | New | 1
1021449 | #1021439 | Story | Feature 1021439: WWTS PWI Triage/Assessment Support | EA 16.1 | New | 1
1021448 | #1021439 | Story | Feature 1021439: Cyber PWI Triage/Assessment Support - 16.1 | EA 16.1 | New | 1
1021447 | #1021439 | Story | Feature 1021439: SIC PWI triage/assessment support 16.1 | EA 16.1 | New | 1
1021446 | #1021439 | Story | Feature 1021439: Okapi PWI Triage/Assessment Support EA 16.1 | EA 16.1 | New | 1
1021445 | #1021439 | Story | Feature 1021439: Falcons PWI Triage/Assessment Support EA 16.1 | EA 16.1 | New | 1
1021444 | #1021439 | Story | Feature 1021439: CSE PWI Triage/Assessment Support | EA 16.1 | New | 1
1021443 | #1021439 | Story | Feature 1021439: MAGIC PWI Triage/Assessment Support - EA 16.1 | EA 16.1 | New | 1
1021441 | #1011150 | Problem | Fix MUOS Geo TT # INC000004746477 | PI 15 | Closed
1021439 | #243395 | Feature | PWI triage and assessment support (recurring) - PI 16 | PI 16 - Candidate | Approved
1021362 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.5 | EA 16.5 | New | 2
1021361 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.5 | EA 16.5 | New | 2
1021360 | #1021122 | Story | Collect metrics for reporting and communication to LM and PMW-146 stakeholders - monthly | EA 16.4 | New | 2
1021359 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.4 | EA 16.4 | New | 2
1021358 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.4 | EA 16.4 | New | 2
1021357 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.3 | EA 16.3 | New | 2
1021356 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.3 | EA 16.3 | New | 2
1021355 | #1021122 | Story | Collect metrics for reporting and communication to LM and PMW-146 stakeholders - monthly | EA 16.2 | New | 2
1021354 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.2 | EA 16.2 | New | 2
1021353 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.2 | EA 16.2 | New | 2
1021352 | #1021122 | Story | Provide support for metric following analysis - EA 16.2 | EA 16.2 | New | 1
1021351 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.1 | EA 16.1 | New | 2
1021350 | #1021122 | Story | Analyze data, Identify issues and communicate metrics - EA 16.1 | EA 16.1 | New | 2
1021335 | #1015439 | Story | TO-6 Respond to questions from ATT | EA 15.5 | New | 1
1021334 | #1015439 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 15.5 | New | 1
1021333 | #1015439 | Story | TO-6 Respond to questions from ATT - SIC SME Support | EA 15.5 | New | 1
1021331 | #1015439 | Story | Feature 1015439: TO-6 Respond to questions from ATT - WWTS SME Support | EA 15.5 | New | 1
1021304 | #1021297 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - 16.5 | EA 16.5 | New | 3
1021302 | #1021297 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - 16.4 | EA 16.4 | New | 3
1021301 | #1021297 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - 16.3 | EA 16.3 | New | 3
1021300 | #1021297 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - 16.2 | EA 16.2 | New | 3
1021298 | #1021297 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - 16.1 | EA 16.1 | New | 3
1021297 | #262134 | Feature | Lab – TXO Ericsson – Test Engineering Testing of Ericsson parts in support of 2030 ILS supply | PI 16 - Candidate | Approved
1021296 | #1021254 | Feature | Explore the plan for how to improve process for Repair and Replace procedures, troubleshooting procedure and reboots & how to institutionalize the changes going forward | Unassigned | Rejected
1021236 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support (16.3) | EA 16.3 | New | 3
1021235 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support (16.2) | EA 16.2 | New | 2
1021205 | #1021169 | Story | Feature 1021169: Perform Iterative Implementation, Integration, development Testing including updating design (Part 2 of 2) | EA 16.2 | New | 8
1021204 | #1021169 | Story | Feature 1021169: Execute STCD Feature Integration and testing including STCD updates identified (Part 2 of 2) | EA 16.4 | New | 2
1021193 | #383958 | Story | Feature 383958: Bulk SAR Code Review (Part 1 of 2) | EA 15.3 | Done | 1
1021183 | #1021169 | Story | Feature 1021169: Initiate CM PDO Processing for all CI's | EA 16.5 | New | 1
1021182 | #1021169 | Story | Feature 1021169: Prep and Perform Feature Demo – Customer Demo Event | EA 16.5 | New | 1 | #1021183
1021181 | #1021169 | Story | Feature 1021169: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 16.4 | New | 2 | #1021182
1021180 | #1021169 | Story | Feature 1021169: Execute STCD Feature Integration and testing including STCD updates identified (Part 1 of 2) | EA 16.3 | New | 5 | #1021182
1021179 | #1021169 | Story | Feature 1021169: Provide Development inputs to common documents | EA 16.4 | New | 2 | #1021182
1021178 | #1021169 | Story | Feature 1021169: Incorporation of I-Level Appendix(99-P61689A) Updates and Integration Support for ETI - External Interference Coefficients Calculation Procedure . | EA 16.4 | New | 1
1021177 | #1021169 | Story | Feature 1021169: Review Ext Interference Coefficients Procedure for Style Guide Compliance and Dry Runs | EA 16.3 | New | 3
1021176 | #1021169 | Story | Feature 1021169: Develop I-Level Appendix(99-P61689A) and Perform Development Testing | EA 16.3 | New | 3 | #1021182
1021175 | #1021169 | Story | Feature 1021169: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 16.3 | New | 1 | #1021182
1021174 | #1021169 | Story | Feature 1021169: Perform Iterative Implementation, Integration, development Testing including updating design (Part 1 of 2) | EA 16.1 | New | 1 | #1021182
1021173 | #1021169 | Story | Feature 1021169: Provide Deployment Notes and Operator Impact Inputs | EA 16.5 | New | 1 | #1021182
1021172 | #1021169 | Story | Feature 1021169: Create STCD and review with stakeholders | EA 16.1 | New | 3 | #1021180 #1021174 #1021182 #1021181
1021171 | #1021169 | Story | Feature 1021169: Document Initial capability specification and detailed design to start Implementation | EA 16.1 | New | 3 | #1021174 #1021172
1021170 | #1021169 | Task | Feature 1021169: Hold Feature Review with SMEs | EA 16.1 | New
1021169 | #1022632 | Feature | ETI - External Interference Coefficients Calculation Procedure | PI 16 | Approved
1021137 | #1014596 | Story | Feature 1014596: Support Channel Processor Dev (Part 3) | EA 15.4 | New | 1
1021136 | #1014596 | Story | Feature 1014596: Support Channel Processor Dev (Part 2) | EA 15.3 | Done | 1
1021135 | #1014596 | Story | Feature 1014596: Support Channel Processor Dev (Part 1) | EA 15.2 | Done | 1
1021122 | #245568 | Feature | Identify and communicate top issues (recurring) - PI 16 | PI 16 - Candidate | Approved
1021075 |  | Task | Plan: End Feature 1008506 | Unassigned | Invalid
1021072 |  | Task | Plan: Start Feature Close-out | Unassigned | Invalid
1021070 |  | Task | Plan: PWIs Completed | Unassigned | Invalid
1021067 |  | Task | Plan: Start PWIs | Unassigned | Invalid
1021066 |  | Task | Plan: PI 15 Troubleshooting Procedures Demo Complete | Unassigned | Invalid
1021062 |  | Task | Plan: PI 16 Troubleshooting Procedures Dry Run Complete | Unassigned | Invalid
1021061 |  | Task | Plan: PI 15 Troubleshooting Procedures Dry Run Complete | Unassigned | Invalid
1021059 | #395114 | Task | Feature 395114: Submit PDO for 99-P53447E – ILS - FRACAS | EA 15.5 | Done
1021058 |  | Task | Plan: Troubleshooting Procedures Reviewed | Unassigned | Invalid
1021057 |  | Task | Plan: PI 16 Troubleshooting Procedures Written | Unassigned | Invalid
1021055 |  | Task | Plan: PI 15 Troubleshooting Procedures Written | Unassigned | Invalid
1021054 |  | Task | Plan: Start PI 15 Troubleshooting Procedures | Unassigned | Invalid
1021053 |  | Task | Plan: Recovery Procedures Dry Run Completed | Unassigned | Invalid
1021052 |  | Task | Plan: Recovery Procedures Reviewed | Unassigned | Invalid
1021050 |  | Task | Plan: Recovery Procedures Written | Unassigned | Invalid
1021049 |  | Task | Plan: Start Recovery Procedures | Unassigned | Invalid
1021046 |  | Task | Plan: Start Feature 1008506 | Unassigned | Invalid
1021044 | #243427 | Feature | ETI - Polatis 6000 Switch Updates (IA, Power Supply) Integrate, Test, and Release | PI 17 | Approved
1021042 | #1015153 | Task | Feature 1015153: Submit PDO for 98-P55613M ET SVD | EA 15.4 | Done
1021038 |  | Feature | Resolving Okapi PWIs addressing Interior routers and HLR time synch faults for PI 16 | PI 16 | Rejected
1021037 | #1023491 | Feature | TO-04 Sustain: Resolve interior routing issues resulting in routing of packets to incorrect interfaces, and HLR time sync faults. | PI 16 - Candidate | Approved
1021028 | #1020797 | Story | Regression testing to ensure SMDC customer dashboards still work with our changes before we deploy | EA 16.5 | New | 2
1021011 | #1020011 | Story | Patch Gen 2 ETT Laptops in the Depot | PI 16 | New | 2 | #1020993
1021010 | #377437 | Task | Feature 377437: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | Done
1021009 | #1004171 | Task | Feature 1004171: Submit PDO for RNC CI: 98-P53511T-GTS-RN-RNC-SVD | EA 15.4 | New
1021007 | #332951 | Task | Feature 332951: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | In Development
1021006 | #396669 | Task | Feature 396669: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | In Development
1021004 | #393265 | Task | Feature 393265: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | New
1020993 | #1019781 | Task | Feature 1019781: Ship Gen 2 ETT Laptops to Site | PI 16 | New
1020992 | #1019781 | Story | Feature 1019781: Upgrade Gen 2 ETT Laptops | PI 16 | New | 2 | #1020993
1020986 | #1014252 | Task | Feature 1014252: Submit PDO for 98-P59419M - NMS - NM - OTAP - SVD | EA 15.4 | New
1020985 | #381524 | Task | Feature 381524: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | In Development
1020984 | #383958 | Task | Feature 383958: Submit PDO for 99-P53449E - ILS - IETM | EA 15.4 | In Development
1020983 | #342163 | Task | Feature 342163: Submit PDO for 99-P53449E - ILS - IETM | EA 15.3 | Done
1020967 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - Carl (16.1) | EA 16.1 | New | 1
1020966 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (16.1) | EA 16.1 | New | 2
1020965 | #1020849 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (16.1) | EA 16.1 | New | 2
1020964 | #1020849 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(16.1) | EA 16.1 | New | 1
1020963 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (16.1) | EA 16.1 | New | 2
1020962 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (16.1) | EA 16.1 | New | 3
1020961 | #1020849 | Story | Feature 1020849: Lab - Maintain OTA Call Banks - SME Support - Loretta (16.1) | EA 16.1 | Invalid | 0
1020960 | #1020849 | Story | Lab - Maintain OTA Call Banks - Carl (16.1) | EA 16.1 | New | 3
1020959 | #1020849 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (16.1) | EA 16.1 | New | 2
1020958 | #1020849 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (16.1) | EA 16.1 | New | 5
1020957 | #1020849 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (16.1) | EA 16.1 | New | 5
1020956 | #1020849 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (16.1) | EA 16.1 | New | 2
1020955 | #1020849 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (16.1) | EA 16.1 | New | 2
1020954 | #1020849 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (16.1) | EA 16.1 | New | 1
1020953 | #1020849 | Story | Feature 1020849: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (16.1) | EA 16.1 | New | 1
1020952 | #1020849 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (16.1) | EA 16.1 | New | 1
1020951 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (16.2) | EA 16.2 | New | 1
1020950 | #1020849 | Story | Lab - Maintain Labs - NMS SME Support - Colin (16.1) | EA 16.1 | New | 1
1020949 | #1020849 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (16.1) | EA 16.1 | New | 5
1020948 | #1020849 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (16.1) | EA 16.1 | New | 5
1020947 | #1020849 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (16.1) | EA 16.1 | New | 1
1020946 | #1020849 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (16.2) | EA 16.2 | New | 2
1020945 | #1020849 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(16.2) | EA 16.2 | New | 1
1020944 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (16.2) | EA 16.2 | New | 2
1020943 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (16.2) | EA 16.2 | New | 3
1020942 | #1020849 | Story | Lab - Maintain OTA Call Banks - Carl (16.2) | EA 16.2 | New | 3
1020941 | #1020849 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (16.2) | EA 16.2 | New | 2
1020940 | #1020849 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (16.2) | EA 16.2 | New | 8
1020939 | #1020849 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (16.2) | EA 16.2 | New | 5
1020938 | #1020849 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (16.2) | EA 16.2 | New | 2
1020937 | #1020849 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (16.2) | EA 16.2 | New | 2
1020936 | #1020849 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (16.2) | EA 16.2 | New | 1
1020935 | #1020849 | Story | Feature 1020489: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (16.2) | EA 16.2 | New | 1
1020934 | #1020849 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (16.2) | EA 16.2 | New | 1
1020933 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (16.3) | EA 16.3 | New | 1
1020932 | #1020849 | Story | Lab - Maintain Labs - NMS SME Support - McCord (Tape) (16.2) | EA 16.2 | New | 1
1020931 | #1020849 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (16.2) | EA 16.2 | New | 5
1020930 | #1020849 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (16.2) | EA 16.2 | New | 5
1020929 | #1020849 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (16.2) | EA 16.2 | New | 1
1020928 | #1020849 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (16.3) | EA 16.3 | New | 3
1020927 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (16.3) | EA 16.3 | New | 2
1020926 | #1020849 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (16.3) | EA 16.3 | New | 2
1020925 | #1020849 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(16.3) | EA 16.3 | New | 1
1020924 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (16.3) | EA 16.3 | New | 2
1020923 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (16.3) | EA 16.3 | New | 3
1020922 | #1020849 | Story | Feature 1020849: Lab - Maintain OTA Call Banks - SME Support - Loretta (16.3) | EA 16.3 | Invalid | 0
1020921 | #1020849 | Story | Lab - Maintain OTA Call Banks - Carl (16.3) | EA 16.3 | New | 3
1020920 | #1020849 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (16.3) | EA 16.3 | New | 2
1020919 | #1020849 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (16.3) | EA 16.3 | New | 5
1020918 | #1020849 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (16.3) | EA 16.3 | New | 2
1020917 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (16.2) | EA 16.2 | New | 2
1020916 | #1020849 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (16.3) | EA 16.3 | New | 2
1020915 | #1020849 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (16.3) | EA 16.3 | New | 1
1020914 | #1020849 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (16.3) | EA 16.3 | New | 1
1020913 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (16.4) | EA 16.4 | New | 1
1020912 | #1020849 | Story | Lab - Maintain Labs - NMS SME Support - McCord (tape) (16.3) | EA 16.3 | New | 1
1020911 | #1020849 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (16.3) | EA 16.3 | New | 5
1020910 | #1020849 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (16.3) | EA 16.3 | New | 5
1020909 | #1020849 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (16.3) | EA 16.3 | New | 1
1020908 | #1020849 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (16.4) | EA 16.4 | New | 2
1020907 | #1020849 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(16.4) | EA 16.4 | New | 1
1020906 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (16.4) | EA 16.4 | New | 2
1020905 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (16.4) | EA 16.4 | New | 3
1020904 | #1020849 | Story | Lab - Maintain OTA Call Banks - Carl (16.4) | EA 16.4 | New | 3
1020903 | #1020849 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (16.4) | EA 16.4 | New | 2
1020902 | #1020849 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (16.4) | EA 16.4 | New | 5
1020901 | #1020849 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (16.4) | EA 16.4 | New | 3
1020900 | #1020849 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (16.4) | EA 16.4 | New | 2
1020899 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (16.4) | EA 16.4 | New | 2
1020898 | #1020849 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (16.4) | EA 16.4 | New | 2
1020897 | #1020849 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (16.4) | EA 16.4 | New | 1
1020896 | #1020849 | Story | Feature 1020849: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (16.4) | EA 16.4 | New | 1
1020895 | #1020849 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (16.4) | EA 16.4 | New | 1
1020894 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (16.5) | EA 16.5 | New | 1
1020893 | #1020849 | Story | Lab - Maintain Labs - NMS SME Support - Colin (16.4) | EA 16.4 | New | 1
1020892 | #1020849 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (16.4) | EA 16.4 | New | 5
1020891 | #1020849 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (16.4) | EA 16.4 | New | 5
1020890 | #1020849 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (16.4) | EA 16.4 | New | 1
1020889 | #1020849 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (16.5) | EA 16.5 | New | 2
1020888 | #1020849 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(16.5) | EA 16.5 | New | 1
1020887 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (16.5) | EA 16.5 | New | 2
1020886 | #1020849 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (16.5) | EA 16.5 | New | 3
1020885 | #1020849 | Story | Feature 1020849: Lab - Maintain OTA Call Banks - SME Support - Loretta (16.1) | EA 16.1 | New | 1
1020884 | #1020849 | Story | Lab - Maintain OTA Call Banks - Carl (16.5) | EA 16.5 | New | 3
1020883 | #1020849 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (16.5) | EA 16.5 | New | 1
1020882 | #1020849 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (16.5) | EA 16.5 | New | 5
1020881 | #1020849 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (16.5) | EA 16.5 | New | 3
1020880 | #1020849 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (16.5) | EA 16.5 | New | 2
1020879 | #1020849 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (16.5) | EA 16.5 | New | 2
1020878 | #1020849 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (16.5) | EA 16.5 | New | 1
1020877 | #1020849 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (16.5) | EA 16.5 | New | 1
1020876 | #1020849 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (16.5) | EA 16.5 | New | 1
1020875 | #1020849 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (16.1) | EA 16.1 | New | 1
1020874 | #1020849 | Story | Lab - Maintain Labs - NMS SME Support - Colin (16.5) | EA 16.5 | New | 1
1020873 | #1020849 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (16.5) | EA 16.5 | New | 5
1020872 | #1020849 | Story | Feature 1013534: Lab - Maintain Labs - Lab Floor Plan Updates (PI-16) | EA 16.5 | New | 2
1020871 | #1020849 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (16.5) | EA 16.5 | New | 5
1020870 | #1020849 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (16.5) | EA 16.5 | New | 1
1020869 | #1020849 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (16.1) | EA 16.1 | New | 1
1020868 | #1020849 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (16.2) | EA 16.2 | New | 1
1020867 | #1020849 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (16.3) | EA 16.3 | New | 1
1020866 | #1020849 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (16.4) | EA 16.4 | New | 1
1020865 | #1020849 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (16.5) | EA 16.5 | New | 1
1020864 | #1020849 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (16.3) | EA 16.3 | New | 1
1020863 | #1020849 | Story | Feature 1020849: Lab - Maintain OTA Call Banks - SME Support - Loretta (16.2) | EA 16.2 | New | 1
1020862 | #1020849 | Story | Feature 1020849: Lab - Maintain OTA Call Banks - SME Support - Loretta (16.4) | EA 16.4 | New | 1
1020861 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (16.1) | EA 16.1 | Invalid | 0
1020860 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (16.2) | EA 16.2 | Invalid | 0
1020859 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (16.3) | EA 16.3 | Invalid | 0
1020858 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (16.4) | EA 16.4 | Invalid | 0
1020857 | #1020849 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (16.5) | EA 16.5 | Invalid | 0
1020856 | #1020849 | Story | Lab - Maintain Labs - DSN GW SME Support - Glen L. (16.1) | EA 16.1 | New | 1
1020855 | #1020849 | Story | Lab - Debug SWIT RNC06/Corben and Core network configurations | EA 16.2 | New | 5
1020849 |  | Feature | Lab - Maintain Labs for Integration, Testing and Test Events with minimal down time (PI-16) | PI 16 - Candidate | Approved
1020847 | #1015153 | Story | Feature 1015153:Help support rebooting a Linux server in support of verifying boot images are working in the target system | EA 15.3 | Done | 1
1020842 | #1020797 | Story | Release Regression - NMS Automation daily runs (xx.1) | EA 16.1 | New | 5
1020841 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 16.1 | New | 5
1020840 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 16.1 | New | 5
1020839 | #1020797 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.1) | EA 16.1 | New | 1
1020838 | #1020797 | Story | Release Regression - EAD15 Regression Test Selection (xx.1) | EA 16.1 | New | 2
1020837 | #1020797 | Story | Release Regression - Call Automation (16.1) | EA 16.1 | New | 1
1020836 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.1) | EA 16.1 | New | 1
1020835 | #1020797 | Story | Release Regression - NMS Automation daily runs (xx.2) | EA 16.2 | New | 5
1020834 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 16.2 | New | 5
1020833 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 16.2 | New | 5
1020832 | #1020797 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.2) | EA 16.2 | New | 1
1020831 | #1020797 | Story | Release Regression - Call Automation (16.2) | EA 16.2 | New | 1
1020830 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.2) | EA 16.2 | New | 1
1020829 | #1020797 | Story | Release Regression - NMS Automation | EA 16.3 | New | 1
1020828 | #1020797 | Story | Release Regression - NMS Automation daily runs (xx.3) | EA 16.3 | New | 5
1020827 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 16.3 | New | 5
1020826 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 16.3 | New | 5
1020825 | #1020797 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.3) | EA 16.3 | New | 1
1020824 | #1020797 | Story | Release Regression - Call Automation (xx.3) | EA 16.3 | New | 1
1020823 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.3) | EA 16.3 | New | 1
1020822 | #1020797 | Story | Release Regression - NMS Automation daily runs (xx.4) | EA 16.4 | New | 5
1020821 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 16.4 | New | 5
1020820 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 16.4 | New | 5
1020819 | #1020797 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.4) | EA 16.4 | New | 1
1020818 | #1020797 | Story | Release Regression - Call Automation (xx.4) | EA 16.4 | New | 1
1020817 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.4) | EA 16.4 | New | 1
1020816 | #1020797 | Story | Release Regression - NMS Automation daily runs (xx.5) | EA 16.5 | New | 1
1020815 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 16.5 | New | 1
1020814 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 16.5 | New | 2
1020813 | #1020797 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.5) | EA 16.5 | New | 1
1020812 | #1020797 | Story | Release Regression - Call Automation (xx.5) | EA 16.5 | New | 1
1020811 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.5) | EA 16.5 | New | 1
1020810 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.1) | EA 16.1 | New | 1
1020809 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.2) | EA 16.2 | New | 2
1020808 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.3) | EA 16.3 | New | 1
1020807 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.4) | EA 16.4 | New | 1
1020806 | #1020797 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.5) | EA 16.5 | New | 1
1020805 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 16.1 | New | 2
1020804 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 16.4 | New | 1
1020803 | #1020797 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 16.4 | New | 1
1020802 | #1020797 | Task | Feature 1020797: Hardware/Software Procurement Request for Release Regression - EAD 17 Regression Testing (PI16) | PI 16 | New
1020801 | #1020797 | Task | Feature 1020797: Procurement Verification and Approvals for Release Regression - EAD 17 Regression Testing (PI16) | PI 16 | New
1020800 | #1020797 | Story | Release Regression - Automate New PI16 Manual Test | EA 16.1 | New | 2
1020797 |  | Feature | Release Regression - EAD 17 Regression Testing (PI16) | PI 16 - Candidate | Approved
1020796 | #1015153 | Story | Feature 1015153:Help support rebooting a Solaris server in support of verifying boot images are working in the target system | EA 15.3 | Done | 1
1020780 | #1007900 | Story | Feature 1007900: Continued STCD Testing of SVD and IETM procedures | EA 15.3 | Done | 5
1020763 | #1020744 | Story | WF CLL Build Support for EA 16.5 | EA 16.5 | New | 2
1020762 | #1020744 | Story | WF CLL Build Support for EA 16.4 | EA 16.4 | New | 2
1020761 | #1020744 | Story | WF CLL Build Support for EA 16.3 | EA 16.3 | New | 2
1020760 | #1020744 | Story | WF CLL Build Support for EA 16.2 | EA 16.2 | New | 2
1020759 | #1020744 | Story | WF CLL Build Support for EA 16.1 | EA 16.1 | New | 2
1020758 | #1020753 | Story | Tools Team Support / LOE for SDE/ODE for EA 16.5 | EA 16.5 | New | 5
1020757 | #1020753 | Story | Tools Team Support / LOE for SDE/ODE for EA 16.4 | EA 16.4 | New | 5
1020756 | #1020753 | Story | Tools Team Support / LOE for SDE/ODE for EA 16.3 | EA 16.3 | New | 5
1020755 | #1020753 | Story | Tools Team Support / LOE for SDE/ODE for EA 16.2 | EA 16.2 | New | 5
1020754 | #1020753 | Story | Tools Team Support / LOE for SDE/ODE for EA 16.1 | EA 16.1 | New | 5
1020753 | #1022632 | Feature | Tools Team Support / LOE for SDE/ODE Environment in PI 16 (Recurring) | EA 16.5 | Approved
1020752 | #1020744 | Story | Tools Team Support / LOE for RAN/RDE for EA 16.5 | EA 16.5 | New | 3
1020751 | #1020744 | Story | Tools Team Support / LOE for RAN/RDE for EA 16.4 | EA 16.4 | New | 3
1020750 | #1020744 | Story | Tools Team Support / LOE for RAN/RDE for EA 16.3 | EA 16.3 | New | 3
1020747 | #1020744 | Story | Tools Team Support / LOE for RAN/RDE for EA 16.2 | EA 16.2 | New | 3
1020745 | #1020744 | Story | Tools Team Support / LOE for RAN/RDE for EA 16.1 | EA 16.1 | New | 3
1020744 | #1022632 | Feature | Tools Team Support / LOE for RAN/RDE Environment in PI 16 (Recurring) | EA 16.5 | Approved
1020724 | #1012748 | Story | UX Support of Canada Capability Outline | EA 15.2 | Done | 2
1020723 | #1007900 | Story | Implement and Test Problem 1001826 for Monitor ePolicy Orchestrator – Normal Operation Procedure for step 2.2.9.4 should be the same as 2.2.9.5 | PI 16 | New | 5
1020718 |  | Task | CM Release of 98-P55506M - Network - HAIPEMgmt - SVD (TEST: new CI Release Tracking Process) | Unassigned | Invalid
1020710 | #1020604 | Feature | TO-9: Develop System Test Cases for ULX System | PI 17 | Analyzing
1020709 | #1020602 | Feature | TO-9: Integrate and Perform Component Level Testing of RF Processor | PI 17 | Analyzing
1020708 | #1020602 | Feature | TO-9: Integrate and Perform Component Level Testing of Preprocessor | PI 17 | Analyzing
1020707 | #1020599 | Feature | TO-9: Build ULX Deliverable System 1 and 2 | PI 17 | Analyzing
1020706 | #1020599 | Feature | TO-9: Develop Release Strategy and Tools for ULX Release | PI 17 | Analyzing
1020705 | #1020597 | Feature | TO-9: Integrate and Component Test of Channel Processor | PI 17 | Analyzing
1020703 | #1020602 | Feature | TO-9: Develop and Test ETISP changes needed for ULX | PI 16 - Candidate | Approved
1020702 | #1020597 | Feature | TO-9: Integrate and Perform Component Level Testing of ULX Manager | PI 16 - Candidate | Approved
1020701 | #1020597 | Feature | TO-9: Integrate and Perform Component Level Testing of Monitor and Control | PI 16 - Candidate | Approved
1020700 | #1020597 | Feature | TO-9: Develop and Unit Test Channel Processor | PI 16 - Candidate | Approved
1020595 |  | Problem | Keysets gets stuck in deprovisioning. Requires manual database update to correct. | Unassigned | Triage
1020520 | #1003390 | Story | Feature 1003390: Finish the Updates of Firewall Network SVD for MGB | EA 15.4 | Implementing | 3
1020516 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Radio simscript reconfig to change the area code & test support | EA 16.3 | New | 1
1020515 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: DSN GW config prep | EA 16.2 | New | 1
1020514 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: CSCF config prep | EA 16.2 | New | 1
1020513 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: HSS and Load Balancer config prep | EA 16.2 | New | 1
1020512 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Rerun and capture results | EA 16.4 | Invalid | 0
1020511 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Make necessary data changes for test | EA 16.4 | Invalid | 0
1020510 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: CSCF Reconfig & test support | EA 16.3 | New | 2
1020509 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: HSS/Load Balancer Reconfig & test support | EA 16.3 | New | 2
1020508 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Make necessary data changes for test | EA 16.3 | Invalid | 0
1020507 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Make necessary data changes for test | EA 16.3 | Invalid | 0
1020506 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Make necessary data changes for test | EA 16.3 | Invalid | 0
1020501 | #1007900 | Task | 1007900: Task for HBSS SVD for Disable of LLMNR and NetBIOS Cyber Bluesheet feature | EA 15.2 | Done
1020489 | #380808 | Story | Feature 380808: Update the Tectia SVD to address Tectia Migration for NMF Workstations | EA 15.3 | Done | 5
1020429 | #1016383 | Story | Resolve Problem 329720 B3 NMS FM - Backup precision probe does not take over when primary probe is down | PI 16 | Invalid | 0
1020417 | #1020412 | Story | Feature 1020412: NW RF Alignment: Prep Tasks to Facilitate Trip (Nadolski) | EA 16.4 | New | 2
1020416 | #1020412 | Story | Feature 1020412: NW RF Alignment: Prep Tasks to Facilitate Trip (Jones) | EA 16.4 | New | 2
1020415 | #1020412 | Story | Feature 1020412: NW RF Alignment: Prep Tasks to Facilitate Trip (Nadolski) | EA 16.3 | New | 1
1020414 | #1020412 | Story | Feature 1020412: NW RF Alignment: Prep Tasks to Facilitate Trip (Jones) | EA 16.3 | New | 2
1020413 | #1020412 | Story | Feature 1020412: NW RF Alignment: Logistics Actions to Support Activities | EA 16.2 | New | 2
1020409 | #1020303 | Story | Feature 1020303: Participate in Dry Runs of Procedures | PI 16 | New | 1
1020408 | #1020303 | Story | Feature 1020303: Training Updates to Ensure O-Level Procedures are Properly Updated | PI 16 | Invalid | 0
1020386 |  | Problem | MTC/AJM Laptop Hostnames Incorrect in Anti-Virus Updates- Normal Operation Procedure | Unassigned | Triage
1020372 | #1020303 | Story | Feature 1020303: Update the JDTA for MUOS RAF GPS Antenna | PI 16 | Invalid | 0
1020363 | #1020303 | Story | Feature 1020303: Create CoCo Review for the Updates Parts Lists and Drawings Related to MUOS RAF GPS Antenna | PI 16 | New | 1
1020358 | #1020303 | Story | Feature 1020303: Provide Deployment Notes and Operator Impact Inputs for MUOS RAF GPS Antenna (Labradors) | PI 16 | Invalid | 0
1020355 | #1020303 | Task | Feature 1020303: Initiate CM PDO Processing for all CI's | PI 16 | New
1020354 | #1020303 | Story | Prep and Perform Feature Demo – Customer Demo Event for Feature 1020303 MUOS RAF GPS Antenna | PI 16 | New | 1 | #1020355
1020352 | #1020303 | Story | Feature 1020303: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 2 | #1020354
1020350 | #1020303 | Story | Feature 1020303: Incorporation of IETM Updates and Integration Support for MUOS RAF GPS Antenna | PI 16 | New | 1
1020349 | #1020303 | Story | Feature 1020303: UX Research and Design Support for MUOS RAF GPS Antenna | PI 16 | Invalid | 0
1020348 | #1020303 | Story | Feature 1020303: Develop IETMs and Perform Development Testing for MUOS RAF GPS Antenna | PI 16 | New | 3 | #1020354
1020347 | #1020303 | Story | Feature 1020303: Update Parts Lists and Drawings Related to MUOS RAF GPS Antenna | PI 16 | New | 3
1020346 | #1020303 | Story | Feature 1020303: Perform Iterative Implementation, Integration, development Testing including updating design | PI 16 | New | 0 | #1020354
1020345 | #1020303 | Story | Feature 1020303: Provide Deployment Notes and Operator Impact Inputs for MUOS RAF GPS Antenna (Octopi) | PI 16 | New | 1 | #1020354
1020344 | #1020303 | Story | Feature 1020303: Create STCD and review with stakeholders | PI 16 | New | 1 | #1020346 #1020352 #1020354
1020343 | #1020303 | Story | Feature 1020303: Document Initial Capability Specification and Detailed Design to Start Implementation for MUOS RAF GPS Antenna | PI 16 | New | 2 | #1020346 #1020344
1020340 | #1020303 | Task | Feature 1020303: Hold Kick-off Meeting for MUOS RAF GPS Antenna | EA 15.2 | Done
1020339 | #1020303 | Story | Feature 1020303: Review IETMs for Style Guide Compliance and Conduct Independent Test (Dry Runs) for the MUOS RAF GPS Antenna | PI 16 | New | 3
1020338 |  | Story | Feature 1020303: Create New Procedures for the RAF GPS Antenna | EA 15.4 | Invalid | 0
1020337 | #1020303 | Task | Feature 1020303: Procurement Verification and Approvals for MUOS RAF GPS Antenna | EA 15.2 | Done
1020331 | #1020303 | Task | Feature 1020303: Hardware/Software Procurement Request for MUOS RAF GPS Antenna | EA 15.2 | Done
1020330 | #1020303 | Story | Feature 1020303: Validate Existing IETM Procedures for the RAF/ET Alignment | PI 16 | New | 1
1020329 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 1 - Investigation) | EA 15.2 | Done | 2
1020303 | #262146 | Feature | MUOS RAF GPS Antenna | PI 16 | Approved
1020302 | #1020291 | Story | Feature 1020291: Complete Customer Response Matrix (CRM) - Training EAD 17 [Deliver Training] | PI 17 | New | 1
1020301 | #1020291 | Story | Feature 1020291: Deliver Training at SMDC - Training EAD 17 [Deliver Training] | EA 16.5 | New | 2
1020300 | #1020291 | Story | Feature 1020291: Deliver Training at NCTAMS - Training EAD 17 [Deliver Training] | PI 17 | New | 5
1020299 | #1020291 | Task | Feature 1020291: Finalize, Print, and Ship Materials - Training EAD 17 [Create Training] | EA 16.4 | New
1020298 | #1020291 | Story | Feature 1020291: Incorporate Comments from Internal Review - Training EAD 17 [Create Training] | EA 16.4 | New | 1
1020297 | #1020291 | Story | Feature 1020291: SysEng SME Review EAD 17 Training Materials | PI 16 | New | 1
1020296 | #1020291 | Story | Feature 1020291: SA SME Review of Training EAD 17 Training Materials | PI 16 | New | 1
1020295 | #1020291 | Story | Feature 1020291: Create Training Materials - Training EAD 17 [Create Training] | EA 16.4 | New | 5
1020294 | #1020291 | Story | Feature 1020291: Create Draft Training Plan - Training EAD 17 [Training Plan] | EA 16.1 | New | 1
1020293 | #1020291 | Story | Feature 1020291: Hold Operator Impact meeting + Action Items - Training EAD 17 [Op Impacts] | EA 16.2 | New | 1
1020292 | #1020291 | Story | Feature 1020291: Finalize Op Impact Briefing Slides - Training EAD 17 [Op Impacts] | EA 16.1 | New | 1
1020291 | #262146 | Feature | Deliver EAD 17 Training | PI 16 - Candidate | Approved
1020281 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Rerun and capture results | EA 16.3 | Invalid | 0
1020280 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: DSN GW Reconfig & radio tests | EA 16.3 | New | 2
1020279 | #1020014 | Story | 1020014: Canada FMS Area Code prototyping: Execute radio tests | EA 16.3 | New | 1
1020278 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MAS' STIGs assessment - Part 2) | EA 15.2 | Done | 2
1020277 | #1020013 | Story | 1020013: Canada FMS TACLANE prototyping: Execute STCD and Capture Results | PI 17 | New | 5
1020276 | #1020013 | Story | 1020013: Canada FMS TACLANE prototyping: Configure Lab to support tests | PI 17 | New | 3
1020274 | #1020013 | Story | 1020013: Canada FMS TACLANE prototyping: Write and review STCD | PI 17 | New | 3
1020268 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Yue-Chain | EA 15.4 | Implementing | 5
1020267 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Yue-Chain | EA 15.3 | Done | 5
1020262 | #1014252 | Story | Feature 1014252: Perform Iterative Implementation, Integration, development Testing including updating design (Part 2b) | EA 15.3 | Done | 1
1020261 | #1014252 | Story | Feature 1014252: Execute STCD Feature Integration and testing including STCD updates identified Part 2 | EA 15.3 | Done | 2
1020260 | #1014252 | Story | Support Final Demo by performing Radio operations in Room 1186 | EA 15.4 | New | 1
1020259 | #1014252 | Story | Acquire access to room 1186 to support cross-training for OTA-FT radio operations | EA 15.2 | Done | 1
1020258 | #1014252 | Story | Cross-training for OTA-FT of testing resource. | EA 15.2 | Done | 2
1020250 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.3 | New | 1
1020249 | #1019464 | Story | Canada FMS Capability Spec v1: Author and SME support for version 1 document | EA 16.2 | New | 1
1020247 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.3 | New | 3
1020246 | #1019473 | Story | Canada FMS Capability Design Doc: Author and SME support for Draft document | EA 16.2 | New | 3
1020233 | #1008506 | Story | Perform Dry Run to test: Problem 332002: "IETM Procedure update from DTA-4 Finding: Action to Restore Service for PRVB0030 alarm." | EA 15.2 | Done | 1
1020227 | #380808 | Story | Feature 380808: Support Splunk team integration with SIEM | EA 15.2 | Done | 2 | #1018830
1020222 | #1007900 | Story | Feature 1007900: OBS HBSS-Manage Review and Dry Run for FM Recovery Procedures | EA 15.2 | Done | 3
1020221 | #380808 | Story | Feature 380808: VLab and Nutanix Support | EA 15.2 | Done | 1
1020220 | #1013750 | Story | Lab - Fix SWIT RNC06/Corben01 configuration | EA 15.3 | Done | 3
1020216 | #1013534 | Story | Lab - Debug SWIT RNC06/Corben and Core network configurations | EA 15.2 | Done | 5
1020214 | #1020011 | Story | Release status report with metrics spreadsheet for July Deployment | EA 16.3 | New | 2
1020213 | #1020011 | Story | September 2020 Patch Deployment - Develop and finalize candidate patch target list | EA 16.3 | New | 3
1020212 | #1020011 | Story | Update Node Config for IA patches | EA 16.1 | New | 1
1020211 | #1020011 | Story | Complete SWIT Testing, and complete VLAB test for July Deployment | EA 16.1 | New | 3
1020210 | #1020011 | Story | Create patch bundle, measure/sign and formally release to CM with final script, download bundle to protected laptop | EA 16.1 | New | 3
1020208 | #380808 | Task | Feature 380808: Submit PDO for 01-P59882M - NMS_NM - Nutanix Server SCD | PI 16 | New
1020207 | #1020011 | Story | Download September patches, and update patching script | EA 16.5 | New | 2
1020202 | #380808 | Story | Feature 380808: Create CoCo Review of the SCD for Nutanix | EA 15.2 | Done | 1
1020201 | #1002381 | Story | Feature 1002381: Continue Creating Redlines Drawings for OBS - HLR: HW/FRCB for HLR Deployment | EA 15.4 | Done | 2
1020199 | #1020011 | Story | Complete SWIT testing For September Patches | EA 16.5 | New | 2
1020198 | #1020011 | Story | Validate September Deployment Patches in SWIT/Vlab vs Site | EA 16.4 | New | 2
1020196 | #1020011 | Story | Update Patch SVDs for with redlines from site and misc cleanup | EA 16.4 | New | 2
1020194 | #1020011 | Story | Scan and review the patch findings from the site and SWIT and VLAB | EA 16.4 | New | 3
1020193 | #1020011 | Story | September 2020 Patch Deployment - Develop and finalize candidate patch target list | EA 16.3 | New | 3
1020192 | #1020011 | Story | Updated HW SW Map for July Patch deployment | EA 16.3 | New | 3
1020191 | #1020011 | Story | Release status report with metrics spreadsheet for July Deployment | EA 16.3 | New | 2
1020189 | #1020011 | Story | Update Node Config for IA patches | EA 16.1 | New | 1
1020188 | #1020011 | Story | Update IA-Server-patch-tracker spreadsheet in Clear Case w/patch bundle installed | EA 16.2 | New | 3
1020187 | #1015153 | Story | Feature 1015153: Verify Boot images are working in the target system | EA 15.3 | Done | 3
1020186 | #1020011 | Story | Complete SWIT Testing, and complete VLAB test for July Deployment | EA 16.1 | New | 3
1020185 | #1015153 | Story | Feature 1015153: Verify Boot images are working in the target system | EA 15.2 | Done | 3
1020184 | #1020011 | Story | Create patch bundle, measure/sign and formally release to CM with final script, download bundle to protected laptop | EA 16.1 | New | 3
1020182 | #380808 | Story | Feature 380808: (IA) MFR 3 – Review with customer and gain concurrence- the Nutanix CAP and update set of applicable STIGs | EA 15.2 | Done | 1
1020161 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Work Proof of Concept [15.2] | EA 15.2 | Done | 2
1020158 | #1006376 | Story | Feature 1006376: Update SVD for MAMA2 Cleanup feature part 2 | EA 15.3 | Done | 2
1020154 | #387446 | Story | Mobility Call Flow Updates | EA 15.5 | New | 2
1020152 | #376446 | Story | Feature 376446: Complete Softphone: PWI Burndown | EA 15.2 | Done | 1
1020149 | #395688 | Story | Complete VlabTesting for May Deployment | EA 15.2 | Done | 2
1020148 | #395688 | Story | Complete VlabTesting for May Deployment | EA 15.2 | Done | 2
1020145 | #1020011 | Story | July 2020 IA Patch Deployment (Kirk) | EA 16.2 | New | 5
1020144 | #1020011 | Story | July 2020 IA Patch Deployment (Johnathan) | EA 16.2 | New | 5
1020135 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.2 (Valverde) | EA 15.2 | Done | 1
1020134 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.2 (Aidan) | EA 15.2 | Done | 1
1020132 | #1020011 | Story | Support PMW Emergent Data Calls - 16.5 | EA 16.5 | New | 1
1020131 | #1020011 | Story | Support PMW Emergent Data Calls - 16.4 | EA 16.4 | New | 1
1020130 | #1020011 | Story | Support PMW Emergent Data Calls - 16.3 | EA 16.3 | New | 1
1020129 | #1020011 | Story | Support PMW Emergent Data Calls - 16.2 | EA 16.2 | New | 1
1020128 | #1020011 | Story | Support PMW Emergent Data Calls - 16.1 | EA 16.1 | New | 1
1020127 | #1020010 | Story | MFR EAD 18 Support - Continuing Support | PI 16 | New | 2
1020126 | #1020010 | Story | Update and review with customer MFR for EAD 18.0 | PI 16 | New | 3
1020125 | #1020010 | Story | Update ACAS Scan Limitations White Paper - EAD 18 | PI 16 | New | 1
1020124 | #1020010 | Story | Review and analyze scan data for EAD 18.0 MFR | PI 16 | New | 3
1020123 | #1020010 | Story | Generate and review with customer MFR for EAD 18.0 | PI 16 | New | 3
1020067 | #1013136 | Story | Feature 1013136: Write down and review with the team regression tests for PI 15 delivered PWIs | EA 15.5 | New | 1
1020053 | #1020010 | Story | Support application review for DADMs applicability - 16.5 | EA 16.5 | New | 1
1020052 | #1020010 | Story | Support application review for DADMs applicability - 16.4 | EA 16.4 | New | 1
1020051 | #1020010 | Story | Support application review for DADMs applicability - 16.3 | EA 16.3 | New | 1
1020050 | #1012485 | Story | Feature 1012485: Review Training IPT Charter and Update JDTA as Needed [Task Analysis] | EA 15.2 | Done | 1
1020049 | #1020010 | Story | Support application review for DADMs applicability - 16.2 | EA 16.2 | New | 1
1020048 | #1020010 | Story | Support application review for DADMs applicability - 16.1 | EA 16.1 | New | 1
1020047 | #1014737 | Story | Support PMW as Needed - 16.5 | EA 16.5 | New | 1
1020046 | #1014737 | Story | Support PMW as Needed - 16.4 | EA 16.4 | New | 1
1020045 | #1014737 | Story | Support PMW as Needed - 16.3 | EA 16.3 | New | 1
1020044 | #1014737 | Story | Support PMW as Needed - 16.2 | EA 16.2 | New | 1
1020041 | #1014737 | Story | Support PMW as Needed - 16.1 | EA 16.1 | New | 1
1020040 | #1014737 | Story | IAVA Intake - 16.5 | EA 16.5 | New | 2
1020039 | #1014737 | Story | IAVA Intake - 16.4 | EA 16.4 | New | 2
1020038 | #1014737 | Story | IAVA Intake - 16.3 | EA 16.3 | New | 2
1020037 | #1014737 | Story | IAVA Intake - 16.2 | EA 16.2 | New | 2
1020035 | #1014737 | Story | IAVA Intake - 16.1 | EA 16.1 | New | 2
1020033 | #387448 | Story | Update P2P Communication Call Flows | EA 15.2 | Done | 3
1020031 | #1020018 | Story | Feature 1020018: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in NW | PI 16 - In Progress | Invalid | 0
1020030 | #1020018 | Story | Feature 1020018: Final Oversight of Vendor Activities and Submission of Final Report for 2020 Preventive Maintenance in NW | EA 16.4 | New | 2
1020029 | #1020018 | Story | Feature 1020018: Continue Oversight of Vendor Activities for 2020 Preventive Maintenance in NW | EA 16.3 | New | 1
1020028 | #1020018 | Story | Feature 1020018: Begin Oversight of Vendor Activities for 2020 Preventive Maintenance in NW | EA 16.2 | New | 1
1020027 | #1020018 | Story | Feature 1020018: Present SOW Associated to 2020 Preventive Maintenance in NW | EA 16.1 | New | 2
1020026 | #1020018 | Story | Feature 1020018: Prepare & Conduct PM Kickoff Meeting with PMW | EA 16.1 | New | 2
1020025 | #1020018 | Task | Feature 1020018: Prepare, Review SOW Associated to 2020 Preventive Maintenance in NW | EA 15.5 | New
1020024 | #1020018 | Task | Feature 1020018: Ship Supplies and Materials to Site for 2020 Preventive Maintenance in NW | EA 15.5 | New
1020023 | #1020018 | Task | Feature 1020018: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in NW | EA 15.4 | In Development
1020022 | #1020018 | Task | Feature 1020018: Confirmation of Vendor, Access to Site, and Schedule of Activities for the 2020 Preventive Maintenance in NW | EA 15.4 | New
1020021 | #1020018 | Task | Feature 1020018: Create and Validate Plan for 2020 Preventive Maintenance Activities in NW | EA 15.4 | Done
1020020 | #1020018 | Story | Feature 1020018: Determine Corrective Actions Based Upon Trouble Tickets Received for 2020 Preventive Maintenance of NW | EA 15.5 | New | 2
1020019 | #1020018 | Story | Feature 1020018: Identification of Consumables Required for 2020 Preventive Maintenance in NW | EA 15.2 | Done | 1
1020018 | #262146 | Feature | NW Preventive Maintenance Activity for 2020 | PI 16 - In Progress | Implementing
1020017 | #343920 | Task | Story 343920: CM Release of 99-P48088V MUOSv1.1.24.0 EAD 16 Test Report for Wahiawa Power Upgrades for NCTAMSPAC SATCOM Wahiawa, HI (EAD 16) | PI 14 - In Progress | Done
1020014 | #1022876 | Feature | Canada FMS Area Code Prototyping | PI 16 - Candidate | Approved
1020013 | #1022876 | Feature | Canada FMS TACLANE Prototyping | PI 17 | Ready for System IPT Approval
1020011 | #245560 | Feature | Cyber: TO3 IA Patching - PI 16 (Recurring) | PI 16 | Approved
1020010 | #245560 | Feature | Cyber: MFR Deployment Support - PI 16 (Recurring) | PI 16 | Approved
1020009 | #377437 | Story | Feature 377437 ETT: Verify PCRs/ PWI (part3) | EA 15.3 | Done | 1 | #1004666
1020000 | #1019997 | Story | Feature 1019997: Address/Incorporate Training Package comments received from PMW | PI 16 | New | 3
1019999 | #1019997 | Story | Feature 1019997: Create Review Package to be provided to PMW | PI 16 | New | 1
1019998 | #1019997 | Story | Feature 1019997: Review Training Package and ensure it contains latest lessons from past year's training | EA 15.5 | New | 5
1019997 | #262146 | Feature | Update and Prepare CBT Source Material/Lessons in Preparation for CBT Update | PI 16 - In Progress | Approved
1019975 |  | Feature | ALICORN TEAM - PLACEHOLDER FOR BUILD DEVELOPMENT ENVIRONMENT FOR LAB (EA15.1) | Unassigned | Rejected
1019963 | #1017680 | Story | Rebase and Test Problem 1006145 Story : FEP SVD needs to be updated to include depot instructions for configuration for new part number dehydrator (15.2) | EA 15.2 | Done | 1
1019962 | #1017680 | Story | Rebase and Test Problem 388760 Story : Need to document ACU configurations (15.2) | EA 15.2 | Done | 1
1019961 | #1017680 | Story | Rebase and Test Problem 1006145 Story : FEP SVD needs to be updated to include depot instructions for configuration for new part number dehydrator (15.2) | EA 15.2 | Done | 1
1019959 | #332951 | Story | Feature 332951: Lab Support of RBS IETM Updates (15.2) | EA 15.2 | Done | 1
1019935 | #342163 | Task | Review MCP Training Recommendations | EA 15.2 | Done
1019923 | #1015438 | Feature | TO-6 Service Management - respond to questions from ATT | PI 17 | Draft
1019922 | #383165 | Story | Feature 383165: Continue Identification of Logistics Considerations (non-IETM) for Nutanix Deployment | EA 15.4 | New | 1
1019921 | #383165 | Story | Feature 383165: Continue Identification of Logistics Considerations (non-IETM) for Nutanix Deployment | EA 15.3 | Done | 1
1019919 | #383165 | Story | Feature 383165: Continue Identification of Logistics Considerations (non-IETM) for Nutanix Deployment | EA 15.2 | Done | 1
1019914 | #393432 | Story | Feature 393432 Auto: Automated Monitoring/Cleanup ILS Incorporation of IETM updates and integration support | PI 16 | Invalid | 0
1019913 | #393432 | Story | Feature 393432 Auto: MFR 1 Support MFR Meeting and Update CAP as Needed | PI 16 | Invalid | 0
1019912 | #393432 | Story | Feature 393432 Auto: MFR 1 – Dev Team Performs Cybersecurity Assessment - part 1 | PI 16 | Invalid | 0
1019911 | #393432 | Task | Feature 393432- Prep and Perform Interim Demo | PI 16 | Invalid
1019910 | #393432 | Story | Feature 393432 Auto: Create STCD and review with stakeholders & dry run | PI 16 | Invalid | 0
1019909 | #393432 | Story | Feature 393432 Auto: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | Invalid | 0
1019908 | #393432 | Story | Feature 393432 Auto: Prep and Perform Feature Demo – Customer Demo Event | PI 16 | Invalid | 0
1019907 | #393432 | Story | Update JDTA to remove any routine tasks that have been automated | PI 16 | Invalid | 0
1019906 | #393432 | Story | Feature 393432 Auto: Assess "MUOS Geolocation Security Log Collection — Normal Operation Procedure," O-level routine procedures | PI 16 | Invalid | 0
1019905 | #393432 | Story | Feature 393432 Auto: Initiate CM PDO Processing for all CI's | PI 16 | Invalid | 0
1019904 | #393432 | Story | Feature 393432 Auto: Develop automation for "MUOS Geolocation Security Log Collection" | PI 16 | Invalid | 0
1019903 | #393432 | Task | Feature 393432: Hold Feature Review with SMEs | PI 16 | Invalid
1019902 | #393432 | Story | Feature 393432 Auto: Provide Deployment Notes and Operator Impact Inputs | PI 16 | Invalid | 0
1019901 | #393432 | Story | Feature 393432 Auto: Update IETMs and Perform Development Testing | PI 16 | Invalid | 0
1019900 | #393432 | Story | Feature 393432 Auto: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 16 | Invalid | 0
1019899 | #393432 | Story | Feature 393432 Auto: Review the SVD updates | PI 16 | Invalid | 0
1019860 |  | Task | Kirk Dewberry - OOP Reminder: | Unassigned | New
1019843 | #378964 | Task | Bernie Southerland PTO (EA 16.3 (7/16 - 7/24) | EA 16.3 | New
1019841 | #378964 | Task | Bernie Southerland PTO (EA 16.2 (7/2 - 7/15) | EA 16.2 | New
1019840 | #378964 | Task | Bernie Southerland PTO (EA 16.1 (6/26 - 7/1) | EA 16.1 | New
1019796 | #1019791 | Story | Feature 1019791: Update CRM Database Entries for (EA 16.5) | EA 16.5 | New | 2
1019795 | #1019791 | Story | Feature 1019791: Update CRM Database Entries for (EA 16.4 | EA 16.4 | New | 2
1019794 | #1019791 | Story | Feature 1019791: Update CRM Database Entries for (EA 16.3) | EA 16.3 | New | 2
1019793 | #1019791 | Story | Feature 1019791: Update CRM Database Entries for (EA 16.2) | EA 16.2 | New | 2
1019792 | #1019791 | Story | Feature 1019791: Update CRM Database Entries for (EA 16.1) | EA 16.1 | New | 2
1019791 | #262146 | Feature | PI 16 Maintain CRM Database (Recurring) | PI 16 - Candidate | Approved
1019786 | #1019781 | Story | Feature 1019781: Octopi Supply Support (EA 16.5) | EA 16.5 | New | 5
1019785 | #1019781 | Story | Feature 1019781: Octopi Supply Support (EA 16.4) | EA 16.4 | New | 5
1019784 | #1019781 | Story | Feature 1019781: Octopi Supply Support (EA 16.3) | EA 16.3 | New | 5
1019783 | #1019781 | Story | Feature 1019781: Octopi Supply Support (EA 16.2) | EA 16.2 | New | 5
1019782 | #1019781 | Story | Feature 1019781: Octopi Supply Support (EA 16.1) | EA 16.1 | New | 5
1019781 | #262146 | Feature | PI 16 Supply Support Tracking (Recurring) | PI 16 - Candidate | Approved
1019778 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | PI 16 | Invalid | 0
1019777 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.5) | EA 16.5 | New | 1
1019776 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.4) | EA 16.4 | New | 1
1019775 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.3) | EA 16.3 | New | 1
1019774 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.2) | EA 16.2 | New | 1
1019773 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.1) | EA 16.1 | New | 1
1019772 |  | Story | <Feature XXXXXX>: Logistics HW FRB Support EA XX.X | PI 16 | Invalid | 0
1019771 | #1019754 | Story | Feature 1019754: Logistics HW FRB Support (EA 16.5) | EA 16.5 | New | 5
1019770 | #1019754 | Story | Feature 1019754: Logistics HW FRB Support (EA 16.4) | EA 16.4 | New | 5
1019769 | #1019754 | Story | Feature 1019754: Logistics HW FRB Support (EA 16.3) | EA 16.3 | New | 5
1019768 | #1019754 | Story | Feature 1019754: Logistics HW FRB Support (EA 16.2) | EA 16.2 | New | 5
1019767 | #1019754 | Story | Feature 1019754: Logistics HW FRB Support (EA 16.1) | EA 16.1 | New | 5
1019766 |  | Story | <Feature XXXXXX>: Lab - Verify Field or Site Declared Failures in the Lab (EA XX.X) | PI 16 | Invalid | 0
1019765 | #1019754 | Story | Feature 1019754: Lab - Verify Field or Site Declared Failures in the Lab (EA 16.5) | EA 16.5 | New | 1
1019764 | #1019754 | Story | Feature 1019754: Lab - Verify Field or Site Declared Failures in the Lab (EA 16.4) | EA 16.4 | New | 1
1019763 | #1019754 | Story | Feature 1019754: Lab - Verify Field or Site Declared Failures in the Lab (EA 16.3) | EA 16.3 | New | 1
1019762 | #1019754 | Story | Feature 1019754: Lab - Verify Field or Site Declared Failures in the Lab (EA 16.2) | EA 16.2 | New | 1
1019761 | #1019754 | Story | Feature 1019754: Lab - Verify Field or Site Declared Failures in the Lab (EA 16.1) | EA 16.1 | New | 1
1019760 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | PI 16 | Invalid | 0
1019759 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.5) | EA 16.5 | New | 1
1019758 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.4) | EA 16.4 | New | 1
1019757 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.3) | EA 16.3 | New | 1
1019756 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.2) | EA 16.2 | New | 1
1019755 | #1019754 | Story | Feature 1019754: Evaluation of HW FRB Support (EA 16.1) | EA 16.1 | New | 1
1019754 | #262146 | Feature | PI 16 HW FRB Support (Recurring) | PI 16 - Candidate | Approved
1019749 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.2 | EA 15.2 | Done | 1
1019748 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.2 | EA 15.2 | Done | 1
1019746 | #1007900 | Story | NM-Security AAA SVD - Wrap-up common document updates for EAD 18 | PI 16 | New | 1
1019745 | #376446 | Story | Feature 376446: IA Posture Improvement - Address issues from IA Scans | EA 15.1 | Done | 5
1019742 | #1013534 | Story | Lab - Maintain Labs - DSN GW SME Support - Glen L. (15.1) | EA 15.1 | Done | 1
1019740 | #1012540 | Story | Feature 1012540: Continue Analysis of all System Parts [CDRL A004] - - Spares planning. | EA 15.3 | Done | 2
1019717 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster Master lost comm (Investigation) | EA 15.3 | Done | 2
1019714 | #1013136 | Problem | Vendor: rlcRetrans problems during MILSTD 04_271 Multi-RAB Intra RNC testing. | EA 16.1 | Close Pending
1019697 | #1012996 | Story | Tools Team Support / LOE for RAN/RDE for EA 15.5 | EA 15.5 | New | 2
1019696 | #1012996 | Story | Tools Team Support / LOE for RAN/RDE for EA 15.4 | EA 15.4 | Implementing | 2
1019695 | #1012996 | Story | Tools Team Support / LOE for RAN/RDE for EA 15.3 | EA 15.3 | Done | 2
1019694 | #1012996 | Story | Tools Team Support / LOE for RAN/RDE for EA 15.2 | EA 15.2 | Done | 2
1019692 |  | Task | Create maintenance doc for Metrics automation code | EA 15.1 | Done
1019656 | #342054 | Task | Feature 342054: Submit PDO for 98-P59858M of NM Splunk Application SVD | PI 16 | New
1019639 | #1019230 | Story | Add Group State to Element4 of the OOS Report in CAI Addendum 20 | Unassigned | New | 5
1019638 | #1019230 | Story | Create OOS Report Instrumentation Messages with a Group State field | Unassigned | New | 13
1019634 | #1019230 | Story | Process OOS Report CDRs with a Group State field | Unassigned | New | 13
1019626 | #1015458 | Story | TO-6 Respond to questions from ATT | EA 16.4 | New | 1
1019625 | #1015458 | Story | Feature 1015439: TO-6 Respond to questions from ATT - WWTS SME Support | EA 16.4 | New | 1
1019624 | #1015458 | Story | Feature 1015439: TO-6 Respond to questions from ATT - WWTS SME Support | EA 16.2 | New | 1
1019622 | #1015458 | Story | TO-6 Respond to questions from ATT - Core SME Support | EA 16.4 | New | 1
1019620 | #1015458 | Story | TO-6 Respond to questions from ATT - Core SME Support | EA 16.2 | New | 1
1019619 | #1015458 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 16.4 | New | 1
1019618 | #1015458 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 16.2 | New | 1
1019617 | #1015458 | Story | TO-6 Respond to questions from ATT - SIC SME Support | EA 16.4 | New | 1
1019615 | #1015458 | Story | TO-6 Respond to questions from ATT - SIC SME Support | EA 16.2 | New | 1
1019614 | #1015458 | Story | TO-6 Respond to questions from ATT | EA 16.3 | New | 1
1019613 | #1015458 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 16.2 | New | 1
1019611 | #1015458 | Story | TO-6 Respond to questions from ATT | EA 16.2 | New | 1
1019609 | #1015458 | Story | TO-6 Respond to questions from ATT | EA 16.1 | New | 1
1019550 | #1002583 | Story | Tools Team Support / LOE for SDE/ODE for EA 15.2 | EA 15.2 | Done | 3
1019527 | #1019513 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 16 | Invalid | 0
1019526 | #1019513 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1 | #1019527
1019525 | #1019513 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 16 | New | 2 | #1019526
1019524 | #1019513 | Story | <Feature 1019513>: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 5 | #1019526
1019523 | #1019513 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 16 | Invalid | 0 | #1019526
1019522 | #1019513 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 16 | Invalid | 0
1019521 | #1019513 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 16 | Invalid | 0
1019520 | #1019513 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 16 | Invalid | 0 | #1019526
1019519 | #1019513 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 16 | Invalid | 0 | #1019526
1019518 | #1019513 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 16 | Invalid | 0 | #1019526
1019517 | #1019513 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 16 | Invalid | 0 | #1019526
1019516 | #1019513 | Story | <Feature xxx>: Create STCD and review with stakeholders | PI 16 | New | 3 | #1019518 #1019525 #1019526 #1019524
1019515 | #1019513 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 16 | Invalid | 0 | #1019516 #1019518
1019514 | #1019513 | Task | <Feature xxx> Hold Feature Review with SMEs | PI 16 | New
1019513 | #204273 | Feature | Include all objects in OTA-FT Update Request | PI 16 - Candidate | Approved
1019490 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store (Investigation) | EA 15.2 | Done | 2
1019489 | #1008506 | Story | Feature 1008506: Insure redlines of AMP are incorporated into final release. | PI 16 | New | 1
1019476 | #380808 | Task | Feature 380808: Submit PDO for 69-P50495E- ILS - INTERCONNECT DIAGRAM - SF/NMF, WAHIAWA | PI 15 | New
1019475 | #380808 | Task | Feature 380808: Submit PDO for PL01-P53572E001 - NMS_NM - NME 12 CABINET ASSEMBLY - NMA, Parts List | PI 15 | New
1019474 | #380808 | Task | Feature 380808: Submit PDO for 01-P53572E001 - NMS_NM - NME 12 CABINET ASSEMBLY - NMA | PI 15 | New
1019471 | #1011295 | Task | Feature 1011295: Submit PDO for 91122A115 - WASHER, SQUARE, 2.00 X 2.00 SQ. X .250 THK, .438 ID | EA 15.4 | Invalid
1019470 | #1011295 | Task | Feature 1011295: Submit PDO for 92314A840 - SCREW, CAP, HEX HEAD, 10-32 X 2.50 | EA 15.4 | Invalid
1019469 | #1011295 | Task | Feature 1011295: Submit PDO for 29505T21 - SCREW MOUNT LIFTING RING, 5/16-18 THREAD, 2 31/32 RING HEIGHT | EA 15.4 | Invalid
1019468 | #1011295 | Task | Feature 1011295: Submit PDO for 64-P41480V001 - PLATE, EYEBOLT MOUNTING | EA 15.5 | New
1019467 | #1011295 | Task | Feature 1011295: Submit PDO for 64-P41480V - PLATE, EYEBOLT MOUNTING | EA 15.5 | New
1019466 | #1011295 | Task | Feature 1011295: Submit PDO for 64-P41479V002 - PLATE, RAIN SHIELD, AZIMUTH MOTOR | EA 15.5 | New
1019465 | #1011295 | Task | Feature 1011295: Submit PDO for 64-P41479V001 - PLATE, RAIN SHIELD, AZIMUTH MOTOR | EA 15.5 | New
1019463 | #1011295 | Task | Feature 1011295: Submit PDO for 64-P41479V - PLATE, RAIN SHIELD, AZIMUTH MOTOR | EA 15.5 | New
1019461 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P41478V001 - SHIELD ASSEMBLY, AZIMUTH MOTOR | EA 15.5 | New
1019460 | #1011295 | Task | Feature 1011295: Submit PDO for PL01-P41478V001 - SHIELD ASSEMBLY, AZIMUTH MOTOR, PARTS LIST | EA 15.5 | New
1019459 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P41478V - SHIELD ASSEMBLY, AZIMUTH MOTOR | EA 15.5 | New
1019443 | #342163 | Task | Feature 342163: Submit PDO for PL01-P53574E - NMS_NM - NMO Assembly, Parts List | EA 15.4 | Done
1019442 | #1011295 | Task | Feature 1011295: Submit PDO for 01-P51766E - GTS - I/O PANEL ASSEMBLY - Earth Terminal Interface Signal Processor (ETISP) | EA 15.5 | New
1019437 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.1 | EA 15.1 | Done | 1
1019436 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.1 | EA 15.1 | Done | 1
1019377 | #342163 | Task | Feature 342163: Create PDO to Release the Parts List Updates for Taclane | EA 15.4 | Invalid
1019376 | #342163 | Story | Feature 342163: Create CoCo Review for Parts List Updates for Taclane | EA 15.3 | Done | 1
1019365 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1019343 | #380808 | Story | Feature 380808: Verify Updates for NME201 (new cabinet) & Model New Server are Complete (EAD 18) | EA 16.1 | New | 1
1019342 | #1015153 | Story | Create Work Items for obsolete disc images | EA 15.2 | Done | 1
1019316 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement IETM Dry Run procedures | EA 15.2 | Done | 2 | #383970
1019308 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search Head Cluster Deployer lost comm (Part 2 - Complete procedure) | EA 15.4 | Implementing | 3
1019307 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 16 - Troubleshooting when search head member cannot send to captain (Part 2 - Complete procedure) | EA 15.3 | Done | 3
1019284 | #1013750 | Story | Lab - Document RANLAN cabling differences from baseline | EA 15.1 | Done | 2
1019247 | #1019230 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
1019246 | #1019230 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #1019239
1019245 | #1019230 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #395544 #1019239
1019244 | #1019230 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | New | 0 | #1019239
1019243 | #1019230 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #1019239
1019242 | #1019230 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #1019239
1019241 | #1019230 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #1019239
1019240 | #1019230 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | New | 3 | #1019245 #1019243 #1019239 #1019242
1019239 | #1019230 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | New | 1 | #1019238
1019238 | #1019230 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
1019237 | #1019230 | Story | <Feature xxx>: MFR 2 – Cyber Performs initial Cybersecurity Assessment | Unassigned | New | 5
1019236 | #1019230 | Story | <Feature xxx>: MFR 2 – Dev Team Supports Initial Cybersecurity Assessment | Unassigned | New | 1
1019235 | #1019230 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves ACAS Scan Findings | Unassigned | New | 3
1019234 | #1019230 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves Final ACAS Scan Findings | Unassigned | New | 3
1019233 | #1019230 | Story | <Feature xxx>: MFR 2 – Cyber Completes Final CAP | Unassigned | New | 5
1019232 | #1019230 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | New | 3
1019231 | #1019230 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #1019245 #1019241 #1019240
1019230 |  | Feature | Include Group State in the UE OOS Report CDR for Proper Splunk Reporting | PI 17 - Candidate | Draft
1019229 | #1019230 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | New
1019219 |  | Problem | Netcool populates with all purple alarms when account is locked out (Whitelist Update) | Unassigned | Assessing
1019215 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.1 | EA 15.1 | Done | 2
1019198 | #1010653 | Task | Feature 1010653: Hold EAD 16 (Minor Release) Operator Impact Brief | EA 15.2 | Done
1019193 |  | Problem | CRL Webserver Redundancy not working as intended per trouble ticket | Unassigned | Assessing
1019191 | #393265 | Story | Feature 393265: Analyze McAfee vs Forcepoint IETM Procedures | EA 15.2 | Done | 1
1019177 |  | Task | Feature 377437: Submit PDO for 01-P59554V - ILS - LAPTOP, MTC-AJM GEN2 ASSEMBLY | EA 15.4 | Invalid
1019176 | #377437 | Task | Feature 377437: Submit PDO for 01-P59548V004 - ILS - ILS LAPTOP GEN2 ASSEMBLY | EA 15.3 | Done
1019175 |  | Task | Feature 377437: Submit PDO for 01-P59548V001 - ILS - ILS LAPTOP GEN2 ASSEMBLY | EA 15.4 | Invalid
1019153 | #332951 | Story | Feature 332951: Provide Deployment Notes and Operator Impact Inputs | EA 15.4 | New | 1
1019150 | #1008506 | Story | Feature 1008506: Create template for Splunk Troubleshooting procedures | EA 15.1 | Done | 1
1019123 | #1019101 | Task | Feature Demo – Customer Demo Event - Feature 1019101: PI 16 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 16.5 | New
1019122 | #1019101 | Task | Feature 1019101: Upload Demo Documentation to GD Site for PI 16 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 16.5 | New |  | #1019123
1019121 | #1019101 | Task | Feature 1019101: Submit PDO for xyz (5) | EA 16.5 | New |  | #1019122
1019120 | #1019101 | Story | Feature 1019101: Create CoCo Review for xyz Parts List/Drawings (Part 5) (XXX | PI 16 | Invalid | 0 | #1019121
1019119 | #1019101 | Story | Feature 1019101: Parts List Updates for EA 16.5 | PI 16 | Invalid | 0 | #1019120
1019118 | #1019101 | Story | Feature 1019101: Drawing Updates for EA 16.5 | PI 16 | Invalid | 0 | #1019120
1019117 | #1019101 | Task | Feature 1019101: Submit PDO for xyz (4) | EA 16.5 | New |  | #1019122
1019116 | #1019101 | Story | Feature 1019101: Create CoCo Review for xyz Parts List/Drawings (Part 4) (EA 16.5) | EA 16.5 | New | 1 | #1019117
1019115 | #1019101 | Story | Feature 1019101: Parts List Updates for EA 16.4 | EA 16.4 | New | 1 | #1019116
1019114 | #1019101 | Story | Feature 1019101: Drawing Updates for EA 16.4 | EA 16.4 | New | 1 | #1019116
1019113 | #1019101 | Task | Feature 1019101: Submit PDO for xyz (3) | EA 16.5 | New |  | #1019122
1019112 | #1019101 | Story | Feature 1019101: Create CoCo Review for xyz Parts List/Drawings (Part 3) (EA 16.4) | EA 16.4 | New | 2 | #1019113
1019111 | #1019101 | Story | Feature 1019101: Parts List Updates for EA 16.3 | EA 16.3 | Invalid | 0 | #1019112
1019110 | #1019101 | Story | Feature 1019101: Drawing Updates for EA 16.3 | EA 16.3 | Invalid | 0 | #1019112
1019109 | #380808 | Task | Feature 380808: Submit PDO for 30-P48079V | EA 16.5 | New
1019108 | #1019101 | Story | Feature 1019101: Create CoCo Review for xyz Parts List/Drawings (Part 2) (EA 16.3) | EA 16.3 | Invalid | 0
1019107 | #1019101 | Story | Feature 1019101: Parts List Updates for EA 16.2 | EA 16.2 | Invalid | 0 | #1019108
1019106 | #1019101 | Story | Feature 1019101: Drawing Updates for EA 16.2 | EA 16.2 | Invalid | 0 | #1019108
1019105 | #380808 | Task | Feature 380808: Submit PDO for 30-P48080V | EA 16.5 | New
1019104 | #1019101 | Story | Feature 1019101: Create CoCo Review for xyz Parts List/Drawings (Part 1) (EA 16.2) | EA 16.2 | Invalid | 0
1019103 | #1019101 | Story | Feature 1019101: Parts List Updates for EA 16.1 | EA 16.1 | Invalid | 0 | #1019104
1019102 | #1019101 | Story | Feature 1019101: Drawing Updates for EA 16.1 | EA 16.1 | Invalid | 0 | #1019104
1019101 | #262146 | Feature | PI 16 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | PI 16 - Candidate | Approved
1018887 | #395114 | Task | Feature 395114: Submit PDO for 99-P53447E – ILS - FRACAS | EA 15.3 | Done
1018873 | #1013452 | Story | Feature 1013452: Provide Development inputs to NEDB common document | PI 16 | New | 1
1018871 | #342054 | Story | Feature 342054: Provide Development inputs to NEDB common document | PI 16 | New | 1
1018842 | #395114 | Story | Feature 395114: Analyze RAX13; RANDOM ACCESS AND RX PRINTED BD ASSEMBLY: PN = ROJ 119 2187/4, SN = TU8G038216 for SR 1108374 / G3164. | EA 15.1 | Done | 1
1018836 | #380808 | Story | Feature 380808: SIEM validation of updates for Nutanix, Splunk, Cisco Switches | EA 15.3 | Invalid | 0
1018835 | #380808 | Story | Feature 380808: SIEM PCR verification of updates for Nutanix, Splunk, Cisco Switches | EA 15.4 | Implementing | 1
1018831 | #380808 | Story | Feature 380808: SIEM updates for Nutanix, Splunk, Cisco Switches Built and ready for V-Lab | EA 15.3 | Done | 1
1018830 | #380808 | Story | Feature 380808: SIEM updates for Nutanix, Splunk, Cisco Switches | EA 15.2 | Done | 3 | #1018831
1018829 | #380808 | Story | Feature 380808: Splunk SIEM configuration | EA 15.2 | Done | 3
1018827 | #342054 | Task | Feature 342054: Provide Development inputs to PKI common document | PI 16 | New
1018826 | #380808 | Task | Feature 380808: Submit PDO to Release the SCD for Nutanix | EA 16.3 | New
1018824 | #380808 | Story | Feature 380808: Complete CoCo Review of the SCD for Nutanix | EA 16.2 | New | 1
1018823 | #383165 | Task | Feature 383165: Review Logistics Considerations (non-IETM) Checklist for Nutanix Deployment | EA 15.5 | New
1018756 | #342054 | Story | Feature 342054: Provide Development inputs to I-Level Procedures common document | PI 16 | New | 2
1018730 | #1011295 | Task | Feature 1011295: Create PDO Release for Items Defined in Story 1018728 | EA 15.4 | Invalid
1018729 | #1011295 | Story | Feature 1011295: Create CoCo Review for Items Defined in Story 1018728 | EA 15.4 | Ready for Acceptance | 1
1018728 | #1011295 | Story | Feature 1011295: Drawing/Part List Updates for EA 15.3 | EA 15.3 | Done | 3
1018683 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P53523T - GIS - SVD | PI 16 | New
1018680 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P55755M - Firewall - Network - SVD | PI 16 | New
1018660 | #380808 | Story | SIEM installation and build, operational verification | EA 15.3 | Done | 1
1018631 | #395114 | Story | Feature 395114: Analyze AIU; ANTENNA INTERFACE UNIT 21 PRINTED BOARD ASSEMBLY: PN = KRY 101 1854/6, SN = TR46522058 for SR 1113432 / G3194 | EA 15.1 | Done | 1
1018617 | #395688 | Story | Support PMW Emergent Data Calls - 15.5 | EA 15.5 | New | 1
1018616 | #395688 | Story | Support PMW Emergent Data Calls - 15.4 | EA 15.4 | Implementing | 1
1018615 | #395688 | Story | Support PMW Emergent Data Calls - 15.3 | EA 15.3 | Done | 1
1018614 | #395688 | Story | Support PMW Emergent Data Calls - 15.2 | EA 15.2 | Done | 1
1018613 | #395688 | Story | Support PMW Emergent Data Calls - 15.1 | EA 15.1 | Done | 1
1018588 | #380808 | Story | Feature 380808: Hold review meeting for Nutanix/Splunk/HBSS Deployment Plan prior to real deployment | PI 16 | New | 1
1018587 | #380808 | Story | Feature 380808: Hold review meeting for Nutanix/Splunk/HBSS Deployment Plan | EA 15.4 | Invalid | 0
1018585 | #377437 | Task | Feature 377437: Submit PDO for 99-P57051M – NMS – NM – GSAM | EA 15.3 | Done
1018583 |  | Task | Story 1011568: CM Release of 99-P59435M – NMS – NM – Common – HW-SW Map (EAD 18) | PI 16 | Invalid
1018582 | #380808 | Task | Feature 380808: Submit PDO for 99-P59435M – NMS – NM – Common – HW-SW Map | PI 16 | New
1018539 |  | Task | Story 1011568: CM Release of 99-P57051M – NMS – NM – GSAM (Duplicate) | PI 16 | Invalid
1018511 | #379001 | Task | Re-apply Problem 1014745 Task for Deployment : Disable LLMWR and NetBIOS on Windows 2003 Machines (Part 1) | Unassigned | New
1018510 | #379001 | Story | Rebase and Test Problem 1014745 Story : Disable LLMWR and NetBIOS on Windows 2003 Machines (Part 1) | Unassigned | New | 2
1018447 |  | Task | Story 1011568: CM Release of 98-P54188T - NMS -NM - Security -AAA - SVD (EAD 18) | PI 16 | Invalid
1018443 |  | Task | Revive MUOS Website on cwapp205 | EA 15.1 | Done
1018429 |  | Task | Feature 1002345: Mateo's Audit_27 Test Procurement | EA 15.1 | Invalid
1018373 |  | Story | Provide support for metric following analysis - EA 15.1 | EA 15.1 | Invalid | 0
1018372 |  | Story | Provide support for metric following analysis - EA 15.2 | EA 15.2 | Invalid | 0
1018371 | #1011001 | Story | Provide support for metric following analysis - EA 15.2 | EA 15.2 | Invalid | 0
1018370 | #1011001 | Story | Provide support for metric following analysis - EA 15.1 | EA 15.1 | Invalid | 0
1018369 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.1 | EA 15.1 | Done | 1
1018368 | #395897 | Story | Support PMW as Needed - 15.5 | EA 15.5 | New | 1
1018367 | #395897 | Story | Support PMW as Needed - 15.4 | EA 15.4 | Implementing | 1
1018366 | #395897 | Story | Support PMW as Needed - 15.3 | EA 15.3 | Invalid | 0
1018365 | #395897 | Story | Support PMW as Needed - 15.2 | EA 15.2 | Done | 1
1018364 | #395897 | Story | Support PMW as Needed - 15.1 | EA 15.1 | Done | 1
1018363 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.5 | EA 15.5 | New | 3
1018362 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.4 | EA 15.4 | Implementing | 2
1018360 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Done | 1
1018359 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.2 | EA 15.2 | Done | 1
1018358 | #1006376 | Story | Feature 1006376: Update Design documentation | EA 15.2 | Done | 3
1018357 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | Done | 2
1018355 | #395897 | Story | Ted Milzarski to Consult with Cyber on transferring ACAS scan Data to SEL | EA 15.5 | New | 1
1018347 | #395897 | Story | Continue work on DADMS disapproved list | EA 15.2 | Done | 5
1018346 | #395897 | Story | Consult with Cyber on Anonymizer Tool for Host Identification | EA 15.2 | Done | 2
1018345 |  | Task | MAGIC: IF the Lab install has not started by EA 16.2, THEN we risk missing the EAD 18 train. | PI 15 | Invalid
1018344 | #395688 | Story | Investigate/Test Jan 2020 Oracle/Solaris Patches | EA 15.2 | Done | 2
1018343 | #395688 | Story | Update Patch Management Plan document | EA 15.2 | Done | 1
1018338 | #380808 | Problem | Splunk cdrComposite update | PI 16 | Approved
1018330 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (15.5) | EA 15.5 | New | 5
1018329 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (15.4) | EA 15.4 | Implementing | 2
1018328 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (15.3) | EA 15.3 | Done | 5
1018327 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (15.2) | EA 15.2 | Done | 5
1018326 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Rich (15.1) | EA 15.1 | Done | 5
1018323 | #353134 | Story | Feature 353134: Resubmit International Site Visit Paperwork/Training (SC) - Trainer 2 | EA 16.1 | New | 1
1018322 | #353134 | Story | Feature 353134: Resubmit International Site Visit Paperwork/Training (SC) - Trainer 1 | EA 16.1 | New | 1
1018320 | #353134 | Story | Feature 353134: Print and Ship Materials- Maintainer Refresher Training SC | PI 16 | New | 1
1018319 | #1008506 | Story | Feature 1008506: Provide Deployment Notes and Operator Impact Inputs - interim | EA 15.4 | Done | 1 | #1021075
1018318 | #1013452 | Story | Feature 1013452: VA process for Problem <number> - UFO Table Updates (June 2020) | EA 16.1 | New | 1
1018316 | #1013452 | Story | Feature 1013452: Implement MPC from Problem <number> - UFO Table Updates (June 2020) | EA 16.1 | New | 1
1018315 | #1013452 | Story | Feature 1013452: Create MPC for UFO Table Updates (June 2020) | PI 16 | New | 2
1018314 | #1013452 | Story | Feature 1013452: Rebase UFO Table - MPC x.y (June 2020) | PI 16 | New | 2
1018312 | #381524 | Story | Feature 381524: Procedure review | EA 15.3 | Invalid | 0
1018310 | #381524 | Story | Feature 381524: Code review | EA 15.1 | Done | 1
1018307 | #1015153 | Story | Feature 1015153: Verify Boot images are working in the target system | EA 15.3 | Done | 5
1018304 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Setup) | EA 16.1 | New | 8
1018303 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Setup) | EA 16.1 | New | 8
1018293 |  | Task | Story 1011568: CM Release of 99-P53449 Interactive Electronic Technical Manual (IETM) – SVD (EAD 18) | PI 17 | New
1018292 | #1018285 | Task | Feature 1018285: Upload Demo Documentation and Demo Status Workbook for Analysis Demo of the Coordinate and Complete Non-Feature IETM Content for EAD 18 (Analysis Demo) | EA 16.4 | New
1018291 | #1018285 | Story | Feature Demo – Customer Demo Event - Feature 1018285 | EA 16.4 | New | 1
1018290 | #1018285 | Story | Feature 1018285: IETM Admin Updates Part 1 of 3 (EA 16.1) | EA 16.1 | New | 2
1018289 | #1018285 | Story | Feature 1018285: IETM Admin Updates Part 2 of 3 (EA 16.2) | EA 16.2 | New | 2
1018288 | #1018285 | Story | Feature 1018285: IETM Admin Updates Part 3 of 3 (EA 16.3) | EA 16.3 | New | 2
1018287 | #1018285 | Story | Feature 1018285: IETM Admin Updates part 4 of 5 (EA xx.4) | PI 16 | Invalid | 0
1018286 | #1018285 | Story | Feature 1018285: IETM Admin Updates part 5 of 5 (EA xx.5) | PI 16 | Invalid | 0
1018285 | #262146 | Feature | Coordinate and Complete Non-Feature IETM Content for EAD 18 (Recurring) | EA 16.4 | Approved
1018282 | #1014596 | Story | Feature 1014596: ULX CP - Prototype ULX Selector (Read N DSP Taps) and Unit Test | EA 15.3 | Done | 3
1018281 | #1014596 | Story | Feature 1014596: ULX CP - Prototype ULX Normalizer (Set Power Level) and Unit Test | EA 15.3 | Done | 3
1018280 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Managers - Health & Status and Logging | EA 16.1 | New | 3
1018279 | #1015153 | Story | Feature 1015153: Create a preliminary STCD to be used for the analysis Feature Demo | EA 15.2 | Done | 2
1018275 | #1015153 | Story | Feature 1015153: Release the ISO Conversion Procedure | EA 15.1 | Done | 3
1018259 | #358656 | Story | Feature 358656 Engineering ET COTS IETM Development and Integration updates (Part 4) | EA 15.1 | Done | 3
1018256 |  | Story | Feature 1014598: 18-02 Setup Development Environment | Unassigned | Invalid | 0
1018255 |  | Story | Feature 1014598: 18-02 Setup Development Environment | Unassigned | Invalid | 0
1018254 | #1014598 | Story | Feature 1014598: 18-02 Setup Development Environment | EA 15.1 | Done | 8
1018253 | #1014598 | Story | Feature 1014598: 18-02 Setup Development Environment | EA 15.1 | Done | 8
1018250 | #342163 | Story | Feature 342163: Update TACLANE STCD (including IETM procedures) - EA 15.4 | EA 15.4 | Done | 1
1018245 |  | Story | Rebase Problem 357946 and Problem 360439 (EA 15.3) | Unassigned | Invalid | 0
1018244 |  | Story | Rebase Problem 347605 Story (EA 15.3) | Unassigned | Invalid | 0
1018243 | #342163 | Task | Rebase Problem 347605 Story (EA 15.2) | EA 15.2 | Done
1018240 | #1006376 | Task | Feature 1006376: Submit PDO for RNC CI: 98-P53511T-GTS-RN-RNC-SVD | EA 15.4 | In Development
1018234 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - Part 2b perform install | EA 15.3 | Invalid | 0
1018233 | #1018204 | Story | Feature 1018204: SME support for enhanced alt-telemetry (attend meetings, follow-on discussions) 15.4 | EA 15.4 | Implementing | 1
1018232 | #1018204 | Story | Feature 1018204: SME support for enhanced alt-telemetry (attend meetings, follow-on discussions) 15.3 | EA 15.3 | Done | 1
1018227 | #1018204 | Story | Feature 1018204: SME support for enhanced alt-telemetry (attend meetings, follow-on discussions) 15.2 | EA 15.2 | Invalid | 0
1018226 | #1018204 | Story | Feature 1018204: SME support for enhanced alt-telemetry (attend meetings, follow-on discussions) 15.1 | EA 15.1 | Done | 1
1018225 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - EMM SVD update only | EA 15.2 | Done | 2
1018224 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - Part 3 perform install | EA 15.4 | Invalid | 0
1018223 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - Part 2a perform install | EA 15.2 | Invalid | 0
1018210 | #395897 | Story | Map Patches to Hostnames - 15.5 | EA 15.5 | New | 3
1018209 | #380808 | Story | Feature 380808: Update Splunk SVDs and review | EA 15.4 | Implementing | 3
1018208 | #395897 | Story | Map Patches to Hostnames - 15.4 | EA 15.4 | Implementing | 3
1018206 | #395897 | Story | Map Patches to Hostnames - 15.3 | EA 15.3 | Invalid | 0
1018205 | #395897 | Story | Map Patches to Hostnames - 15.2 | EA 15.2 | Done | 3
1018204 | #243422 | Feature | TD 20-06: MUOS space support enhanced alternate telemetry (part 2 of 2) | EA 15.4 | Implementing
1018203 | #395897 | Story | Map Patches to Hostnames - 15.1 | EA 15.1 | Done | 3
1018201 | #1017680 | Task | Feature 1017680: Submit PDO for 98-P55613M ET SVD | EA 15.3 | Done
1018200 |  | Task | Feature 1015153: Submit PDO for 98-P59405M NM Microsoft SQL Server SVD | PI 15 | Invalid
1018199 | #395897 | Story | Adjudicate Findings from POAM Lists and Audits - 15.5 | EA 15.5 | New | 3
1018198 | #395897 | Story | Adjudicate Findings from POAM Lists and Audits - 15.4 | EA 15.4 | Implementing | 3
1018197 |  | Task | Feature 1015153: Submit PDO for 98-P59437M NM Tape Library, SVD | PI 15 | Invalid
1018196 | #395897 | Story | Adjudicate Findings from POAM Lists and Audits - 15.3 | EA 15.3 | Done | 3
1018194 | #395897 | Story | Adjudicate Findings from POAM Lists and Audits - 15.2 | EA 15.2 | Done | 3
1018193 | #395897 | Story | Generate PWIs from 2020 POAM List - 15.1 | EA 15.2 | Done | 3
1018192 | #395897 | Story | Adjudicate Findings from POAM Lists and Audits - 15.1 | EA 15.1 | Done | 3
1018191 | #1015153 | Task | Feature 1015153: Submit PDO for 98-P54190T NM Ericsson Multi Mediation, SVD | EA 15.4 | Done
1018188 | #343920 | Task | Story 343920: CM Release of 99-P61689A – SEIT (EAD 16) [aka MUOS I-Level Procedures and Supporting Material] | Unassigned | Done
1018187 | #376446 | Story | Feature 376446: Regression Testing (MultiHAL) Pt.3 | EA 15.3 | Done | 8
1018186 | #376446 | Story | Feature 376446: Regression Testing (MultiHAL) Pt.2 | EA 15.2 | Done | 8
1018185 | #380808 | Story | Feature 380808: Get SWIT network working for Nutanix SuperMicro | EA 15.1 | Done | 1
1018184 | #395897 | Story | Associate Hostnames to IAVA - 15.5 | EA 15.5 | New | 2
1018183 | #1015153 | Story | Investigate non-problematic disc images (.iso files) | EA 15.1 | Done | 5 | #1019342
1018182 | #395897 | Story | Associate Hostnames to IAVA - 15.4 | EA 15.4 | Implementing | 2
1018181 | #395897 | Story | Associate Hostnames to IAVA - 15.3 | EA 15.3 | Done | 2
1018180 | #380808 | Story | Feature 380808: Install Nutanix in SWIT | EA 15.1 | Done | 3
1018179 | #395897 | Story | Associate Hostnames to IAVA - 15.2 | EA 15.2 | Done | 2
1018178 | #395897 | Story | Associate Hostnames to IAVA - 15.1 | EA 15.1 | Invalid | 0
1018177 | #395688 | Story | Support Deploy of January Solaris Patches to Target Hosts | EA 15.4 | Implementing | 1
1018176 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - Part 5 verification | EA 15.4 | Done | 2
1018175 | #1015153 | Story | Update 98-P55613M ET SVD to no longer require Roxio | EA 15.3 | Done | 3 | #1021042
1018174 | #395688 | Story | Investigate Jan 2020 Oracle/Solaris Patches | EA 15.1 | Done | 3
1018171 | #1013234 | Story | Feature 1013234: Relay knowledge objects and fundamental building blocks for Spring MVC / Prototype | EA 15.2 | Done | 1
1018170 | #1015153 | Story | Update 98-P59405M NM Microsoft SQL Server SVD to no longer require Roxio | EA 15.3 | Invalid | 0
1018167 | #1013234 | Story | Feature 1013234: Test/verify MS-SQL 2019 compatibility w/ current PPA and Hibernate LIB - Greg M | EA 15.4 | Done | 3
1018163 | #1015153 | Story | Update 98-P59437M NM Tape Library, SVD to no longer require Roxio | EA 15.3 | Invalid | 0
1018158 |  | Story | Update 98-P59437M NM Tape Library, SVD to no longer require Roxio | EA 15.1 | Invalid | 0
1018155 | #1015153 | Story | Update 98-P54190T NM Ericsson Multi Mediation, SVD to no longer require Roxio - Part 1 Analyze new ISO image | EA 15.1 | Done | 1
1018154 | #1013750 | Story | Feature 1013750: Lab - Support from RAN | EA 15.4 | New | 1
1018147 | #1015153 | Story | Investigate non-problematic disc images (.iso files) | EA 15.1 | Done | 5 | #1019342
1018134 | #380808 | Story | Feature 380808: Create SCD for Nutanix | EA 15.1 | Done | 1
1018133 | #396669 | Story | Feature 396669: Finish STCD test execution | EA 15.3 | Done | 1
1018131 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support (16.1) | EA 16.1 | New | 2
1018129 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support | EA 15.5 | New | 1
1018128 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support | EA 15.4 | Implementing | 1
1018117 | #380808 | Story | Feature 380808: Planning for future MUOS rack migration plan with Nutanox | EA 15.1 | Done | 3
1018096 | #1006376 | Problem | RNC support of MAMA2 Response raDifferent flag does not comply with MUOS CAI | EA 15.4 | Approved
1018089 | #1006191 | Story | Fix SWIT Lab Drive Mapping and Install ClearCase/ClearQuest 7.1.2.14 on masV2XP VM | EA 15.1 | Done | 1
1018084 |  | Story | Feature 342054: Update FM topology to handle new AWARE node names from Fault Notifier | Unassigned | Invalid | 0
1018078 | #1008506 | Story | Feature 1008506: ILS support - Review of Splunk HA recovery procedures | EA 15.4 | Implementing | 3
1018072 | #1001912 | Story | Feature 1001912: Complete Softphone: PWI Burndown | EA 15.1 | Done | 2
1018071 | #332951 | Story | Feature 332951: Finish and Review STCD | EA 15.4 | Implementing | 1
1018070 | #332951 | Story | Feature 332951: SME Support of RBS IETM Updates (15.1) | EA 15.1 | Invalid | 0
1018069 | #332951 | Story | Feature 332951: Cross train on RBS IETMs | EA 15.1 | Done | 1
1018066 | #389561 | Task | CM Release of Obsolescence Capabilities Specification Document for DSN Gateway - Initial Release | EA 14.5 | Done
1018064 | #1002583 | Story | Correct known issues for hard drive footprint generation | EA 15.4 | Done | 3
1018063 | #1002583 | Story | Diagnose known issues for hard drive footprint generation | EA 15.1 | Done | 3
1018062 | #1002345 | Story | Fix Problem 375419: Signaling Link Unavailable alarm includes specifics in "Summary" such that O-Level could not find this specific alarm and perform recovery procedure. | EA 15.2 | Done | 3
1018061 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MFR package preparation) | EA 15.3 | Done | 1
1018060 | #1005321 | Story | Feature 1005321: Populate the Spreadsheet Created to Capture all the MUOS Servers Impacted by IA Patching with IA Patching Information | EA 15.3 | Done | 3
1018038 | #396669 | Story | Feature 396669: IETM Cross Training for Alarm Recovery Procedures for RCG Alarms (15.2) | EA 15.2 | Done | 1
1018037 | #396669 | Story | Feature 396669: IETM Cross Training for Alarm Recovery Procedures for RCG Alarms (15.1) | EA 15.1 | Done | 1
1018036 | #396669 | Story | Feature 396669: IETM Cross Training for Alarm Recovery Procedures for RCG Alarms (15.3) | EA 15.3 | Done | 1
1018035 | #396669 | Story | Feature 396669: IETM Cross Training for Alarm Recovery Procedures for RCG Alarms (15.4) | EA 15.4 | New | 1
1018033 | #332951 | Story | Feature 332951: ILS Cross Training | EA 15.4 | Implementing | 1
1018032 | #332951 | Story | Feature 332951: ILS Cross Training | EA 15.3 | Done | 1
1018031 | #332951 | Story | Feature 332951: IETM Cross Training for Alarm Recovery Procedures for RBS Alarms (15.3) | EA 15.3 | Done | 1
1018030 | #332951 | Story | Feature 332951: IETM Cross Training for Alarm Recovery Procedures for RBS Alarms (15.1) | EA 15.1 | Done | 1
1018029 | #395853 | Story | Generate and review with customer MFR for EAD 17.0 (Part 2) | EA 15.5 | New | 2
1018028 | #332951 | Story | Feature 332951: UX/ILS Support for RBS Alarm Recovery Procedures (15.3) | EA 15.3 | Done | 2
1018027 | #332951 | Story | Feature 332951: IETM Cross Training for Alarm Recovery Procedures for RBS Alarms (15.2) | EA 15.2 | Done | 1
1018025 | #332951 | Story | Feature 332951: Update RNC Health Check to check the number of groups provisioned at NMS | EA 15.1 | Done | 2
1018022 | #1007536 | Story | Feature 1007536: Write Up CONOPS section 6 Operational scenarios and Informal Review | EA 15.4 | Implementing | 2 | #1010788 #1010790
1018018 | #1007536 | Story | Feature 1007536: Convert draft scenarios into Workflows/Graphics for CONOPS section 6 Operational scenarios | EA 15.3 | Done | 3 | #1018022
1018011 | #380808 | Story | Feature 380808: (IA) IA evaluation of RHEL 7.8 image & give feedback to developer | EA 15.3 | Done | 3
1018009 | #380808 | Story | Feature 380808: Prep for Perform hardening of RHEL 7.8 image | EA 15.1 | Done | 1
1018008 | #380808 | Story | Feature 380808: Perform hardening of RHEL 7.8 image | EA 15.2 | Done | 5
1018007 | #380808 | Story | Feature 380808: Perform hardening of RHEL 7.8 image | EA 15.3 | Done | 5
1018002 | #395897 | Story | 8) Work with PMW to disposition resolved/mitigated CAT1s | EA 15.3 | Invalid | 0
1018001 | #395897 | Story | Complete Vulnerability Assessment Guidance document-Part 3 | EA 15.4 | New | 3
1017991 | #1015153 | Story | Windows 10 Disc image conversion from corrupted .iso/.gi to .iso and testing in lab | EA 15.1 | Done | 2 | #1015334
1017980 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.5 | EA 15.5 | New | 2
1017978 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (part 2) | EA 15.4 | Implementing | 1
1017977 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.4 | EA 15.4 | Implementing | 2
1017972 |  | Problem | In the FOUO Enclave, it is not possible to log into some Firewalls using a Radius (domain) Account. The following Firewalls cannot be logged into using a Radius Account: "auiasrfw1", "hqiascfw1", "hqiascfw2" | Unassigned | Assessing
1017971 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.3 | EA 15.3 | Done | 2
1017969 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.2 | EA 15.2 | Done | 2
1017967 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.1 | EA 15.1 | Done | 2
1017954 | #1015911 | Story | Feature 1015911: Create deployment notes and operational impacts | PI 16 | New | 1
1017953 | #1015911 | Story | Feature Demo - Customer Demo Event: Feature 1015911: Implement DL Power Spike fix | PI 16 | New | 5
1017951 | #358656 | Story | Feature 358656 Engineering ET IETM Research, Development, and Integration Alarm Procedure (Part 2 - No Procedures Exist) | EA 15.1 | Done | 8
1017948 | #1006191 | Story | Feature 1006191 Provide estimate for WF robustness (15.2) | EA 15.2 | Done | 1
1017945 | #1004171 | Story | Feature 1004171: Monitor logs - Part D | EA 15.5 | Invalid | 0
1017944 | #1004171 | Story | Feature 1004171: Monitor logs - Part C | EA 15.4 | New | 2
1017933 | #1014491 | Story | Define additional KPIs | EA 15.2 | Done | 2
1017932 | #1014491 | Story | Define additional KPIs | EA 15.1 | Done | 1
1017929 | #1006191 | Story | Feature 1006191 Review all CAT 1 and CAT 2 findings and provide estimate to address | EA 15.1 | Done | 1
1017924 | #358656 | Story | Feature 358656 Engineering ET IETM Development and Integration updates (Part 1 - No Procedures Exist) | EA 15.1 | Done | 8
1017920 | #1009453 | Story | Feature 1009453: Execute tests for DL power spike investigation (Lab team) | EA 15.1 | Done | 1
1017918 | #1004171 | Story | Feature 1004171: Build RNC OPI | EA 16.2 | New | 1
1017917 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MAS' STIGs assessment - Part 2) | EA 15.1 | Invalid | 0
1017915 | #1004171 | Story | Feature 1004171: Update RNC OPI document | EA 15.4 | Invalid | 0 | #1017918
1017895 | #1015153 | Story | <Feature 1015153>- Demo Support | EA 15.2 | Invalid | 0
1017882 | #395688 | Story | Download May and June patches, and update patching script Part B | EA 15.5 | New | 2
1017880 | #1011394 | Story | Feature 1011394: ILS Support of DMSMS Tracker | EA 15.5 | New | 5
1017879 | #1011394 | Story | Feature 1011394: ILS Support of DMSMS Tracker | EA 15.3 | Done | 5
1017878 | #1011394 | Story | Feature 1011394: ILS Support of DMSMS Tracker | EA 15.1 | Done | 5
1017876 | #1004171 | Story | Feature 1004171: Execute Tests on Final RNC Build | EA 15.4 | New | 1
1017875 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Done | 5
1017874 | #1011441 | Story | Feature 1011441: Review CDRL A010 with 2019 LORA for IETM Impacts | EA 15.3 | Done | 1
1017872 | #1017837 | Task | Test Task: Prototype of new CM release task - CI3 | Unassigned | New
1017867 | #1007900 | Story | Feature 1007900: Verification for SVD's Modified due to changes to HBSS. PI-16 | PI 16 | New | 5
1017864 | #1004171 | Story | Feature 1004171: Create STCD | EA 15.1 | Done | 2
1017860 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.4 | New | 2
1017859 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.3 | Done | 3
1017855 | #377437 | Story | Feature 377437 ETT Laptop - Feature Demo assist | EA 15.3 | Invalid | 0
1017845 | #1014597 | Story | Feature 1014597: Support & Delivery of ULX Manager (Axure HTML Model) – Version 2 | EA 15.4 | Implementing | 2
1017843 | #1014597 | Story | Feature 1014597: Support & Delivery of ULX Manager (Axure HTML Model) – Version 1 | EA 15.3 | Done | 3
1017842 | #1014597 | Story | Feature 1014597: Delivery of ULX Manager Heuristic Analysis Report | EA 15.2 | Done | 3
1017834 | #1006376 | Story | Feature 1006376: Create custom WF build to test RNC corner cases | EA 15.1 | Invalid | 0
1017833 | #377437 | Story | Feature 377437 ETT: Verify PCRs (part2) | EA 15.2 | Done | 1
1017830 | #380808 | Story | Feature 380808: Regression test after Splunk install Part 2 | EA 15.3 | Done | 2
1017816 | #395855 | Story | Feature Demo – Customer Demo Event - Feature 395855: PI 14 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 15.1 | Done | 1
1017813 | #1013657 | Story | Release Regression - CSCF IETM Procedure | EA 15.1 | Done | 2
1017810 | #1013534 | Story | Feature 1013534: Lab - Maintain OTA Call Banks - SME Support - Loretta (15.4) | EA 15.4 | Invalid | 0
1017808 | #1013534 | Story | Feature 1013534: Lab - Maintain OTA Call Banks - SME Support - Loretta (15.2) | EA 15.2 | Done | 1
1017806 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (15.31) | EA 15.3 | Done | 1
1017785 | #1005321 | Story | Update the Spreadsheet Capturing all the MUOS Servers Impacted by IA Patching Part B | EA 15.3 | Invalid | 0
1017784 | #1005321 | Story | Update the Spreadsheet Capturing all the MUOS Servers Impacted by IA Patching | EA 15.3 | Invalid | 0
1017775 | #1012485 | Story | Feature 1012485: Update the JDTA for WH ACAS scanning | EA 15.1 | Invalid | 0
1017773 | #395688 | Story | Updated HW SW Map for May Patch deployment Part B | EA 15.1 | Invalid | 0
1017769 | #1007900 | Story | Feature 1007900: Monitor and document HIPS and MAC exceptions identified during development of HBSS on High side. | EA 15.3 | Done | 1
1017768 | #395688 | Story | Update Node Config for IA patches Part B | EA 15.5 | New | 1
1017767 | #1007900 | Story | Feature 1007900: Monitor and document HIPS and MAC exceptions identified during development of HBSS on High side. | EA 15.2 | Done | 1
1017758 | #395688 | Story | Update Patch SVDs for with redlines from site and misc cleanup Part B | EA 15.3 | Invalid | 0
1017752 | #395688 | Story | Download patches, and update patching script Part B | EA 15.1 | Done | 1
1017751 | #395688 | Story | Download patches, and update patching script Part A | EA 15.1 | Done | 1
1017743 |  | Story | Feature 1007900: Update MUOS_IG_GS_NMS_NM_Common_TSM_SVD_98-P59401M003 to add ePO201 from this server- Part 2 (Code Collaborator Done) | EA 15.4 | Invalid | 0
1017742 | #243427 | Task | Support obsolescence roadmap- Steve Cox | EA 15.2 | Done
1017741 | #243427 | Task | Support obsolescence roadmap- Steve Cox | EA 15.3 | Done
1017740 | #243427 | Task | Support obsolescence roadmap- Brandon Ebert | EA 15.3 | Done
1017739 | #243427 | Task | Support obsolescence roadmap- Randy Afdahl | EA 15.3 | Done
1017738 | #243427 | Task | Support obsolescence roadmap- Randy Afdahl | EA 15.2 | Done
1017737 | #243427 | Task | Support obsolescence roadmap- Aaron Smith | EA 15.1 | Done
1017694 | #1017680 | Story | <Feature 1017680>: Initiate CM PDO Processing for all CI's | EA 15.2 | Invalid | 0
1017693 | #1017680 | Story | <Feature 1017680>- Prep and Perform Feature Demo – Customer Demo Event | EA 15.3 | Invalid | 0 | #1017694
1017692 | #1017680 | Story | <Feature 1017680>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.3 | Invalid | 0 | #1017693
1017691 | #1017680 | Story | <Feature 1017680>: Execute STCD Feature Integration and testing including STCD updates identified | EA 15.2 | Invalid | 0 | #1017693
1017690 | #1017680 | Story | <Feature 1017680>: Provide Development inputs to common documents | EA 15.5 | Invalid | 0 | #1017693
1017689 | #1017680 | Story | <Feature 1017680>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | EA 15.3 | Invalid | 0
1017688 | #1017680 | Story | <Feature 1017680> UX Research and Design Support (Change back to UX Team) | EA 15.1 | Invalid | 0
1017687 | #1017680 | Story | <Feature 1017680>: Develop IETMs and Perform Development Testing | EA 15.5 | Invalid | 0 | #1017693
1017686 | #1017680 | Story | <Feature 1017680>: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 15.2 | Invalid | 0 | #1017693
1017685 | #1017680 | Story | <Feature 1017680>: Perform Iterative Implementation, Integration, development Testing including updating design | EA 15.5 | Invalid | 0 | #1017693
1017684 | #1017680 | Story | <Feature 1017680>: Provide Deployment Notes and Operator Impact Inputs | EA 15.2 | Invalid | 0 | #1017693
1017683 | #1017680 | Story | <Feature 1017680>: Create STCD and review with stakeholders | EA 15.1 | Invalid | 0 | #1017692 #1017685 #1017693 #1017691
1017682 | #1017680 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | EA 15.5 | Invalid | 0 | #1017685 #1017683
1017681 | #1017680 | Task | <Feature 1017680> Hold Feature Review with SMEs | EA 15.1 | Done
1017680 | #262146 | Feature | ET SVD MPC Rebases - Dehydrator, FEP, ACU | EA 15.3 | Done
1017678 | #243502 | Story | CM Release Work for EAD 18 OOC | PI 16 | New | 1
1017676 |  | Problem | Dashboard Pie-Charts are Difficult to Read When Small Number of Errors | Unassigned | Assessing
1017673 | #1012996 | Story | WF CLL Build Support for EA 15.5 | EA 15.5 | New | 1
1017672 | #1012996 | Story | WF CLL Build Support for EA 15.4 | EA 15.4 | Implementing | 1
1017671 | #1012996 | Story | WF CLL Build Support for EA 15.3 | EA 15.3 | Done | 1
1017670 | #1012996 | Story | WF CLL Build Support for EA 15.2 | EA 15.2 | Done | 1
1017669 | #1012996 | Story | WF CLL Build Support for EA 15.1 | EA 15.1 | Done | 1
1017664 | #379001 | Task | Re-apply Problem 1015622 Task for Deployment : Update Diameter configurations in NW CSCF/HSS due to troubleticket. | Unassigned | New
1017663 | #393391 | Story | Rebase and Test Problem 1015622 Story : Update Diameter configurations in NW CSCF/HSS due to troubleticket. | Unassigned | New | 2
1017656 | #388053 | Story | U pdate the capability design to remove containers and re-assess hardware requirements. | EA 15.4 | Implementing | 3
1017653 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs and Build and Share expertise | EA 15.2 | Done | 1
1017652 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs and Build and Share expertise | EA 15.3 | Done | 1
1017651 | #379001 | Task | Re-apply Problem 366270 Task for Deployment : Inconsistent configuration of the /etc/ipf/pfil.ap file for ipfilter on gis-xx servers for ipfilter functionality | Unassigned | New
1017650 | #379001 | Story | Rebase and Test Problem 366270 Story : Inconsistent configuration of the /etc/ipf/pfil.ap file for ipfilter on gis-xx servers for ipfilter functionality | Unassigned | New | 2
1017649 | #379001 | Task | Re-apply Problem 364509 Task for Deployment : MAS /etc/hosts need update to work for both VAS install and mas-mas communication | Unassigned | New
1017648 | #379001 | Story | Rebase and Test Problem 364509 Story : MAS /etc/hosts need update to work for both VAS install and mas-mas communication | Unassigned | New | 2
1017646 | #379001 | Task | Re-apply Problem 334428 Task for Deployment : Site printer install instructions will not support printing from all WIn10 and XP workstations | Unassigned | New
1017645 | #379001 | Story | Rebase and Test Problem 334428 Story : Site printer install instructions will not support printing from all WIn10 and XP workstations | Unassigned | New | 2
1017639 | #342054 | Task | Feature 342054: Submit PDO for 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD | PI 16 | New
1017626 | #1006376 | Story | Feature 1006376: Create custom WF build to test RNC corner cases | EA 15.3 | Done | 2
1017623 | #388053 | Story | Design PPA Replacement | EA 15.3 | Done | 2
1017617 | #1013452 | Task | Feature 1013452: Submit PDO for 98-P55755M - Firewall - Network - SVD | PI 16 | New
1017613 | #1006376 | Story | Feature 1006376: Execute Tests on Final RNC Build | EA 15.4 | New | 1
1017612 | #1006376 | Story | Feature 1006376: Execute Tests - Part C | EA 15.3 | Done | 3
1017611 | #1006376 | Story | Feature 1006376: Execute Tests - Part B | EA 15.2 | Done | 5
1017608 | #1006376 | Story | Feature 1006376: Execute Tests - Part A | EA 15.1 | Done | 3
1017570 | #332951 | Story | Feature 332951: UX/ILS Support for RBS Alarm Recovery Procedures (15.4) | EA 15.4 | Implementing | 1
1017569 | #396669 | Story | Feature 396669: Execute STCD Feature Integration and testing including STCD updates identified | EA 15.4 | Invalid | 0
1017568 | #396669 | Story | Feature 396669: UX IETM Support for Alarm Recovery Procedures for RCG Alarms (15.3) | EA 15.3 | Done | 1
1017567 | #396669 | Story | Feature 396669: UX IETM Support for Alarm Recovery Procedures for RCG Alarms (15.2) | EA 15.2 | Done | 1
1017563 | #1011001 | Story | Collect metrics for reporting and communication to LM and PMW-146 stakeholders - monthly | EA 15.4 | Implementing | 2
1017562 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.5 | EA 15.5 | New | 2
1017558 | #381524 | Story | Feature 381524: Fix 381547: Unit testing and coverage reports for Provisioning Bridge database contention can bring down terminal provisioning (INC000004253880) | EA 15.1 | Done | 1
1017557 | #381524 | Story | Feature 381524: Create and Review STCD (Part 2) | EA 15.3 | Done | 3
1017556 | #1015005 | Story | Capability Specification Development | EA 15.4 | Implementing | 3
1017555 | #1015005 | Story | Capability Specification Development | EA 15.3 | Done | 2
1017554 | #388053 | Story | Design FCAPS Replacement | EA 15.3 | Done | 3
1017550 | #380808 | Story | Feature 380808: Work with development to implement Nutanix hardening instructions in Nutanix SVD | EA 15.2 | Done | 1
1017549 | #380808 | Story | Feature 380808: Work with IA to implement Nutanix hardening instructions in Nutanix SVD | EA 15.2 | Done | 3
1017548 | #380808 | Story | Feature 380808: (IA) MFR 3 – Update previous Nutanix CAP and update set of applicable STIGs & achieve customer concurrence | EA 15.1 | Done | 3
1017547 | #1014597 | Story | Feature 1014597: Support ULX Manager, Mon & Control Development (Part 3) | EA 15.4 | Implementing | 1
1017546 | #1014597 | Story | Feature 1014597: Support ULX Manager, Mon & Control Development (Part 2) | EA 15.3 | Done | 2
1017541 | #384136 | Story | Feature 384136: Perform dry run testing of HBSS IETM procedures - EA 14.5 | EA 14.5 | Done | 2
1017530 | #1013234 | Story | Feature 1013234: Implement Spring MVC prototype (Part 2b) | EA 15.2 | Done | 2
1017529 | #1004171 | Story | Feature 1004171: create ICM Release records for RNC PDOs | EA 16.1 | New | 1 | #1015856 #381617
1017528 | #1013234 | Story | Feature 1013234: Test/validate compatibility of TomeEE JMS / ActiveMQ | EA 15.1 | Done | 3
1017527 | #1004171 | Story | Feature 1004171: Build RNC for final testing, demo and release | EA 15.4 | Implementing | 5
1017526 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master lost comm | EA 15.2 | Done | 2
1017520 | #1008506 | Story | Feature 1008506: Write recovery Procedure 4- Recover from cluster master going down | EA 15.1 | Invalid | 0
1017517 | #380808 | Story | Feature 380808: SIC team support: Install Splunk VMs from Scratch and regression (2600) Nutanix, Splunk HA | EA 15.2 | Done | 3
1017514 | #354871 | Task | Feature 354871: Submit PDO for 98-P59291M - SCS - OA - SVD | PI 16 | New
1017513 | #1008506 | Story | Feature 1008506: Sprint 15.4 UX support review of Splunk HA recovery procedures | EA 15.4 | Implementing | 1
1017512 | #1008506 | Story | Feature 1008506: Sprint 15.3 UX support review of Splunk HA recovery procedures | EA 15.3 | Done | 1
1017511 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Design Documentation and Review Support) | EA 15.4 | Implementing | 2
1017510 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Design Documentation and Review Support) | EA 15.3 | Done | 2
1017509 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Design Documentation and Review Support) | EA 15.2 | Done | 1
1017497 | #1008506 | Story | Feature 1008506: Implement - Problem 1010043 | EA 15.4 | Implementing | 2
1017496 | #1008506 | Story | Feature 1008506: Implement - Problem 1010039 | EA 15.4 | Implementing | 2
1017494 | #1008506 | Story | Feature 1008506: Recovery procedures for Splunk HA - SME support for interim demo | EA 15.5 | New | 1
1017492 | #1008506 | Story | Feature 1008506: Splunk HA recovery procedures - Create and review STCD for interim demo | EA 15.3 | Done | 2
1017491 | #1008506 | Story | Feature 1008506: Perform dry-run of STCD for interim demo | EA 15.5 | New | 1
1017484 | #1008506 | Story | Interim Demo for Feature - Feature 1008506 | EA 15.5 | New | 1
1017482 | #1008506 | Story | Feature 1008506: Developer perform troubleshooting procedure dry-runs (Part 4) | PI 16 | New | 3
1017480 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 17 - Data rebalancing for indexers new or offline for an extended period of time | PI 16 | New | 5
1017478 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 16 - Troubleshooting when search head member cannot send to captain (Part 1 - investigation) | EA 15.1 | Done | 2
1017477 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 15 - Troubleshooting procedure to fix dbconnect rpc issue with error showing incorrect java version or python issue | PI 16 | New | 5
1017476 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 14 - Troubleshooting procedure for Replication Factor not met | PI 16 | New | 5
1017475 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 13 - Troubleshooting procedure for Search Factor not met | EA 15.4 | Implementing | 5
1017474 | #1008506 | Story | Feature 1008506: Developer perform troubleshooting procedure dry-runs (Part 3) | PI 16 | New | 2
1017472 | #1008506 | Story | Feature 1008506: Developer perform troubleshooting procedure dry-runs (Part 2) | PI 16 | New | 2
1017471 | #1008506 | Story | Feature 1008506: Developer perform troubleshooting procedure dry-runs (Part 1) | PI 16 | New | 2
1017465 | #1008506 | Story | Feature 1008506: Developer perform recovery procedure dry-runs (Part 1) | EA 15.2 | Done | 1
1017463 | #1008506 | Story | Feature 1008506: Developer perform recovery procedure dry-runs (Part 2) | EA 15.3 | Done | 1
1017458 | #1008506 | Story | Feature 1008506: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 2) | EA 15.3 | Done | 1
1017456 | #1008506 | Story | Feature 1008506: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 1) | EA 15.2 | Done | 1
1017454 | #1007900 | Story | Feature 1007900: MFR 3 – CSE Start Write-up MFR 3 package for CAP | EA 15.3 | Done | 3
1017453 | #1007900 | Story | Feature 1007900: Update MUOS_IG_GS_NMS_NM_Common_TSM_SVD_98-P59401M003 to add ePO201 from this server | EA 15.3 | Done | 5
1017452 | #1008506 | Story | Feature 1008506: Sprint 15.4 Support review of Splunk HA recovery procedures (leader) | EA 15.4 | Implementing | 3
1017451 | #1008506 | Story | Feature 1008506: Sprint 15.3 Support review of Splunk HA recovery procedures (leader) | EA 15.3 | Done | 3
1017450 | #1008506 | Story | Feature 1008506: Create and support review of Splunk HA recovery procedures | EA 15.2 | Done | 2
1017449 | #1008506 | Story | Feature 1008506: Write recovery Procedure 6- Decoder recovery procedure for lost heartbeat alarm | EA 15.1 | Done | 3
1017447 | #1013234 | Story | Feature 1013234: Develop a proof of concept library using JDBC for DB communication alternative to hibernate | EA 15.1 | Done | 3
1017444 | #380808 | Story | Feature 380808: Re-Scan and STIG HA VM after RHEL Image | EA 15.2 | Done | 2
1017440 | #343920 | Task | Story 343920: CM Release of 01-P52960E001 - SITE - INSTALLATION KIT - SF/NMF (EAD 16) | EA 15.1 | Done
1017434 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Complete Instantiation & Configuration (via JSON Config File)Test | EA 15.4 | Implementing | 2
1017433 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Complete Instantiation & Configuration (via JSON Config File) | EA 15.4 | Implementing | 2
1017431 | #343920 | Task | Story 343920: CM Release of 30-P48080V - SITE - CABLE ASSEMBLY, RACK POWER, 208V 50AMP, SF/NMF (MsWord doc.)(EAD 16) | EA 15.1 | Done
1017430 | #343920 | Task | Story 343920: CM Release of 53-P52490E - SITE - AC POWER DISTRIBUTION - WAHIAWA (AutoCAD) (EAD 16) | EA 15.1 | In Development
1017428 | #358656 | Story | Feature 358656 Engineering ET COTS IETM Development and Integration updates (Part 5) | EA 16.1 | New | 5
1017427 | #358656 | Story | Feature 358656 Engineering ET Custom Alarms IETM Development and Integration updates (Part 3) | EA 15.3 | Done | 5
1017417 | #380808 | Story | Feature 380808: Assist with Nutanix STCD dev & test | EA 15.4 | Implementing | 1
1017416 | #380808 | Story | Feature 380808: Assist with Nutanix STCD dev & test | EA 15.3 | Invalid | 0
1017415 | #380808 | Story | Feature 380808: Load baseline and execute STCD in the VLab | EA 15.4 | New | 5
1017414 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Information Assurance Design - Continued from EA 15.1 [15.2] | EA 15.2 | Done | 1
1017413 |  | Story | Feature 1008506: UX review and input for recovery Procedure 1- Recover from Indexer going down | PI 15 | Invalid | 0
1017409 | #1018285 | Task | Feature 1018285: Submit PDO for 99-P53449E - ILS - IETM | EA 16.4 | New
1017406 | #385632 | Story | FM Whitelist updates for PI15: Complete filter logic | EA 15.3 | Done | 1
1017405 | #1002583 | Story | Investigate SWIT ClearCase 9 Installation for Windows 10 Hosts | EA 15.1 | Done | 3
1017404 | #1015911 | Story | Feature 1015911: Create Site validation plan | PI 16 | New | 2
1017403 | #1014596 | Story | Feature 1014596: ULX CP - Develop B2U SBC Combiner/Resampler and Unit Test | EA 16.1 | New | 8
1017401 | #1014596 | Story | Feature 1014596: ULX CP - Develop L2 Unit Tests & Integrate to Pipeline | EA 16.1 | New | 5
1017393 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C00XX Verification Plan | EA 16.1 | New | 5
1017392 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C0059 User's Manual (Draft) | EA 16.1 | New | 5
1017387 | #1014595 | Story | Feature 1014595: ULX DD - Subcontract Management Support (AMS & RINCON) | EA 16.1 | New | 1
1017386 | #1014595 | Story | Feature 1014595: ULX DD - Subcontract Management Support (AMS & RINCON) | EA 15.4 | Implementing | 1
1017385 | #1014595 | Story | Feature 1014595: ULX DD - Subcontract Management Support (AMS & RINCON) | EA 15.3 | Done | 1
1017384 | #1014595 | Story | Feature 1014595: ULX DD - Subcontract Management Support (AMS & RINCON) | EA 15.2 | Done | 1
1017376 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C00XX Verification Plan | EA 16.1 | New | 2
1017375 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C00XX Verification Plan | EA 15.4 | Implementing | 2
1017374 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C00XX Verification Plan | EA 15.3 | Done | 2
1017373 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C00XX Verification Plan | EA 15.2 | Done | 2
1017372 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C0059 User's Manual (Draft) | EA 16.1 | New | 3
1017365 | #384084 | Story | Feature 384084: Prep and Perform Interim Feature Demo – Customer Interim Demo Event | EA 14.5 | Done | 1
1017364 |  | Task | lklklk test | Unassigned | Invalid
1017361 | #1012748 | Story | Canada FMS Capability Spec: lead author of Service Mgmt sections | EA 15.5 | New | 2
1017360 | #1012748 | Story | Canada FMS Capability Spec: support and consult for Core impacts | EA 15.4 | Implementing | 2
1017359 | #1012748 | Story | Canada FMS Capability Spec: support and consult for Core impacts | EA 15.3 | Done | 2
1017358 | #1012748 | Story | Canada FMS Capability Spec: Support creation of SA section | EA 15.4 | Implementing | 2
1017357 | #1012748 | Story | Canada FMS Capability Spec: Support creation of SA section | EA 15.3 | Done | 2
1017356 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review and Final cleanup | EA 16.1 | New | 1
1017355 | #1012748 | Story | Canada FMS Capability Spec: lead author of ILS section | EA 15.4 | Done | 2
1017354 | #1012748 | Story | Canada FMS Capability Spec: author ILS section | EA 15.3 | Done | 2
1017353 | #1012748 | Story | Canada FMS Capability Spec: author ILS section | EA 15.2 | Done | 1
1017352 | #1012748 | Story | Canada FMS Capability Spec: Support creation of IA sections | EA 16.1 | New | 1
1017351 | #1012748 | Story | Canada FMS Capability Spec: Support creation of IA sections | EA 15.3 | Done | 1
1017350 | #1012748 | Story | Canada FMS Capability Spec: Support creation of IA sections | EA 15.2 | Done | 1
1017349 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.5 | New | 1
1017348 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.3 | Done | 1
1017347 | #1012748 | Story | Canada FMS Capability Spec: Support creation of FCAPS and NMF sections | EA 15.4 | Done | 2
1017346 | #1012748 | Story | Canada FMS Capability Spec: Support creation of FCAPS and NMF sections | EA 15.3 | Done | 2
1017345 | #1012748 | Story | Canada FMS Capability Spec: Support creation of Network impacting sections | EA 15.4 | Implementing | 2
1017344 | #1012748 | Story | Canada FMS Capability Spec: Support creation of Network impacting sections | EA 15.3 | Done | 2
1017342 | #1008506 | Story | Feature 1008506: UX Support for HA Splunk - Nutanix Procedures (Part 3 of 3) | PI 16 | New | 5
1017341 | #1008506 | Story | Feature 1008506: UX Support for HA Splunk - Nutanix Procedures (Part 2 of 3) | PI 16 | New | 5
1017340 | #1008506 | Story | Feature 1008506: UX Support for HA Splunk - Recovery Procedures only (Part 1 of 3) | EA 15.1 | Done | 1
1017339 | #1012748 | Story | Canada FMS Capability Spec: Support creation of GDS and HAIPE sections | EA 15.4 | Implementing | 2
1017338 | #1012748 | Story | Canada FMS Capability Spec: Support creation of GDS and HAIPE sections | EA 15.3 | Done | 2
1017337 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.5 | New | 2
1017336 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.4 | New | 2
1017335 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.4 | New | 2
1017334 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.3 | Done | 2
1017333 | #332951 | Story | Feature 332951: SME Support of RBS IETM Updates (15.4) | EA 15.4 | Implementing | 1
1017332 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.3 | Done | 2
1017331 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.2 | Done | 2
1017330 | #332951 | Story | Feature 332951: SME Support of RBS IETM Updates (15.2) | EA 15.2 | Done | 1
1017329 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.5 | New | 2
1017328 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.4 | New | 2
1017327 | #1005740 | Story | IA Support for DSN Gateway Capability Spec & Initial Design | EA 14.5 | Done | 1
1017326 | #332951 | Story | Feature 332951: Cleanup old ARP and address PWIs | EA 15.3 | Invalid | 0
1017325 | #332951 | Story | Feature 332951: Cleanup old ARP and address PWIs | EA 15.2 | Invalid | 0
1017324 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (Cyber) | EA 14.5 | Done | 3
1017320 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.3 | EA 15.3 | Done | 2
1017316 | #1013750 | Story | Lab - Prepare for implementation of NMS and RAN SWIT lab updates - Dave | EA 15.5 | New | 2
1017315 | #1013750 | Story | Lab - Develop and review plan to complete the work listed in the BOE - Dave | EA 15.4 | Implementing | 5
1017314 | #1013750 | Story | Lab - Complete engineering drawing updates - Dave | EA 15.3 | Done | 3
1017313 | #1015153 | Story | Investigate problematic disc images (.iso/.gi files) | EA 15.1 | Done | 3 | #1019342
1017312 | #1013750 | Story | Lab - Gather drawings, redlines to document existings configuration - Dave | EA 15.2 | Done | 3
1017310 | #1013750 | Story | Lab - Assess current state of SWIT lab - Dave | EA 15.1 | Done | 3
1017309 | #332951 | Story | Feature 332951: Test RBS Alarm Recovery Procedures and support reviews (15.3) | EA 15.3 | Done | 3
1017308 | #332951 | Story | Feature 332951: Test RBS Alarm Recovery Procedures and support reviews (15.2) | EA 15.2 | Done | 3
1017307 | #332951 | Story | Feature 332951: Engineering RBS IETM updates - Developer (15.4) | EA 15.4 | New | 2
1017305 | #332951 | Story | Feature 332951: Engineering RBS IETM updates - Developer (15.3) | EA 15.3 | Done | 2
1017304 | #332951 | Story | Feature 332951: Engineering RBS IETM updates - Developer (15.2) | EA 15.2 | Done | 3
1017301 | #379001 | Task | Re-apply Problem 347605 Task for Deployment : Possible GDS Registration Failures After C0 CT IP Change | Unassigned | New
1017300 | #379001 | Story | Rebase and Test Problem 347605 Story : Possible GDS Registration Failures After C0 CT IP Change | Unassigned | Invalid | 0
1017299 | #1011295 | Task | Feature 1011295: Submit PDO for PL01-P51664E001 - GTS - Signal Processor Cabinet Assembly | EA 15.5 | New
1017298 | #379001 | Task | Re-apply Problem 381036 Task for Deployment : Feature 371037: MPC only: Update the NM ETI Configuration Tool configuration files | Unassigned | New
1017297 | #379001 | Story | Rebase and Test Problem 381036 Story : Feature 371037: MPC only: Update the NM ETI Configuration Tool configuration files | Unassigned | New | 2
1017295 | #395373 | Story | IA Posture Improvement - AMS-GS Intermediate Assessment | EA 14.5 | Done | 3
1017292 | #354871 | Story | Feature 354871: Support load baseline and incorporate redlines | EA 16.3 | New | 3
1017290 | #354871 | Story | Feature 354871: Assist and support test engineer in feature demo event | EA 16.4 | New | 2
1017289 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 2 of 2) | EA 16.4 | New | 3
1017288 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 1 of 2) | EA 16.3 | New | 3
1017287 | #354871 | Story | Feature 354871: IETM review (part 4 of 4) | EA 16.1 | New | 1
1017286 | #354871 | Story | Feature 354871: IETM review (part 4 of 4) | EA 16.1 | New | 1
1017285 | #354871 | Story | Feature 354871: IETM reviews and Code reviews (part 3 of 4) | EA 15.4 | New | 1
1017284 | #354871 | Story | Feature 354871: IETM reviews and Code reviews (part 2 of 4) | EA 15.3 | Done | 1
1017283 | #354871 | Task | Feature 354871: IETM reviews and Code reviews (part 1 of 4) | EA 15.2 | Done
1017282 | #354871 | Story | Feature 354871: IETM review (part 4 of 4) | EA 16.1 | New | 1
1017280 | #354871 | Story | Feature 354871: IETM review (part 3 of 4) | EA 15.4 | Implementing | 1
1017279 | #354871 | Story | Feature 354871: IETM review (part 2 of 4) | EA 15.3 | Done | 1
1017277 | #380808 | Story | Feature 380808: Rebuild NME201 and NME202 in SWIT with DX2600 and DX360 hardware | EA 16.1 | New | 5
1017276 | #354871 | Story | Feature 354871: IETM review (part 1 of 4) | EA 15.2 | Done | 1
1017274 | #354871 | Story | Feature 354871: ILS IETM support of OA Workstation upgrade (part 4 of 4) | EA 16.1 | New | 3
1017273 |  | Story | Feature 1004171: Execute Test Cases - Part B | EA 15.2 | Invalid | 0
1017272 | #1004171 | Story | Feature 1004171: Support test case execution - Part B | EA 15.3 | Done | 2
1017271 | #354871 | Story | Feature 354871: ILS IETM support of OA Workstation upgrade (part 3 of 4) | EA 15.4 | New | 3
1017270 | #1004171 | Story | Feature 1004171: Support test case execution - Part A | EA 15.2 | Done | 1
1017269 | #354871 | Story | Feature 354871: ILS IETM support of OA Workstation upgrade (part 2 of 4) | EA 15.3 | Done | 3
1017268 | #1004171 | Story | Feature 1004171: Execute Test Cases - Part A | EA 15.2 | Done | 3
1017267 | #354871 | Story | Feature 354871: ILS IETM support of OA Workstation upgrade (part 1 of 4) | EA 15.2 | Done | 3
1017265 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 2 of 2) | EA 16.2 | New | 2
1017264 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 2 of 2) | EA 16.2 | New | 2
1017263 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 2 of 2) | EA 16.2 | New | 2
1017262 | #354871 | Story | Feature 354871: IETM updates (OA software/procedures) OA Workstation upgrade (part 3 of 3) | EA 15.4 | Implementing | 3
1017253 | #379001 | Task | Re-apply Problem 350070 Task for Deployment : Windows XP FOUO workstation suffers highly degraded performance during AV scans | Unassigned | New
1017252 | #379001 | Story | Rebase and Test Problem 350070 Story : Windows XP FOUO workstation suffers highly degraded performance during AV scans | Unassigned | New | 2
1017251 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 1 of 2) | EA 15.5 | New | 1
1017249 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 1 of 2) | EA 15.5 | New | 1
1017248 | #1007900 | Task | Re-apply Problem 338982 Task for Deployment : EAD-9 Windows 10 issues found during and after deployment | PI 16 | New
1017247 | #1007900 | Story | Rebase and Test Problem 338982 Story : EAD-9 Windows 10 issues found during and after deployment | PI 16 | New | 2
1017246 | #354871 | Story | Feature 354871: Create/update SVD for OA Workstation (part 3 of 3) | EA 15.4 | Implementing | 2
1017240 | #1013234 | Story | Feature 1013234: Test/validate compatibility of TomeEE JMS / ActiveMQ - part 2 | EA 15.2 | Done | 8
1017239 | #354871 | Story | Feature 354871: Create/update SVD for OA Workstation (part 2 of 3) | EA 15.3 | Done | 3
1017237 | #354871 | Story | Feature 354871: Code reviews (15.1) | EA 15.1 | Done | 1
1017236 |  | Task | Feature 354871: Code reviews (15.1) | EA 15.1 | Done
1017234 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (part 3 of 4) | EA 15.3 | Done | 5
1017233 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (part 2 of 4) | EA 15.2 | Done | 5
1017232 | #354871 | Story | Feature 354871: Code reviews (15.1) | EA 15.1 | Done | 1
1017231 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (15.1) | EA 15.1 | Done | 3
1017228 | #380808 | Story | Feature 380808: MFR 3 – CSE performs final STIG checklist eval of the Cisco switch | PI 16 | New | 2
1017227 | #380808 | Story | Feature 380808: MFR 3 – CSE Completes Final CAP for Cisco Switch | PI 16 | New | 3
1017226 | #380808 | Story | Feature 380808: MFR 3 – Developer fixes final STIG findings for Cisco 9K switch | PI 16 | New | 2
1017225 | #380808 | Story | Feature 380808: MFR 3 – CSE performs final scan of the Cisco switch | PI 16 | New | 1
1017224 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C0059 User's Manual (Draft) | EA 15.4 | Implementing | 3
1017223 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C0059 User's Manual (Draft) | EA 15.3 | Done | 2
1017222 | #1014595 | Story | Feature 1014595: ULX DD - TO 009 CDRL C0059 User's Manual (Draft) | EA 15.2 | Done | 3
1017221 | #1012996 | Story | Setup and test Solaris OS patching procedure(s) | EA 15.4 | Implementing | 5
1017220 | #1012996 | Story | Setup and test Windows OS patching procedure(s) | EA 15.4 | Implementing | 5
1017219 | #380808 | Story | Feature 380808: MFR 3 – Developer fixes interim STIG findings for Cisco 9K switch | EA 15.4 | New | 2
1017217 | #380808 | Story | Feature 380808: MFR 3 – CSE performs interim STIG checklist eval of the Cisco switch | EA 15.3 | Done | 2
1017216 | #380808 | Story | Feature 380808: MFR 3 – CSE performs interim scan of the Cisco switch | EA 15.3 | Done | 1
1017211 | #1014252 | Story | Feature 1014252: Perform Iterative Implementation, Integration, development Testing including updating design (Part 2a) | EA 15.2 | Done | 2
1017209 | #1009453 | Story | Feature 1009453: Developer discover root cause and propose a solution to the DL Power Spike | EA 15.2 | Done | 3
1017195 |  | Feature | OBS - NET: Develop the Network Capability Design Specification for the MUOS Ground System | PI 16 - In Progress | Rejected
1017193 | #379001 | Task | Re-apply Problem 388760 Task for Deployment : Need to document ACU configurations | Unassigned | Invalid
1017192 | #1017680 | Story | Rebase and Test Problem 388760 Story : Need to document ACU configurations | EA 15.1 | Done | 1
1017191 | #379001 | Task | Re-apply Problem 325778 Task for Deployment : ETI Configuration Tool logging configuration contains an error | Unassigned | New
1017190 | #379001 | Story | Rebase and Test Problem 325778 Story : ETI Configuration Tool logging configuration contains an error | Unassigned | New | 2
1017188 | #379001 | Task | Re-apply Problem 345370 Task for Deployment : FEP Logging does not include several parameters and has other issues per I-Level feedback and MPC modification | Unassigned | New
1017187 | #1017680 | Story | Rebase and Test Problem 345370 Story : FEP Logging does not include several parameters and has other issues per I-Level feedback and MPC modification | EA 15.1 | Done | 2
1017185 | #332951 | Story | Interim Demo for Feature 332951 (15.4) | EA 15.4 | Invalid | 0
1017184 | #332951 | Story | Interim Demo for Feature 332951 (15.3) | EA 15.3 | Done | 1
1017182 | #1009453 | Story | Feature 1009453: Execute tests for DL power spike investigation (WWTS team) | EA 15.4 | New | 2
1017173 | #1009453 | Story | Feature 1009453: Developer needs to understand Power Control for RBS | EA 15.1 | Done | 3
1017171 | #392058 | Story | Feature 392058: Develop/create IETM Procedures for ERS - Review, lab test and support resolution IETM updates and update STCD. | EA 15.1 | Done | 3
1017170 | #392058 | Story | Feature 392058: Develop/create IETM Procedures for ET/ETI - Alarm resolution development and preliminary IETM documentation update STCD. | EA 15.2 | Done | 5
1017168 | #392058 | Story | Feature 392058: Develop/create IETM Procedures for ERS - Alarm investigation and detailed analysis including lab replication (if applicable). | EA 15.1 | Done | 2
1017165 | #1009453 | Story | Feature 1009453: Developer needs to understand Power Control for RNC / Group | EA 15.1 | Done | 3
1017163 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1017162 | #1009453 | Story | Feature 1009453: TBD | EA 15.5 | Invalid | 0
1017161 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1017085 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1017084 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1017083 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1017075 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 6 Initial Computing Resource Budgets and Estimate - Part 2 | PI 16 | New | 1
1017049 | #395174 | Story | Feature 395174: Analyze AIU; ANTENNA INTERFACE UNIT 21 PRINTED BOARD ASSEMBLY: PN = KRY 101 1854/6, SN = TR46519359 for SR 1110153 / G3172 | EA 14.5 | Done | 1
1017041 | #1013234 | Story | Feature 1013234: SME Support (NMS - PPA Components) 15.4 | EA 15.4 | Implementing | 1
1017040 | #1013234 | Story | Feature 1013234: SME Support (NMS - PPA Components) 15.3 | EA 15.3 | Done | 1
1017039 | #1013234 | Story | Feature 1013234: SME Support (NMS - PPA Components) 15.2 | EA 15.2 | Done | 1
1017038 | #1013234 | Story | Feature 1013234: SME Support (NMS - PPA Components) 15.1 | EA 15.1 | Done | 1
1017036 | #1013234 | Story | Feature 1013234: Prototype Review (SE / team) | EA 15.3 | Invalid | 0
1017033 | #1013234 | Story | Feature 1013234: Consolidate prototype findings (results documentation) | EA 15.2 | Invalid | 0
1017030 | #1013234 | Story | Feature 1013234: Test/Verify compatibility of latest Hibernate library on PPA and MS-SQL 2005 | EA 15.3 | Done | 2
1017027 | #1013234 | Story | Feature 1013234: Test/Verify the compatibility of the new ActiveMQ server (TomEE) and older versions of the JMS protocol | EA 15.3 | Invalid | 0
1017017 | #1009453 | Story | Feature 1009453: SE needs to understand Power Control for RBS | EA 15.2 | Done | 2
1017016 | #1009453 | Story | Feature 1009453: SE needs to understand Power Control for RNC / Group | EA 15.2 | Done | 2
1017008 | #380808 | Story | Feature 380808: (IA) MFR 3 – CSE achieves concurrence with PMW on applicable STIGs for Cisco switch | EA 15.2 | Done | 1
1017002 |  | Task | Story 1011568: CM Release of 99-P57050M - NMS - NM Common PKI (EAD 18) | PI 16 | Invalid
1016969 | #381524 | Story | Feature 381524: Fix 381547: Unit testing and coverage reports for Provisioning Bridge database contention can bring down terminal provisioning (INC000004253880) | EA 15.1 | Done | 1
1016968 | #380808 | Story | Feature 380808: MFR 3 – CSE Completes FInal CAP for Cisco Switch | PI 16 | New | 3
1016964 | #385632 | Story | FM Whitelist updates for PI15: Test | EA 15.3 | Done | 1
1016952 | #1015771 | Story | Expand Docker configuration into a Swarm | Unassigned | Invalid | 0
1016925 | #1007536 | Task | <Feature 1007536> Hold Feature Review with SMEs | EA 14.5 | Done
1016913 | #395373 | Story | VMP: Peer Review Scan Assessment Guidance document-Part 2b (Feature 395373 Cyber Sustainment Activities) | EA 15.4 | Invalid | 0
1016909 | #1015771 | Story | Identify and Test Failure Scenarios | Unassigned | Invalid | 0
1016908 | #1015771 | Story | Expand container for Logging | Unassigned | Invalid | 0
1016907 | #1015771 | Story | Configure Docker Health Checks and Restarts | Unassigned | Invalid | 0
1016900 | #1022224 | Feature | WinOBS: PPA Functional Prototyping | PI 16 - Candidate | Approved |  | #1022681 #1022683
1016898 | #396669 | Problem | IETM update for Radio Network Controller (RNC) GroupKeySet_GroupKeystreamUnavailable Alarm Recovery Procedure (INC000004735075) | EA 15.4 | Verifying
1016895 | #384036 | Story | Feature 384036: Various SVD updates | EA 14.5 | Done | 3
1016892 | #383165 | Story | Feature 383165: Redline Parts Lists, Drawings, BOM for Splunk Server Removal | EA 15.2 | Done | 3
1016891 | #1011295 | Story | Feature 1011295: Support Update Drawings for GEO Removal Problem 392388 | EA 15.2 | Invalid | 0
1016880 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Channel Conditioner and Unit Test (No Algorithm) | EA 15.3 | Done | 3
1016879 | #1015153 | Story | <Feature 1015153>: MFR 1 Ð Dev Team Performs Cybersecurity Assessment (ACAS Scans) | EA 15.1 | Invalid | 0 | #1015159
1016877 | #1011441 | Story | Feature 1011441: Review CDRL A010 with 2019 LORA | EA 15.3 | Done | 1
1016876 | #1011441 | Story | Feature 1011441: Review CDRL A010 with 2019 LORA | EA 15.3 | Done | 1
1016875 | #1014596 | Story | Feature 1014596: ULX CP - Prototype SBC Resampler and Unit Test (Part 1 of 2) | EA 15.3 | Done | 3
1016873 | #1011295 | Story | Feature 1011295: Finalize CCB Slide Creation for EAD 17 | EA 15.4 | New | 1
1016871 | #1011295 | Story | Feature 1011295: Pre-CCB Slide Creation for EAD 17 | EA 15.2 | Done | 1
1016870 | #1012540 | Story | Feature 1012540: Complete Analysis of all System Parts [CDRL A004] - - Spares planning. | EA 15.4 | Implementing | 2
1016869 | #1012540 | Task | Feature 1012540: Review with Customer [CDRL A004] | EA 16.2 | New
1016867 |  | Story | Feature 395114: RBD Analysis for PI 15 (CDRL A009) | EA 15.5 | Invalid | 0
1016831 | #395373 | Story | VMP: Update Scan Assessment Guidance document-Part 2b (Feature 395373 Cyber Sustainment Activities) | EA 14.5 | Done | 5
1016801 | #1013234 | Story | Feature 1013234: Cyber Review of PPA Prototype | EA 15.4 | Implementing | 2
1016800 | #1016900 | Story | Feature 1016900: Test/verify existing .m files on Matlab R2020a Runtime | EA 16.4 | New | 5
1016799 | #1013234 | Story | Feature 1013234: Protoype java interface for Active MQ | EA 15.2 | Invalid | 0
1016798 | #1016900 | Story | Feature 1016900: Mapping software Initial Prototyping, capturing clicks to create geometries (usability and functionality) Part 2 | EA 16.4 | New | 8
1016797 | #1016900 | Story | Feature 1016900: Mapping software Initial Prototyping, capturing clicks to create geometries (usability and functionality) Part 1 | EA 16.3 | New | 5
1016796 | #1022398 | Story | Feature 1016900: Develop PPA Custom Web Components Part 3 | EA 16.4 | New | 5
1016795 | #1022398 | Story | Feature 1016900: Develop PPA Custom Web Components Part 2 | EA 16.3 | New | 8
1016794 | #1022398 | Story | Feature 1016900: Develop PPA Custom Web Components Part 1 | EA 16.2 | New | 8
1016793 | #1016900 | Story | Feature 1016900: PPA 3rd Party Libraries -determine libraries overlap (e.g. XML libs, DOM vs JaxB, … est. 15 libraries) Part 2 | EA 16.3 | New | 13
1016792 | #1016900 | Story | Feature 1016900: PPA 3rd Party Libraries -determine libraries overlap (e.g. XML libs, DOM vs JaxB, … est. 15 libraries) Part 1 | EA 16.2 | New | 1
1016791 | #1013234 | Story | Feature 1013234: Test/verify MS-SQL 2019 compatibility w/ current PPA and Hibernate LIB - part 2 | EA 15.4 | Implementing | 3
1016790 | #1013234 | Story | Feature 1013234: Develop a proof of concept library using JDBC for DB communication alternative to hibernate | EA 15.2 | Done | 5
1016789 | #1013234 | Story | Feature 1013234: Test/verify Log4J API, TomEE Log4j2, Spring MVC | EA 15.1 | Done | 3
1016788 | #1013234 | Story | Feature 1013234: Prototype interface for Spring MVC to SQL DB (Part 1) | EA 15.3 | Done | 5
1016785 | #376446 | Task | Feature 376446: Procurement Verification and Approvals for Update Call Bank Servers to Use Connected AWARE Architecture to support IATT | EA 14.5 | Done |  | #1016784
1016784 | #376446 | Task | Feature 376446: Hardware/Software Procurement Request for Update Call Bank Servers to Use Connected AWARE Architecture to support IATT ( Procure 11 Redhat Licenses) | EA 15.2 | Done
1016783 | #1014597 | Task | Feature 1014597: Procurement Verification and Approvals for TO-9: Develop and Test ULX Manager and Monitor and Control | EA 15.3 | Done |  | #1016782
1016782 | #1014597 | Task | Feature 1014597: Hardware/Software Procurement Request for TO-9: Develop and Test ULX Manager and Monitor and Control | EA 15.3 | Done
1016781 | #1014602 | Task | Feature 1014602: Procurement Verification and Approvals for TO-9: Build ULX System 1 and 2 | EA 15.3 | Done
1016780 | #1014602 | Task | Feature 1014602: Hardware/Software Procurement Request for TO-9: Build ULX System 1 and 2 | EA 15.2 | In Development
1016779 | #1014598 | Task | Feature 1014598: Procurement Verification and Approvals for TO-9: Develop Build and Development Tools | EA 15.3 | Done
1016778 | #1014598 | Task | Feature 1014598: Hardware/Software Procurement Request for TO-9: Develop Build and Development Tools | EA 15.2 | In Development
1016777 | #1014596 | Task | Feature 1014596: Procurement Verification and Approvals for TO-9: Develop Channel Processor Prototype for ULX | EA 15.3 | Done
1016776 | #1014596 | Task | Feature 1014596: Hardware/Software Procurement Request for TO-9: Develop Channel Processor Prototype for ULX | EA 15.2 | In Development
1016775 | #1013657 | Task | Feature 1013657: Procurement Verification and Approvals for Release Regression - EAD 16 Regression Testing (PI15) | PI 15 | Done |  | #1016774
1016774 | #1013657 | Task | Feature 1013657: Hardware/Software Procurement Request for Release Regression - EAD 16 Regression Testing (PI15) | PI 15 | New
1016773 |  | Task | Feature 1007900: Procurement Verification and Approvals for OBS - HBSS: Prepare HBSS for Deployment to Site | PI 15 | Invalid |  | #1016772
1016772 |  | Task | Feature 1007900: Hardware/Software Procurement Request for OBS - HBSS: Prepare HBSS for Deployment to Site | PI 15 | Invalid
1016771 |  | Task | Feature 395114: Procurement Verification and Approvals for PI 15 HW FRB Support (CDRL A008) (Recurring) | EA 14.5 | Invalid |  | #1016770
1016770 | #395114 | Task | Feature 395114: Hardware/Software Procurement Request for PI 15 HW FRB Support (CDRL A008) (Recurring) | EA 14.5 | Done
1016769 |  | Task | Feature 342054: Procurement Verification and Approvals for Complete Development of Sicily Connected AWARE | Unassigned | Invalid |  | #1016768
1016768 |  | Task | Feature 342054: Hardware/Software Procurement Request for Complete Development of Sicily Connected AWARE | Unassigned | Invalid
1016767 | #1002345 | Task | Feature 1002345: Procurement Verification and Approvals for OBS - HLR: Upgrade HP HLR/AuC HW & SW | EA 14.5 | Done |  | #1016766
1016766 | #1002345 | Task | Feature 1002345: Hardware/Software Procurement Request for OBS - HLR: Upgrade HP HLR/AuC HW & SW | EA 14.5 | Done
1016761 | #1002381 | Task | Feature 1002381: Procurement Verification and Approvals for OBS - HLR: HW/FRCB for HLR Deployment | PI 15 | Invalid |  | #1012042
1016759 | #383958 | Story | Feature 383958: Bulk SAR Code Review (Part 2 of 2) | EA 15.4 | Implementing | 2
1016758 | #383958 | Story | Feature 383958: Bulk SAR Code Review | EA 15.4 | Implementing | 3
1016757 | #383958 | Story | Feature 383958: Bulk SAR Code Review | EA 15.4 | Implementing | 3
1016756 | #383958 | Story | Feature 383958: Bulk SAR PPA Implementation, Integration, development Testing including updating design - part 3R | EA 15.2 | Done | 5
1016755 | #383958 | Story | Feature 383958: Bulk SAR PPA Implementation, Integration, development Testing including updating design - part 3R | EA 15.1 | Done | 5
1016744 | #1013452 | Story | Feature 1013452: Incorporate Zeta redline versions of IETMs | PI 16 | New | 1
1016743 | #1013452 | Story | Feature 1013452: Install & Unit Test Final Zeta Delivery (including IA) | PI 16 | New | 3
1016704 | #387446 | Story | Mobility Call Flow Updates | EA 15.3 | Done | 1
1016701 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (part 1 of 4) | EA 15.1 | Done | 5
1016682 | #384084 | Story | Interim Demo for Feature – - Feature 384084 | EA 15.4 | Invalid | 0
1016679 | #384084 | Story | Feature 384084: FM STCD Dry Run/Execution | PI 16 | New | 1
1016678 | #384084 | Story | Feature 384084: FM STCD Review | PI 16 | New | 1
1016677 | #384084 | Story | Feature 384084: Update FM STCDs for final demo | PI 16 | New | 2
1016676 | #1007900 | Story | Feature 1007900: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 16 | New | 3
1016675 | #384084 | Story | Feature 384084: Support HBSS SNMP integration testing with FM | EA 15.4 | Ready for Acceptance | 2
1016674 | #384084 | Story | Feature 384084: Perform HBSS SNMP integration testing with FM | EA 15.4 | Ready for Acceptance | 3
1016668 | #1007900 | Story | Feature 1007900 Continued STCD Testing of Migration of ePO 200 to Nutanix and importing ePO201 into Nutanix provide redlines to development team. | EA 15.4 | Implementing | 5
1016656 | #380808 | Story | Feature 380808: Development IETM Development and Integration Updates for Nutanix Deployment (Sprint 4) | EA 15.4 | New | 2 | #1013509
1016655 | #380808 | Story | Feature 380808: Development IETM Development and Integration Updates for Nutanix Deployment (Sprint 3) | EA 15.3 | Done | 3
1016654 | #380808 | Story | Feature 380808: Development IETM Development and Integration Updates for Nutanix Deployment (Sprint 2) | EA 15.2 | Done | 3
1016653 | #380808 | Story | Feature 380808: Development IETM Development and Integration Updates for Nutanix Deployment (Sprint 1) | EA 15.1 | Done | 3
1016651 | #384084 | Story | Feature 384084: Perfrom translating of new HBSS MIBS to FMS | EA 15.3 | Done | 3
1016649 | #384084 | Story | Feature 384084: HBSS provide updated MIBS for FM | EA 15.3 | Invalid | 0
1016647 | #384084 | Story | Feature 384084: Update MFR package for Cisco Switch and FM | EA 15.2 | Done | 1
1016646 | #384084 | Story | Feature 384084: Support Cisco switch SNMP integration testing with FM | EA 15.2 | Done | 3
1016644 | #384084 | Story | Feature 384084: Perform Cisco switch SNMP integration testing with FM | EA 15.3 | Done | 3
1016643 | #384084 | Story | Feature 384084: Perform Cisco switch MIB translations into FM part 2 of 2 | EA 15.2 | Done | 3
1016642 | #384084 | Story | Feature 384084: Perform Cisco switch MIB translations into FM part 1 of 2 | EA 15.1 | Done | 2
1016641 | #384084 | Story | Feature 384084: Support Nutanix node SNMP Integration testing with FM | EA 15.1 | Done | 3
1016639 | #384084 | Story | Feature 384084: Perform Nutanix node SNMP Integration testing with FM | EA 15.1 | Done | 3
1016609 | #1007900 | Task | Re-apply Problem 315607 Task for Deployment : [Urgent] SR 984301 / INC000003355751: MUOS -McAfee preventing ETISP to go into running | PI 16 - In Progress | Done
1016608 | #1007900 | Story | Rebase and Test Problem 315607 Story : [Urgent] SR 984301 / INC000003355751: MUOS -McAfee preventing ETISP to go into running | EA 15.1 | Done | 5
1016601 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.4 | Implementing | 3
1016600 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.4 | Implementing | 3
1016599 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.3 | Done | 3
1016598 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.3 | Done | 3
1016597 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.2 | Done | 3
1016596 | #1014595 | Story | Feature 1014595: ULX DD - Test Plan & Systems Test Approaches (Input Test Vector Stimulus + Expected Results) | EA 15.2 | Done | 3
1016561 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Fernando | EA 15.3 | Done | 5
1016560 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Leslie | EA 15.4 | Invalid | 0
1016559 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Matt | EA 15.1 | Done | 2
1016558 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Matt | EA 15.2 | Done | 2
1016557 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Matt | EA 15.3 | Done | 2
1016556 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Matt | EA 15.4 | New | 2
1016555 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Jim | PI 15 | Invalid | 0
1016554 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Jim | PI 15 | Invalid | 0
1016553 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Jim | EA 15.2 | Done | 5
1016552 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Jim | EA 15.3 | Done | 5
1016551 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Jim | EA 15.4 | Implementing | 5
1016549 | #1013136 | Story | Feature 1013136: WF PWI Burndown - John | EA 15.1 | Done | 2
1016547 | #1013136 | Story | Feature 1013136: WF PWI Burndown - John | EA 15.2 | Done | 2
1016546 | #1013136 | Story | Feature 1013136: WF PWI Burndown - John | EA 15.3 | Done | 2
1016544 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Leslie | EA 15.1 | Done | 3
1016543 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Leslie | EA 15.2 | Done | 2
1016542 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Leslie | EA 15.3 | Invalid | 0
1016541 | #1013136 | Story | Feature 1013136: WF PWI Burndown - John | EA 15.4 | New | 2
1016540 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Ty | EA 15.2 | Done | 2
1016539 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Ty | EA 15.3 | Done | 1
1016538 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Ty | EA 15.4 | Implementing | 1
1016537 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Ty | EA 15.1 | Done | 2
1016536 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Fernando | EA 15.4 | New | 5
1016535 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Fernando | EA 15.2 | Done | 5
1016534 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Fernando | EA 15.1 | Done | 5
1016533 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Yue-Chain | EA 15.2 | Done | 5
1016532 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Yue-Chain | EA 15.1 | Done | 5
1016531 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Tim | EA 15.4 | New | 2
1016530 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Tim | EA 15.3 | Invalid | 0
1016529 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Tim | EA 15.2 | Done | 3
1016528 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Tim | EA 15.3 | Invalid | 0
1016527 | #1013136 | Story | Feature 1013136: WF PWI Burndown and testing - Sang | EA 15.4 | New | 3
1016526 | #1013136 | Story | Feature 1013136: WF PWI Burndown and testing - Sang | EA 15.3 | Done | 5
1016525 | #1013136 | Story | Feature 1013136: WF PWI Burndown and testing - Sang | EA 15.2 | Done | 5
1016474 | #1015005 | Story | Develop Capability Design Doc for ActiveMQ Replacement | EA 16.3 | New | 5
1016473 | #1015005 | Story | Capability Specification Development | EA 15.4 | Implementing | 3
1016467 |  | Problem | IETM update for NMS PCC0018 Registration Request Refused By CSL Recovery – Normal Operation Procedure (INC000004697647) | Unassigned | Assessing
1016462 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (800-53 Controls review and Cyber System Documentation) | EA 15.4 | New | 2
1016461 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MFR package preparation) | EA 15.3 | Done | 1
1016460 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MAS' STIGs assessment - Part 2) | EA 15.2 | Done | 2
1016459 | #1006191 | Story | Feature 1006191 IA Support (Reviews and Analysis) (MAS' STIGs Assessment - Part 1) | EA 15.1 | Done | 2
1016452 | #380808 | Story | Feature 380808: Update and Review Splunk SVD | PI 16 | New | 5
1016451 | #380808 | Story | Feature 380808: Update RHEL SVDs and review | EA 15.4 | Implementing | 5
1016450 | #380808 | Story | Feature 380808: Perform hardening of RHEL 7.8 image | EA 15.4 | Implementing | 1
1016449 | #380808 | Story | Feature 380808: Finalize and test RPM List | EA 15.2 | Invalid | 0
1016448 | #380808 | Story | Feature 380808: Get concurrence from Aware for new hardened RHEL 7.7 image | EA 15.1 | Done | 1
1016447 | #380808 | Story | Feature 380808: Perform post install site cleanup | PI 16 | New | 2
1016446 | #380808 | Story | Feature 380808: Regression test after Splunk install Part 3 | PI 16 | New | 5
1016444 | #380808 | Story | Feature 380808: Regression test after Splunk install Part 1 | EA 15.3 | Done | 3
1016443 | #380808 | Story | Feature 380808: Update and Review Splunk SVD | PI 16 | Invalid | 0
1016437 | #380808 | Story | Feature 380808: Complete Extreme Switch SVD for new connections to LAN221/222 | EA 15.1 | Done | 3
1016420 | #392530 | Story | Feature 392530 - Update Patch Management Document (Part 2) 14.5 | EA 14.5 | Done | 1
1016419 | #392530 | Story | Feature 392530 - Create Patch Management Document (Part 1) 14.4 | EA 14.4 | Done | 2
1016417 | #380808 | Task | Feature 380808: Submit PDO for 00-P50231E – SEIT - SYSTEM DRAWING TREE - MUOS GROUND SYSTEM | PI 16 | Done
1016416 | #1005403 | Task | Feature 1005403: Obtain Updated Quote from PM Vendors Concerning GEO Antenna Activities | EA 15.1 | Done
1016415 | #1005403 | Story | Feature 1005403: Develop MRC Content for the GEO Antenna | EA 15.2 | Done | 3
1016408 | #387446 | Story | Prepare and release the 97-P55463M003 Design Doc, RNC Managed Object Model Updates | EA 15.4 | Implementing | 1
1016404 | #380808 | Story | Feature 380808: Incorporate review updates for Nutanix IETM procedures (and impacted procedures) | EA 15.4 | Implementing | 3
1016403 | #380808 | Story | Feature 380808: Review of all Nutanix IETM procedures (and impacted procedures) | EA 15.3 | Done | 5
1016402 | #380808 | Story | Feature 380808: Figure out Off-Line LCM in Nutanix and add procedure to update device firmware to SVD | EA 15.2 | Done | 3
1016396 | #380808 | Story | Feature 380808: Nutanix SVD updates Sprint 1 (Improve procedures & other SVD issues found) | EA 15.2 | Done | 3
1016394 | #385632 | Story | FM Whitelist updates for PI15: Submit MPC | EA 15.4 | Done | 1
1016393 | #385632 | Story | FM Whitelist updates for PI15: Engineering Whitelist updates (Implement, Test, Review) | EA 15.3 | Done | 3
1016388 | #384036 | Story | Feature 384036: Assess state of IETM and SVD for Nutanix | EA 14.5 | Done | 3
1016387 | #384036 | Story | Feature 384036: Assess state of IETM and SVD for Nutanix | EA 14.5 | Done | 3
1016383 | #216351 | Feature | FM Whitelist updates for PI 16: Update whitelist and filter logic | PI 16 - Candidate | Approved
1016369 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Manager - Startup & Shutdown | EA 16.1 | New | 2
1016368 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Managers - Health & Status and Logging | EA 15.4 | Implementing | 2
1016367 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Managers - Configuration and Fault | EA 15.3 | Done | 2
1016366 | #1014597 | Story | Feature 1014597: ULX M&C - Create Framework - Structure and Message Controller | EA 15.2 | Done | 2
1016365 | #378964 | Task | Cherie Gano PTO (EA 15.2 (5/1)) | EA 15.2 | Done
1016361 | #380808 | Story | Feature 380808: Deployment Notes and Operator Impact Inputs- Final | PI 16 | New | 3
1016360 | #380808 | Story | Feature 380808: Nutanix SVD updates Sprint 4 | EA 15.4 | Implementing | 3
1016359 | #380808 | Story | Feature 380808: Nutanix SVD updates Sprint 3 | EA 15.3 | Done | 3
1016358 | #380808 | Story | Feature 380808: Nutanix SVD updates Sprint 2 | EA 15.2 | Done | 3
1016357 | #380808 | Story | Feature 380808: Nutanix SVD updates Sprint 1 | EA 15.1 | Done | 3
1016348 | #380808 | Story | Feature 380808: Rebuild NME201 and NME202 in V-Lab for final Nutanix 360 | EA 15.4 | Implementing | 3
1016343 | #380808 | Story | Feature 380808: Move NME201 and NME202 with 360 Equipment into VLab | EA 15.5 | New | 3
1016342 | #380808 | Story | SIC team support: Install Splunk VMs from Scratch and regression (360) Nutanix, Splunk HA | EA 16.2 | New | 8
1016340 | #380808 | Story | Address issues from IA Refresh Scan/STIG of Cisco (360) | PI 16 | New | 1
1016339 | #332951 | Story | Feature 332951: Lab Support of RBS IETM Updates (15.4) | EA 15.4 | Implementing | 1
1016338 | #332951 | Story | Feature 332951: Lab Support of RBS IETM Updates (15.3) | EA 15.3 | Done | 3
1016333 | #385442 | Story | Feature 385442:Capabilities Specification Documentation - Finalize Internal Peer Review document | EA 15.4 | Implementing | 5
1016332 | #385442 | Story | Feature 385442:Capabilities Specification Documentation - Finalize Internal Peer Review document | EA 15.4 | Implementing | 5
1016331 | #385442 | Story | Feature 385442: Capabilities Design Documentation - Information Assurance Design | EA 15.4 | Implementing | 3
1016330 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Finalize and Review document [15.3] | EA 15.3 | Done | 5
1016329 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Finalize and Review document [15.3] | EA 15.3 | Done | 5
1016325 | #1004171 | Story | Feature 1004171: Finalize the output format for the script to mine the logs from Feature 381608 to get a baseline of the frequency of the issue with the module acceptance of group provisioning from Central GNH | EA 14.5 | Invalid | 0
1016324 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Integration and Test Strategy | EA 15.1 | Done | 2
1016323 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Finalize and Review document [15.2] | EA 15.2 | Done | 3
1016321 | #380808 | Story | Updating SVD for redlines and IA freshness for: Cisco Switch (360) | PI 16 | New | 1
1016320 | #343920 | Task | Story 343920: CM Release of 99-P53557E - NM - FCAPS - IDD (EAD 16) | EA 14.5 | Done
1016319 | #385442 | Story | Feature 385442: Capabilities Specification - Continue from 14.4 Section 7 Interface Design | EA 15.1 | Done | 5
1016318 | #343920 | Task | Story 343920: CM Release of 97-P55765M - MultiHAL Software Design Description (SWDD) (EAD 16) | EA 14.5 | Done
1016317 | #395897 | Story | IA Posture Improvement - AMS-GS Intermediate Assessment | EA 15.1 | Invalid | 0
1016316 | #343920 | Task | Story 343920: CM Release of 63-P55767M - AWARE Detailed Design Document (DDD) (EAD 16) | EA 14.5 | Done
1016315 | #380808 | Story | Install Nutanix SVD from scratch in the V-Lab on 360 hardware | PI 16 | New | 5
1016313 | #380808 | Story | Feature 380808 Re-Scan and STIG Cisco Switch (360) after the 4/17 refresh date. | PI 16 | New | 1
1016310 | #380808 | Story | HBSS team support: Install (360) HBSS VMs from Scratch and regression Nutanix, HBSS | PI 16 | New | 3
1016309 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Information Assurance Design - Continued from PI 14.5 [15.1] | EA 15.1 | Done | 1
1016307 | #384136 | Story | Feature 384136: HBSS STIG Findings - Prepare Vulnerator Spreadsheets for Checklist Ingestion | EA 14.5 | Done | 1
1016304 | #1015153 | Story | Update the SVD Ð 98-P54141T ILS LAPTOP GEN2 SVD - Part 2 | EA 15.1 | Invalid | 0 | #1009630
1016288 | #384084 | Story | Feature 384084: final Review/Rework FM - PI 16 | EA 16.3 | New | 3
1016287 | #384084 | Story | Feature 384084: interim Review/Rework FM - PI 15 | EA 15.5 | New | 3
1016284 |  | Task | Story 353837: CM Release of 99-P59550V Software to Hardware Mapping ILS Laptop Gen2 (Tools) | EA 15.2 | Invalid
1016283 |  | Task | Story 353837: CM Release of PL01-P59548V002 ILS Laptop Gen2 Parts List (Tools) | EA 15.2 | Invalid
1016273 |  | Task | Story 353837: CM Release of 98-P54141T ILS Laptop Gen2 SVD | EA 15.2 | Invalid
1016262 | #384136 | Story | Feature 348136: Peer Review HBSS SVD | EA 14.5 | Done | 2
1016261 | #384136 | Story | Feature 348136: Peer Review HBSS SVD | EA 14.5 | Done | 2
1016260 | #384136 | Story | Feature 348136: Peer Review HBSS SVD | EA 14.5 | Done | 2
1016238 | #343920 | Task | Story 343920 CM Release 99-P54142T - ILS - Software to Hardware Mapping - Gen2 Laptop (EAD 16) | EA 14.5 | Done
1016237 | #343920 | Task | Story 343920: CM Release of 99-P59552V - ILS - Software to Hardware Mapping - Laptop GEN2 - ETT (EAD 16) | EA 14.5 | Done
1016235 | #343920 | Task | Story 343920: CM Release of 99-P59553V - ILS - Software to Hardware Mapping - Laptop GEN2 - MTC-AJM (EAD 16) | EA 14.5 | Done
1016232 | #380808 | Story | Feature 380808:Prep Feature Demo (EAD 18) Nutanix 360 - Developer Support | PI 16 | New | 3
1016231 | #380808 | Story | Feature 380808:Prep Feature Demo (EAD 18) Nutanix 360 | PI 16 | New | 3
1016222 | #395373 | Story | Develop Scan Assessment Guidance document-Part 2 (Feature 395373 Cyber Sustainment Activities) | EA 14.5 | Done | 2
1016221 |  | Task | Story 1011568: CM Release of 99-P53449 Interactive Electronic Technical Manual (IETM) – SVD (EAD 18) | EA 16.2 | Invalid
1016219 | #1006191 | Story | Feature 1006191 Review all CAT 1 and CAT 2 findings and provide estimate to address | EA 15.2 | Done | 2
1016212 | #393213 | Task | Story 393213: Submit PDO for 98-P56582V – WH Site SVD (EAD 17) | EA 15.5 | New
1016204 | #393213 | Task | Story 393213: Submit PDO for 98-P56577V – AU Site SVD (EAD 17) | EA 15.5 | New
1016203 | #393213 | Task | Story 393213: Submit PDO for 98-P56580V – NW Site SVD (EAD 17) | EA 15.5 | New
1016202 | #393213 | Task | Story 393213: Submit PDO for 98-P56578V – DD Site SVD (EAD 17) | EA 15.5 | New
1016201 | #393213 | Task | Story 393213: Submit PDO for 98-P56579V – HQ Site SVD (EAD 17) | EA 15.5 | New
1016200 | #393213 | Task | Story 393213: Submit PDO for 98-P56581V – SC Site SVD (EAD 17) | EA 15.5 | New
1016198 |  | Problem | PPA is taking longer than 2 minutes to respond to a request during the nightly automation load runs. | Unassigned | Assessing
1016196 | #380808 | Story | Feature 380808: Complete CoCo review and send Nutanix Capability Design Doc to customer for review | EA 15.4 | New | 2
1016195 | #380808 | Story | Feature 380808: Finalize and CoCo review Nutanix Capability Design Doc | EA 15.3 | Done | 2
1016176 | #1007900 | Story | Feature 1007900: SVD Development and Test Support and IETM Support | EA 15.2 | Done | 3
1016175 | #1007900 | Story | Feature 1007900: SVD Development and Test Support and IETM Support EA15.3 | EA 15.3 | Done | 5
1016174 | #1007900 | Story | Feature 1007900: SVD Development and Test Support EA15.1 Part 1 | EA 15.2 | Done | 5
1016164 |  | Story | Feature 1007900: Update MUOS_IG_GS_NMS_NM_Common_SANSwitch_SVD_98-P59430M003 to remove ePO from this SVD | PI 15 | Invalid | 0
1016159 | #342054 | Story | Feature 342054: Update Splunk Dashboard to handle new AWARE node names from Fault Notifier | EA 15.1 | Done | 2
1016119 | #396415 | Story | NMS dev stream nightly rebases | EA 14.5 | Done | 1
1016020 | #363573 | Story | Analysis of Troubleshooting Approach -UX: Support Data Analysis/Create Report of Findings and Recommendations | PI 17 | New | 3
1016019 | #342054 | Story | Feature 342054: Complete the AWARE RF tray SN003 calibrations and update errors in the calibration spreadsheet | EA 14.5 | Done | 2
1016016 |  | Task | deploy test WIP metrics calculations | EA 14.5 | Done
1016005 | #1014598 | Story | Feature 1014598: Develop ULX Build Environment (Support Teams with CI/CD Extensions) | EA 15.4 | Done | 2
1016004 | #1014598 | Story | Feature 1014598: Develop ULX Build Environment (Move Equipment to SWIT/VLAB) | EA 15.3 | Done | 3
1016003 | #1014598 | Story | Feature 1014598: Develop ULX Build Environment (Clone Template CI/CD Pipeline to Other ULX Teams) | EA 15.2 | Done | 3
1016002 | #1012485 | Story | Feature 1012485: Update the SMDC (ARSTRAT) and RSSC tabs to reflect actual roles (JDTA) (Part 3) | EA 16.1 | New | 3
1016000 | #1014598 | Story | Feature 1014598: Support of ULX Build Environment (SWIT/VLAB Connectivity, Attend Sprint Review) | EA 15.4 | Implementing | 3
1015999 | #1014598 | Story | Feature 1014598: Support of ULX Build Environment (SWIT/VLAB Connectivity, Attend Sprint Review) | EA 15.3 | Done | 3
1015998 | #1014598 | Story | Feature 1014598: Support of ULX Build Environment (SWIT/VLAB Connectivity, Attend Sprint Reviews) | EA 15.2 | Done | 3
1015997 |  | Story | Feature 1014602: Build ULX System 1 and 2 | EA 15.4 | Invalid | 0
1015996 |  | Story | Feature 1014602: Build ULX System 1 and 2 | Unassigned | Invalid | 0
1015995 |  | Story | Feature 1014602: Build ULX System 1 and 2 | EA 15.2 | Invalid | 0
1015994 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Maintenance) | EA 15.4 | New | 2
1015993 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Setup) | EA 15.3 | Done | 2
1015992 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Design to Accommodate Two ULX Units) | EA 15.2 | Done | 1
1015974 | #1014595 | Story | Feature 1014595: ULX DD - IA/Cyber Support of ULX Design | EA 15.4 | Implementing | 2
1015973 | #1014595 | Story | Feature 1014595: ULX DD - IA/Cyber Support of ULX Design | EA 15.2 | Done | 3
1015972 | #1014595 | Story | Feature 1014595: ULX DD - IA/Cyber Support of ULX Design | EA 15.3 | Done | 3
1015971 | #392058 | Story | Feature 392058: Develop IETM Procedures for ETISP (Part 1) | EA 15.1 | Done | 5
1015970 | #392058 | Story | Feature 392058: Develop IETM Procedures for ETISP (Part 3) | EA 16.1 | New | 5
1015969 | #392058 | Story | Feature 392058: Develop IETM Procedures for ETISP (Part 2) | EA 15.1 | Done | 5
1015967 | #384036 | Story | Feature 384036: Complete Spares Analysis for the new Nutanix HW/SW Direction of DX-360 | EA 14.4 | Done | 1
1015911 | #1016405 | Feature | Implement Solution for the DL Power Spike | PI 16 | Approved
1015885 | #395853 | Story | Update DADMS Disapproved Spreadsheet | EA 15.1 | Done | 5
1015880 | #297335 | Story | Feature 297335: RDE System Test in VLab of Automated RAN RNC Build | EA 15.4 | Invalid | 0
1015874 | #297335 | Story | RDE BuildForge - Complete Automation of RDE Builds | EA 16.1 | Invalid | 0
1015873 | #388549 | Story | Feature 388549: ULX Support (Nadolski) | EA 14.5 | Done | 2
1015871 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Gale (14.5) | EA 14.5 | Done | 2
1015863 | #368860 | Story | Feature 368860: High-Level System Architecture for Canadian FMS ~ UX/Training | EA 14.4 | Done | 2
1015858 | #1002345 | Problem | ITK Management IETM procedure missing instruction to save index from Step 2.8.1 | PI 16 | Approved
1015856 | #1006376 | Story | Feature 1006376: Submit the PDO for RNC SVD and RNC OPI CIs | EA 16.1 | New | 1
1015855 | #1006376 | Story | Feature Demo – Customer Demo Event: Feature 1006376: | EA 16.1 | New | 2
1015854 | #1006376 | Story | Feature 1006376: Update SVD for MAMA2 Cleanup feature | EA 15.1 | Done | 1
1015826 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Manager - Startup & Shutdown | EA 16.1 | New | 5
1015825 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Managers - Health & Status and Logging | EA 15.4 | Implementing | 5
1015824 | #1014597 | Story | Feature 1014597: ULX M&C - Develop Managers - Configuration and Fault | EA 15.3 | Done | 8
1015823 | #1014597 | Story | Feature 1014597: ULX MGR - Prototype User Interface - User Screens | EA 15.2 | Done | 5
1015822 | #1014597 | Story | Feature 1014597: ULX MGR - Prototype User Interface - ULX Configuration | EA 16.1 | New | 5
1015821 | #1014597 | Story | Feature 1014597: ULX MGR - Prototype User Interface - Complete Messaging | EA 15.4 | Implementing | 5
1015820 | #1014597 | Story | Feature 1014597: ULX MGR - Prototype User Interface - Connection and Messaging | EA 15.3 | Done | 5
1015819 | #1014597 | Story | Feature 1014597: ULX M&C - Create Framework - Structure and Message Controller | EA 15.2 | Done | 8
1015818 | #1014596 | Story | Feature 1014596: ULX CP - MBSE Inputs for Algorithm & Test Vector Support | EA 16.1 | New | 3
1015817 | #1011001 | Story | Collect metrics for reporting and communication to LM and PMW-146 stakeholders - monthly | EA 15.2 | Done | 2
1015815 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.5 | EA 15.5 | New | 3
1015814 | #1014596 | Story | Feature 1014596: ULX CP - Prototype MATLAB Script - Input Stimulus Script (ULX Normalizer, ULX Signals) | EA 15.4 | Implementing | 3
1015813 | #1014596 | Story | Feature 1014596: ULX CP - Prototype MATLAB Script - Input Stimulus Script (ULX Selector, ULX Signals) | EA 15.3 | Done | 3
1015812 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.4 | EA 15.4 | Implementing | 1
1015811 | #1015005 | Story | ActiveMQ replacement prototyping | EA 16.2 | New | 5
1015810 | #1015005 | Story | ActiveMQ replacement prototyping | EA 16.1 | New | 5
1015809 | #1015005 | Story | Capability Specification Development | EA 15.2 | Done | 3
1015808 | #1015005 | Story | Capability Specification Development | EA 15.3 | Done | 3
1015807 | #1015005 | Story | Capability Specification Development | EA 15.1 | Done | 3
1015806 | #1015005 | Story | Capability Specification Development | EA 15.2 | Done | 2
1015805 | #1006191 | Story | Feature 1006191 Set MAS dev environment | EA 15.1 | Done | 5
1015804 | #1011001 | Story | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics - EA 15.1 | EA 15.1 | Invalid | 0
1015803 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | Done | 5
1015802 | #1014596 | Story | Feature 1014596: ULX CP - Prototype MATLAB Script - Input Stimulus Script (SBC w/ a ULX, Reuse from TLS) | EA 15.2 | Done | 3
1015801 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, SE Assessment Inputs | EA 15.3 | Done | 3
1015800 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, SE Assessment Inputs | EA 15.2 | Done | 5
1015798 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, Subcontract Management (AMS) | EA 15.4 | Implementing | 3
1015797 | #1014595 | Story | Feature 1014595: ULX DD - Data Model + Demo Business Value, Subcontract Management (RINCON) | EA 15.4 | Implementing | 3
1015796 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, Subcontract Management (AMS) | EA 15.3 | Done | 5
1015795 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, Subcontract Management (RINCON) | EA 15.3 | Done | 5
1015787 | #1012748 | Story | Canada FMS Capability Spec: lead author of Service Mgmt sections | EA 15.4 | Implementing | 3
1015786 | #1012748 | Story | Canada FMS Capability Spec: lead author of Service Mgmt sections | EA 15.3 | Done | 3
1015785 | #1012748 | Story | Canada FMS Capability Spec: lead author of Service Mgmt sections | EA 15.2 | Done | 3
1015784 | #1012748 | Story | Canada FMS Capability Spec: lead author of Service Mgmt sections | EA 15.1 | Done | 2
1015783 | #1012748 | Story | Canada FMS Capability Spec: UX support of creation of SA section | EA 15.3 | Done | 2
1015782 | #1012748 | Story | Canada FMS Capability Spec: UX support of creation of SA section | EA 15.4 | Implementing | 2
1015781 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 2
1015780 | #1012748 | Story | Canada FMS Capability Spec PI 15 placeholder | EA 15.4 | Invalid | 0
1015778 | #1012748 | Story | Canada FMS Capability Spec: lead author of GDS sections | EA 15.4 | Implementing | 5
1015777 | #1012748 | Story | Canada FMS Capability Spec: lead author of GDS sections | EA 15.3 | Done | 5
1015775 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, Subcontract Management (AMS) | EA 15.2 | Done | 5
1015771 | #388154 | Feature | OBS - Container Prototyping | Unassigned | Rejected
1015763 | #1001912 | Story | Feature 1001912: Regression test PI 14 delivered PWIs | EA 15.1 | Done | 3
1015753 | #395897 | Story | Baseline Image Management - Part 2 | EA 15.2 | Done | 3
1015751 | #1008506 | Story | Resolve Problem 332002: "IETM Procedure update from DTA-4 Finding: Action to Restore Service for PRVB0030 alarm." | EA 15.1 | Done | 1
1015744 | #395174 | Story | Feature 395174: Analyze GPB53, 1GHZ, 1GB/1.5-2GB PRINTED BOARD ASSEMBLY: PN = ROJ 119 2106/53, SN = A401056233 for SR 1109133 / G3171. | EA 14.5 | Done | 1
1015741 | #1002583 | Story | Support Branch/Merge Strategy for PRISM ETISP Build | EA 15.2 | Done | 3
1015737 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.4 | EA 15.4 | Implementing | 2
1015713 |  | Story | Feature 384036: Update AAA/DNS to support the Nutanix implementation | EA 14.5 | Done | 1
1015711 | #1014595 | Story | Feature 1014595: ULX DD - Updates to Detailed Design, Subcontract Management (RINCON) | EA 15.2 | Done | 5
1015702 | #354680 | Story | Feature 354680: Support the Splunk HA demo | EA 14.5 | Done | 1
1015687 | #1011150 | Problem | ET tracking alignment does not copy SUT1 parameters to SUT2 configuration set | EA 15.3 | Closed
1015624 | #379001 | Task | Re-apply Problem 1015622 Task for Deployment : Update Diameter configurations in NW CSCF/HSS due to troubleticket. | Unassigned | New
1015623 | #393391 | Story | Rebase and Test Problem 1015622 Story : Update Diameter configurations in NW CSCF/HSS due to troubleticket. | Unassigned | New | 2
1015622 | #1015623 | Problem | Update Diameter configurations in NW CSCF/HSS due to troubleticket. | EA 14.3 | Closed
1015615 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Complete Instantiation & Configuration (via JSON Config File) | EA 15.4 | Implementing | 5
1015614 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Complete Instantiation & Configuration (via JSON Config File)Test | EA 15.4 | Implementing | 5
1015613 | #1014596 | Story | Feature 1014596: ULX CP - Prototype ULX Normalizer (Set Power Level) and Unit Test | EA 15.3 | Done | 5
1015612 | #1014596 | Story | Feature 1014596: ULX CP - Prototype ULX Selector (Read N DSP Taps) and Unit Test | EA 15.3 | Done | 5
1015611 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Streamer Rx/Tx w/ Vita49.2 + Unit Test | EA 15.2 | Done | 8
1015610 | #1014596 | Story | Feature 1014596: ULX CP - Prototype Instantiation & Configuration of Components (Streamer & Cropper) | EA 15.2 | Done | 8
1015609 | #1014596 | Story | Feature 1014596: ULX CP - Setup Build & Unit Test Environment for Channel Processor & MITRE GPGPU Framework | EA 15.1 | Done | 5
1015608 | #1014596 | Story | Feature 1014596: ULX CP - Setup Build & Unit Test Environment for Channel Processor & MITRE GPGPU Framework | EA 15.1 | Done | 8
1015603 | #216364 | Feature | Add/update IETM alarm recovery procedures for RCG alarms Part 3 | PI 16 - Candidate | Approved
1015594 | #1013452 | Story | Feature 1013452: Provide Development inputs to PKI common document | PI 16 | New | 2
1015593 | #384084 | Task | Perform Regression Test of Splunk Interim Feature Demo | EA 16.4 | New
1015576 | #1013136 | Story | Feature 1013136: Regression test PI 15 delivered PWIs | EA 16.1 | New | 5
1015569 | #343920 | Task | Story 343920: CM Release of 98-P56581V – SC Site SVD (EAD 16) | PI 14 - In Progress | New
1015568 | #343920 | Task | Story 343920: CM Release of 98-P56579V – HQ Site SVD (EAD 16) | PI 14 - In Progress | New
1015567 | #343920 | Task | Story 343920: CM Release of 98-P56578V – DD Site SVD (EAD 16) | PI 14 - In Progress | New
1015566 | #343920 | Task | Story 343920: CM Release of 98-P56580V – NW Site SVD (EAD 16) | PI 14 - In Progress | New
1015565 | #216364 | Feature | Add/update IETM alarm recovery procedures for RBS alarms (6 of 6) | PI 16 - Candidate | Approved
1015564 | #343920 | Task | Story 343920: CM Release of 98-P56577V – AU Site SVD (EAD 16) | PI 14 - In Progress | New
1015563 | #343920 | Task | Story 343920: CM Release of 98-P56582V – WH Site SVD (EAD 16) | PI 14 - In Progress | New
1015562 |  | Problem | fiber mux AID is incorrect for DTE/DCE setting | Unassigned | Assessing
1015556 | #1017680 | Problem | ET SW Interface Verification Test Procedure 99-P57052M is blank on hard disk | EA 15.3 | Closed
1015541 | #1015603 | Story | Feature 1015603: IETM Support for RCG Alarms (EA 16.1) | EA 16.1 | New | 3
1015537 | #1015603 | Story | Feature 1015603: IETM Support for RCG Alarms (EA 16.2) | EA 16.2 | New | 3
1015536 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015535 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015534 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015533 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015532 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015531 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015530 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015529 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015528 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015527 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015525 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015523 | #1015603 | Story | <Feature 396669>: Develop IETM and Perform Development Testing | PI 16 - Candidate | New | 20
1015522 | #1015603 | Story | <Feature 396669>: Develop IETM Perform Development Testing | PI 16 - Candidate | New | 20
1015521 | #1015603 | Story | <Feature 396669>: Develop IETM and Perform Development Testing | PI 16 - Candidate | New | 20
1015520 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0
1015516 | #396669 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 15 | Invalid | 0
1015515 | #396669 | Story | Feature 396669: Develop RCG Alarm Recovery Procedures (15.4) | EA 15.4 | New | 1
1015514 | #396669 | Story | Feature 396669: Develop RCG Alarm Recovery Procedures (15.3) | EA 15.3 | Done | 2
1015512 | #396669 | Story | Feature 396669: Develop RCG Alarm Recovery Procedures (15.2) | EA 15.2 | Done | 3
1015511 | #396669 | Story | Feature 396669: Develop RCG Alarm Recovery Procedures (15.1) | EA 15.1 | Done | 5
1015509 | #1015603 | Story | Feature 1015603: IETM Support for RCG Alarms (EA 16.3) | EA 16.3 | New | 3
1015508 | #1015603 | Story | Feature 1015603: IETM Support for RCG Alarms (EA 16.4) | EA 16.4 | New | 3
1015458 | #1015438 | Feature | TO-6 Service Management - respond to questions from ATT | PI 16 - Candidate | Approved
1015457 | #1015439 | Story | TO-6 Respond to questions from ATT - Core SME Support | EA 15.2 | Invalid | 0
1015456 | #1015439 | Story | TO-6 Respond to questions from ATT - Core SME Support | EA 15.4 | Implementing | 1
1015455 | #1015439 | Story | Feature 1015439: TO-6 Respond to questions from ATT - WWTS SME Support | EA 15.4 | New | 1
1015454 | #1015439 | Story | Feature 1015439: TO-6 Respond to questions from ATT - WWTS SME Support | EA 15.2 | Invalid | 0
1015453 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ FCAPS | EA 14.4 | Done | 2
1015452 | #1015439 | Story | TO-6 Respond to questions from ATT - SIC SME Support | EA 15.2 | Invalid | 0
1015451 | #1015439 | Story | TO-6 Respond to questions from ATT - SIC SME Support | EA 15.3 | Invalid | 0
1015449 | #1015439 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 15.3 | Done | 1
1015448 | #1015439 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 15.2 | Invalid | 0
1015447 | #1015439 | Story | TO-6 Respond to questions from ATT - SE SME Support | EA 15.4 | New | 1
1015446 | #1015439 | Story | TO-6 Respond to questions from ATT | EA 15.4 | New | 1
1015445 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.2 | EA 15.2 | Done | 2
1015444 | #1015439 | Story | TO-6 Respond to questions from ATT | EA 15.3 | Invalid | 0
1015443 | #1015439 | Story | TO-6 Respond to questions from ATT | EA 15.2 | Invalid | 0
1015442 | #1015439 | Story | TO-6 Respond to questions from ATT | EA 15.1 | Invalid | 0
1015440 | #1011001 | Story | Analyze data, Identify issues and communicate metrics - EA 15.1 | EA 15.1 | Done | 2
1015439 | #1015438 | Feature | TO-6 Service Management - respond to questions from ATT | EA 15.5 | Implementing
1015385 | #297335 | Story | ODE ClearCase Repository Cleanup | EA 14.5 | Done | 5
1015383 | #380808 | Story | HBSS team support: Install (2600) HBSS VMs from Scratch and regression Nutanix, HBSS | EA 15.1 | Invalid | 0
1015368 | #384036 | Story | Feature 384036: Continue IETM Analysis for Nutanix | EA 14.5 | Done | 5
1015367 | #384036 | Story | Feature 384036: Continue IETM Analysis for Nutanix | EA 14.5 | Done | 5
1015366 |  | Story | Feature 384136: OBS HBSS- Finalize IETMs for Style Guide Compliance (EA 14.5) | Unassigned | Invalid | 0
1015334 | #1015153 | Story | Disc image (.iso/.gi) testing in lab | EA 15.1 | Done | 5
1015333 | #1015400 | Story | Investigate iso/gi files to find ones no longer applicable and write PWIs to clean up manifests | Unassigned | New | 8
1015332 | #1015153 | Story | Acquire new Roxio software | EA 14.5 | Done | 1 | #1015272 #1015328
1015331 | #1015153 | Story | IETM Updates on how to use Windows 10 to burn images | Unassigned | Invalid | 0
1015329 | #1015153 | Story | Feature 1015153: IETM Updates for new procedure on how to use Roxio | PI 15 | Invalid | 0
1015328 | #1015153 | Story | Update the HSM - 99-P59552V Software to Hardware Mapping ILS Laptop GEN2 Ð ETT | EA 14.5 | Done | 2 | #1015327
1015327 | #1015153 | Story | Feature 1015153: Update the PL01-P59548V004 ILS LAPTOP GEN2 PARTS LIST (Used at WH, NW, AU, SC – ETT) | EA 15.1 | Invalid | 0
1015319 | #1014023 | Story | Feature 1014023: Track Availability KPIs implemented in PI-14 | EA 15.2 | Done | 2
1015314 | #387446 | Story | Lab Support for Mobility Call Flow Updates | EA 15.3 | Done | 1
1015304 |  | Task | debug metrics automation copy issue | EA 14.4 | Done
1015287 | #376446 | Story | Feature 376446: Obtain RHEL license | EA 14.4 | Done | 2
1015276 | #1015153 | Story | Create Technical IETM inputs on how to use Windows 10 to burn images | Unassigned | Invalid | 0 | #1015331
1015275 |  | Task | Retire the MTB | PI 16 | New
1015273 | #1015153 | Story | Create Technical IETM inputs for new procedure on how to use Roxio | EA 15.1 | Invalid | 0 | #1015329 #1015334
1015272 | #1015153 | Story | Update the SVD Ð 98-P54141T ILS LAPTOP GEN2 SVD - Part 1 | EA 14.5 | Done | 3 | #1015334
1015271 | #1015153 | Story | Update the HSM - 99-P59551V Software to Hardware Mapping ILS Laptop GEN2 - NAVSOC | Unassigned | Invalid | 0
1015270 | #1015153 | Story | Update the HSM - 99-P59550V Software to Hardware Mapping ILS Laptop GEN2 Ð Tools | EA 15.1 | Invalid | 0 | #1015267
1015269 | #1015153 | Story | Update the PL01-P59548V003 ILS LAPTOP GEN2 PARTS LIST (Used at NAVSOC HQ and NAVSOC DD) | Unassigned | Invalid | 0
1015267 | #1015153 | Story | Feature 1015153: Update the PL01-P59548V002 ILS LAPTOP GEN2 PARTS LIST (Used at WH, NW, AU, SC Ð Tools) | EA 15.3 | Invalid | 0
1015259 |  | Task | Story 393213: CM Release of 98-P55616M – IA – SVD (EAD 17) May 2020 Update | PI 15 | Invalid
1015258 | #1014595 | Story | Feature 1014595: ULX DD - IA/Cyber Support of ULX Design | EA 15.1 | Done | 2
1015254 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 Cyber (part 1) | EA 15.3 | Done | 1
1015253 | #1014597 | Story | Feature 1014597: Support ULX Manager, Mon & Control Development (Part 1) | EA 15.2 | Done | 2
1015248 | #377437 | Task | Feature 377437: Submit PDO for PL01-P59554V001 - ILS - PARTS LIST, LAPTOP, MTC-AJM GEN2 ASSEMBLY | EA 15.4 | Done
1015247 | #377437 | Task | Feature 377437: Submit PDO for PL01-P59548V001 - ILS - ILS LAPTOP GEN2 ASSEMBLY, Parts List | EA 15.2 | Done
1015246 | #377437 | Task | Feature 377437: Submit PDO for PL01-P59548V004 - ILS - ILS LAPTOP GEN2 ASSEMBLY, Parts List | EA 15.2 | Done
1015241 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: WWTS WF SME Support | EA 16.2 | New | 2
1015240 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering SME Support | EA 16.2 | New | 1
1015239 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering SME Support | EA 16.2 | New | 1
1015238 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: IA and COMSEC | EA 16.1 | New | 3
1015237 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.1 | New | 5
1015236 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support (WF) | EA 16.1 | New | 8
1015235 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Engineering Tech Lead | EA 16.1 | New | 5
1015234 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: WWTS WF SME Support | EA 16.1 | New | 2
1015233 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.1 | New | 1
1015232 | #1014362 | Story | TO-8 Unclass GDS Capability Spec: Author and SME support | EA 16.1 | New | 1
1015225 | #1012485 | Story | Feature 1012485: Update the SMDC (ARSTRAT) and RSSC tabs to reflect actual roles (JDTA) (Part 2) | EA 16.1 | Invalid | 0
1015222 | #1014491 | Story | Implement the WCDMA Reliability Metrics (Group Call CSSR) defined in PI-14 | EA 15.1 | Done | 3
1015217 | #1013063 | Task | Feature 1013063: Submit PDO for MUOS_IG_GS_NMS_NM_Provisioning_OTAP_SVD_98-P59419M | PI 16 | New
1015216 |  | Task | Story 393213: CM Release of 98-P59412M - NMS - NM - Provisioning - KeyMgmt - SVD | PI 15 | Invalid
1015213 | #1013452 | Story | Feature 1013452: Update PKI Certs CI with M2M based authentication between EGS and UI servers | PI 16 | New | 5
1015211 | #380808 | Story | Feature 380808: PCR resolution using 360 Nutanix | PI 16 | New | 8
1015210 | #380808 | Story | Feature 380808: Install DX2600 Nutanix HW in V-Lab | EA 15.1 | Done | 3
1015209 | #380808 | Story | Feature 380808: Create Extreme Switch cleanup configuration config to apply after Nutanix/Splunk/HBSS installation | EA 15.2 | Done | 3
1015208 | #380808 | Story | Feature 380808: Create F5 load balancer cleanup configuration config to apply after Nutanix/Splunk/HBSS installation | EA 15.2 | Done | 3
1015207 | #380808 | Story | Feature 380808: Create McAfee firewall cleanup configuration config to apply after Nutanix/Splunk/HBSS installation | EA 15.2 | Done | 3
1015206 | #380808 | Story | Feature 380808: Create router cleanup configuration config to apply after Nutanix/Splunk/HBSS installation | EA 15.3 | Done | 3
1015205 | #380808 | Story | Feature 380808: Analyze Cisco Switch config to determine post-installation cleanup to be done | PI 15 | Invalid | 0
1015204 | #380808 | Story | Feature 380808: Analyze McAfee firewall config to determine post-installation cleanup to be done | EA 15.1 | Done | 3
1015203 | #380808 | Story | Feature 380808: Analyze Extreme Switch config to determine post-installation cleanup to be done | EA 15.1 | Done | 2
1015202 | #380808 | Story | Feature 380808: Analyze F5 Load Balancer config to determine post-installation cleanup to be done | EA 15.1 | Done | 2
1015201 | #380808 | Story | Feature 380808: Analyze Router config to determine post-installation cleanup to be done | EA 15.1 | Done | 2
1015195 | #1014491 | Story | Define additional KPIs | EA 15.4 | Implementing | 3
1015189 | #396001 | Story | Feature 396001: OSS-RC install, integrate, and perform STCD at WH under directions of FRB 2018-12 (part 1 of 2) | EA 16.1 | New | 2
1015187 | #1005403 | Story | Feature 1005403: Review INC000004378757 MRCs for Antenna & ET Lubrications | EA 14.5 | Done | 2
1015167 | #1015153 | Story | <Feature 1015153>: Initiate CM PDO Processing for all CI's | EA 15.4 | Invalid | 0
1015166 | #1015153 | Story | Feature Demo - Customer Demo Event <Feature 1015153>- Prep and Perform Feature Demo- Analysis | EA 15.4 | New | 1 | #1015167
1015165 | #1015153 | Story | <Feature 1015153>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.1 | Invalid | 0 | #1015166
1015164 | #1015153 | Story | <Feature 1015153>: Execute STCD Feature Integration and testing including STCD updates identified | EA 15.1 | Invalid | 0 | #1015166
1015163 | #1015153 | Story | <Feature 1015153>: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1015166
1015162 | #1015153 | Story | Feature 1015153: ILS Incorporation of IETM updates and Integration Support for Installation of Roxio | PI 15 | Invalid | 0
1015161 | #1015153 | Story | <Feature 1015153> UX Research and Design Support | PI 15 | Invalid | 0
1015160 | #1015153 | Story | <Feature 1015153>: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1015166
1015159 | #1015153 | Story | <Feature 1015153>: MFR 1 Ð Dev Team Performs Cybersecurity Assessment | EA 15.1 | Invalid | 0 | #1015166
1015158 | #1015153 | Story | <Feature 1015153>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 | Invalid | 0 | #1015166
1015157 | #1015153 | Story | <Feature 1015153>: Provide Deployment Notes and Operator Impact Inputs | EA 15.2 | Done | 1 | #1015166
1015156 | #1015153 | Story | <Feature 1015153>: Create Analysis STCD and review with stakeholders | EA 15.3 | Invalid | 0 | #1015166
1015155 | #1015153 | Story | <Feature 1015153> Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #1015156 #1015158
1015154 | #1015153 | Task | <Feature 1015153> Hold Feature Review with SMEs | EA 14.5 | Done
1015153 | #251622 | Feature | Fix disc images on MUOS to no longer require Roxio | EA 15.4 | Implementing
1015146 | #386935 | Story | IA Posture Improvement - AMS-GS Intermediate Assessment | EA 14.4 | Done | 2
1015142 |  | Story | Feature PI 15 Whitelist: Provide Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0
1015141 | #1016383 | Story | FM Whitelist updates for PI 16 (1st release): Review EAD 18 features and identify any alarms that need to be added to the whitelist | EA 16.2 | New | 1
1015140 | #1016383 | Story | Feature Demo – Customer Demo Event - Feature 1016383 | EA 16.4 | New | 1
1015139 | #1016383 | Story | FM Whitelist updates for PI 16 (1st release): Identify Whitelist content (Systems) - including severity changes | EA 16.1 | New | 2
1015138 | #1016383 | Story | FM Whitelist updates for PI 16 (1st release): Engineering Whitelist updates (Implement, Test, Review) | EA 16.4 | New | 5
1015137 | #1016383 | Story | FM Whitelist updates for PI 16 (1st release): Identify Whitelist content (Systems) | EA 16.2 | New | 2
1015136 | #1016383 | Story | Feature 1016383 FM Whitelist: MFR 1 write up | EA 16.3 | New | 1
1015135 | #1012485 | Story | Feature 1012485: Update the SMDC (ARSTRAT) and RSSC tabs to reflect actual roles (JDTA) (Part 2) | EA 15.3 | Invalid | 0
1015134 | #1002477 | Story | Feature 1002477: Obtain New Graphics for the NMS Splunk Operations & MUOS SA App Lessons (Part 2) | EA 15.2 | Done | 2
1015132 | #1016383 | Story | Resolve Problem 1009425:"Update Whitelist and QuestDoor with 3 additional alarms" | PI 16 | New | 3
1015128 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.4 | EA 14.4 | Done | 1
1015120 | #1021169 | Problem | Additional Scope for RAF Alignments | Unassigned | Assessing
1015118 | #1004171 | Story | Feature 1004171: Make updates to the script to mine the logs from Feature 381608 to get a baseline of the frequency of the issue with the module acceptance of group provisioning from Central GNH | EA 15.2 | Done | 1
1015116 | #395855 | Problem | Modification of ETT Assembly | EA 14.4 | Closed
1015011 | #1015004 | Story | Capability Specification Development | PI 16 | New | 40
1015010 | #1015005 | Story | Support ActiveMQ replacement prototyping | EA 16.1 | New | 3
1015008 | #1015004 | Story | Support Capability Specification Development | PI 16 | New | 3
1015007 | #1015005 | Story | Support Capability Specification Development | EA 15.4 | Implementing | 3
1015005 | #1015251 | Feature | WinOBS: Active MQ: Create Design for Active MQ Replacement | PI 16 - In Progress | Implementing
1015004 | #1015250 | Feature | WinOBS: MS SQL Create Capability Specification for SQL Server Replacement | PI 16 - Candidate | Approved
1014927 | #395174 | Story | Feature 395174: WAH SR 1105953, PN ROJ 119 2164/1, SN AE55638925 | EA 14.4 | Done | 1
1014915 | #388053 | Story | PPA Capability Design Document Review | EA 15.4 | New | 3
1014914 | #388053 | Story | Design PPA Replacement | EA 15.1 | Done | 3
1014910 | #387448 | Story | Feature 387448: SME Support for P2P Call Flow Updates | EA 15.1 | Done | 3
1014909 | #387448 | Story | Update P2P Communication Call Flows | EA 15.1 | Done | 2
1014908 | #387448 | Story | Update P2P Communication Call Flows | EA 14.4 | Done | 3
1014906 | #396437 | Story | Feature 396437: Attempt last effort to do a build on azdc-clrdev14 | EA 14.4 | Done | 2
1014892 | #395897 | Story | Update Call Banks with latest patches EA 15.5 | EA 15.5 | New | 2
1014891 | #395897 | Story | Update Call Banks with latest patches EA 15.3 | EA 15.3 | Done | 2
1014890 | #395897 | Story | Update Call Banks with latest patches EA 15.1 | EA 15.1 | Done | 2
1014889 | #1012485 | Story | Feature 1012485: Update the JDTA for ACAS scanning and other Scanning | EA 15.1 | Done | 1
1014887 | #354680 | Story | Develop process for adding Domain accounts to Splunk HA. | EA 14.4 | Done | 2
1014884 | #384084 | Story | Feature 384084: Netcool Correlations - Complete Iterative Implementation, Integration, development Testing including updating design - part 4 | EA 14.4 | Done | 2 | #380808
1014881 | #395373 | Story | Baseline Image Management Process Document | EA 14.5 | Done | 5
1014880 | #395373 | Story | Collaborate on Scan Assessment Guidance document-Part 1 (Feature 395373 Cyber Sustainment Activities) | EA 14.4 | Done | 3
1014857 | #1001912 | Story | Feature 1001912: WF PWI burndown - Fernando | EA 14.4 | Done | 5
1014854 | #1001912 | Story | Feature 1001912: WF PWI burndown - Yue-Chain | EA 14.4 | Done | 5
1014844 | #384036 | Story | Feature 384036: Update Nutanix config for automatic snapshots | EA 14.4 | Done | 2
1014843 | #384036 | Story | Feature 384036: Update Nutanix config for operator roles to make it functional | EA 14.4 | Done | 2
1014840 | #384036 | Story | Exercise Nutanix SVD by rebuilding the Nutanix Cluster 200 in SWIT Lab | EA 14.4 | Done | 2
1014829 | #377437 | Story | Feature 377437 ETT: Rebuild the ETT Laptop Image | EA 15.1 | Done | 3 | #377441
1014824 |  | Problem | EAD-15 Deployment: Port configuration for the ETT laptop is incorrect in baseline. | Unassigned | Triage
1014823 | #377437 | Story | Feature 377437 ETT: Review the new RF Alignment Tool | EA 14.4 | Done | 1
1014820 | #384136 | Story | Feature 384136: OBS HBSS- Review IA Related IETMs for Compliance (EA 14.4) | EA 14.5 | Done | 2
1014801 | #384036 | Story | Feature 384036: Review all SVD and IETM procedures for Nutanix | EA 14.4 | Done | 3
1014796 |  | Task | Story 393213: CM Release of 98-P59428M - NMS_NM - NM SIEM-Security Information Event Management, SVD (EAD 17) | PI 15 | Invalid
1014795 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P59411M - NMS_NM - NM McAfee External Network Intrusion Detection | PI 16 | New
1014794 |  | Task | Story 393213: CM Release of 99-P57051M - NMS_NM - MUOS Ground System Account Maintenance Plan (Duplicate) | PI 15 | Invalid
1014793 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P554477M - GTS - RN - RANI, SVD | PI 16 | New
1014792 | #384036 | Story | Feature 384036: Support Impact Assessment of Nutanix HW Changes | EA 14.4 | Done | 1
1014791 | #384036 | Story | Feature 384036: Support Impact Assessment of Nutanix HW Changes | EA 14.4 | Done | 1
1014790 |  | Task | Story 1011568: CM Release of 98-P55755M - GS_Network - GS Firewall Network, SVD (EAD 18) | PI 15 | Invalid
1014789 | #384036 | Story | Support Impact Assessment of Nutanix HW Changes | EA 14.4 | Done | 2
1014788 | #384036 | Story | Support Impact Assessment of Nutanix HW Changes | EA 14.4 | Done | 2
1014787 |  | Task | Story 393213: CM Release of 98-P54199T - NMS_NM - NM AV/HIDS-Antivirus/Host Intrusion Detection System, SVD (EAD 17) | PI 15 | Invalid
1014786 |  | Task | Story 393213: CM Release of 98-P54191T - NMS_NM - NM Fault Management, SVD (EAD 17) | PI 15 | Invalid
1014785 |  | Task | Story 393213: CM Release of 98-P54188T003 - NMS - NM AAA-Authentication Authorization Accounting, SVD (EAD 17) | PI 15 | Invalid
1014784 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P53546T002GTS CSA/PSA L2/L3 Switch, Software Version Description (SVD) | PI 16 | New
1014783 |  | Task | Story 393213: CM Release of 98-P53523TGIS, Build 1, Software Version Description (SVD) (EAD 17) | PI 15 | Invalid
1014781 | #1003390 | Task | Feature 1003390: Submit PDO for 63-P53199T - SEIT - Functional Block Diagram MUOS Ground System | PI 16 | New
1014780 |  | Task | Story 393213: CM Release of 63-P53199T - SEIT - Functional Block Diagram MUOS Ground System (EAD 17) | PI 15 | Invalid
1014779 |  | Task | Story 393213: CM Release of 99-P53199T - SEIT - NEDB (EAD 17) | PI 15 | Invalid
1014777 | #1003390 | Task | Feature 1003390: Submit PDO for 99-P52204E - GTS - Software to Hardware Mapping - IP CORE 2 | PI 16 | New
1014771 | #1003390 | Task | Feature 1003390: Submit PDO for 01-P51736E - GTS - RFA Cabinet Assembly - RAF | PI 16 | New
1014770 | #1003390 | Task | Feature 1003390: Submit PDO for 01-P51735E - GTS - IP CORE 2, Cabinet Assembly, PSA | PI 16 | New
1014769 | #1003390 | Task | Feature 1003390: Submit PDO for 98-P55503M003 - GS_OS - GS Red Hat Enterprise Linux, SVD | PI 16 | New
1014760 | #1002345 | Story | Feature 1002345: Support HP integration and Validation into VLab (Week 3) | PI 16 | New | 3
1014759 | #1002345 | Story | Feature 1002345: Support HP integration and Validation into VLab (Week 2) | PI 16 | New | 5
1014747 | #390286 | Story | Disable LLMWR and NetBIOS on Windows 2003 Machines (Part 2) | EA 14.5 | Done | 8
1014745 | #390286 | Story | Disable LLMWR and NetBIOS on Windows 2003 Machines (Part 1) | EA 14.4 | Done | 8
1014741 | #1014737 | Story | Scan Call Banks for RMF IATT Continuous Monitoring - 16.1 | EA 16.1 | New | 2
1014737 | #245560 | Feature | Cyber: RMF Continuous Monitoring - PI 16 (Recurring) | PI 16 | Approved
1014729 | #377437 | Story | Feature 377437 ETT: Update the RF Alignment Procedure to use the new RF Alignment Tool instead of the Simulation Framework | EA 15.1 | Done | 5
1014715 | #1007900 | Story | Feature 1007900: OBS HBSS- Make IETM updates and Perform IETM Dry Runs for FM Recovery Procedures | EA 15.1 | Done | 8
1014702 | #368860 | Story | Feature 368860: Canada Cost Estimate ~ GDS | EA 14.4 | Done | 1
1014700 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.4 | Done | 1
1014699 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.3 | Done | 2
1014694 |  | Problem | INC000004671222: NAVSOC HQ-OAS - Momentum adjusts within 24 hours of EWSK | Unassigned | Assessing
1014690 | #395871 | Story | Feature 395871: PI 14 SA TT Support - cleanup of “stuck” profiles - part 3 MPC admin | EA 14.4 | Done | 2
1014689 | #293338 | Story | Developer testing and acceptance of Virtualized Developer Workstations (Part 2) | EA 14.4 | Done | 2
1014686 | #385856 | Task | Feature 385856: CM Task to Release TD20-04 ACC Artifacts documents | EA 14.3 | Done
1014676 | #1006191 | Story | Feature 1006191 Provide estimate for WF robustness (15.1) | EA 15.1 | Done | 2
1014665 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.3 | Done | 1
1014658 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.5 | EA 15.5 | New | 2
1014657 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.4 | EA 14.4 | Done | 2
1014656 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.5 | EA 14.5 | Invalid | 0
1014654 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.4 | EA 15.4 | Implementing | 2
1014653 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.3 | EA 15.3 | Done | 2
1014652 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.2 | EA 15.2 | Done | 5
1014651 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.1 | EA 15.2 | Done | 2
1014650 | #343920 | Task | Story 343920: CM Release of 99-P53447E – ILS - FRACAS (EAD 16) | EA 14.4 | Done
1014646 | #1013452 | Story | Feature 1013452: MUOS Geolocation Support/Maintenance EAD 18: GEO SVD updates, Incorporate EAD 16 Deployment Redlines (Part 2) | PI 16 | New | 2
1014645 | #1013452 | Story | Feature 1013452: Review STCD (includes Site Functional Plan) and attend 3 internal review meetings | EA 15.4 | New | 1
1014644 | #1013452 | Story | Feature 1013452: Iterative STCD Development and Site Functional Plan | Unassigned | Invalid | 0
1014643 | #1013452 | Story | Feature 1013452: Coordinate Final STCD Review Meeting (internal) | PI 16 | New | 1
1014642 | #1013452 | Story | Feature 1013452: GEO SVD Review and Closeout | PI 16 | New | 2
1014641 | #1013452 | Story | Feature 1013452: Agile Team Test (PCR Verification & Test) | PI 16 | New | 2
1014640 | #1013452 | Task | Feature 1013452: Incorporation of User Manual and IETM Updates and Integration Support for MUOS Geolocation Support, Maintenance Zeta EAD 18 | PI 16 | New
1014639 | #1013452 | Story | Feature 1013452: Review Intermediate STCD and attend review meeting | Unassigned | Invalid | 0
1014638 | #1013452 | Story | Feature 1013452: Iterative STCD Development and Site Functional Plan | PI 16 | New | 1
1014637 |  | Story | Feature 1013452: Coordinate Intermediate STCD Review Meeting (Internal) | EA 15.4 | Invalid | 0
1014636 | #1013452 | Story | Feature 1013452: MUOS Geolocation Support/Maintenance EAD 18: GEO SVD updates, Incorporate EAD 16 Deployment Redlines (Part 1) | PI 16 | New | 3
1014635 | #1013452 | Story | Feature 1013452: Engineering Review of Zeta User Manual | PI 16 | New | 2
1014634 | #1013452 | Story | Feature 1013452: IETM Updates and Integration Support for MUOS Geolocation Support, Maintenance Zeta EAD 18 | PI 16 | New | 1
1014633 | #1013452 | Story | Feature 1013452: Review Initial Test Plan (STCD) and attend internal Planning Meeting | Unassigned | Invalid | 0
1014632 | #1013452 | Story | Feature 1013452: Submit initial GEO EAD18 STCD to customer and request feedback (includes Ephemeris) | EA 15.4 | Implementing | 1
1014631 | #1013452 | Story | Feature 1013452: Coordinate Initial Test Planning (STCD) Meeting (Internal) | EA 15.4 | New | 1
1014630 | #1013452 | Story | Feature 1013452: UX Review of Zeta User Manual | PI 16 | New | 1
1014629 | #1013452 | Story | Feature 1013452: Install & Unit Test Zeta Delivery (minus IA) - RPM updates and scratch install of delivered ISOs | EA 15.3 | Done | 3
1014628 | #1013452 | Story | Feature 1013452: Iterative STCD Development and Site Functional Plan | PI 16 | New | 3
1014604 | #1014602 | Story | Feature 1014602: Build ULX System 1 and 2 (Lab Design to Accommodate Two ULX Units) | EA 15.1 | Done | 2
1014603 |  | Story | Feature 1014602: Build ULX System 1 and 2 | Unassigned | Invalid | 0
1014602 | #1020599 | Feature | TO-9: Build ULX System 1 and 2 | PI 16 - In Progress | Implementing
1014601 | #392058 | Story | Feature 392058: Support Alarm IETMs Reviews | EA 15.1 | Done | 1
1014600 | #1014598 | Story | Feature 1014598: Develop ULX Build Environment (GitLab Accounts, Create Template CI/CD Pipeline) | EA 15.1 | Done | 5
1014599 | #1014598 | Story | Feature 1014598: Support of ULX Build Environment (SWIT/VLAB Connectivity, Attend Sprint Reviews) | EA 15.1 | Done | 3
1014598 | #1020599 | Feature | TO-9: Develop Build and Development Tools | EA 15.4 | Implementing
1014597 | #1020597 | Feature | TO-9: Develop and Unit Test ULX Manager and Monitor and Control | PI 16 - In Progress | Implementing
1014596 | #1020597 | Feature | TO-9: Develop Channel Processor Prototype for ULX | PI 16 - In Progress | Implementing
1014595 | #1020602 | Feature | TO-9: Update ULX Detailed Design (Design Specification, Verification Plan, Draft Users Guide) | PI 16 - In Progress | Implementing
1014594 | #395897 | Story | Baseline Image Management - Part 1 | EA 15.1 | Done | 3
1014591 | #1014737 | Story | Scan Call Banks for RMF IATT Continuous Monitoring - 16.5 | EA 16.5 | New | 2
1014589 | #1014737 | Story | Scan Call Banks for RMF IATT Continuous Monitoring - 16.3 | EA 16.3 | New | 2
1014587 |  | Story | Scan Call Banks for RMF IATT Continuous Monitoring - 15.1 | Unassigned | Invalid | 0
1014581 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.5 | EA 15.5 | New | 3
1014578 | #257560 | Story | Feature 257560: Submit PDOs | EA 14.4 | Done | 1
1014571 | #1007536 | Story | Feature 1007536: Update critical path for PI 15 | EA 15.1 | Done | 1
1014560 | #1006191 | Story | Review DSN GW Obs Design artifacts | EA 16.1 | New | 2
1014559 | #1006191 | Story | Feature 1006191 Assist in the low level design effort, including DSN GW Prototype work, for DSN GW Obs effort | EA 15.4 | Implementing | 2
1014558 | #1006191 | Story | Feature 1006191 Assist in the low level design effort, including DSN GW Prototype work, for DSN GW Obs effort | EA 15.3 | Done | 2
1014557 | #1006191 | Story | Feature 1006191 Assist in the low level design effort, including DSN GW Prototype work, for DSN GW Obs effort | EA 15.2 | Done | 2
1014556 | #1006191 | Story | Feature 1006191 Assist in the low level design effort, including DSN GW Prototype work, for DSN GW Obs effort | EA 15.1 | Done | 2
1014555 | #1006191 | Story | Feature 1006191 Provide router configuration expertise for ASR 1001-X/SBC | EA 15.4 | Implementing | 1
1014554 | #1006191 | Story | Feature 1006191 Provide router configuration expertise for ASR 1001-X/SBC | EA 15.3 | Done | 1
1014553 | #1006191 | Story | Feature 1006191 Provide router configuration expertise for ASR 1001-X/SBC | EA 15.2 | Done | 1
1014552 | #1006191 | Story | Feature 1006191 Provide router configuration expertise for ASR 1001-X/SBC | EA 15.1 | Done | 1
1014550 | #1006191 | Story | Feature 1006191 Develop and Share Configuration Expertise for ASR 1001-X/SBC | EA 15.4 | Invalid | 0
1014549 | #378964 | Task | Steve LeBlanc PTO (EA 15.5 (6/8 - 6/11)) | EA 15.5 | Invalid
1014548 | #1006191 | Story | Feature 1006191 Develop and Share Configuration Expertise for ASR 1001-X/SBC | EA 15.3 | Invalid | 0
1014547 | #378964 | Task | Mark Sederstrom PTO (EA 15.4 (6/4)) | EA 15.4 | New
1014546 | #1006191 | Story | Feature 1006191 Develop and Share Configuration Expertise for ASR 1001-X/SBC | EA 15.2 | Invalid | 0
1014545 | #1006191 | Story | Feature 1006191 Develop and Share Configuration Expertise for ASR 1001-X/SBC | EA 15.1 | Invalid | 0
1014544 | #378964 | Task | Steve LeBlanc PTO (EA 15.4 (5/28)) | EA 15.4 | Invalid
1014543 | #1006191 | Story | Feature 1006191 Develop and Share Configuration Expertise for ASR 1001-X/SBC | PI 16 | New | 3
1014542 | #378964 | Task | Steve LeBlanc PTO (EA 15.1 (4/21 - 4/22)) | EA 15.1 | Invalid
1014541 | #378964 | Task | Steve LeBlanc PTO (EA 15.2 (4/23 - 4/24)) | EA 15.2 | Invalid
1014540 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs | PI 16 | Invalid | 0
1014539 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs | EA 15.4 | Invalid | 0
1014537 | #378964 | Task | Steve LeBlanc PTO (EA 15.1 (4/10)) | EA 15.1 | Invalid
1014536 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs | EA 15.3 | Invalid | 0
1014535 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs | EA 15.2 | Invalid | 0
1014534 | #1006191 | Story | Feature 1006191 Assist with Management of Overlapping Work Efforts between DSN GW Obs and TIS Obs and Build and Share expertise | EA 15.2 | Done | 8
1014532 |  | Task | Feature 1007900: Continued STCD Testing of IETM procedures | EA 15.2 | Invalid
1014531 | #1006191 | Story | Feature 1006191 Assist with Lab Activities for DSN GW Prototype | PI 16 | Invalid | 0
1014530 | #1006191 | Story | Feature 1006191 Assist with Lab Activities for DSN GW Prototype | EA 15.4 | Invalid | 0
1014529 | #1006191 | Story | Feature 1006191 Assist with Lab Activities for DSN GW Prototype | EA 15.3 | Done | 2
1014528 | #1006191 | Story | Feature 1006191 Assist with Lab Activities for DSN GW Prototype | EA 15.2 | Done | 2
1014527 | #1006191 | Story | Feature 1006191 Assist with Lab Activities for DSN GW Prototype | EA 15.1 | Done | 2
1014526 | #1006191 | Story | Review DSN GW Obs Design artifacts | EA 16.1 | New | 2
1014525 | #1006191 | Story | Review Detailed Design artifacts for DSN GW Obs | EA 15.4 | New | 2
1014524 | #1006191 | Story | Review Detailed Design artifacts for DSN GW Obs | EA 15.3 | Done | 2
1014523 | #1006191 | Story | Review and Deliver to CM DSN GW Obs Design Artifacts | EA 16.1 | New | 8
1014521 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.4 | New | 5
1014520 | #1006191 | Story | Assist with development of SBC-related FCAPS sections of the TIS Capability Design Document. | EA 16.2 | New | 2
1014519 | #1006191 | Story | Assist with development of SBC-related FCAPS sections of the TIS Capability Design Document. | EA 16.2 | New | 2
1014518 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.3 | Done | 5
1014517 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.2 | Done | 5
1014516 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.2 | Done | 2
1014515 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.1 | Done | 2
1014514 | #1006191 | Story | Lead the DSN GW Obs Effort Related to Detailed Design and DSN GW Prototype | EA 15.1 | Done | 5
1014512 | #1013452 | Story | Resolve Problem 348514: Update switch configuration for swtiches in Extreme Switch SVD to match port disabling performed during MPC EAD 9.24 updates | PI 16 | New | 2
1014510 | #395688 | Story | May 2020 IA Patch Deployment (Part 2) | EA 15.3 | Invalid | 0
1014509 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - IA Scans/CAP | EA 14.3 | Done | 1
1014508 | #395688 | Story | Release status report with metrics spreadsheet for May Deployment Part A | EA 15.4 | Invalid | 0
1014507 | #395688 | Story | Complete SWIT testing for May and June Patches Part A | EA 15.5 | New | 3
1014506 | #395688 | Story | Download May and June patches, and update patching script Part A | EA 15.5 | New | 2
1014505 | #395688 | Story | Complete SWIT Testing for May Deployment | EA 15.1 | Done | 3 | #1020148
1014504 | #395688 | Story | Cross-training: Create patch bundle, measure/sign and formally release to CM with final script, download bundle to protected laptop | EA 15.2 | Done | 3
1014503 | #395688 | Story | Validate May and July Patches in SWIT/Vlab vs Site Part A | EA 15.5 | New | 2
1014502 | #395688 | Story | Scan and review the patch findings from the site and SWIT and VLAB Part B | EA 15.4 | New | 2
1014501 | #395688 | Story | July 2020 Patch Deployment - Develop and finalize candidate patch target list Part A | EA 15.4 | Implementing | 3
1014500 | #395688 | Story | Dry Run May 2020 IA Patch Deployment Part B | EA 15.3 | Done | 3
1014498 | #1014387 | Story | Feature 1014387: MPC work, customer tag up | EA 16.2 | New | 1
1014497 | #1014387 | Story | Feature 1014387: CM/PDO release process | EA 16.1 | New | 1
1014496 | #1014387 | Story | Feature 1014387: Tools Support for Build | EA 15.2 | Done | 2
1014495 | #1014387 | Story | Feature 1014387: Test build in lab | EA 15.3 | Done | 2
1014494 | #1014387 | Story | Feature 1014387: Test build in lab | EA 15.3 | Done | 2
1014493 | #1014387 | Story | Feature 1014387: Create a full release build of ETISP SW (See Comments) | EA 15.2 | Done | 3
1014491 | #1014021 | Feature | Implement WCDMA reliability metrics (group call CSSR) defined in PI 14; define retainability metrics, identify/define additional metrics for WCDMA services | EA 15.4 | Implementing
1014484 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 15.4 | Implementing | 1
1014483 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 15.4 | Implementing | 1
1014482 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 15.1 | Invalid | 0
1014480 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.5) | EA 15.5 | New | 1
1014478 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.4) | EA 15.4 | New | 1
1014477 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.3) | EA 15.3 | Done | 1
1014476 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.2) | EA 15.2 | Done | 1
1014474 | #392743 | Story | Feature 392743 ATO: Fix Problem 354579 - Support update SVD to include verification steps & review | EA 14.3 | Done | 2
1014472 | #353256 | Story | Feature 353256: Travel from AU Site to PHX After Maintainer Refresher Training in AU (Trainer 2) | EA 16.3 | New | 3
1014471 | #354174 | Story | Feature 354174 Splunk IETM: Feature demo prep | EA 14.4 | Done | 1
1014465 |  | Task | Support H/W S/W Map | EA 14.4 | Done
1014461 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.1) | EA 15.1 | Done | 1
1014460 | #396437 | Story | Install and configure Samba Service on rdeadm2 | EA 14.4 | Done | 8
1014459 |  | Problem | PROVISION KPK-UK event gets stuck IN PROGRESS in KMS | Unassigned | Triage
1014456 | #354174 | Story | Feature 354174 Update Splunk IETM STCD | EA 14.4 | Invalid | 0
1014432 | #376446 | Story | Feature 376446: Call Bank SCAP Scanning cross-training. | Unassigned | Invalid | 0
1014426 | #1007900 | Story | Feature 1007900: Continued STCD Testing of SVD and IETM procedures | EA 15.2 | Done | 8
1014425 | #1007900 | Story | Feature 1007900 Continued STCD Testing of Migration of ePO 200 to Nutanix and importing ePO201 into Nutanix provide redlines to development team. | EA 15.1 | Done | 2
1014424 | #1007900 | Story | Feature 1007900: PCR Verification of SVDs associated with HBSS | EA 15.2 | Done | 5
1014423 | #1007900 | Story | Feature 1007900: Perform Customer Demo – Customer Demo Event | PI 16 | New | 1
1014421 | #387446 | Story | Feature 387446: Prepare and release the 97-P55766M AWARE RF Block Diagram updates | EA 15.4 | Implementing | 2
1014420 | #387452 | Story | Mobility Call Flow Updates | EA 16.4 | New | 1
1014419 | #387452 | Story | Mobility Call Flow Updates | EA 16.3 | New | 1
1014418 | #387452 | Story | Mobility Call Flow Updates | EA 16.2 | New | 1
1014417 |  | Story | SME Support for Provisioning Call Flow Creation | PI 16 | Invalid | 0
1014416 | #387452 | Story | Mobility Call Flow Updates | EA 16.1 | New | 1
1014415 | #387446 | Story | SME Support for Mobility Call Flow Updates | EA 15.3 | Done | 2
1014414 | #387446 | Story | SME Support for Mobility Call Flow Updates | EA 15.2 | Done | 1
1014413 | #387446 | Story | SME Support for Mobility Call Flow Updates | EA 15.1 | Done | 2
1014412 |  | Story | Call Flow Creation, Update, and Review 16.4 | EA 16.4 | Invalid | 0
1014411 | #387446 | Story | Mobility Call Flow Updates | EA 15.4 | New | 3
1014410 | #387446 | Story | Mobility Call Flow Updates | EA 15.3 | Done | 3
1014409 | #387446 | Story | Mobility Call Flow Updates | EA 15.2 | Done | 3
1014408 | #387446 | Story | Mobility Call Flow Updates | EA 15.1 | Invalid | 0
1014406 | #387452 | Story | Mobility Call Flow Updates | EA 16.4 | New | 2
1014405 | #387452 | Story | Mobility Call Flow Updates | EA 16.3 | New | 2
1014404 | #387452 | Story | Mobility Call Flow Updates | EA 16.2 | New | 2
1014403 | #387452 | Story | Mobility Call Flow Updates | EA 16.1 | New | 2
1014402 | #387446 | Story | Mobility Call Flow Updates | EA 15.4 | New | 1
1014401 | #387446 | Story | SME Support for Mobility Call Flow Updates | EA 15.4 | Implementing | 3
1014400 | #387446 | Story | Mobility Call Flow Updates | EA 15.2 | Invalid | 0
1014399 | #387446 | Story | Mobility Call Flow Updates | EA 15.2 | Done | 1
1014394 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - WH debrief, expenses, etc | EA 16.5 | New | 1
1014393 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM - WH on site support | EA 16.3 | New | 3
1014392 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM - WH on site support | PI 16 | New | 0
1014391 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM - WH on site support | EA 16.4 | New | 8
1014390 | #1014387 | Story | Feature 1014387:IA MFR & FRCB Support ONLY (not submittal) | EA 15.4 | Implementing | 2
1014389 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support | EA 15.3 | Done | 1
1014388 | #1014387 | Story | Feature 1014387: ADI/EMI/PRISM Support - POC Support | EA 15.2 | Done | 1
1014387 | #1022691 | Feature | TO 6: ETI - Support of ADI/EMI/PRISM Integration | PI 16 - In Progress | Implementing
1014386 | #354871 | Story | Feature 354871: IETM updates (OA software/procedures) OA Workstation upgrade (part 2 of 3) | EA 15.3 | Done | 3
1014385 | #354871 | Story | Feature 354871: IETM updates (OA software/procedures) OA Workstation upgrade (part 1 of 3) | EA 15.2 | Done | 3
1014384 | #354871 | Story | Feature 354871: Create Win 10 image for OA WS, update SVD (part 2 of 2) | EA 16.2 | New | 3
1014383 | #354871 | Story | Feature 354871: Create Win 10 image for OA WS, update SVD (part 1 of 2) | EA 16.1 | New | 3
1014382 | #354871 | Story | Feature 354871: Create/update SVD for OA Workstation (part 1 of 3) | EA 15.2 | Done | 2
1014381 | #384036 | Story | Identification of applicable Cat II vulnerabilities for Cisco Switch | EA 14.4 | Done | 1
1014380 | #384036 | Story | Cat II IA Stig'ing of Cisco Switch | EA 14.4 | Done | 3
1014379 | #354871 | Story | Feature 354871: Feature Demo - Customer Demo Event | EA 16.4 | New | 2
1014378 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 2 of 2) | EA 16.4 | New | 3
1014376 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 1 of 2) | EA 16.3 | New | 3
1014375 | #297335 | Story | Post RBS Build - Check in modified scripts from RBS build | EA 15.5 | New | 2
1014372 | #1001062 | Story | Check in modified scripts to support RNC BLD to source control | EA 15.3 | Done | 1
1014362 | #249368 | Feature | TO-8 Unclass GDS Capability Spec | PI 16 - Candidate | Approved
1014360 | #1019513 | Problem | Trouble ticket: INC000004670352 - WH- 1/3 of MUOS terminals not downloading most current freq profile. | PI 16 | Approved
1014349 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store | EA 15.2 | Done | 3
1014348 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 11- Recover from UF/HF Forwarders <-> Deployment Server lost comm | EA 15.3 | Done | 3
1014347 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master lost comm | EA 15.3 | Done | 3
1014346 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 9 - Recover from Cluster Master <-> Indexer Cluster lost comm | EA 15.4 | Implementing | 5
1014345 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search Head Cluster Deployer lost comm (Part 1 - Investigation) | EA 15.1 | Done | 2
1014344 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster Master lost comm | PI 16 | New | 3
1014343 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 6 - Recover from Indexer <-> Search Head lost comm | PI 16 | New | 5
1014342 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 5 - Recover from Forwarder <-> Indexer lost comm | PI 16 | New | 5
1014341 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 2 - Complete procedure) | EA 15.3 | Done | 3
1014340 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 3 - Recover from Decoder going down | EA 15.4 | New | 5
1014339 | #1008506 | Story | Feature 1008506: Write recovery Procedure 4- Recover from cluster master going down | EA 15.2 | Invalid | 0
1014338 | #1008506 | Story | Feature 1008506: Write recovery Procedure 5 - Recover from deployment server going down | EA 15.1 | Invalid | 0
1014337 | #1008506 | Story | Feature 1008506: Write Troubleshooting procedure 2 - Recover from solaris universal forwarders going down | EA 15.3 | Done | 5 | #1021055
1014336 | #1008506 | Story | Feature 1008506: Write Troubleshooting Procedure 1 - Recover from windows universal forwarders going down | EA 15.2 | Done | 5 | #1021055
1014335 | #1008506 | Story | Feature 1008506: Write recovery Procedure 3 - Recover from heavy forwarders going down | EA 15.1 | Invalid | 0
1014334 | #1008506 | Story | Feature 1008506: Write recovery Procedure 2 - Recover from search head going down | EA 15.1 | Invalid | 0
1014333 | #1008506 | Story | Feature 1008506: Write recovery Procedure 1- Recover from Indexer going down | EA 15.1 | Invalid | 0
1014329 | #395174 | Story | Feature 395174: Analyze SPB21; 5PROC 600 MHZ, 640MB/- PRINTED BOARD ASSEMBLY: SN TU8G023478 for SR 1101598 / G3134 | EA 14.4 | Done | 1
1014318 | #343920 | Task | Story 343920: CM Release of 99-P48087V - System Operational Verification Test (SOVT) for MUOSv1.1.24.0 (EAD-16) Wahiawa Power Upgrades for NCTAMSPAC SATCOM Wahiawa | EA 14.4 | Done
1014307 | #1013234 | Story | Feature 1013234: Implement Spring MVC prototype (Part 2a) | EA 15.2 | Invalid | 0
1014305 | #1015771 | Story | Implement a Simple Container | Unassigned | Invalid | 0
1014303 |  | Task | Greg OOP reminder: 6/28-7/6; 7/17-7/24 | EA 16.1 | New
1014301 | #1019101 | Problem | Change site configuration for CSCF and HSS Cabinets to the baseline configuration to lab baseline configuration | PI 16 | Triage
1014300 | #1013234 | Story | PPA Prototyping Support (SE) Part 5 | EA 15.5 | Invalid | 0
1014299 | #1013234 | Story | Feature 1013234: Update capability design document for PPA Prototyping Support (SE) 15.4 | EA 15.4 | Done | 2
1014298 | #1013234 | Story | Feature 1013234: PPA Prototyping Support (SE) 15.3 | EA 15.3 | Done | 2
1014297 | #383165 | Task | Feature 383165: Create PDO for the Release of New Rack Documentation, Drawings, and Parts List for Nutanix (FRCB Release) | EA 16.1 | Invalid
1014296 | #383165 | Task | Feature 383165: Create PDO to Release for NME 8, 9 (FRCB Release) | EA 16.1 | Invalid
1014266 | #1014252 | Story | Feature 1014252: Initiate CM PDO Processing OTAP (aka OTA-FT) CI | EA 15.4 | Implementing | 1
1014265 | #1014252 | Story | Feature Demo – Customer Demo Event Feature 1014252: OTA-FT | EA 15.4 | New | 1 | #1014266
1014264 | #1014252 | Story | Feature 1014252: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.3 | Done | 3 | #1014265
1014263 | #1014252 | Story | Feature 1014252: Execute STCD Feature Integration and testing including STCD updates identified Part 1 | EA 15.2 | Done | 2 | #1014265
1014262 | #1014252 | Story | Feature 1014252 Notify MFTs to perform OTA-FT following bootstrap OTA-FT: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1014265
1014261 | #1014252 | Story | Feature 1014252 Notify MFTs to perform OTA-FT following bootstrap OTA-FT: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 15 | Invalid | 0
1014260 | #1014252 | Story | Feature 1014252 Notify MFTs to perform OTA-FT following bootstrap OTA-FT: UX Research and Design Support (Change back to UX Team) | PI 15 | Invalid | 0
1014259 | #1014252 | Story | Feature 1014252 Notify MFTs to perform OTA-FT following bootstrap OTA-FT: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1014265
1014258 | #1014252 | Story | Feature 1014252: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 15.2 | Done | 1 | #1014265
1014257 | #1014252 | Story | Feature 1014252: Perform Iterative Implementation, Integration, development Testing including updating design (Part 1) | EA 15.1 | Done | 3 | #1014265 #1017211
1014256 | #1014252 | Story | Feature 1014252: Provide Deployment Notes and Operator Impact Inputs | EA 15.3 | Done | 1 | #1014265
1014255 | #1014252 | Story | Feature 1014252: Create STCD and review with stakeholders | EA 15.1 | Done | 3 | #1014257 #1014264 #1014265 #1014263
1014254 | #1014252 | Story | Feature 1014252: Document design to start Implementation | PI 15 | Invalid | 0 | #1014255 #1014257
1014253 | #1014252 | Task | Feature 1014252: Hold Feature Review with SMEs | EA 15.1 | Invalid
1014252 | #1015467 | Feature | Notify MFTs to perform OTA-FT following bootstrap OTA-FT (trouble ticket INC000004670352) | EA 15.4 | Ready for Feature Demo
1014183 | #396437 | Story | WF CLL Build Support for EA 14.5 | EA 14.5 | Done | 1
1014182 | #396437 | Story | WF CLL Build Support for EA 14.4 | EA 14.4 | Done | 1
1014181 | #396437 | Story | WF CLL Build Support for EA 14.3 | EA 14.3 | Done | 1
1014167 | #1014162 | Story | Feature 1014162: Cyber Support ETISP Vender Requirements and Specification | EA 16.1 | New | 1
1014166 | #1014162 | Story | Feature 1014162: Develop ETISP Vender Requirements and Specification | EA 16.1 | New | 5
1014165 | #342054 | Story | Fix Problem 1007246: AWARE - EAD14 Deployment - Common Group Key update caused AWARE failure (Part 1) | EA 15.3 | Done | 5
1014162 | #1023808 | Feature | TO-5: Develop Requirements and Interface Specification for Vendor | PI 16 - Candidate | Approved
1014150 | #380808 | Story | Feature 380808: Create CoCo Review for NME202 (new cabinet) (EAD 18) | EA 16.1 | New | 1
1014146 | #380808 | Story | Feature 380808: Create CoCo Review for NME201 (new cabinet) (EAD 18) | EA 16.1 | New | 1
1014143 | #1013961 | Story | Feature 1013961: UX Support ETISP Capabilities Specification Development | PI 16 | New | 2
1014142 | #332951 | Story | Feature 332951: Incorporate new steps into the RNC Health Check IETM | EA 15.3 | Done | 2
1014141 | #332951 | Story | Feature 332951: UX/ILS Support for RBS Alarm Recovery Procedures (15.2) | EA 15.2 | Done | 2
1014139 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Monitor regression testing of new OTAP software. | EA 14.4 | Done | 1
1014137 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Submit and verify build. | EA 14.4 | Done | 1
1014120 | #1001912 | Story | Feature 1001912: Softphone: PWI Burndown | EA 14.5 | Done | 3
1014118 | #1006819 | Task | develop Java infrastructure for WIP metrics calculations | EA 14.4 | Done
1014117 | #1012996 | Story | Virtualize primary RAN admin server | EA 15.2 | Done | 3
1014115 | #396437 | Story | Reroute power cables for lab networking devices | EA 14.3 | Done | 1
1014114 | #380808 | Task | Feature 380808: PCR Verification of Tectia Removal (ARC201-WH-NMA) | PI 15 | New
1014113 | #380808 | Task | Feature 380808: PCR Verification of Splunk Backup Removal (ARC201-WH-NMA) | PI 15 | New
1014100 | #354174 | Story | Review and Dry run for Splunk HA IETM | EA 14.4 | Done | 3
1014092 | #353134 | Story | Feature 353134: Travel from Site to Conduct Maintainer Refresher Training in SC (Trainer 2) | EA 16.5 | New | 2
1014091 | #353134 | Story | Feature 353134: Conduct Maintainer Refresher Training in SC (Trainer 2) | EA 16.5 | New | 2
1014089 | #342054 | Story | Fix problem 1012862 and problem 1010770 | EA 15.3 | Done | 1
1014082 | #396819 | Story | Build tools laptop for Vlab | EA 14.5 | Done | 3
1014033 | #395174 | Story | Feature 395174: FRB Evaluation and Testing of WILDSTAR_ASSEMBLY_6, PN = WS2P/GDMUOS006, SN = 1000269 | EA 14.4 | Done | 2
1014028 | #1014023 | Story | Feature 1014023: Track Availability KPIs implemented in PI-14 | EA 15.4 | Implementing | 3
1014025 | #1014023 | Story | Implement the WCDMA Reliability metric (CSSR) as defined in PI-14 | EA 15.2 | Done | 3
1014023 | #1014021 | Feature | Implement WCDMA reliability metrics (CSSR) defined in PI 14; track availability-related metrics implemented in PI 14 | EA 15.4 | Implementing
1013999 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Update, test and review SVD | PI 16 | New | 3
1013998 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Unit Testing | PI 16 | New | 5
1013995 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Add new filed to OtapMuosCaller | PI 16 | New | 1
1013994 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Update OtapNotificationDaoImpl | PI 16 | New | 3
1013993 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Update UeSipMessageHandler | PI 16 | New | 1
1013975 | #393265 | Problem | RFA Cabinet - Functional Description IETM Lists incorrect Hostnames, Server Types, OS, Etc. | EA 15.4 | Approved
1013966 |  | Story | Develop ETISP Design (2) | Unassigned | Invalid | 0
1013965 | #1013961 | Story | Feature 1013961: Develop Capability Specification for Replacement ERS | PI 16 | New | 20
1013964 | #1013961 | Story | Feature 1013961: Cyber Support ETISP Capabilities Specification Development | PI 16 | New | 5
1013963 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - ROJ 208 452/1 PMD Printed Board Assembly x 1 | EA 15.5 | New | 1
1013961 | #1023808 | Feature | TO-5: Develop Capability Specification for Replacement ETISP | PI 16 - Candidate | Approved
1013954 | #353134 | Story | Feature 353134: Conduct Maintainer Refresher Training in SC Days 4-5 (Trainer 1) | EA 16.5 | New | 2
1013952 | #353134 | Story | Feature 353134: Travel from SC to PHX for Maintainer Refresher Training in SC (Trainer 1) | EA 16.5 | New | 2
1013929 |  | Task | Code cleanup and refactor of query Customer Report derived field code | EA 14.3 | Done
1013926 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (Part 4 of 8) | EA 15.2 | Done | 3
1013925 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (Part 3 of 8) | EA 15.2 | Done | 3
1013924 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (Part 2 of 8) | EA 15.1 | Done | 3
1013923 | #396001 | Story | Feature 396001: OSS-RC install, integrate, and perform STCD at WH under directions of FRB 2018-12 (part 2 of 2) | EA 16.1 | New | 8
1013921 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (part 8 of 8) | EA 15.4 | Implementing | 3
1013920 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (part 7 of 8) | EA 15.4 | Implementing | 3
1013919 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (part 6 of 8) | EA 15.3 | Done | 3
1013902 | #384084 | Story | Feature 384084: Feature Integration and testing including STCD updates identified (part 2 of 2) | EA 14.4 | Done | 3
1013894 | #342054 | Task | Feature 342054: Submit PDO for 99-P48074V - SEIT - IDP - SC - MUOSv1.1.26.0 (EAD-18) Connected AWARE - SC Installation Design Plan | PI 16 | Done
1013893 | #342054 | Task | Feature 342054: Submit PDO for 99-P48075V - SEIT - BESEP Source Material for MUOSv1.1.26.0 (EAD-18) Connected AWARE – Sicily | PI 16 | Done
1013892 | #342054 | Task | Feature 342054: Submit PDO for 99-P48076V - SEIT - SOVT for MUOSv1.1.26.0 (EAD-18) Connected AWARE – Sicily) | PI 16 | New
1013891 | #342054 | Task | Feature 342054: Submit PDO for 98-P54199T - NMS - NM - Security - AntiVirusHIDS - SVD | PI 16 | New
1013890 |  | Task | Story 393213: CM Release of 63-P53199T - ILS - Functional Block Diagram (EAD 17) | PI 15 | Invalid
1013889 | #342054 | Task | Feature 342054: Submit PDO for 98-P59405M – NMS – NM – Common – MSSQLServer – SVD | PI 16 | New
1013888 | #342054 | Task | Feature 342054: Submit PDO for 99-P55760M – GTS – SW/HW – ERS-AWARE | PI 16 | New
1013887 | #342054 | Task | Feature 342054: Submit PDO for 98-P55510M – GTS – RN – ETI – AWARE – SVD | PI 16 | New
1013886 | #342054 | Story | Feature 342054: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.4 | New | 2
1013885 | #342054 | Story | Feature 342054: Provide Development inputs to common documents (AMP) | EA 16.1 | New | 3
1013884 | #342054 | Story | Feature 342054: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 1
1013883 | #342054 | Story | Feature 342054: MFR 2 – Dev Team Supports Initial Cybersecurity Assessment | PI 16 | New | 1
1013882 | #342054 | Story | Feature 342054: MFR 2 – Dev Team Resolves Final ACAS Scan Findings | PI 16 | New | 3
1013881 | #342054 | Story | Feature 342054: MFR 2 – Dev Team Resolves ACAS Scan Findings | PI 16 | New | 3
1013880 | #342054 | Story | Feature 342054: MFR 2 – Cyber Performs initial Cybersecurity Assessment | PI 16 | New | 5
1013879 | #342054 | Story | Feature 342054: MFR 2 – Cyber Completes Final CAP | PI 16 | New | 5
1013878 | #342054 | Story | Feature 342054: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
1013877 | #342054 | Story | Feature 342054: ILS Incorporation of IETM updates and integration support - Complete development of Sicily Connected AWARE | PI 16 | New | 1
1013876 | #342054 | Story | Feature 342054: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 3
1013875 | #342054 | Story | Feature 342054: Update IETMs and Perform Development Testing | EA 15.4 | Implementing | 3 | #1013877 #1012804 #1013872
1013874 | #342054 | Story | Feature 342054: Create STCD and review with stakeholders | EA 15.1 | Done | 3
1013873 | #342054 | Story | Feature 342054- Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1
1013872 | #342054 | Story | Feature 342054: Style Guide Review of AWARE IETMs and Recovery Procedures (SC Connected AWARE) | EA 15.4 | Implementing | 3 | #1013877
1013868 | #1013452 | Task | Feature 1013452: Submit PDO for 98-P54107T – GEO – AMS-GS SVD | PI 16 | New
1013867 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 2
1013866 | #1012748 | Story | Canada FMS Capability Spec: authoring of key material impacts and IA sections | EA 15.4 | Implementing | 3
1013865 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1013864 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1013863 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1013862 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1013861 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review | EA 16.1 | New | 1
1013860 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review and Final cleanup | EA 16.1 | New | 2
1013859 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.4 | Implementing | 3
1013858 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review and Final cleanup | EA 16.1 | New | 5
1013857 | #1012748 | Story | Canada FMS Capability Spec: Lead Code Collab Review, final cleanup, EMR/FMR, and CM release | EA 16.1 | New | 5
1013856 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.2 | Done | 5
1013855 | #1012748 | Story | Canada FMS Capability Spec: Kickoff and coordination of CS, cost estimates, IMS; author selected sections | EA 15.1 | Done | 5
1013854 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review and Final cleanup | EA 16.1 | New | 5
1013853 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.2 | Done | 2
1013852 | #1012748 | Story | Canada FMS Capability Spec: Code Collab Review and Final cleanup | EA 16.1 | New | 5
1013851 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.3 | Done | 2
1013850 | #1012748 | Story | Canada FMS Capability Spec: authoring of key material impacts and IA sections | EA 15.3 | Done | 3
1013849 | #1012748 | Story | Canada FMS Capability Spec: authoring of key material impacts and IA sections | EA 15.2 | Done | 3
1013848 | #1012748 | Story | Canada FMS Capability Spec: Support creation of SA section | EA 15.2 | Done | 1
1013847 | #1012748 | Story | Canada FMS Capability Spec: Support creation of FCAPS and NMF sections | EA 15.2 | Done | 1
1013846 | #1012748 | Story | Canada FMS Capability Spec: Support creation of Network impacting sections | EA 15.2 | Done | 1
1013845 | #1012748 | Story | Canada FMS Capability Spec: support and consult for Core impacts | EA 15.2 | Done | 1
1013844 | #1012748 | Story | Canada FMS Capability Spec: Support creation of GDS and HAIPE sections | EA 15.2 | Done | 1
1013843 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.3 | Done | 3
1013842 | #1012748 | Story | Canada FMS Capability Spec: lead author of SA section | EA 15.2 | Done | 2
1013841 | #1012748 | Story | Canada FMS Capability Spec: lead author of GDS sections | EA 15.5 | New | 1
1013840 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.5 | New | 3
1013839 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.4 | New | 2
1013838 | #1012748 | Story | Canada FMS Capability Spec: Coordination of CS, cost estimates, IMS; author selected sections | EA 15.3 | Done | 3
1013837 | #1012748 | Story | Canada FMS Capability Spec: lead author of GDS sections | EA 15.2 | Done | 5
1013836 | #1012748 | Story | Canada FMS Capability Spec: lead author of GDS sections | EA 15.1 | Done | 5
1013835 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.1 | Done | 2
1013834 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.1 | Done | 2
1013833 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.2 | Done | 2
1013827 | #1013233 | Story | SME support for User Service Profile Rekey Issues design | PI 16 | New | 3
1013822 | #1013795 | Story | Lab - Complete document differences and suggested category | PI 17 | New | 3
1013821 | #1013795 | Story | Lab - Complete document differences and suggested category | PI 17 | New | 5
1013820 | #1013795 | Story | Lab - Support from CORE | PI 17 | New | 1
1013819 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:Other (AWARE, TFDU) | PI 17 | New | 5
1013818 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:Other (ETI) | PI 17 | New | 8
1013817 | #1013795 | Story | Lab - Support from SF (IASS, CSA, TIS) | PI 17 | New | 1
1013816 | #1013795 | Story | Lab - Research, Identify, Document Diffs: SF (CSA) | PI 17 | New | 5
1013815 | #1013795 | Story | Lab - Research, Identify, Document Diffs: SF (IASS, TIS) | PI 17 | New | 8
1013814 | #1013795 | Story | Feature 1013795: Lab - Support from RAF:Core (PSA, IASR) | PI 17 | New | 1
1013813 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:Core (IASR) | PI 17 | New | 5
1013812 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:Core (PSA) | PI 17 | New | 8
1013811 | #1013795 | Story | Feature 1013795: Lab - Support from RAF:RAN (All) | PI 17 | New | 1
1013810 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:RAN (All) | PI 17 | New | 5
1013809 | #1013795 | Story | Lab - Research, Identify, Document Diffs: RAF:RAN (All) | PI 17 | New | 8
1013797 | #377437 | Task | Feature 377437: Submit PDO for 01-P59554V001 - ILS - LAPTOP, MTC-AJM GEN2 ASSEMBLY Rev DASH to A | EA 15.2 | Done
1013796 | #377437 | Task | Feature 377437: Submit PDO for 01-P59548V - ILS LAPTOP GEN2 ASSEMBLY | EA 15.4 | Invalid
1013795 | #1012102 | Feature | Lab - Make V-Lab more like site - Research, Identify, Document Diffs: RAF:(RAN, CORE, ETI) and SF | PI 17 | Approved
1013793 | #377437 | Story | Feature 377437: Parts List Updates for ILS LAPTOP GEN2 ASSEMBLY ARSTRAT / AJM-MTC / ETT | EA 14.3 | Done | 2
1013791 | #342054 | Story | Create MPC for FM SC AWARE EAD-15 release | EA 14.4 | Done | 1
1013787 | #1013750 | Story | Lab - Prepare for implementation of NMS and RAN SWIT lab updates - Carl | EA 15.5 | New | 1
1013786 | #1013750 | Story | Lab - Develop and review plan to complete the work listed in the BOE - Carl | EA 15.4 | New | 1
1013785 | #1013750 | Story | Lab - Support from Core network | EA 15.3 | Done | 1
1013784 | #1013750 | Story | Lab - Complete engineering drawing updates - Carl | EA 15.3 | Done | 2
1013783 | #1013750 | Story | Lab - Support from NMS | EA 15.2 | Done | 1
1013782 | #1013750 | Story | Lab - Support from Core network | EA 15.2 | Done | 1
1013781 | #1013750 | Story | Feature 1013750: Lab - Support from RAN | EA 15.5 | New | 1
1013780 | #1013750 | Story | Lab - Gather drawings, redlines to document existings configuration - Carl | EA 15.2 | Done | 2
1013779 | #1013750 | Story | Lab - Support from NMS (train tester on weekly Tape maintenance) | EA 15.1 | Done | 1
1013778 | #1013750 | Story | Feature 1013750: Lab - Support from RAN | EA 15.4 | Implementing | 1
1013777 | #1013750 | Story | Lab - Assess current state of SWIT lab - Carl | EA 15.1 | Done | 2
1013773 |  | Story | IA SME to support the validation of the GFI-CMDB | PI 17 | New | 5
1013771 |  | Story | SIC dB developer to support the validation of the GFI-CMDB - 1 | PI 17 | New | 20
1013768 | #380808 | Story | Feature 380808: Network device PCR verification / Scratch install | EA 15.1 | Done | 3
1013766 | #384036 | Story | Feature 384036: Revert Vlab to network baseline config before Nutanix install | EA 14.5 | Done | 3
1013750 | #1012099 | Feature | Lab - SWIT Revitalize - Assessment, inventory, drawings, plan RAN and SWIT (1st of 3 Features) | EA 15.5 | Implementing
1013733 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.5) | EA 15.5 | New | 1
1013732 | #1013657 | Story | Release Regression - Call Automation (xx.5) | EA 15.5 | New | 1
1013731 | #1013657 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.5) | EA 15.5 | New | 1
1013730 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 15.5 | New | 2
1013729 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 15.5 | New | 1
1013728 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.5) | EA 15.5 | New | 1
1013727 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.4) | EA 15.4 | New | 1
1013726 | #1013657 | Story | Release Regression - Call Automation (15.4) | EA 15.4 | Implementing | 1
1013725 | #1013657 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.4) | EA 15.4 | New | 1
1013724 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 15.4 | Implementing | 5
1013723 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 15.4 | Implementing | 3
1013722 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.4) | EA 15.4 | Implementing | 5
1013721 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.3) | EA 15.3 | Done | 1
1013720 | #1013657 | Story | Release Regression - Call Automation (15.3) | EA 15.3 | Done | 1
1013719 | #1013657 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.3) | EA 15.3 | Done | 1
1013718 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 15.3 | Done | 5
1013717 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 15.3 | Done | 5
1013716 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.3) | EA 15.3 | Invalid | 0
1013715 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.3) | EA 15.3 | Done | 5
1013714 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.2) | EA 15.2 | Done | 1
1013713 | #1013657 | Story | Release Regression - Call Automation (15.2) | EA 15.2 | Done | 1
1013712 | #1013657 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.2) | EA 15.2 | Done | 1
1013711 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 15.2 | Done | 5
1013710 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 15.2 | Done | 5
1013709 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.2) | EA 15.2 | Done | 5
1013708 | #1013657 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.1) | EA 15.1 | Done | 1
1013707 | #1013657 | Story | Release Regression - Call Automation (15.1) | EA 15.1 | Done | 1
1013706 | #1013657 | Story | Release Regression - EAD15 Regression Test Selection (xx.1) | EA 15.1 | Done | 2
1013705 | #1013657 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.1) | EA 15.1 | Done | 1
1013704 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 15.1 | Done | 5
1013703 | #1013657 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 15.1 | Done | 5
1013702 | #1013657 | Story | Release Regression - NMS Automation daily runs (xx.1) | EA 15.1 | Done | 5
1013701 | #1007900 | Story | Feature 1007900: MFR 3 – CSE Write-up MFR 3 package for Final CAP | PI 16 | New | 8
1013699 | #1007900 | Story | Feature 1007900: OBS – HBSS Development IETM and SVD Support Test and IETM Reviews. | EA 15.4 | Implementing | 5
1013698 | #1007900 | Story | Feature 1007900: MFR 3 – CSE Completes IA Freshness Review | EA 15.1 | Done | 5 | #387230
1013676 | #380808 | Story | Feature 384036: Create new CI for Cluster 200 HW/SW Map | EA 15.2 | Invalid | 0
1013675 | #1010421 | Story | Feature 1010421: Resolve SPAS00000171676: ISEA Requires SME support to resolve TFBR 0173-16 | EA 15.3 | Done | 2
1013672 | #389930 | Story | Obsolescence Engineering Support for Service Management | PI 15 | Invalid | 0
1013669 | #384036 | Story | HBSS Update Node Config in the VLab | EA 14.3 | Done | 2
1013668 | #354680 | Story | Feature 354680: Implement using domain logins for the splunk servers. | EA 14.4 | Done | 2
1013665 | #384036 | Story | Update the Netcool Alarm Whitelist spreadsheet with Rationale to obtain customer conensus | EA 14.4 | Done | 1
1013663 | #354680 | Story | Feature 354680 (Site): Support Splunk HA Site Demo prep | EA 14.4 | Done | 3
1013661 | #380808 | Story | Feature 380808: Updating SVD for redlines and IA freshness for- Routers, Switches, Firewall, Load Balancer- SVD | PI 16 | New | 5
1013659 | #380808 | Story | Feature 380808: Updating SVD for redlines and IA freshness for: Cisco Switch (2600) | PI 16 | New | 1
1013657 | #262134 | Feature | Release Regression - EAD 16 Regression Testing (PI15) | EA 15.5 | Implementing
1013650 | #1013534 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 15.5 | EA 15.5 | Invalid | 0
1013649 | #1013534 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 15.4 | EA 15.4 | Invalid | 0
1013648 | #1013534 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 15.3 | EA 15.3 | Invalid | 0
1013647 | #1013534 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (15.5) | EA 15.5 | New | 1
1013646 | #1013534 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (15.4) | EA 15.4 | Implementing | 1
1013645 | #1013534 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (15.3) | EA 15.3 | Done | 1
1013644 | #1013534 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (15.2) | EA 15.2 | Done | 1
1013643 | #1013534 | Story | Lab - Maintain Labs - Facility Management, and custodian tasks - Tim (15.1) | EA 15.1 | Done | 1
1013642 | #1013534 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (15.5) | EA 15.5 | New | 1
1013641 | #1013534 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (15.5) | EA 15.5 | New | 5
1013640 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - Lab Floor Plan Updates (PI-15) | EA 15.5 | New | 2
1013639 | #1013534 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (15.5) | EA 15.5 | New | 5
1013638 | #1013534 | Story | Lab - Maintain Labs - NMS SME Support - Colin (15.5) | EA 15.5 | New | 1
1013637 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (15.1) | EA 15.1 | Done | 1
1013636 | #1013534 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (15.5) | EA 15.5 | New | 1
1013635 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (15.5) | EA 15.5 | New | 1
1013634 | #1013534 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (15.5) | EA 15.5 | New | 1
1013633 | #1013534 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (15.5) | EA 15.5 | New | 2
1013632 | #1013534 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (15.5) | EA 15.5 | New | 2
1013631 | #1013534 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (15.5) | EA 15.5 | New | 3
1013630 | #1013534 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (15.5) | EA 15.5 | New | 5
1013629 | #1013534 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (15.5) | EA 15.5 | New | 1
1013628 | #1013534 | Story | Lab - Maintain OTA Call Banks - Carl (15.5) | EA 15.5 | New | 3
1013627 | #1013534 | Story | Feature 1013534: Lab - Maintain OTA Call Banks - SME Support - Loretta (15.5) | EA 15.5 | New | 1
1013626 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (15.5) | EA 15.5 | New | 3
1013625 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (15.5) | EA 15.5 | New | 2
1013624 | #1013534 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(15.5) | EA 15.5 | New | 1
1013623 | #1013534 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 15.2 | EA 15.2 | Invalid | 0
1013622 | #1013534 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (15.5) | EA 15.5 | New | 2
1013621 | #1013534 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (15.4) | EA 15.4 | New | 1
1013620 | #1013534 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (15.4) | EA 15.4 | Implementing | 5
1013619 | #1013534 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (15.4) | EA 15.4 | Ready for Acceptance | 5
1013618 | #1013534 | Story | Lab - Maintain Labs - NMS SME Support - Colin (15.4) | EA 15.4 | Implementing | 1
1013617 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (15.5) | EA 15.5 | New | 1
1013616 | #1013534 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (15.4) | EA 15.4 | Implementing | 1
1013615 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (15.4) | EA 15.4 | New | 1
1013614 | #1013534 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (15.4) | EA 15.4 | Implementing | 1
1013613 | #1013534 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (15.4) | EA 15.4 | Implementing | 2
1013612 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (15.4) | EA 15.4 | Implementing | 2
1013611 | #1013534 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (15.4) | EA 15.4 | Ready for Acceptance | 2
1013610 | #1013534 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (15.4) | EA 15.4 | Implementing | 3
1013609 | #1013534 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (15.4) | EA 15.4 | Implementing | 3
1013608 | #1013534 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (15.4) | EA 15.4 | Implementing | 2
1013607 | #1013534 | Story | Lab - Maintain OTA Call Banks - Carl (15.4) | EA 15.4 | Implementing | 3
1013606 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (15.4) | EA 15.4 | Implementing | 3
1013605 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (15.4) | EA 15.4 | Implementing | 2
1013604 | #1013534 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(15.4) | EA 15.4 | Implementing | 1
1013603 | #1013534 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (15.4) | EA 15.4 | New | 2
1013602 | #1013534 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (15.3) | EA 15.3 | Done | 1
1013601 | #1013534 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (15.3) | EA 15.3 | Done | 5
1013600 | #1013534 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (15.3) | EA 15.3 | Done | 5
1013599 | #1013534 | Story | Lab - Maintain Labs - NMS SME Support - McCord (tape) (15.3) | EA 15.3 | Done | 1
1013598 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (15.4) | EA 15.4 | Implementing | 1
1013597 | #1013534 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (15.3) | EA 15.3 | Done | 1
1013596 | #1013534 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (15.3) | EA 15.3 | Done | 1
1013595 | #1013534 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (15.3) | EA 15.3 | Done | 2
1013594 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (15.2) | EA 15.2 | Done | 2
1013593 | #1013534 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (15.3) | EA 15.3 | Done | 2
1013592 | #1013534 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (15.3) | EA 15.3 | Done | 5
1013591 | #1013534 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (15.3) | EA 15.3 | Done | 2
1013590 | #1013534 | Story | Lab - Maintain OTA Call Banks - Carl (15.3) | EA 15.3 | Done | 3
1013589 | #1013534 | Story | Feature 1013534: Lab - Maintain OTA Call Banks - SME Support - Loretta (15.3) | EA 15.3 | Done | 1
1013588 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (15.3) | EA 15.3 | Done | 3
1013587 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (15.3) | EA 15.3 | Done | 2
1013586 | #1013534 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(15.3) | EA 15.3 | Done | 1
1013585 | #1013534 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 15.1 | EA 15.1 | Invalid | 0
1013584 | #1013534 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (15.3) | EA 15.3 | Done | 2
1013583 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (15.3) | EA 15.3 | Done | 2
1013582 | #1013534 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (15.3) | EA 15.3 | Done | 3
1013581 | #1013534 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (15.2) | EA 15.2 | Done | 1
1013580 | #1013534 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (15.2) | EA 15.2 | Done | 5
1013579 | #1013534 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (15.2) | EA 15.2 | Done | 5
1013578 | #1013534 | Story | Lab - Maintain Labs - NMS SME Support - McCord (Tape) (15.2) | EA 15.2 | Done | 1
1013577 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (15.3) | EA 15.3 | Done | 1
1013576 | #1013534 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (15.2) | EA 15.2 | Done | 1
1013575 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (15.2) | EA 15.2 | Done | 1
1013574 | #1013534 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (15.2) | EA 15.2 | Done | 1
1013573 | #1013534 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (15.2) | EA 15.2 | Done | 2
1013572 | #1013534 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (15.2) | EA 15.2 | Done | 2
1013571 | #1013534 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (15.2) | EA 15.2 | Done | 5
1013570 | #1013534 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (15.2) | EA 15.2 | Done | 8
1013569 | #1013534 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (15.2) | EA 15.2 | Done | 2
1013568 | #1013534 | Story | Lab - Maintain OTA Call Banks - Carl (15.2) | EA 15.2 | Done | 3
1013567 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (15.2) | EA 15.2 | Done | 3
1013566 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (15.2) | EA 15.2 | Done | 2
1013565 | #1013534 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(15.2) | EA 15.2 | Done | 1
1013564 | #1013534 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (15.2) | EA 15.2 | Done | 2
1013563 | #1013534 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (15.1) | EA 15.1 | Done | 1
1013562 | #1013534 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (15.1) | EA 15.1 | Done | 5
1013561 | #1013534 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (15.1) | EA 15.1 | Done | 5
1013560 | #1013534 | Story | Lab - Maintain Labs - NMS SME Support - Colin (15.1) | EA 15.1 | Done | 1
1013559 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - McCord (15.2) | EA 15.2 | Done | 1
1013558 | #1013534 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (15.1) | EA 15.1 | Done | 1
1013557 | #1013534 | Story | Feature 1013534: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (15.1) | EA 15.1 | Done | 1
1013556 | #1013534 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (15.1) | EA 15.1 | Done | 1
1013555 | #1013534 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (15.1) | EA 15.1 | Done | 2
1013554 | #1013534 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (15.1) | EA 15.1 | Done | 2
1013553 | #1013534 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (15.1) | EA 15.1 | Done | 5
1013552 | #1013534 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (15.1) | EA 15.1 | Done | 5
1013551 | #1013534 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (15.1) | EA 15.1 | Done | 2
1013550 | #1013534 | Story | Lab - Maintain OTA Call Banks - Carl (15.1) | EA 15.1 | Done | 3
1013549 | #1013534 | Story | Feature 1013534: Lab - Maintain OTA Call Banks - SME Support - Loretta (15.1) | EA 15.1 | Done | 1
1013548 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (15.1) | EA 15.1 | Done | 3
1013547 | #1013534 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (15.1) | EA 15.1 | Done | 2
1013546 | #1013534 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(15.1) | EA 15.1 | Done | 1
1013545 | #1013534 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (15.1) | EA 15.1 | Done | 2
1013544 | #1013534 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom OR Glen (15.1) | EA 15.1 | Done | 2
1013543 | #1013534 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - Carl (15.1) | EA 15.1 | Invalid | 0
1013535 | #387109 | Story | Lab SME support for installation of HW in VLAB lab | Unassigned | Invalid | 0
1013534 | #262134 | Feature | Lab - Maintain Labs for Integration, Testing and Test Events with minimal down time (PI-15) | EA 15.5 | Implementing
1013524 | #1015771 | Story | Install and configure a Docker single instance | Unassigned | Invalid | 0 | #1014305
1013523 | #1013234 | Story | Feature 1013234: Implement Spring MVC prototype (Part 1) | EA 15.1 | Done | 5
1013522 | #1013234 | Story | Feature 1013234: Configure Spring/TomEE environment | EA 15.1 | Done | 3
1013521 | #1013234 | Story | Feature 1013234: PPA Prototyping Support (SE) 15.2 | EA 15.2 | Done | 2
1013520 | #1013234 | Story | Feature 1013234: PPA Prototyping Support (SE) 15.1 | EA 15.1 | Done | 2
1013512 | #380808 | Story | Feature 380808 Verify that existing Nutanix 360 IETM Alarm Recovery Procedures are ready for a Feature Demo | PI 16 | New | 3
1013511 | #384136 | Story | Feature 384136: Incorporate Alarm Recovery Procedures into Nutanix STCD | EA 14.4 | Done | 3
1013510 | #380808 | Story | Feature 380808: UX Research and Design Support for Nutanix and Cisco | PI 15 | Invalid | 0
1013509 | #380808 | Story | Feature 380808: Update the JDTA and KSAs for Nutanix and Cisco | PI 16 | New | 3
1013508 | #380808 | Story | Feature 380808: Patch the Firewall and Load Balancer in SWIT | EA 15.2 | Done | 2
1013507 | #1013496 | Story | Incorporate Review Comments to Answers to PMW-146 Questions Related to Top Secret WCDMA Operation | PI 16 | New | 1
1013506 | #384036 | Story | Feature 384036: Perform Initial Scan of Cisco Switch | EA 14.4 | Done | 1
1013504 | #1013496 | Story | Review Answers to PMW-146 Questions Related to Top Secret WCDMA Operation | PI 16 | New | 1
1013503 | #384036 | Story | Feature 384036: Review and Build the Cisco Switch | EA 14.5 | Done | 2
1013502 | #1013496 | Story | Answer PMW-146 Questions Related to Top Secret WCDMA Operation | PI 16 | Implementing | 3
1013500 | #380808 | Story | Feature 380808: (IA) MFR 3 – CSE Completes Early CAP for Cisco Switch | EA 15.2 | Done | 3
1013499 | #380808 | Story | Feature 380808: MFR 3 – CSE Completes Final CAP for Cisco Switch | PI 16 | New | 1
1013498 | #380808 | Story | Feature 380808: Address issues from IA Refresh Scan/STIG of Cisco (2600) | EA 15.2 | Invalid | 0
1013497 | #380808 | Story | Feature 380808 Re-Scan and STIG Cisco Switch (2600) after the 4/17 refresh date. | EA 15.1 | Invalid | 0
1013496 | #243422 | Feature | Investigate PMW-146 Questions Related to Top Secret WCDMA Services | PI 16 - Candidate | Implementing
1013494 |  | Task | Story 393213: CM Release of 99-TBD– Cluster 200 – HW-SW Map (EAD 17) | PI 15 | Invalid
1013493 | #380808 | Story | Complete Peer Review and Update: 99-TBD–Cluster 200 – HW-SW Map for final Nutanix 360 Configuration | PI 16 | New | 2
1013491 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.3 | EA 14.3 | Done | 1
1013484 | #1012748 | Story | Canada FMS Capability Spec PI 16 placeholder #1 | PI 16 | Invalid | 0
1013483 | #1012748 | Story | Canada FMS Capability Spec PI 16 placeholder | PI 16 | Invalid | 0
1013481 | #1012748 | Story | Canada FMS Capability Spec PI 16 placeholder | PI 16 | Invalid | 0
1013477 | #1012748 | Story | Canada FMS Capability Spec PI 15 placeholder #2 | PI 15 | Invalid | 0
1013476 | #1012748 | Story | Canada FMS Capability Spec: Authoring and technical lead of CS | EA 15.1 | Done | 3
1013471 | #354680 | Story | Feature 354680 Splunk Backup Removal Impacts - Tectia Updates (Part 2) | EA 14.4 | Done | 3
1013470 | #1013452 | Story | Feature 1013452: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
1013469 | #1013452 | Story | Feature 1013452:- Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1 | #1013470
1013468 | #1013452 | Story | Feature 1013452: Review the Final STCD (including Site Functional Test Plan) and get customer stakeholder approval | PI 16 | New | 2 | #1013469
1013467 | #1013452 | Story | Feature 1013452: FInalize, Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 2 | #1013469
1013466 | #1013452 | Story | Feature 1013452: Provide Development inputs to AMP common document | PI 16 | New | 2 | #1013469
1013465 | #1013452 | Story | Feature 1013452: MFR 3 - CSE Completes Final CAP (Ephemeris push) | PI 16 | New | 5 | #1013469
1013464 | #1013452 | Story | Feature 1013452: MFR 3 - Dev Team Resolves Final ACAS Scan and STIG Findings (Ephemeris push) - WILL BE DONE BY ZETA | Unassigned | Invalid | 0 | #1013465 #1013469
1013463 | #1013452 | Story | Feature 1013452: Incorporation of IETM updates and integration support - Geolocation Support, Maintenance Zeta EAD 18 (includes Ephemeris to SIPRNet) | EA 15.5 | New | 1
1013462 | #1013452 | Story | Feature 1013452: Review IETM Updates for Geo EAD 18 (Ephemeris push) | PI 16 | New | 3
1013461 | #1013452 | Story | Feature 1013452: Update PKI doc for Ephemeris access | EA 15.4 | New | 3 | #1013469 #1013463
1013460 | #1013452 | Story | Feature 1013452:MFR 3 - Dev Team Resolves ACAS Scan and STIG Findings (Ephemeris push) - WILL BE DONE BY ZETA | Unassigned | Invalid | 0 | #1013464
1013459 | #1013452 | Story | Feature 1013452: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment (Ephemeris push) - WILL BE DONE BY ZETA | Unassigned | Invalid | 0 | #1013460
1013458 | #1013452 | Story | Feature 1013452: MFR 3 - CSE Performs initial Cybersecurity Assessment (Ephemeris push) | PI 16 | New | 5 | #1013459
1013457 | #1013452 | Story | Feature 1013452: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #1013458 #1013469
1013456 | #1013452 | Story | Feature 1013452: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 1 | #1013469
1013455 | #1013452 | Story | Feature 1013452: Update SIPRNet workstation for Ephemeris | EA 15.2 | Done | 3 | #1013469 #1013467 #1013457 #1013468
1013454 | #1013452 | Story | Feature 1013452: Support Zeta EAD 18 Release (EA 15.4) | EA 15.4 | Implementing | 1
1013453 | #1013452 | Task | Feature 1013452: Hold Feature Review with SMEs | EA 15.2 | Done
1013452 | #1006483 | Feature | MUOS Geolocation Support, Maintenance Zeta EAD 18 (includes Ephemeris to SIPRNet) | PI 16 - In Progress | Implementing
1013449 | #1013431 | Task | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid
1013448 | #1013431 | Task | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid |  | #1013449
1013447 | #1013431 | Task | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid |  | #1013448
1013446 | #1013431 | Task | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid |  | #1013448
1013445 | #1013431 | Task | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid |  | #1013448
1013444 | #1013431 | Task | <Feature xxx>: MFR 3 – CSE Completes Final CAP (Change back to Cyber) | Unassigned | Invalid |  | #1013448
1013443 | #1013431 | Task | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid |  | #1013444 #1013448
1013442 | #1013431 | Task | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid
1013441 | #1013431 | Task | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid
1013440 | #1013431 | Task | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid |  | #1013448
1013439 | #1013431 | Task | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid |  | #1013443
1013438 | #1013431 | Task | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid |  | #1013439
1013437 | #1013431 | Task | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid |  | #1013438
1013436 | #1013431 | Task | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid |  | #1013437 #1013448
1013435 | #1013431 | Task | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid |  | #1013448
1013434 | #1013431 | Task | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid |  | #1013446 #1013448 #1013447 #1013436
1013433 | #1013431 | Task | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid |  | #1013435 #1013436 #1013434
1013432 | #1013431 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
1013431 |  | Feature | <Feature xxx> MFR3 Template | Unassigned | Rejected
1013430 | #1013452 | Story | Feature 1013452: Support Zeta EAD 18 Release (EA 15.3) | EA 15.3 | Done | 3
1013426 | #1013452 | Story | Feature 1013452: Update MUOS Geo M2M Interface document with Instructions | EA 15.4 | Implementing | 3
1013425 | #1013452 | Story | Feature 1013452: Implement and test LB Configs for Ephemeris push - investigation needed | EA 15.2 | Done | 3 | #1013426
1013424 | #1013452 | Story | Feature 1013452: Integrate Zeta drop for Ephemeris push (EA 15.3) | EA 15.3 | Done | 5
1013423 | #1013452 | Story | Feature 1013452: Support Zeta EAD 18 Release (EA 16.3) | PI 16 | New | 1
1013422 | #1013452 | Story | Feature 1013452: Support Zeta EAD 18 Release (EA 16.1) | PI 16 | New | 1
1013408 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Loretta | EA 15.4 | New | 2
1013407 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Loretta | EA 15.3 | Done | 3
1013406 | #1013136 | Story | Feature 1013136: WF PWI Burndown -Leslie | EA 15.2 | Done | 2
1013405 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Loretta | EA 15.1 | Invalid | 0
1013404 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Hy | EA 15.4 | Implementing | 3
1013403 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Hy | EA 15.3 | Done | 5
1013402 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Hy | EA 15.2 | Done | 3
1013400 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Hy | EA 15.1 | Done | 2
1013399 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Anton | EA 15.4 | New | 5
1013396 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Anton | EA 15.3 | Done | 5
1013394 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Anton | EA 15.2 | Done | 5
1013393 | #1003390 | Story | Feature 1003390: MFR 3 – CSE Performs initial Cybersecurity Assessment (Part 2) | EA 14.4 | Invalid | 0
1013392 | #380808 | Story | Re-Scan and STIG Nutanix after the 6/26 IA refresh date. | EA 16.2 | New | 8
1013390 | #380808 | Story | Address issues from IA Refresh Scan/STIG of Nutanix 360 | PI 16 | New | 5
1013389 | #384036 | Story | Feature 384036: Continue IETM Analysis for Nutanix | EA 14.4 | Done | 3
1013388 | #384036 | Story | Feature 384036: Continue IETM Analysis for Nutanix | EA 14.4 | Done | 3
1013378 | #384036 | Story | Feature 384036: Initial IETM Analysis for Nutanix | EA 14.3 | Done | 2
1013364 | #354174 | Story | UX support for creation and review of IETM procedures related to monitoring Splunk Health (Feature 354174) | EA 14.3 | Done | 3
1013363 | #1013136 | Story | Feature 1013136: WF PWI Burndown - Anton | EA 15.1 | Done | 5
1013361 | #354174 | Story | Update routine maintenance procedure for Cluster Master and Deployment Server (Feature 354174) | EA 14.3 | Done | 5
1013353 | #1011001 | Story | Investigate and determine if there are indications within PM or alarm data that indicate preemption/congestion | EA 15.1 | Invalid | 0
1013334 | #378964 | Task | Sonia Montalvo-Johnson PTO (EA 16.4 (8/6 - 8/11)) | EA 16.4 | New
1013333 | #379175 | Task | Sonia Montalvo-Johnson PTO (EA 16.4 (8/6 - 8/11)) | EA 16.4 | New
1013332 | #279283 | Story | Lab - TXO Ericcson - Finalize TXO RBS document | EA 14.3 | Done | 2
1013331 |  | Problem | fiber mux software installation verification instructions are incorrect | Unassigned | Assessing
1013308 | #1001912 | Story | Feature 1001912: Softphone: PWI Burndown | EA 14.4 | Done | 2
1013303 | #1013292 | Story | Networking SME Support for Engineering Studies | PI 17 | New | 3
1013302 | #1013292 | Story | SIC SME Support for Engineering Studies | PI 17 | New | 3
1013301 | #1013292 | Story | Core SME Support for Engineering Studies | PI 17 | New | 3
1013300 | #1013292 | Story | WWTS SME Support for Engineering Studies | PI 17 | New | 3
1013299 | #1013292 | Story | IA SME Support for Engineering Studies | PI 17 | New | 3
1013298 | #1013292 | Story | IA SME Support for Engineering Studies | PI 16 | New | 3
1013297 | #1013292 | Story | Networking SME Support for Engineering Studies | PI 16 | New | 3
1013296 | #1013292 | Story | SIC SME Support for Engineering Studies | PI 16 | New | 3
1013295 | #1013292 | Story | Core SME Support for Engineering Studies | PI 16 | New | 3
1013294 | #1013292 | Story | WWTS SME Support for Engineering Studies | PI 16 | New | 3
1013290 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 17 | Invalid | 0
1013289 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 17 | New | 8
1013288 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 16 | New | 8
1013287 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 16 | New | 5
1013286 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 17 | New | 5
1013285 | #1013284 | Story | Conduct and Deliver TO-6 Engineering Studies | PI 16 | New | 8
1013283 | #1013280 | Story | Plan for TO-6 Trade Studies | PI 16 | New | 1
1013282 | #1013280 | Story | Plan for TO-6 Trade Studies | PI 16 | New | 2
1013281 | #1013280 | Story | Plan for TO-6 Trade Studies | PI 16 | New | 3
1013278 |  | Task | Feature 384036 Nutanix: SVD Work (Load Balancer) Container Task | PI 14 | Invalid
1013277 | #1013271 | Task | Feature 384036 Nutanix: SVD Work (Firewall) Container Task | PI 14 | Invalid
1013276 | #1013271 | Task | Feature 384036 Nutanix: SVD Work (Router) Container Task | PI 14 | Invalid
1013275 | #1013271 | Task | Feature 384036 Nutanix: SVD Work (Extreme Switch) Container Task | PI 14 | Invalid
1013274 | #1013271 | Task | Feature 384036 Nutanix: SVD Work (Nutanix) Container Task | PI 14 | Invalid
1013273 | #1013270 | Task | Feature 384036 Nutanix: Cisco IETM Stories Container Tasks | PI 14 | Invalid
1013272 |  | Task | Feature 384036 Nutanix: Nutanix IETM Stories Container Tasks | PI 14 | Invalid
1013271 | #384036 | Task | Feature 384036 Nutanix: SVD Work Category Container Task | PI 14 | Invalid
1013270 | #384036 | Task | Feature 384036 Nutanix: IETM Work Category Container Task | PI 14 | Invalid
1013259 | #243395 | Feature | PI 17 Deployment On-site Support (Recurring) | PI 17 | Draft
1013237 | #1013233 | Story | Review User Service Profile Rekey Issues design and incorporate changes | PI 16 | New | 5
1013236 | #1013233 | Story | Create User Service Profile Rekey Issues design - part 2 | PI 16 | New | 5
1013235 | #1013233 | Story | Create User Service Profile Rekey Issues design - part 1 | PI 16 | New | 5
1013234 | #388154 | Feature | OBS - PPA Prototyping | EA 15.5 | Implementing
1013233 | #1013220 | Feature | Address User Service Profile Rekey Issues (Design) | PI 16 - Candidate | Approved
1013188 |  | Story | Feature 1012503: Generate patch Installation and verification instructions for the NMS RM Guards in SWIT/VLAB (part 2) | EA 14.3 | Invalid | 0
1013187 |  | Story | Feature 1012503: Perform SWIT testing for the patch and installation instructions of the NMS RM Guards (part 2) | EA 14.4 | Invalid | 0
1013178 | #1012485 | Story | Feature 1012485: Update to include Cyber Inputs (JDTA) | EA 16.1 | Invalid | 0
1013151 |  | Problem | Nominal Telemetry in the generateMuosDatabase Script | Unassigned | Assessing
1013150 | #1013136 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 - Candidate | Invalid | 0
1013149 | #1013136 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | PI 15 - Candidate | Invalid | 0 | #1013150
1013148 | #1013136 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 15 - Candidate | Invalid | 0 | #1013149
1013147 | #1013136 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | PI 15 - Candidate | Invalid | 0 | #1013149
1013146 | #1013136 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 15 - Candidate | Invalid | 0 | #1013149
1013145 | #1013136 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 15 - Candidate | Invalid | 0
1013144 | #1013136 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 15 - Candidate | Invalid | 0
1013143 | #1013136 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 15 - Candidate | Invalid | 0 | #1013149
1013142 | #1013136 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 15 - Candidate | Invalid | 0 | #1013149
1013141 | #1013136 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 - Candidate | Invalid | 0 | #1013149
1013140 | #1013136 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 15 - Candidate | Invalid | 0 | #1013149
1013139 | #1013136 | Story | <Feature xxx>: Create STCD and review with stakeholders | PI 15 - Candidate | Invalid | 0 | #1013147 #1013141 #1013148 #1013149
1013138 | #1013136 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 15 - Candidate | Invalid | 0 | #1013141 #1013139
1013137 | #1013136 | Story | Feature 1013136: WF PWI Burndown and testing - Sang | EA 15.1 | Done | 5
1013136 | #245573 | Feature | Burn Down the WF PWI Backlog with Priority | PI 16 - In Progress | Implementing
1013125 | #379175 | Task | Holly Traver PTO (EA 15.4 (5/21)) | EA 15.4 | Invalid
1013115 | #378964 | Task | Bernie Southerland PTO (EA 15.3 (5/7 - 5/8)) | EA 15.3 | Invalid
1013114 | #1002345 | Problem | Account recovery for user NODE.DPA has incorrect command | PI 16 | Approved
1013113 | #378964 | Task | Cecilia Reynolds PTO (EA 15.5 (6/5)) | EA 15.5 | New
1013111 | #379001 | Task | Re-apply Problem 1013107 Task for Deployment : New eRxIM Values after Relocation | Unassigned | New
1013110 | #379001 | Story | Rebase and Test Problem 1013107 Story : New eRxIM Values after Relocation | Unassigned | New | 2
1013109 | #378964 | Task | Anthony Silva PTO (EA 15.3 (5/7 - 5/15)) | EA 15.3 | Done
1013108 | #378964 | Task | Anthony Silva PTO (EA 15.2 (4/28 - 5/6)) | EA 15.2 | Done
1013101 |  | Task | Testing Date Assigned - Not Asessed yet | Unassigned | Invalid
1013100 | #1013086 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 14 - Candidate | Invalid | 0
1013099 | #1013086 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | PI 14 - Candidate | Invalid | 0 | #1013100
1013098 | #1013086 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 14 - Candidate | Invalid | 0 | #1013099
1013097 | #1013086 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | PI 14 - Candidate | Invalid | 0 | #1013099
1013096 | #1013086 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 14 - Candidate | Invalid | 0 | #1013099
1013095 | #1013086 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 14 - Candidate | Invalid | 0
1013094 | #1013086 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 14 - Candidate | Invalid | 0
1013093 | #1013086 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 14 - Candidate | Invalid | 0 | #1013099
1013092 | #1013086 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 14 - Candidate | Invalid | 0 | #1013099
1013091 | #1013086 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 14 - Candidate | Invalid | 0 | #1013099
1013090 | #1013086 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 14 - Candidate | Invalid | 0 | #1013099
1013089 | #1013086 | Story | <Feature xxx>: Create STCD and review with stakeholders | PI 14 - Candidate | Invalid | 0 | #1013091 #1013099 #1013097 #1013098
1013088 | #1013086 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 14 - Candidate | Invalid | 0 | #1013091 #1013089
1013087 | #1013086 | Task | <Feature xxx> Hold Feature Review with SMEs | PI 14 - Candidate | Invalid
1013086 |  | Feature | <Feature xxx> MFR1 Template | PI 14 - Candidate | Rejected
1013077 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
1013076 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1 | #1013077
1013075 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 16 | New | 1 | #1013076
1013074 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 5 | #1013076
1013073 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Provide Development inputs to common documents | PI 16 | Invalid | 0 | #1013076
1013072 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 16 | Invalid | 0
1013071 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: UX Research and Design Support (Change back to UX Team) | PI 16 | Invalid | 0
1013070 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Develop IETMs and Perform Development Testing | PI 16 | Invalid | 0 | #1013076
1013069 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 16 | New | 1 | #1013076
1013068 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Update database schema to add new "last update date" to OtapMuosCaller table | PI 16 | New | 3 | #1013076
1013067 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 1 | #1013076
1013066 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Create STCD and review with stakeholders | PI 16 | New | 2 | #1013075 #1013074 #1013068 #1013076
1013065 | #1013063 | Story | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Document detailed design to start Implementation | PI 16 | New | 1 | #1013068 #1013066
1013064 | #1013063 | Task | Feature 1013063 Periodically notify MFTs to perform OTA-FT: Hold Feature Review with SMEs | PI 16 | New
1013063 | #204273 | Feature | Periodically notify MFTs to perform OTA-FT | PI 16 | Approved
1013056 | #380808 | Story | Feature 380808: MFR 3 – CSE Completes Final CAP for Nutanix | EA 16.2 | New | 2 | #1013060
1013032 | #284257 | Feature | Bulk Edit of User Service Profiles (Design) | PI 17 | Draft
1013001 | #1002583 | Story | Tools Team Support / LOE for SDE/ODE for EA 15.3 | EA 15.3 | Done | 1
1013000 | #1002583 | Story | Tools Team Support / LOE for SDE/ODE for EA 15.5 | EA 15.5 | New | 1
1012999 | #1002583 | Story | Tools Team Support / LOE for SDE/ODE for EA 15.4 | EA 15.4 | Implementing | 1
1012998 | #1002583 | Story | Tools Team Support / LOE for SDE/ODE for EA 15.1 | EA 15.1 | Done | 1
1012997 | #1012996 | Story | Tools Team Support / LOE for RAN/RDE for EA 15.1 | EA 15.1 | Done | 3
1012996 | #243505 | Feature | Tools Team Support / LOE for RAN/RDE Environment in PI 15 | EA 15.5 | Implementing
1012994 | #1001912 | Story | Feature 1001912: WF PWI burndown - Fernando | EA 14.3 | Done | 3
1012988 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | EA 14.5 | Invalid | 0
1012987 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | EA 14.5 | Done | 1
1012986 |  | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | Unassigned | Invalid | 0
1012932 | #381524 | Story | IETM update to fix problem 359338 Alarm Recovery GP__9022: Clarify which section to perform of Referenced Procedure | EA 15.2 | Done | 2
1012921 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | EA 14.3 | Done | 1
1012890 | #386935 | Story | Feature 386935: MUOS Geolocation Support/Maintenance EAD 16: Support Emory with document support for customer concurrence on Geo EAD16 release | EA 14.4 | Done | 2
1012888 | #354174 | Story | Feature 354174 Splunk IETM: Test/Dry run procedure 313670 fix (Part 2) | EA 14.3 | Done | 2
1012884 | #396663 | Story | Feature 396663: JDTA Redlines Associated with PI 13/EAD 15 [Task Analysis] | EA 14.3 | Done | 1
1012862 | #342054 | Problem | AWARE MariaDB general log file is getting too large | PI 16 | Implementing
1012859 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.3) | EA 14.3 | Done | 3
1012856 | #395114 | Story | Feature 395114: Capture Updates to be Used in the CDRL A009 Report | EA 15.5 | New | 1
1012855 | #395174 | Story | Feature 395174: Capture Updates to be Used in the CDRL A009 Report (RBD Report) | EA 14.5 | Done | 1
1012853 | #1012847 | Task | Feature 1012847: Submit PDO to Release CDRL A009 | PI 17 | New
1012852 | #1012847 | Story | Feature 1012847: Finalize CDRL A009 | PI 17 | New | 1
1012851 | #1012847 | Task | Feature 1012847: Internally Review Updates to the CDRL A009 | PI 17 | New
1012850 | #1012847 | Story | Feature 1012847: Update CDRL A009 with Modification Discovered in Prior Submissions and Current State | PI 17 | New | 1
1012849 | #1012847 | Story | Feature 1012847: Review Modifications from Prior Submittals | PI 17 | New | 2
1012848 | #1012847 | Story | Feature 1012847: Review Previous RBD Submittal | PI 17 | New | 1
1012847 | #262146 | Feature | Reliability & Maintainability (R&M) Block Diagrams & Mathematical Models Report (CDRL A009) | PI 16 - Candidate | Approved
1012839 | #342054 | Story | Feature 342054: Dry run and capture Redlines for AWARE alignment procedure installation section | EA 15.4 | New | 3
1012824 | #384036 | Story | Feature 384036: Nutanix SVD update with password recovery procedure | EA 14.4 | Done | 3
1012823 | #384036 | Story | Feature 384036: Cisco switch SVD updates (mostly non-technical content) | EA 14.4 | Done | 3
1012822 | #384036 | Story | Feature 384036: Complete IETM procedures for Cisco 10 GIG Switch | EA 14.3 | Done | 5
1012821 | #380808 | Story | Feature 380808: Complete review, build & release Extreme Switch SVD | PI 16 | New | 2
1012820 | #384036 | Story | Feature 384036: Update Extreme Switch SVD for new connections to LAN221/222 | EA 14.3 | Done | 3
1012819 | #384036 | Story | Feature 384036: complete SVD migration instructions in Nutanix SVDs | EA 14.4 | Invalid | 0
1012818 | #380808 | Story | Feature 380808: Install Nutanix SuperMicro loaner equipment into SWIT NME 201 | EA 15.1 | Done | 1
1012817 | #384036 | Story | Feature 384036: Move NME201 and NME202 from SWIT to V-lab | EA 14.5 | Invalid | 0
1012816 | #384036 | Story | Feature 384036: Build NME201and NME202 in SWIT to production spec | EA 14.5 | Invalid | 0
1012809 | #342054 | Story | Fix Problem 1009580: MUOSAT-MHAL: sle_cpp - connection to SLE refused to open after being open in previous scenarios | EA 14.3 | Done | 1 | #1012804
1012808 | #342054 | Story | Analyze Problem 1010770: AWARE: AHM_0003 Alarm being incorrectly cleared by AHM_0004 | EA 14.3 | Done | 5 | #1012804
1012807 | #342054 | Story | Analyze Problem 1010770: AWARE: AHM_0003 Alarm being incorrectly cleared by AHM_0004 | EA 14.3 | Done | 5 | #1012804
1012806 | #342054 | Story | Feature 342054: Add Sicily installation back into the AV/HIDS SVD | PI 16 | New | 3
1012805 | #342054 | Story | Feature 342054: Add Sicily installation back into the AWARE SVD | PI 16 | New | 3
1012804 | #342054 | Story | Feature 342054: Sicily Connected AWARE IETM Updates | Unassigned | Invalid | 0
1012803 | #342054 | Story | Feature 342054: Create MPCs related to PWI 1009580 (EAD 15 release) | EA 14.3 | Done | 1
1012780 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.3 | EA 14.3 | Done | 5
1012777 | #376446 | Story | Feature 376446: Develop PPP Driver/Configuration | EA 14.4 | Done | 3
1012763 | #1012847 | Task | Feature 1012847: Submit PDO of REL_GD-A547A_004: CDRL A009 – ILS – R&M Block Diagrams (EAD 19) | PI 17 | New
1012762 |  | Task | Story 393213: CM Release of 69-P50495E - INTERCONNECT DIAGRAM - SF/NMF, WAHIAWA (EAD 17) | PI 15 | Invalid
1012761 | #380808 | Task | Feature 380808: Submit PDO for 69-P57163M - INTERCONNECT DIAGRAM - NME 9 | PI 15 | New
1012759 | #380808 | Task | Feature 380808: Submit PDO for 01-P53569E - NME 9 CABINET ASSEMBLY - NMA | PI 15 | New
1012758 | #380808 | Task | Feature 380808: Submit PDO for 69-P57162M - NMS_NM - INTERCONNECT DIAGRAM - NME 8 | PI 15 | New
1012757 | #380808 | Task | Feature 380808: Submit PDO for PL01-P53578E001 - NMS_NM - NME 8 CABINET ASSEMBLY | PI 15 | New
1012756 | #380808 | Task | Feature 380808: Submit PDO for 01-P53578E - NMS_NM - NME 8 CABINET ASSEMBLY – NM | PI 15 | New
1012755 |  | Task | Story 393213: CM Release of 69-P50495E - INTERCONNECT DIAGRAM - SF/NMF, WAHIAWA (EAD 17) | PI 15 | Invalid
1012754 | #380808 | Task | Feature 380808: Submit PDO for 69-P59873M - INTERCONNECT DIAGRAM - NME 202 - NMS | PI 15 | New
1012750 | #380808 | Task | Feature 380808: Submit PDO for 69-P59869M - INTERCONNECT DIAGRAM - NME 201 - NMS | PI 15 | New
1012748 | #1022874 | Feature | Canada FMS Capability Spec Initial Draft | PI 16 - In Progress | Implementing
1012747 | #1012503 | Story | Feature 1012503: Provide TOFF SME (system admin) support for patching RM Guards in the labs (part 1) | EA 14.3 | Done | 2
1012743 | #396437 | Story | Feature 396437: Document the RCG build process and generate a baseline build on azdc-clrdev14 | EA 14.3 | Done | 2
1012737 | #342054 | Task | Re-apply Problem 1009580 Task for Deployment : MUOSAT-MHAL: sle_cpp - connection to SLE refused to open after being open in previous scenarios | EA 15.4 | New
1012736 | #342054 | Story | Rebase and Test Problem 1009580 Story : MUOSAT-MHAL: sle_cpp - connection to SLE refused to open after being open in previous scenarios | EA 15.4 | Implementing | 2
1012727 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis | EA 14.3 | Done | 1
1012726 | #343920 | Task | Story 343920: CM Release of 62-P51610E - GTS Switch - Core Network Product Specification (EAD 16) | EA 14.4 | Done
1012719 | #1012503 | Task | Feature 1012503: TASK = Place the RM Guard patch installation instructions and patch CD under CM control | EA 14.3 | Done
1012715 | #368860 | Story | Feature 368860: BOE Development and Estimate for Canadian Foreign Military Sales Phase 1 | EA 14.3 | Done | 2
1012714 | #386935 | Story | Feature 386935: Integration/Test for Zeta Delivery | EA 14.3 | Done | 2
1012713 | #395855 | Story | Feature 395855: Create PDO to Release 01-P51661E and 53-P52819E_Rev E | EA 14.3 | Done | 1
1012711 | #384036 | Story | Feature 384036: Create and Finish IETM Procedures for Physically Installing and Removing Nutanix Hardware | EA 14.3 | Done | 3
1012652 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.2 | Done | 2
1012645 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.2 | Done | 1
1012636 | #354680 | Story | Investigate and resolve HBSS user permissions issues related to Splunk HA. | EA 14.3 | Done | 1
1012635 | #354680 | Story | Investigate and resolve HBSS user permissions issues related to Splunk HA. | EA 14.3 | Done | 1
1012634 | #354680 | Story | Investigate and resolve HBSS user permissions issues related to Splunk HA. | EA 14.3 | Done | 1
1012619 | #1007900 | Story | Feature 1007900 Generate HBSS Test Report for FRCB | PI 16 | New | 2 | #388477
1012614 | #332951 | Story | Feature 332951: Create RBS Functional Diagram | EA 15.1 | Done | 1
1012611 | #332951 | Story | Feature Demo – Customer Demo Event: Feature 332951 INSPECTION | EA 15.4 | New | 1
1012609 | #332951 | Story | Feature 332951: Cleanup old ARP and address PWIs (15.1) | EA 15.1 | Invalid | 0
1012608 | #332951 | Story | Feature 332951: Test RBS Alarm Recovery Procedures and support reviews (15.4) | EA 15.4 | Implementing | 2
1012606 | #332951 | Story | Feature 332951: Create STCD and provide test support | EA 15.1 | Done | 1
1012605 | #332951 | Story | Feature 332951: Engineering RBS IETM updates - Developer (15.1) | EA 15.1 | Done | 2 | #1004314
1012601 | #1012588 | Story | Feature 1012588: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in WH | PI 16 - In Progress | Invalid | 0
1012597 | #1012588 | Story | Feature 1012588: Prepare & Conduct PM Kickoff Meeting with Vendor | EA 16.4 | New | 1
1012596 | #1012588 | Task | Feature 1012588: Ship Supplies and Materials to Site for 2020 Preventive Maintenance in WH | EA 16.3 | New
1012595 | #1012588 | Story | Feature 1012588: Determine Corrective Actions Based Upon Trouble Tickets Received for 2020 Preventive Maintenance of WH | EA 16.2 | New | 2
1012594 | #1012588 | Story | Feature 1012588: Present SOW Associated to 2020 Preventive Maintenance in WH | EA 16.2 | New | 2
1012593 | #1012588 | Task | Feature 1012588: Create and Validate Plan for 2020 Preventive Maintenance Activities in WH | EA 16.2 | New
1012592 | #1012588 | Task | Feature 1012588: Confirmation of Vendor, Access to Site, and WHhedule of Activities for the 2020 Preventive Maintenance in WH | EA 16.1 | New
1012591 | #1012588 | Task | Feature 1012588: Prepare, Review SOW Associated to 2020 Preventive Maintenance in WH | EA 16.1 | New
1012590 | #1012588 | Task | Feature 1012588: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in WH | PI 16 | New
1012589 | #1012588 | Story | Feature 1012588: Identification of Consumables Required for 2020 Preventive Maintenance in WH | PI 16 | New | 1
1012583 | #1012570 | Story | Feature 1012570: Request Creation & Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in SC | EA 15.4 | Invalid | 0
1012578 | #1012570 | Task | Feature 1012570: Ship Supplies and Materials to Site for 2020 Preventive Maintenance in SC | EA 16.5 | New
1012577 | #1012570 | Story | Feature 1012570: Determine Corrective Actions Based Upon Trouble Tickets Received for 2020 Preventive Maintenance of SC | EA 16.5 | New | 2
1012575 | #1012570 | Task | Feature 1012570: Create and Validate Plan for 2020 Preventive Maintenance Activities in SC | EA 16.4 | New
1012574 | #1012570 | Task | Feature 1012570: Confirmation of Vendor, Access to Site, and Schedule of Activities for the 2020 Preventive Maintenance in SC | EA 16.4 | New
1012573 | #1012570 | Task | Feature 1012570: Prepare, Review SOW Associated to 2020 Preventive Maintenance in SC | EA 16.4 | New
1012572 | #1012570 | Task | Feature 1012570: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in SC | EA 16.4 | New
1012571 | #1012570 | Story | Feature 1012570: Identification of Consumables Required for 2020 Preventive Maintenance in SC | EA 15.5 | New | 1
1012565 | #1012540 | Task | Feature 1012540: Submit PDO to Release Spares Plan [CDRL A004] | EA 16.3 | New
1012564 | #1012540 | Story | Feature 1012540: Finalize Spares Plan [CDRL A004] | EA 16.1 | New | 2
1012563 | #1012540 | Story | Feature 1012540: Participate in Internal Peer Review of the Spares Plan [CDRL A004] | EA 15.5 | New | 1
1012562 | #1012540 | Story | Feature 1012540: Internal Peer Review & Capture Redlines of the Spares Plan [CDRL A004] | EA 15.5 | New | 2
1012561 | #1012540 | Story | Feature 1012540: SME Support for Changes Through EAD 16 (5/19/20) Deployment Updates [CDRL A004] | EA 16.3 (archived) | Invalid | 0
1012560 | #1012540 | Story | Feature 1012540: Review Items Accounted Resulting from Changes Through EAD 16 (5/19/20) Deployment | EA 16.3 | New | 2
1012559 | #1012540 | Story | Feature 1012540: SME Support for LORA Updates [CDRL A004] | EA 16.2 (archived) | Invalid | 0
1012558 | #1012540 | Story | Feature 1012540: Capture Updates Reflected in the 2020 LORA for the Spares Plan [CDRL A004] | EA 16.2 | New | 2
1012557 | #1012540 | Story | Feature 1012540: SME Support for Table 1-6 (Depot Support Non-MSI) Updates [CDRL A004] | EA 16.1 (archived) | Invalid | 0
1012556 | #1012540 | Story | Feature 1012540: Revise Table 1-6 (Depot Support Non-MSI) [CDRL A004] | EA 15.4 | Implementing | 2
1012555 | #1012540 | Story | Feature 1012540: SME Support for Parts Nomenclature to Match BOM Changes Updates [CDRL A004] | EA 15.4 | Invalid | 0
1012554 | #1012540 | Story | Feature 1012540: Revise the Parts Nomenclature to Match BOM Changes [CDRL A004] | EA 15.4 | Implementing | 1
1012553 | #1012540 | Story | Feature 1012540: SME Support for Comprehensive Pricing Update Updates [CDRL A004] | EA 15.3 | Invalid | 0
1012552 | #1012540 | Story | Feature 1012540: Acquire a Comprehensive Pricing Update [CDRL A004] | EA 15.4 | Implementing | 1
1012551 | #1012540 | Story | Feature 1012540: SME Support for Hardware Additions & Deletions Updates [CDRL A004] | EA 15.2 | Invalid | 0
1012550 | #1012540 | Story | Feature 1012540: Document Hardware Additions & Deletions [CDRL A004] | EA 15.2 | Done | 2
1012549 | #1012540 | Story | Feature 1012540: SME Support for Alternate Part Numbers Updates [CDRL A004] | EA 15.1 | Invalid | 0
1012548 | #1012540 | Story | Feature 1012540: Include Alternate Part Numbers for Clarity / Usability [CDRL A004] | EA 15.1 | Done | 2
1012547 | #1012540 | Story | Feature 1012540: Begin Analysis of all System Parts [CDRL A004] - - Spares planning. | EA 15.2 | Done | 2
1012546 | #1012540 | Task | Feature 1012540: Kickoff Meeting for Spare Plan [CDRL A004] | EA 15.1 | Done
1012540 | #262146 | Feature | Spares Plan (CDRL A004) | PI 16 - In Progress | Implementing
1012524 | #393265 | Story | Feature 393265: Fix Problem 1011372 - Update IETM Procedure " Add Domain Account to McAfee Firewall - Normal Operation Procedure" with special note and update title | PI 15 | Invalid | 0
1012517 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
1012516 |  | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #1012517
1012515 |  | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #1012516
1012514 |  | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #1012516
1012513 |  | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #1012516
1012512 |  | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
1012511 |  | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
1012510 |  | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #1012516
1012509 |  | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #1012516
1012507 |  | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #1012516
1012504 |  | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
1012499 | #1012485 | Story | Feature 1012485: Standardize the Language for all KSA Statements to Remove Duplicates/Similar but Slightly Different Wording JDTA [Task Analysis] | EA 15.2 | Invalid | 0
1012495 | #1012485 | Task | Feature 1012485: Submit PDO for 99-P59545V – CDRL A011 – ILS – JDTA | EA 16.3 | New
1012493 |  | Task | Feature 1012485: Create PDO to Release JDTA [Task Analysis] | EA 16.3 | Invalid
1012492 | #1012485 | Story | Feature 1012485: Finalize JDTA [Task Analysis] | EA 16.3 | Invalid | 0
1012491 | #1012485 | Story | Feature 1012485: Participate in Peer Review JDTA [Task Analysis] | EA 16.2 | New | 2
1012490 | #1012485 | Story | Feature 1012485: Lead JDTA Peer Review and Incorporate Comments [Task Analysis] | EA 16.2 | New | 1
1012489 | #1012485 | Story | Feature 1012485: Review Differences Between JDTA and IETM Required Persons and Make Decisions on Corrective Actions [Task Analysis] | EA 16.1 (archived) | Invalid | 0
1012488 | #1012485 | Story | Feature 1012485: Update the SMDC (ARSTRAT) and RSSC tabs to reflect actual roles (JDTA) (Part 1) | EA 15.2 | Invalid | 0
1012487 | #1012485 | Story | Feature 1012485: Check that the KSAs from the O&M Tabs Match Those Reflected on the KSA Details Tabs for the JDTA [Task Analysis] | EA 15.3 | Invalid | 0
1012486 | #1012485 | Story | Feature 1012485: Compare IETM Modules "Required Persons" Table with JDTA [Task Analysis] | EA 15.3 | Invalid | 0
1012485 | #262146 | Feature | Task Analysis (JDTA) (CDRL A011) | PI 16 - In Progress | Implementing
1012475 |  | Task | Update script that relaunches the Jenkins service | EA 15.1 | Done
1012408 | #380808 | Story | Address issues from IA Refresh Scan/STIG for Splunk (6/26/20 on 360) | PI 16 | New | 8
1012406 | #380808 | Story | Re-Scan and STIG HA VM after 6/26 refresh date. | PI 16 | New | 8 | #1012408
1012346 | #384136 | Story | Feature 384136: Development of ePO 200 SVD updates on how to create qcow2 image file and create epo200 image to a Nutanix qcow2 file | EA 14.4 | Done | 8
1012322 | #1006818 | Task | improve error handling for Muos Metrics automation | EA 14.3 | Done
1012273 | #384136 | Story | Feature 384136: Perform STCD testing in VLAB by performing IETM, SVD and design instructions as developed by STCD (part 3 or 3) | EA 14.5 | Invalid | 0
1012164 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.2 | EA 14.2 | Done | 2
1012135 | #385438 | Story | Complete Load Balancer Trade Study | EA 14.2 | Done | 1
1012132 | #384036 | Story | Support Nutanix STCD Reviews | EA 14.4 | Invalid | 0
1012131 | #384036 | Story | Support Nutanix STCD Reviews | EA 14.3 | Done | 1
1012130 | #384036 | Story | Support Nutanix STCD Reviews | EA 14.2 | Done | 1
1012079 | #395373 | Story | Review VMP: Complete Scan Assessment Guidance document (Feature 395373 Cyber Sustainment Activities) | EA 14.5 | Invalid | 0
1012059 | #395373 | Story | Review DTA Process Document for MUOS (Feature 395373 Cyber Sustainment Activities) | EA 14.3 | Done | 3
1012052 | #1001248 | Story | Feature 1001248 OTAP: Review the OTAP code updates. | EA 14.4 | Done | 1
1012049 | #1010708 | Task | Story 1010708: CM Release of 99-P48093V - PPA Obsolescence Capability Specification - Initial Release | EA 14.2 | Done
1012042 | #1002381 | Task | Feature 1002381: Hardware/Software Procurement Request for OBS - HLR: HW/FRCB for HLR Deployment | PI 15 | Invalid
1012038 | #383110 | Feature | Nutanix Cleanup for EAD 18 | PI 16 | Rejected
1012018 | #354680 | Story | Feature 354680 Splunk Backup Removal Impacts - HW/SW & Parts List Updates | EA 14.3 | Done | 1
1012017 | #354680 | Story | Feature 354680 Splunk Backup Removal Impacts - Tectia Updates (Part 1) | EA 14.3 | Done | 2
1012009 | #395871 | Story | Feature 395871: MAGIC TT Support for INC000004634236 (NW-DSN GATEWAY LOSS OF SYNC CONDITION) | EA 14.2 | Done | 1
1012008 | #396819 | Story | Lab - Support - Aidan (EA 14.2) | EA 14.2 | Done | 1
1012006 | #396819 | Story | Lab - Support - G. Lyon (14.2) | EA 14.2 | Done | 1
1012004 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Orders 4 & 8 (EA 14.2) | EA 14.2 | Done | 2
1012003 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Orders 4 & 8 (EA 14.1) | EA 14.1 | Done | 2
1012000 | #1005740 | Story | IA Support for DSN Gateway Capability Spec & Initial Design | EA 14.2 | Done | 1
1011999 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Order 8 (EA 14.2) | EA 14.2 | Done | 1
1011998 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Order 8 (EA 14.1) | EA 14.1 | Done | 2
1011996 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Order 4 (EA 14.2) | EA 14.2 | Done | 1
1011995 | #396002 | Story | Feature 396002: BOE Proposal Support for Task Order 4 (EA 14.1) | EA 14.1 | Done | 2
1011986 | #395174 | Story | Feature 395174: FRB Testing of the AIR DEHYDRATOR, ADH3-COM of PN = 17479 (SC), SN = 1268 | EA 14.2 | Done | 1
1011965 | #355229 | Story | Feature 355229: Pre alignment procedure review | EA 14.2 | Done | 2
1011921 |  | Problem | IETM Update: KPK-UK Rekey, if failed due to Insufficient Keys Error, operator should retry | Unassigned | Assessing
1011920 |  | Problem | Splunk GUI locks up and becomes unresponsive | Unassigned | Assessing
1011910 | #380808 | Story | Complete Peer Review and Update: 99-P59435M – NMS – NM – Common – HW-SW Map | PI 16 | New | 2 | #1024083
1011909 | #380808 | Story | Complete Peer Review and Update: 98-P55755M - Firewall - Network - SVD (EAD 17) | PI 16 | New | 2
1011908 | #380808 | Story | Complete Peer Review and Update: 98-P59428M - NMS - NM - Security - SIEM - SVD | PI 16 | New | 2
1011907 | #380808 | Story | Complete Peer Review and Update: 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD (EAD 18) | PI 16 | New | 2
1011906 | #380808 | Story | Complete Peer Review and Update: 98-P59856M - Network - ExtremeSwitch - SVD (EAD 18) | PI 16 | New | 2
1011905 | #380808 | Story | Complete Peer Review and Update: 99-P57050M - NMS - NM Common PKI (EAD 18) | PI 16 | New | 2
1011904 | #380808 | Story | Complete Peer Review and Update: 98-P59434M_NM_CSCI_SVD (EAD 18) | PI 16 | New | 2
1011903 | #380808 | Story | Complete Peer Review and Update: Nutanix_HP_SVD_98-P55764M (EAD 17) | PI 16 | New | 2
1011902 | #380808 | Story | Complete Peer Review and Update: 98-P54188T - NMS -NM - Security -AAA - SVD (EAD 18) | PI 16 | Invalid | 0
1011901 | #380808 | Story | Complete Peer Review and Update: 98-P59414M – NMS – NM – Security – GSKey – SVD (GSKM) (EAD 18) | PI 16 | New | 2
1011900 | #380808 | Story | Complete Peer Review and Update: 99-P57051M – NMS – NM – GSAM (EAD 18) | PI 16 | New | 2
1011899 | #380808 | Story | Complete Peer Review and Update: 99-P53198T – NMS – NM – NEDB (EAD 18) | PI 16 | New | 2
1011898 | #380808 | Story | Complete Peer Review and Update: 98-P59410M003 – NMS – NM – FCAP – F5BIG-IP – SVD (EAD 17) | PI 16 | New | 2
1011897 | #380808 | Story | Complete Peer Review and Update: 98-P55509M_Network_Router_SVD.doc (EAD 17) | PI 16 | New | 2
1011896 | #380808 | Story | Feature 380808: Complete Peer Review and Update: Cisco Switch SVD | PI 16 | New | 3
1011895 | #380808 | Story | Feature 380808: Update:NME201 (new cabinet) & Model New Server (EAD 18) | EA 15.1 | Done | 3 | #1014146
1011894 | #380808 | Story | Feature 380808: Update: NME202 (new cabinet) (EAD 18) | EA 15.2 | Done | 3 | #1014150
1011782 |  | Problem | Node Config for our LABS needs to be CleanUP’d/Trued in a lot of areas. It is leading to a lot of confusion. | Unassigned | Triage
1011718 |  | Task | Measure average WIP daily per person for each team | EA 15.2 | Done
1011717 | #1006818 | Task | Automate update of PI X Metric file | EA 14.3 | Done
1011714 | #1006817 | Task | Add Inc_all derived columns to Java implementation | Unassigned | Done
1011713 | #1006817 | Task | document Jenkins Server setup | EA 14.2 | Done
1011707 | #1006817 | Task | Deploy metrics automation to Jenkins server | EA 14.2 | Done
1011704 | #1009453 | Story | SE discover root cause and propose a solution to the DL Power Spike | EA 15.3 | Done | 2
1011684 | #342054 | Story | Create MPC for Splunk AWARE EAD-15 release | EA 14.2 | Done | 1
1011658 | #1011652 | Story | Feature 396663: JDTA Redlines Associated with PI 16/EAD 18 [Task Analysis] | EA 16.5 | New | 1
1011657 | #1011652 | Story | Feature 1011652: Release Notes/Feature Demos Sprint 16.5 [Assess Training Needs] | EA 16.5 | New | 1
1011656 | #1011652 | Story | Feature 1011652: Release Notes/Feature Demos Sprint 16.4 [Assess Training Needs] | EA 16.4 | New | 1
1011655 | #1011652 | Story | Feature 1011652: Release Notes/Feature Demos Sprint 16.3 [Assess Training Needs] | EA 16.3 | New | 1
1011654 | #1011652 | Story | Feature 1011652: Release Notes/Feature Demos Sprint 16.2 [Assess Training Needs] | EA 16.2 | New | 1
1011653 | #1011652 | Story | Feature 1011652: Release Notes/Feature Demos Sprint 16.1 [Assess Training Needs] | EA 16.1 | New | 1
1011652 | #262146 | Feature | Assess Training Needs and Plan Training for Development During PI 16 (Recurring) | EA 16.5 | Approved
1011650 | #1011652 | Task | Feature 1011652: Create CM Release Request for DRAFT Training Materials (CDRL A014) Related for EAD 15 | EA 16.1 (archived) | New
1011649 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.2 | EA 14.2 | Done | 2
1011646 | #1007536 | Task | Feature 1007536: Submit PDO for 62-P48096V 2-Factor Authentication Capabilities Specification | PI 16 | New
1011645 | #1007536 | Story | Feature 1007536: Submit PDO for Capabilities Specification | PI 16 | New | 1 | #1011646
1011644 | #1007536 | Story | Feature 1007536: Capabilities Specification Review (Developer #2) | PI 16 | New | 2 | #1011645
1011643 | #1007536 | Story | Feature 1007536: Capabilities Specification Review (Developer #1) | PI 16 | New | 2 | #1011645
1011642 | #1007536 | Story | Feature 1007536: Capabilities Specification Review (Feature Lead) | PI 16 | New | 2 | #1011645
1011641 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 19 Acronyms | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011640 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 18 Documents and Standards | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011639 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 17 Proof of Concept | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011638 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 16 Preliminary Deployment & Cutover Strategy | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011637 | #393265 | Task | Feature 393265: Create CM Release Request for DRAFT IETM (CDRL A012) Procedures Related to EAD 16 | EA 15.1 | Done
1011636 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 15 Development Phasing | PI 16 | New | 1 | #1011642 #1011643
1011635 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 14 Integration and Test Strategy | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011634 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 13 ILS Impacts | PI 16 | New | 2 | #1011642 #1011643 #1011644
1011633 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 12 IA and Cyber Strategy | EA 15.4 | New | 1 | #1011642 #1011643 #1011644
1011632 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 11 Risks | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011631 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 10 Constraints | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011630 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 9 Performance and Capacity | EA 15.1 | Done | 3 | #1011642 #1011643 #1011644
1011629 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 8 System Level Management Design Concept | EA 15.4 | Implementing | 8 | #1011642 #1011643 #1011644
1011628 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 7 Preliminary Interface Designs | PI 16 | New | 1 | #1011642 #1011643 #1011644
1011627 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 6 Initial Computing Resource Budgets and Estimate - Part 1 | EA 15.1 | Done | 3 | #1011642 #1011643 #1011644 #1017075
1011626 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 5 System Level Design Concept | EA 15.2 | Done | 5 | #1011642 #1011643 #1011644
1011624 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 4 System Level Capability Requirements | EA 15.2 | Done | 2 | #1011642 #1011643 #1011644
1011623 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 3 Operational Concept | EA 15.2 | Done | 1 | #1011642 #1011643 #1011644
1011622 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 2 Value Proposition | EA 15.2 | Done | 2 | #1011642 #1011643 #1011644
1011621 | #1007536 | Story | Feature 1007536: Define Capabilities Specification section 1 Problem Statement | EA 15.2 | Done | 1 | #1011642 #1011643 #1011644
1011620 | #1007536 | Story | Feature 1007536: Create blank Capabilities Specification template | EA 15.1 | Done | 1 | #1011626 #1011624 #1011622 #1011621 #1011638 #1011636 #1011633 #1011640 #1011639 #1011634 #1011629 #1011623 #1011632 #1011631 #1011628 #1011635 #1011641
1011619 | #1007536 | Story | Feature 1007536: Create CI for 2-Factor Authentication Capabilities Specification | EA 15.2 | Invalid | 0
1011602 | #1011426 | Story | Feature 1011426: Prepare Preventive Maintenance of SC Report | EA 16.5 (archived) | Invalid | 0
1011568 | #243502 | Story | CM Release Work for EAD 18 | PI 17 | New | 1
1011565 | #1011441 | Task | Feature 1011441: Create PDO to Release LORA via the CM Release Process | EA 16.2 | Invalid
1011563 | #1011441 | Story | Feature 1011441: Finalize and Submit Updated 2020 LORA to PMW via CM Release Process | EA 16.2 | New | 1
1011562 | #1011441 | Story | Feature 1011441: Incorporate Comments/Feedback from Internal Review of the LORA | EA 16.1 | New | 2
1011560 | #1011441 | Story | Feature 1011441: Internal Review of Updated LORA | EA 16.1 | New | 1
1011559 |  | Story | Feature 1011441: Continue LORA Updates (Part 3) | EA 15.5 | Invalid | 0
1011558 |  | Story | Feature 1011441: Continue LORA Updates (Part 2) | EA 15.4 | Invalid | 0
1011486 | #396819 | Story | Lab - Support - G. Lyon (14.1) | EA 14.1 | Done | 1
1011484 | #385856 | Story | Feature 385856: Conversion to ACC - Capability Spec Writeup for Ground System (Part 1) | EA 14.3 | Done | 2
1011483 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort (EA 14.3 - part 2 of 2) | EA 14.3 | Done | 3
1011475 |  | Problem | IETM update to RNC Health Check - Normal Operation Procedure | Unassigned | Assessing
1011472 | #395114 | Story | Feature 395114: Complete Spares Analysis for EAD 17 | EA 15.5 | New | 2
1011471 | #395174 | Story | Feature 395174: Complete Spares Analysis for EAD 16 | EA 14.5 | Done | 2
1011470 |  | Story | Feature 1011441: Begin 2020 LORA Updates | EA 15.3 | Invalid | 0
1011469 | #1011441 | Story | Feature 1011441: Incoroporates Updates Needed to the LORA Based Upon Findings and Comments from CDRL A004 | EA 15.4 | Implementing | 3
1011468 | #1011441 | Task | Feature 1011441: SME Support for LORA Updates | EA 15.3 | Done
1011467 | #1011441 | Story | Feature 1011441: Review CDRL A010 with 2019 LORA | EA 15.3 | Done | 2
1011464 | #1011441 | Task | Feature 1011441: Kickoff Meeting for the LORA 2020 Updates | EA 15.2 | Done
1011462 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.5) | EA 15.5 | Invalid | 0
1011461 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.4) | EA 15.4 | Invalid | 0
1011460 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.3) | EA 15.3 | Invalid | 0
1011459 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.2) | EA 15.2 | Invalid | 0
1011458 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.1) | EA 15.1 | Invalid | 0
1011457 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.5) | EA 15.5 | Invalid | 0
1011456 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.4) | EA 15.4 | Invalid | 0
1011455 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.3) | EA 15.3 | Invalid | 0
1011454 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.2) | EA 15.2 | Invalid | 0
1011453 | #1010889 | Story | Feature 1010889: PI 15 PWI Triage/Assessment Support (EA 15.1) | EA 15.1 | Invalid | 0
1011441 | #262146 | Feature | Annual Level of Repair Assessment (LORA): Review & Update the LORA Created and Delivered in 2019 (CDRL A010) | PI 16 - In Progress | Implementing
1011439 | #1011426 | Story | Feature 1011426: Final Oversight of Vendor Activities and Submission of Final Report for 2020 Preventive Maintenance in SC | EA 16.5 (archived) | Invalid | 0
1011438 | #1011426 | Story | Feature 1011426: Continue Oversight of Vendor Activities for 2020 Preventive Maintenance in SC (EA 16.4) | EA 16.4 (archived) | Invalid | 0
1011437 | #1011426 | Story | Feature 1011426: Continue Oversight of Vendor Activities for 2020 Preventive Maintenance in SC (EA 16.3) | EA 16.3 (archived) | Invalid | 0
1011436 | #1011426 | Story | Feature 1011426: Begin Oversight of Vendor Activities for 2020 Preventive Maintenance in SC | EA 16.2 (archived) | Invalid | 0
1011435 | #1011426 | Story | Feature 1011426: Present SOW Associated to 2020 Preventive Maintenance in SC | EA 16.1 (archived) | Invalid | 0
1011434 | #1011426 | Story | Feature 1011426: Prepare & Conduct PM Kickoff Meeting with the Vendor | EA 16.1 (archived) | Invalid | 0
1011433 | #1011426 | Story | Feature 1011426: Ship Supplies and Materials to Site for 2020 Preventive Maintenance in SC | EA 15.5 | Invalid | 0
1011432 | #1011426 | Story | Feature 1011426: Prepare, Review SOW Associated to 2020 Preventive Maintenance in SC | EA 15.4 | Invalid | 0
1011431 | #1011426 | Task | Feature 1011426: Create and Validate Plan for 2020 Preventive Maintenance Activities in SC | EA 15.3 | Invalid
1011430 | #1011426 | Task | Feature 1011426: Confirmation of Vendor, Access to Site, and Schedule of Activities for the 2020 Preventive Maintenance in SC | EA 15.3 | Invalid
1011429 | #1011426 | Story | Feature 1011426: Request Creation & Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in SC | EA 15.2 | Invalid | 0
1011428 | #1011426 | Story | Feature 1011426: Determine Corrective Actions Based Upon Trouble Tickets Received for 2020 Preventive Maintenance of SC | EA 15.3 | Invalid | 0
1011427 | #1011426 | Story | Feature 1011426: Identification of Consumables Required for 2020 Preventive Maintenance in SC | EA 15.3 | Invalid | 0
1011425 | #1011419 | Story | Feature 1011419: Update CRM Database Entries for EA 15.5 | EA 15.5 | New | 2
1011423 | #1011419 | Story | Feature 1011419: Update CRM Database Entries for EA 15.4 | EA 15.4 | Implementing | 2
1011422 | #1011419 | Story | Feature 1011419: Update CRM Database Entries for EA 15.3 | EA 15.3 | Done | 2
1011421 | #1011419 | Story | Feature 1011419: Update CRM Database Entries for EA 15.1 | EA 15.1 | Done | 2
1011420 | #1011419 | Story | Feature 1011419: Update CRM Database Entries for EA 15.2 | EA 15.2 | Done | 2
1011419 | #262146 | Feature | PI 15 Maintain CRM Database (Recurring) | EA 15.5 | Implementing
1011399 | #1011394 | Story | Feature 1011394: Finalize DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations and Capture PMW Redlines Prior to Meeting (Jun 2020) | EA 15.5 | Invalid | 0
1011398 | #1011394 | Story | Feature 1011394: ILS Support of DMSMS Tracker | EA 15.4 | Implementing | 5
1011397 | #1011394 | Story | Feature 1011394: Finalize DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations and Capture PMW Redlines Prior to Meeting (May 2020) | EA 15.3 | Invalid | 0
1011396 | #1011394 | Story | Feature 1011394: ILS Support of DMSMS Tracker | EA 15.2 | Done | 5
1011395 | #1011394 | Story | Feature 1011394: Finalize DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations and Capture PMW Redlines Prior to Meeting (Apr 2020) | EA 15.1 | Invalid | 0
1011394 | #262146 | Feature | PI 15 DMSMS Support (Recurring) | EA 15.5 | Implementing
1011381 | #377408 | Problem | Two versions of ILS Maintenance Laptop Applications — Normal Operation Procedure in the IETM | EA 14.3 | Closed
1011372 | #393265 | Problem | Update IETM Procedure " Add Domain Account to McAfee Firewall - Normal Operation Procedure" with special note and update title | EA 15.3 | Closed
1011370 | #384036 | Story | Feature 384036: Create Cisco Switch PKI Instructions | EA 14.3 | Done | 2 | #1006877
1011368 | #1015153 | Problem | Feature 1015153: Antenna Control ISO cannot be burnt with the new ILSLAPTOPS using Windows 10 - Looks like Roxio might be needed | EA 15.4 | Approved
1011356 | #1004171 | Story | Feature 1004171: Create a script to mine the logs from Feature 381608 to get a baseline of the frequency of the issue with the module acceptance of group provisioning from Central GNH | EA 14.4 | Done | 2
1011354 | #1011126 | Story | Feature 1011126: WWTS PI 15 Technical Support | EA 15.3 | Invalid | 0
1011349 | #384036 | Story | Feature 384036: Replace TBDs with IETM Procedures in Nutanix FM alarm whitelist | EA 14.2 | Done | 2
1011346 | #384036 | Story | Feature 384036 SNMP for Cisco Switch Whitelist Development | EA 14.2 | Done | 2
1011344 | #384036 | Story | Feature 384036: Sumarization of the Nutanix Alert Recovery Procedures Testing | EA 14.2 | Done | 1
1011339 | #354680 | Story | Feature 354680 (Site): IA - Initial Scan on Splunk HA loaner equipment (Part 2) | EA 14.2 | Done | 3
1011338 | #1011329 | Story | Feature 1011329: ILS Support of DMSMS Tracker | EA 16.5 | New | 5
1011337 | #1011329 | Story | Feature 1011329: ILS Support of DMSMS Tracker | EA 16.4 | New | 5
1011336 | #1011329 | Story | Feature 1011329: ILS Support of DMSMS Tracker | EA 16.3 | New | 5
1011334 | #1011329 | Story | Feature 1011329: ILS Support of DMSMS Tracker | EA 16.2 | New | 5
1011333 | #354680 | Story | Feature 354680 (Site): IA Patching and STIGs (Wrap-up) | EA 14.2 | Done | 1
1011331 | #1011329 | Story | Feature 1011329: ILS Support of DMSMS Tracker | EA 16.1 | New | 5
1011329 | #262146 | Feature | PI 16 DMSMS Support (Recurring) | PI 16 - Candidate | Approved
1011325 | #1011295 | Story | Feature 1011295: Provide Deployment Notes and Operator Impact Inputs | EA 15.5 | New | 1
1011317 | #1011295 | Story | Feature Demo - Customer Demo Event - Feature 1011295: PI 15 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) - Analysis Demo | EA 15.5 | New | 1
1011316 | #1011295 | Task | Feature 1011295: Upload Demo Documentation to GD Site for PI 15 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 15.4 | Done |  | #1011317
1011315 | #395855 | Task | Feature 395855: Create PDO to Release Parts List/Drawings Supporting EAD15 Power Upgrades in Wahiawa | EA 14.5 | Done |  | #1011316
1011314 | #1002381 | Story | Feature 1002381: Create CoCo Review for Hardware Drawings for HLR AuK | EA 15.5 | New | 2
1011313 | #1011295 | Story | Feature 1011295: Parts List Updates for EA 15.5 | EA 15.5 | Invalid | 0
1011312 | #1011295 | Story | Feature 1011295: Drawing Updates for EA 15.5 | EA 15.5 | Invalid | 0
1011311 | #1011295 | Task | Feature 1011295: Create PDO to Release Parts List/Drawings (Part 4) (EA 15.4) | EA 15.4 | Invalid |  | #1011316
1011310 | #395855 | Story | Feature 395855: Create CoCo Review for EAD15 Power Upgrades in Wahiawa | EA 14.5 | Done | 1 | #1011311
1011309 | #342163 | Story | Feature 342163: Parts List Updates for Taclane | EA 15.3 | Done | 1 | #1019376
1011308 | #1011295 | Story | Feature 1011295: Drawing Updates for EA 15.4 | EA 15.4 | Invalid | 0 | #1011310
1011307 | #1011295 | Task | Feature 1011295: Create PDO to Release Parts Alternate Parts List | EA 15.4 | Invalid |  | #1011316
1011306 | #1011295 | Story | Feature 1011295: Create CoCo Review for Alternate Parts List | EA 15.4 | Invalid | 0 | #1011307
1011305 | #395855 | Task | Feature 395855: Parts List Updates to Support EAD16 Power Upgrades in Wahiawa | EA 14.5 | Done
1011304 | #1002381 | Story | Feature 1002381: Continue Creating Redlines Drawings for OBS - HLR: HW/FRCB for HLR Deployment | EA 15.1 | Done | 2 | #1011314
1011303 | #1011295 | Task | Feature 1011295: Create PDO to Release Parts List/Drawings (Part 2) (EA 15.2) | EA 15.2 | Invalid |  | #1011316
1011302 | #377437 | Story | Feature 377437: Create CoCo Review for ETT: Update ETT Laptop - Parts List | EA 15.3 | Done | 1
1011301 | #1011295 | Story | Feature 1011295: Alternate Parts List Update | EA 15.3 | Invalid | 0
1011300 | #1011295 | Story | Feature 1011295: Analyze Drawings for GEO Removal Problem 392388 | EA 15.2 | Done | 2
1011299 | #1011295 | Task | Feature 1011295: Create PDO to Release Parts List/Drawings (Part 1) (EA 15.1) | EA 15.1 | Invalid |  | #1011316
1011298 | #1011295 | Story | Feature 1011295: Create CoCo Review for xyz Parts List/Drawings (Part 1) (EA 15.1) | EA 15.1 | Invalid | 0 | #1011299
1011297 | #1011295 | Story | Feature 1011295: Parts List Updates for EA 15.1 | EA 15.1 | Invalid | 0 | #1011298
1011296 | #1011295 | Story | Feature 1011295: Drawing Updates for EA 15.1 | EA 15.1 | Invalid | 0 | #1011298
1011295 | #262146 | Feature | PI 15 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 15.5 | Implementing
1011279 | #251622 | Feature | Depot: Laptop Efforts for EAD 15 | EA 14.3 | Done
1011277 | #353345 | Story | Feature 353345: Travel from Site to Conduct Refresher Training at WH (Trainer 1) | EA 14.2 | Done | 1
1011276 | #353345 | Story | Feature 353345: Travel from Site to Conduct Refresher Training at WH (Trainer 2) | EA 14.2 | Done | 1
1011274 | #390286 | Story | Feature 390286: Final Deployment Notes and Operator Impact Inputs for Blue Sheets EAD 16 | EA 14.3 | Invalid | 0
1011260 | #384036 | Story | Feature 384036: Test Nutanix Power Supply Failure Alert Recovery Procedure | EA 14.2 | Done | 1
1011259 | #384036 | Story | Feature 384036: Test Nutanix Node Failure Alert Recovery Procedure | EA 14.2 | Done | 1
1011258 | #384036 | Story | Feature 384036: Test Nutanix High Disk Space Utilization Alert Recovery Procedure | EA 14.2 | Done | 2
1011257 | #384036 | Story | Feature 384036: Test Nutanix Disk Removal Alert Recovery Procedure | EA 14.2 | Done | 1
1011256 | #384036 | Story | Feature 384036: Test Nutanix Disk Failure Alert Recovery Procedure | EA 14.2 | Done | 2
1011249 | #1011150 | Story | Feature 1011150: WWTS Waveform Analysis and Issue Support (1) | EA 15.1 | Done | 1
1011248 | #1011150 | Story | Feature 1011150: WWTS Waveform Analysis and Issue Support (2) | EA 15.2 | Done | 1
1011247 | #1011150 | Story | Feature 1011150: WWTS Waveform Analysis and Issue Support (3) | EA 15.3 | Done | 1
1011246 | #1011150 | Story | Feature 1011150: WWTS Waveform Analysis and Issue Support (4) | EA 15.4 | Implementing | 1
1011245 | #1011150 | Story | Feature 1011150: WWTS Waveform Analysis and Issue Support (5) | EA 15.5 | New | 1
1011244 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.1 | Invalid | 0
1011243 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.2 | Invalid | 0
1011242 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.3 | Done | 1
1011241 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.4 | Implementing | 1
1011240 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.5 | Implementing | 1
1011239 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.1 | Done | 1
1011238 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.3 | Invalid | 0
1011237 | #1011150 | Story | Feature 1011150: WWTS Trouble Ticket Support | EA 15.5 | New | 1
1011236 | #1011150 | Story | Feature 1011150: WWTS front-end CRM TT support (Bob) 15.1 | EA 15.1 | Invalid | 0
1011235 | #1011150 | Story | Feature 1011150: WWTS front-end CRM TT support (Bob) 15.2 | EA 15.2 | Invalid | 0
1011234 | #1011150 | Story | Feature 1011150: WWTS front-end CRM TT support (Bob) 15.3 | EA 15.3 | Invalid | 0
1011233 | #1011150 | Story | Feature 1011150: WWTS front-end CRM TT support (Bob) 15.4 | EA 15.4 | Invalid | 0
1011232 | #1011150 | Story | Feature 1011150: WWTS front-end CRM TT support (Bob) 15.5 | EA 15.5 | Invalid | 0
1011231 | #1011150 | Story | Feature 1011150: TOFF LOE - FRB Support - EA 15.1 | EA 15.1 | Done | 2
1011230 | #1011150 | Story | Feature 1011150: TOFF LOE - FRB Support - EA 15.2 | EA 15.2 | Done | 2
1011229 | #1011150 | Story | Feature 1011150: TOFF LOE - FRB Support - EA 15.3 | EA 15.3 | Done | 1
1011228 | #1011150 | Story | Feature 1011150: TOFF LOE - FRB Support - EA 15.4 | EA 15.4 | Implementing | 1
1011227 | #1011150 | Story | Feature 1011150: TOFF LOE - FRB Support - EA 15.5 | EA 15.5 | New | 1
1011226 | #1011150 | Story | Feature 1011150: TOFF LOE - MPC Support - EA 15.1 | EA 15.1 | Done | 1
1011225 | #1011150 | Story | Feature 1011150: TOFF LOE - MPC Support - EA 15.2 | EA 15.2 | Done | 2
1011224 | #1011150 | Story | Feature 1011150: TOFF LOE - MPC Support - EA 15.3 | EA 15.3 | Done | 1
1011223 | #1011150 | Story | Feature 1011150: TOFF LOE - MPC Support - EA 15.4 | EA 15.4 | Implementing | 1
1011222 | #1011150 | Story | Feature 1011150: TOFF LOE - MPC Support - EA 15.5 | EA 15.5 | New | 1
1011221 | #1011150 | Story | Feature 1011150: TOFF LOE - Site Support and PWI generation - EA 15.1 | EA 15.1 | Done | 1
1011220 | #1011150 | Story | Feature 1011150: TOFF LOE - Site Support and PWI generation - EA 15.2 | EA 15.2 | Done | 1
1011219 | #1011150 | Story | Feature 1011150: TOFF LOE - Site Support and PWI generation - EA 15.3 | EA 15.3 | Done | 1
1011218 | #1011150 | Story | Feature 1011150: TOFF LOE - Site Support and PWI generation - EA 15.4 | EA 15.4 | Implementing | 1
1011217 | #1011150 | Story | Feature 1011150: TOFF LOE - Site Support and PWI generation - EA 15.5 | EA 15.5 | New | 1
1011216 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | Done | 3
1011215 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.2 | EA 15.2 | Done | 3
1011214 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Done | 1
1011213 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.4 | EA 15.4 | Implementing | 3
1011212 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.5 | EA 15.5 | New | 1
1011211 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.1 | EA 15.1 | Done | 3
1011210 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.2 | EA 15.2 | Done | 2
1011209 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.3 | EA 15.3 | Done | 1
1011208 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.4 | EA 15.4 | Implementing | 1
1011207 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.5 | EA 15.5 | New | 2
1011206 | #1011150 | Task | Feature 1011150: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | New
1011205 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.2 | EA 15.2 | Done | 1
1011204 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1011203 | #1011150 | Task | Feature 1011150: TOFF LOE - TT Support - EA 15.4 | EA 15.4 | New
1011202 | #1011150 | Story | Feature 1011150: TOFF LOE - TT Support - EA 15.5 | EA 15.5 | New | 2
1011201 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.1 | EA 15.1 | Done | 1
1011200 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.2 | EA 15.2 | Done | 1
1011199 | #1011150 | Story | Feature 1011150: TOFF LOE TT Support - EA 15.3 | EA 15.3 | Done | 1
1011198 | #1011150 | Task | Feature 1011150: TOFF LOE TT Support - EA 15.4 | EA 15.4 | New
1011197 | #1011150 | Task | Feature 1011150: TOFF LOE TT Support - EA 15.5 | EA 15.5 | New
1011196 | #1011150 | Story | Feature 1011150: TOFF front-end CRM TT support (Sally) 15.3 | EA 15.3 | Invalid | 0
1011195 | #1011150 | Story | Feature 1011150: TOFF front-end CRM TT support (Sally) 15.5 | EA 15.5 | Invalid | 0
1011194 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.1 | EA 15.1 | Done | 1
1011193 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.1 | EA 15.1 | Done | 2
1011192 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1011191 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.3 | EA 15.3 | Done | 2
1011190 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.4 | EA 15.4 | Implementing | 2
1011189 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.5 | EA 15.5 | New | 1
1011188 | #1011150 | Story | Feature 1011150: PI 15 SA TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1011187 | #1011150 | Story | Feature 1011150: Laptops Trouble Ticket Support - 15.1 | EA 15.1 | Done | 1
1011186 | #1011150 | Story | Feature 1011150: Laptops Trouble Ticket Support - 15.2 | EA 15.2 | Done | 1
1011185 | #1011150 | Story | Feature 1011150: Laptops Trouble Ticket Support - 15.3 | EA 15.3 | Done | 1
1011184 | #1011150 | Story | Feature 1011150: Laptops Trouble Ticket Support - 15.4 | EA 15.4 | New | 1
1011183 | #1011150 | Story | Feature 1011150: Laptops Trouble Ticket Support - 15.5 | EA 15.5 | New | 1
1011182 | #1011150 | Story | Feature 1011150: Okapi Trouble Ticket Support - 15.1 | EA 15.1 | Done | 1
1011181 | #1011150 | Story | Feature 1011150: Okapi Trouble Ticket Support - 15.2 | EA 15.2 | Done | 1
1011180 | #1011150 | Story | Feature 1011150: Okapi Trouble Ticket Support - 15.3 | EA 15.3 | Done | 1
1011179 | #1011150 | Story | Feature 1011150: Okapi Trouble Ticket Support - 15.4 | EA 15.4 | New | 1
1011178 | #1011150 | Story | Feature 1011150: MAGIC TT Support - EA 15.1 | EA 15.1 | Done | 2
1011177 | #1011150 | Story | Feature 1011150: MAGIC TT Support - EA 15.2 (Anil) | EA 15.2 | Done | 2
1011176 | #1011150 | Story | Feature 1011150: MAGIC TT Support - EA 15.3 | EA 15.3 | Done | 2
1011175 | #1011150 | Story | Feature 1011150: MAGIC TT Support - EA 15.4 | EA 15.4 | New | 2
1011174 | #1011150 | Story | Feature 1011150: MAGIC TT Support - EA 15.5 | EA 15.5 | New | 2
1011173 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.1 | EA 15.1 | Done | 2
1011172 | #1011150 | Story | Feature 1011150: Labradors TT Support - EA 15.2 | EA 15.2 | Done | 2
1011171 | #1011150 | Story | Feature 1011150: Alicorn Trouble Ticket Support - 15.1 | EA 15.1 | Done | 1
1011170 | #1011150 | Story | Feature 1011150: Alicorn Trouble Ticket Support - 15.2 | EA 15.2 | Done | 1
1011169 | #1011150 | Story | Feature 1011150: Alicorn Trouble Ticket Support - 15.3 | EA 15.3 | Done | 1
1011168 | #1011150 | Story | Feature 1011150: Alicorn Trouble Ticket Support - 15.4 | EA 15.4 | Implementing | 1
1011166 | #395871 | Story | Feature 395871: Labradors - Evaluation of severity/probability for ET recovery procedures - EA 14.2 | EA 14.2 | Done | 1
1011165 | #1011001 | Story | Firewall Health Check and capture metrics - EA 15.5 | EA 15.5 | Invalid | 0
1011164 | #1011001 | Task | TFDU Health Check and Report incidents - EA 15.5 | EA 15.5 | Invalid
1011163 | #1011001 | Story | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics- EA 15.5 | EA 15.5 | Invalid | 0
1011162 | #1011001 | Story | Firewall Health Check and capture metrics - EA 15.3 | EA 15.3 | Invalid | 0
1011161 | #1011001 | Task | TFDU Health Check and Report incidents - EA 15.4 | EA 15.4 | Invalid
1011160 | #1011001 | Story | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics - EA 15.4 | EA 15.4 | Invalid | 0
1011159 | #1011001 | Task | TFDU Health Check and Report incidents - EA 15.3 | EA 15.3 | Invalid
1011158 | #1011001 | Task | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics - EA 15.3 | EA 15.3 | Invalid
1011157 | #1011001 | Story | Firewall Health Check and capture metrics - EA 15.2 | EA 15.2 | Invalid | 0
1011156 | #1011001 | Task | TFDU Health Check and Report incidents - EA 15.2 | EA 15.2 | Invalid
1011155 | #1011001 | Story | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics - EA 15.2 | EA 15.2 | Invalid | 0
1011154 | #1011001 | Story | Firewall Health Check and capture metrics - EA 15.1 | EA 15.1 | Invalid | 0
1011153 | #1011001 | Task | TFDU Health Check and Report incidents - EA 15.1 | EA 15.1 | Invalid
1011152 | #1011001 | Task | Feature #1011001: Weekly RAN Ground Health Check and Incident Capture for MUOS System Metrics - EA 15.1 | EA 15.1 | Invalid
1011150 | #245568 | Feature | TT support; ID, report, prioritize, and resolve incidents (recurring) - PI 15 | EA 15.5 | Implementing
1011148 | #1011126 | Story | Feature 1011126: WWTS PI 15 Technical Support | EA 15.1 | Invalid | 0
1011147 | #1011126 | Story | Feature 1011126: WWTS PI 15 Technical Support | EA 15.2 | Invalid | 0
1011146 | #1011126 | Story | Feature 1011126: WWTS PI 15 Technical Support | EA 15.4 | Invalid | 0
1011145 | #1011126 | Story | Feature 1011126: WWTS PI 15 Technical Support | EA 15.5 | Invalid | 0
1011144 | #1011126 | Story | Feature 1011126: TOFF PI 15 Technical Support - EA 15.1 | EA 15.1 | Invalid | 0
1011143 | #1011126 | Story | Feature 1011126: TOFF PI 15 Technical Support - EA 15.2 | EA 15.2 | Invalid | 0
1011142 | #1011126 | Story | Feature 1011126: TOFF PI 15 Technical Support - EA 15.3 | EA 15.3 | Invalid | 0
1011141 | #1011126 | Story | Feature 1011126: TOFF PI 15 Technical Support - EA 15.4 | EA 15.4 | Invalid | 0
1011140 | #1011126 | Story | Feature 1011126: TOFF PI 15 Technical Support - EA 15.5 | EA 15.5 | Invalid | 0
1011139 | #1011126 | Story | Feature 1011126: SIC PI 15 Technical Support - EA 15.1 | EA 15.1 | Invalid | 0
1011138 | #1011126 | Story | Feature 1011126: SIC PI 15 Technical Support - EA 15.2 | EA 15.2 | Invalid | 0
1011137 | #1011126 | Story | Feature 1011126: SIC PI 15 Technical Support - EA 15.3 | EA 15.3 | Invalid | 0
1011136 | #1011126 | Story | Feature 1011126: SIC PI 15 Technical Support - EA 15.4 | EA 15.4 | Invalid | 0
1011135 | #1011126 | Story | Feature 1011126: SIC PI 15 Technical Support - EA 15.5 | EA 15.5 | Invalid | 0
1011134 | #1011126 | Story | Feature 1011126: MAGIC PI 15 Technical Support - EA 15.1 | EA 15.1 | Invalid | 0
1011133 | #1011126 | Story | Feature 1011126: MAGIC PI 15 Technical Support - EA 15.2 | Unassigned | Invalid | 0
1011132 | #1011126 | Story | Feature 1011126: MAGIC PI 15 Technical Support - EA 15.3 | EA 15.3 | Invalid | 0
1011131 | #1011126 | Story | Feature 1011126: MAGIC PI 15 Technical Support - EA 15.4 | EA 15.4 | Invalid | 0
1011130 | #1011126 | Story | Feature 1011126: MAGIC PI 15 Technical Support - EA 15.5 | EA 15.5 | Invalid | 0
1011129 | #1013136 | Problem | Vendor: Asnas unjoins a group without telling the Red side. Reboot required. | EA 16.1 | Implementing
1011126 | #243395 | Feature | PI 15 Technical Support (Recurring) | EA 15.5 | Rejected
1011125 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.1 | Done | 1
1011124 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.2 | Done | 1
1011123 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.3 | Done | 1
1011122 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.5 | Implementing | 1
1011121 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.4 | Implementing | 1
1011120 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.1 | Done | 1
1011119 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.2 | Done | 1
1011118 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.3 | Done | 1
1011117 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.4 | Implementing | 1
1011116 | #1011070 | Story | Feature 1011070: WWTS PWI Triage/Assessment Support | EA 15.5 | New | 1
1011115 | #1011070 | Story | Feature 1011070: TOFF PWI triage/assessment support 15.1 | EA 15.1 | Done | 1
1011114 | #1011070 | Story | Feature 1011070: TOFF PWI triage/assessment support 15.2 | EA 15.2 | Done | 1
1011113 | #1011070 | Story | Feature 1011070: TOFF PWI triage/assessment support 15.3 | EA 15.3 | Done | 1
1011112 | #1011070 | Story | Feature 1011070: TOFF PWI triage/assessment support 15.4 | EA 15.4 | Implementing | 1
1011111 | #1011070 | Story | Feature 1011070: TOFF PWI triage/assessment support 15.5 | EA 15.5 | New | 1
1011110 | #1011070 | Story | Feature 1011070: CSE PWI Triage/Assessment Support | EA 15.1 | Done | 1
1011109 | #1011070 | Story | Feature 1011070: CSE PWI Triage/Assessment Support | EA 15.2 | Done | 1
1011108 | #1011070 | Story | Feature 1011070: CSE PWI Triage/Assessment Support | EA 15.3 | Done | 1
1011107 | #1011070 | Story | Feature 1011070: CSE PWI Triage/Assessment Support | EA 15.3 | Done | 1
1011106 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.1 | EA 15.1 | Done | 2
1011105 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.2 | EA 15.2 | Done | 2
1011104 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.3 | EA 15.3 | Done | 2
1011103 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.4 | EA 15.4 | Done | 2
1011102 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.5 | EA 15.5 | New | 1
1011101 | #1011070 | Story | Feature 1011070: SA PWI Support - EA 15.1 | EA 15.1 | Done | 5
1011100 | #1011070 | Story | Feature 1011070: Okapi PWI Triage/Assessment Support EA 15.1 | EA 15.1 | Done | 1
1011099 | #1011070 | Story | Feature 1011070: Okapi PWI Triage/Assessment Support EA 15.2 | EA 15.2 | Done | 1
1011098 | #1011070 | Story | Feature 1011070: Okapi PWI Triage/Assessment Support EA 15.3 | EA 15.3 | Done | 1
1011097 | #1011070 | Story | Feature 1011070: Okapi PWI Triage/Assessment Support EA 15.4 | EA 15.4 | New | 1
1011096 | #1011070 | Story | Feature 1011070: Octopi PWI Triage/Assessment Support EA 15.1 | EA 15.1 | Done | 1
1011095 | #1011070 | Story | Feature 1011070: Octopi PWI Triage/Assessment Support EA 15.2 | EA 15.2 | Done | 1
1011094 | #1011070 | Story | Feature 1011070: Octopi PWI Triage/Assessment Support EA 15.3 | EA 15.3 | Done | 1
1011093 | #1011070 | Story | Feature 1011070: Octopi PWI Triage/Assessment Support EA 15.4 | EA 15.4 | Implementing | 1
1011092 | #1011070 | Story | Feature 1011070: Octopi PWI Triage/Assessment Support EA 15.5 | EA 15.5 | New | 1
1011091 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.1 | EA 15.1 | Done | 2
1011090 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.2 (Anil) | EA 15.2 | Done | 1
1011089 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.3 | EA 15.3 | Done | 2
1011088 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.4 | EA 15.4 | New | 2
1011087 | #1011070 | Story | Feature 1011070: MAGIC PWI Triage/Assessment Support - EA 15.5 | EA 15.5 | New | 2
1011086 | #1011070 | Story | Feature 1011070: Falcons PWI Triage/Assessment Support EA 15.1 | EA 15.1 | Done | 1
1011085 | #1011070 | Story | Feature 1011070: Falcons PWI Triage/Assessment Support EA 15.2 | EA 15.2 | Done | 1
1011084 | #1011070 | Story | Feature 1011070: Falcons PWI Triage/Assessment Support EA 15.3 | EA 15.3 | Done | 1
1011083 | #1011070 | Story | Feature 1011070: Falcons PWI Triage/Assessment Support EA 15.4 | EA 15.4 | Implementing | 1
1011082 | #1011070 | Story | Feature 1011070: Falcons PWI Triage/Assessment Support EA 15.5 | EA 15.5 | New | 1
1011081 | #1011070 | Story | Feature 1011070: Cyber PWI Triage/Assessment Support - 15.1 | EA 15.1 | Done | 1
1011080 | #1011070 | Story | Feature 1011070: Cyber PWI Triage/Assessment Support - 15.2 | EA 15.2 | Done | 1
1011079 | #1011070 | Story | Feature 1011070: Cyber PWI Triage/Assessment Support - 15.3 | EA 15.3 | Done | 1
1011078 | #1011070 | Story | Feature 1011070: Cyber PWI Triage/Assessment Support - 15.4 | EA 15.4 | Implementing | 1
1011077 | #1011070 | Story | Feature 1011070: Cyber PWI Triage/Assessment Support - 15.5 | EA 15.5 | New | 1
1011076 | #1011070 | Story | Feature 1011070: PWI Triage/Assessment Support EA 15.1 (LOE) | EA 15.1 | Done | 1
1011075 | #1011070 | Story | Feature 1011070: PWI Triage/Assessment Support EA 15.2 (LOE) | EA 15.2 | Done | 1
1011074 | #1011070 | Story | Feature 1011070: PWI Triage/Assessment Support EA 15.3 (LOE) | EA 15.3 | Done | 1
1011073 | #1011070 | Story | Feature 1011070: PWI Triage/Assessment Support EA 15.4 (LOE) | EA 15.4 | Implementing | 1
1011070 | #243395 | Feature | PWI triage and assessment support (recurring) - PI 15 | EA 15.5 | Implementing
1011057 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid
1011056 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1011055 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1011049 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.2 | EA 14.2 | Done | 3
1011023 | #388076 | Story | Feature 388076: Do PWI work for Problem 347180 | EA 14.2 | Done | 2
1011022 | #342054 | Story | Feature 342054: WH alignment MPC work | EA 14.2 | Done | 3
1011010 | #388076 | Story | Feature 388076: Do PWI work for Problem 345802 | EA 14.2 | Done | 2
1011001 | #245568 | Feature | Identify and communicate top issues (recurring) - PI 15 | EA 15.5 | Implementing
1010997 | #1010895 | Story | Feature 1010895: TOFF front-end CRM TT support (Sally) 15.5 | EA 15.5 | Invalid | 0
1010996 | #1010895 | Story | Feature 1010895: Laptops Trouble Ticket Support - 15.5 | EA 15.5 | Invalid | 0
1010995 | #1010895 | Story | Feature 1010895: WWTS Waveform Analysis and Issue Support (5) | EA 15.5 | Invalid | 0
1010994 | #1010895 | Task | Feature 1010895: TOFF LOE TT Support - EA 15.5 | EA 15.5 | Invalid
1010993 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010992 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010991 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.5 | Invalid | 0
1010990 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.5 | Invalid | 0
1010989 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010988 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010987 | #1010895 | Story | Feature 1010895: WWTS front-end CRM TT support (Bob) 15.5 | EA 15.5 | Invalid | 0
1010986 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010985 | #1010895 | Story | Feature 1010895: TOFF LOE - Site Support and PWI generation - EA 15.5 | EA 15.5 | Invalid | 0
1010984 | #1010895 | Story | Feature 1010895: TOFF LOE - MPC Support - EA 15.5 | EA 15.5 | Invalid | 0
1010983 | #1010895 | Story | Feature 1010895: TOFF LOE - FRB Support - EA 15.5 | EA 15.5 | Invalid | 0
1010982 | #1010895 | Story | Feature 1010895: MAGIC TT Support - EA 15.5 | EA 15.5 | Invalid | 0
1010981 | #1010895 | Story | Feature 1010895: Trouble Ticket Support - 15.4 | EA 15.4 | Invalid | 0
1010980 | #1010895 | Story | Feature 1010895: WWTS Waveform Analysis and Issue Support (4) | EA 15.4 | Invalid | 0
1010979 | #1010895 | Task | Feature 1010895: TOFF LOE TT Support - EA 15.4 | EA 15.4 | Invalid
1010978 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010977 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010976 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.4 | Invalid | 0
1010975 | #1010895 | Story | Feature 1010895: Laptops Trouble Ticket Support - 15.4 | EA 15.4 | Invalid | 0
1010974 | #1010895 | Story | Feature 1010895: Okapi Trouble Ticket Support - 15.4 | EA 15.4 | Invalid | 0
1010973 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010972 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010971 | #1010895 | Story | Feature 1010895: WWTS front-end CRM TT support (Bob) 15.4 | EA 15.4 | Invalid | 0
1010970 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010969 | #1010895 | Story | Feature 1010895: TOFF LOE - Site Support and PWI generation - EA 15.4 | EA 15.4 | Invalid | 0
1010968 | #1010895 | Story | Feature 1010895: TOFF LOE - MPC Support - EA 15.4 | EA 15.4 | Invalid | 0
1010967 | #1010895 | Story | Feature 1010895: TOFF LOE - FRB Support - EA 15.4 | EA 15.4 | Invalid | 0
1010966 | #1010895 | Story | Feature 1010895: MAGIC TT Support - EA 15.4 | EA 15.4 | Invalid | 0
1010965 | #1010895 | Story | Feature 1010895: TOFF front-end CRM TT support (Sally) 15.3 | EA 15.3 | Invalid | 0
1010964 | #1010895 | Story | Feature 1010895: Trouble Ticket Support - 15.3 | EA 15.3 | Invalid | 0
1010963 | #1010895 | Story | Feature 1010895: WWTS Waveform Analysis and Issue Support (3) | EA 15.3 | Invalid | 0
1010962 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010961 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010960 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010959 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.3 | Invalid | 0
1010958 | #1010895 | Story | Feature 1010895: Laptops Trouble Ticket Support - 15.3 | EA 15.3 | Invalid | 0
1010957 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.3 | Invalid | 0
1010956 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010955 | #1010895 | Story | Feature 1010895: Okapi Trouble Ticket Support - 15.3 | EA 15.3 | Invalid | 0
1010954 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010953 | #1010895 | Story | Feature 1010895: WWTS front-end CRM TT support (Bob) 15.3 | EA 15.3 | Invalid | 0
1010952 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010951 | #1010895 | Story | Feature 1010895: TOFF LOE - Site Support and PWI generation - EA 15.3 | EA 15.3 | Invalid | 0
1010950 | #1010895 | Story | Feature 1010895: TOFF LOE - MPC Support - EA 15.3 | EA 15.3 | Invalid | 0
1010949 | #1010895 | Story | Feature 1010895: TOFF LOE - FRB Support - EA 15.3 | EA 15.3 | Invalid | 0
1010948 | #1010895 | Story | Feature 1010895: MAGIC TT Support - EA 15.3 | EA 15.3 | Invalid | 0
1010947 | #1010895 | Story | Feature 1010895: Trouble Ticket Support - 15.2 | EA 15.2 | Invalid | 0
1010946 | #1010895 | Story | Feature 1010895: WWTS Waveform Analysis and Issue Support (2) | EA 15.2 | Invalid | 0
1010945 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010944 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010943 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010942 | #1010895 | Story | Feature 1010895: Labradors TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010941 | #1010895 | Story | Feature 1010895: Laptops Trouble Ticket Support - 15.2 | EA 15.2 | Invalid | 0
1010940 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010939 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010938 | #1010895 | Story | Feature 1010895: Okapi Trouble Ticket Support - 15.2 | EA 15.2 | Invalid | 0
1010937 | #1010895 | Story | Feature 1010895: WWTS front-end CRM TT support (Bob) 15.2 | EA 15.2 | Invalid | 0
1010936 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.2 | EA 15.2 | Invalid | 0
1010935 | #1010895 | Story | Feature 1010895: TOFF LOE - Site Support and PWI generation - EA 15.2 | EA 15.2 | Invalid | 0
1010934 | #1010895 | Story | Feature 1010895: TOFF LOE - MPC Support - EA 15.2 | EA 15.2 | Invalid | 0
1010933 | #1010895 | Story | Feature 1010895: TOFF LOE - FRB Support - EA 15.2 | EA 15.2 | Invalid | 0
1010932 | #1010895 | Story | Feature 1010895: MAGIC TT Support - EA 15.2 | Unassigned | Invalid | 0
1010931 | #1010895 | Story | Feature 1010895: WWTS Waveform Analysis and Issue Support (1) | EA 15.1 | Invalid | 0
1010930 | #1010895 | Story | Feature 1010895: WWTS Trouble Ticket Support | EA 15.1 | Invalid | 0
1010929 | #1010895 | Story | Feature 1010895: WWTS front-end CRM TT support (Bob) 15.1 | EA 15.1 | Invalid | 0
1010928 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010927 | #1010895 | Story | Feature 1010895: TOFF LOE TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010926 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010925 | #1010895 | Story | Feature 1010895: TOFF LOE - TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010924 | #1010895 | Story | Feature 1010895: TOFF LOE - Site Support and PWI generation - EA 15.1 | EA 15.1 | Invalid | 0
1010923 | #1010895 | Story | Feature 1010895: TOFF LOE - MPC Support - EA 15.1 | EA 15.1 | Invalid | 0
1010922 | #1010895 | Story | Feature 1010895: TOFF LOE - FRB Support - EA 15.1 | EA 15.1 | Invalid | 0
1010921 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010920 | #1010895 | Story | Feature 1010895: SA TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010919 | #1010895 | Story | Feature 1010895: Okapi Trouble Ticket Support - 15.1 | EA 15.1 | Invalid | 0
1010918 | #1010895 | Story | Feature 1010895: MAGIC TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010917 | #1010895 | Story | Feature 1010895: Laptops Trouble Ticket Support - 15.1 | EA 15.1 | Invalid | 0
1010916 | #1010895 | Story | Feature 1010895: Labradors TT Support - EA 15.1 | EA 15.1 | Invalid | 0
1010913 | #1013136 | Problem | Vendor: Mobility during Configuring state where routing area changes causes waveform to hang. | EA 16.1 | Close Pending
1010907 | #342054 | Problem | AWARE: AMP incorrectly calls out 90-day expiration period | PI 16 | Implementing
1010897 | #388076 | Story | Feature 388076: Do PWI work for Problem 345718 | EA 14.2 | Done | 3
1010896 | #386935 | Story | Feature 386935: IETM Updates and Integration Support for MUOS Geolocation Support, Maintenance Zeta EAD 15 | EA 14.2 | Done | 1
1010895 |  | Feature | ***Rejected Duplicate***Identify, Report, Prioritize, Support Incidents & Trouble Tickets (Recurring) | PI 15 | Rejected
1010889 |  | Feature | ***Rejected Duplicate*** PWI Triage/Assessment Support (Recurring) | Unassigned | Rejected
1010887 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.2 | Done | 2
1010885 | #354646 | Story | MUOS Terminal Trade | EA 14.3 | Done | 3
1010883 | #1005740 | Story | Lead DSN GW Obs work | EA 14.1 | Done | 1
1010882 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis | EA 14.2 | Done | 1
1010881 | #387448 | Story | Update P2P Communication Call Flows | EA 14.2 | Invalid | 0
1010880 | #377437 | Story | Investigate the build process for Simulation Framework and perform a test build if possible | EA 14.2 | Done | 2
1010879 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support | EA 14.1 | Done | 1
1010854 |  | Problem | RBS reporting incorrect power measurements to RNC when measured power outside table lookup | Unassigned | Assessing
1010790 | #1007536 | Story | Feature 1007536: CONOPS Review (Developer #2) | PI 16 | New | 2
1010789 | #1007536 | Story | Feature 1007536: CONOPS Review (Developer #1) | PI 16 | New | 2
1010788 | #1007536 | Story | Feature 1007536: CONOPS Review (Feature Lead) | PI 16 | New | 2
1010785 | #1007536 | Story | Feature 1007536: Define CONOPS section 11 Glossary | PI 16 | New | 1 | #1010788 #1010789 #1010790
1010784 | #1007536 | Story | Feature 1007536: Define CONOPS section 10 Appendices | PI 16 | New | 1 | #1010788 #1010789 #1010790
1010783 | #1007536 | Story | Feature 1007536: Define CONOPS section 9 Notes | PI 16 | New | 1 | #1010788 #1010789 #1010790
1010782 | #1007536 | Story | Feature 1007536: Define CONOPS section 8 Analysis of the proposed system | PI 16 | New | 2 | #1010788 #1010789 #1010790
1010781 | #1007536 | Story | Feature 1007536: Define CONOPS section 7 Summary of impacts | PI 16 | New | 2 | #1010788 #1010789 #1010790
1010770 | #342054 | Problem | AWARE: AHM_0003 Alarm being incorrectly cleared by AHM_0004 | PI 16 | Implementing
1010769 | #377437 | Story | Feature 377437 ETT: Update ETT Laptop - Parts List | EA 15.3 | Done | 1 | #1011302
1010749 | #1007536 | Story | Feature 1007536: Draft Operational Scenarios for CONOPS section 6 Operational scenarios | EA 15.1 | Done | 3 | #1018018
1010747 | #1007536 | Story | Feature 1007536: Define CONOPS section 5 Concepts for the proposed system | EA 15.3 | Done | 5 | #1010788 #1010789 #1010790
1010736 | #1007536 | Story | Feature 1007536: Define CONOPS section 4 Justification for and nature of changes | PI 16 | New | 5 | #1010788 #1010789 #1010790
1010733 | #1007536 | Story | Feature 1007536: Define CONOPS section 3 Current system or situation | EA 15.3 | Done | 5 | #1010788 #1010789 #1010790
1010727 | #1007536 | Story | Feature 1007536: Define CONOPS section 2 Referenced documents | PI 16 | New | 1 | #1010788 #1010789 #1010790
1010726 | #1007536 | Story | Feature 1007536: Define CONOPS section 1 Scope | EA 15.3 | Done | 2 | #1010788 #1010789 #1010790
1010718 | #1007536 | Story | Feature 1007536: Create blank CONOPS Appendix template for Capability Specification | EA 15.1 | Done | 1 | #1010727 #1010726 #1010733 #1010783 #1010736 #1010749 #1010747 #1010781 #1010784 #1010785
1010713 | #377437 | Story | Feature 377437: Update Account Maintenance Plan (EAD 17) | EA 14.5 | Done | 3
1010710 | #390286 | Task | Feature 390286: Cyber Blue Sheets: Coordinate incorporation of changes to AMP with Laptop team. | EA 14.1 | Done
1010708 | #389549 | Story | Support PPA | EA 14.2 | Done | 1
1010706 | #378000 | Task | Feature 378000: Fix Errors in AWARE Alarm Recovery Procedures | EA 14.1 | Done
1010696 | #343918 | Task | Story 343918: CM Release of PL01-P52843E001 – ILS – RAF Install SC (EAD-15 OOC - Remove AWARE-ERS from EAD-15) | EA 14.2 | Done
1010670 | #1007383 | Task | Resolve createView.pl issues | EA 14.2 | Done
1010663 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom G (14.2) | EA 14.2 | Done | 2
1010659 | #1010653 | Story | Feature 1010653: JDTA Redlines Associated with PI 15/EAD 17 [Task Analysis] | EA 15.5 | New | 1
1010658 | #1010653 | Story | Feature 1010653: Release Notes/Feature Demos Sprint EA 15.5 [Assess Training Needs] | EA 15.5 | New | 1
1010657 | #1010653 | Story | Feature 1010653: Release Notes/Feature Demos Sprint EA 15.4 [Assess Training Needs] | EA 15.4 | Implementing | 2
1010656 | #1010653 | Story | Feature 1010653: Release Notes/Feature Demos Sprint EA 15.3 [Assess Training Needs] | EA 15.3 | Done | 1
1010655 | #1010653 | Story | Feature 1010653: Release Notes/Feature Demos Sprint EA 15.2 [Assess Training Needs] | EA 15.2 | Done | 1
1010654 | #1010653 | Story | Feature 1010653: Release Notes/Feature Demos Sprint EA 15.1 [Assess Training Needs] | EA 15.1 | Done | 1
1010653 | #262146 | Feature | Assess Training Needs and Plan Training for Development During PI 15 (Recurring) | EA 15.5 | Implementing
1010640 | #343920 | Task | Story 343920: CM Release of 99-P48085V IDP (Installation Design Plan) for Wahiawa Power Updates (EAD 16) | PI 14 - In Progress | Done
1010639 | #343920 | Task | Story 343920: CM Release of 99-P48086V BESEP (Base Electronic System Engineering Plan) for Wahiawa Power Updates (EAD 16) | PI 14 - In Progress | Done
1010634 | #393265 | Story | Feature 393265: Provide Deployment Notes and Operator Impact Inputs | EA 15.4 | Implementing | 1
1010633 |  | Task | Feature 393265: Upload Demo Documentation and Demo Status Workbook for Analysis Demo of the Coordinate and Complete Non-Feature IETM Content for EAD 17 (Analysis Demo) | EA 15.4 | Invalid
1010632 | #393265 | Story | Feature 393265: IETM Admin Updates (EA 15.4) | EA 15.4 | Invalid | 0
1010631 | #393265 | Story | Feature 393265: IETM Admin Updates (EA 15.3) | EA 15.3 | Done | 1
1010630 | #393265 | Story | Feature 393265: IETM Admin Updates (EA 15.2) | EA 15.2 | Done | 1
1010629 | #393265 | Story | Feature 393265: IETM Admin Updates (EA 15.1) | EA 15.1 | Done | 3
1010517 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59852M MUOS_IG_GS_NMS_NM_OS_WindowsServer2012_SVD | PI 16 | New
1010516 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59401M NMS-NM-Common-TSM | PI 16 | New
1010515 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59430M MUOS_IG_GS_NMS_NM_Common_SANSwitch_SVD | PI 16 | New
1010514 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59436M MUOS_IG_GS_NMS_NM_Common_RAIDArray_SVD | PI 16 | New
1010513 |  | Task | Story 1011568: CM Release of 98-P54107T GS GEO: MUOS_IG_GS_GEO_SVD (Invalid) | Unassigned | Invalid
1010512 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59813M MUOS_IG_GS_NMS_NM_Common_Tectia_SVD | PI 16 | New
1010511 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P55464M MUOS_IG_GS_Network_LB_SVD | PI 16 | New
1010510 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P55509M – Network – Router – SVD | PI 16 | New
1010509 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59860M MUOS_IG_GS_NMS_NM_OS_Win10Workstation_SVD | PI 16 | New
1010508 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59854M MUOS_IG_GS_NMS_NM_Security_HBSS_SVD | PI 16 | New
1010460 | #380808 | Story | Feature 380808: Test the WH Nutanix Cluster power-down/ power-up procedures for Nutanix | EA 15.3 | Done | 2
1010459 | #384036 | Story | Update the WH NMF power-down /power-up procedures to include Nutanix | EA 14.3 | Invalid | 0
1010440 | #1010421 | Story | Feature 1010421: Octopi Supply Support EA 15.5 | EA 15.5 | New | 5
1010439 | #1010421 | Story | Feature 1010421: Octopi Supply Support EA 15.4 | EA 15.4 | Implementing | 3
1010432 | #395855 | Story | Feature 395855: Update 01-P52843E001 for Removing Connected AWARE | EA 14.2 | Done | 1
1010425 | #1010421 | Story | Feature 1010421: Octopi Supply Support EA 15.3 | EA 15.3 | Done | 5
1010424 | #1010421 | Story | Feature 1010421: Octopi Supply Support EA 15.2 | EA 15.2 | Done | 5
1010423 | #1010421 | Story | Feature 1010421: Octopi Supply Support EA 15.1 | EA 15.1 | Done | 5
1010421 | #262146 | Feature | PI 15 Supply Support Tracking (Recurring) | EA 15.5 | Implementing
1010416 | #380808 | Task | Feature 380808: Submit PDO for 01-PXXXXX NME202 (new cabinet) | PI 16 | New
1010415 | #380808 | Task | Feature 380808: Submit PDO for NME201 (new cabinet) | PI 16 | New
1010414 | #380808 | Task | Feature 380808: Submit PDO for XX-XXXXX Cisco Switch SVD | PI 16 | New
1010412 |  | Task | Story 1011568: CM Release of 98-P59421M NM Juniper Router (EAD 18) | PI 16 | Invalid
1010405 | #395174 | Story | Feature 395174: FRB Testing of the 1536_MHZ_ CLOCK_ SYNTHESIZER_ CARD, PN = WS2P/CLKGEN/1536, SN = 1000211 | EA 14.5 | Done | 3
1010396 | #380808 | Task | Feature 380808: Submit PDO for 98-P59410M003 – NMS – NM – FCAP – F5BIG-IP – SVD | PI 16 | New
1010395 | #342054 | Task | Feature 342054: Submit PDO for 99-P53198T – NMS – NM – NEDB | PI 16 | New
1010394 | #342054 | Task | Feature 342054: Submit PDO for 99-P57051M – NMS – NM – GSAM | PI 16 | New
1010393 | #390286 | Story | Feature 390286: Resolve Issues with “MUOS Password Policy" document | EA 14.2 | Done | 2
1010392 | #1007900 | Task | Feature 1007900: Submit PDO for 98-P59414M – NMS – NM – Security – GSKey – SVD (GSKM) | PI 16 | New
1010389 | #342054 | Task | Feature 342054: Submit PDO for 98-P54188T - NMS -NM - Security -AAA - SVD | PI 16 | New
1010388 | #380808 | Task | Feature 380808: Submit PDO for 98-P55764M Nutanix_HP_SVD | PI 16 | New
1010387 | #380808 | Task | Feature 380808: Submit PDO for 98-P59434M_NM_CSCI_SVD | PI 16 | New
1010377 | #380808 | Story | Feature 380808: SIC team support: Install Splunk VMs from Scratch and regression (2600) Nutanix, Splunk HA | EA 15.2 | Done | 5
1010375 | #380808 | Story | Feature 380808: Install Nutanix SVD from scratch in the V-Lab on 2600 hardware | EA 15.2 | Done | 3
1010351 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48092V - SEIT - MUOSv1.1.26.0 (EAD-18) HLR End Of Life - NW Test Report - NAVSATCOMMFAC NORTHWEST | PI 16 | New
1010350 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48069V - SEIT - MUOSv1.1.26.0 (EAD-18) HLR End Of Life - WH Test Report - NCTAMSPAC SATCOM Wahiawa, HI | PI 16 | New
1010349 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48091V - SEIT - System Operational Verification Test (SOVT) for MUOSv1.1.26.0 (EAD-18 HLR End Of Life) – NAVSATCOMMFAC NORTHWEST | PI 15 | New
1010348 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48068V - SEIT - System Operational Verification Test (SOVT) for MUOSv1.1.26.0 (EAD-18 HLR End Of Life) – NCTAMSPAC SATCOM Wahiawa, HI | PI 15 | New
1010347 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48067V - SEIT - BESEP (Base Electronic System Engineer Plan) Source Material for MUOSv1.1.26.0 (EAD-18 HLR End Of Life) - Wahiawa at NCTAMSPAC SATCOM Wahiawa, HI | PI 15 | New
1010346 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48090V - SEIT - BESEP (Base Electronic System Engineer Plan) Source Material for MUOSv1.1.26.0 (EAD-18 HLR End Of Life) - NAVSATCOMMFAC NORTHWEST | PI 15 | New
1010345 | #1002381 | Task | Feature 1002381: 99-P48089V - SEIT - IDP - SC - MUOSv1.1.26.0 (EAD-18 HLR End Of Life - Northwest) Installation Design Plan NAVSATCOMMFAC NORTHWEST | PI 15 | New
1010344 | #1002381 | Task | Feature 1002381: Submit PDO for 99-P48066V - SEIT - IDP - SC - MUOSv1.1.26.0 (EAD-18 HLR End Of Life - Wahiawa) Installation Design Plan NCTAMSPAC SATCOM Wahiawa, HI | PI 15 | New
1010343 | #386935 | Story | Feature 386935: Review Final STCD and attend review meeting | EA 14.4 | Invalid | 0
1010342 | #386935 | Story | Feature 386935: Review Intermediate STCD and attend review meeting | EA 14.3 | Invalid | 0
1010341 | #1002345 | Story | Feature 1002345: Review Initial Test Plan (STCD) and attend internal Planning Meeting | EA 14.3 | Invalid | 0
1010340 | #386935 | Story | Feature 386935: Review Initial Test Plan (STCD) and attend internal Planning Meeting | EA 14.2 | Invalid | 0
1010273 | #378000 | Story | Feature 378000: AWARE O-Level Procedure Updates - Support of Independent Test (Dry Runs) | EA 14.1 | Done | 2
1010121 | #343918 | Task | Story 343918: CM Release of 99-P58905M – AMS-GS SOW (EAD 15 OOC) | EA 14.1 | Done
1010120 | #396819 | Story | Lab - Maintain Labs - Facility Management, come up to speed on lab custodian tasks - Carl (14.1) | EA 14.1 | Done | 3
1010095 | #378000 | Task | Feature 378000: EAD 15 AWARE-related I-Level Procedure update | EA 14.1 | Done
1010043 | #1008506 | Problem | IETM Style Guide update for "Splunk Enterprise - Account Administration - Normal Operation Procedure" | PI 16 | Ready for IRM Approval
1010040 | #353837 | Task | Story 353837: CM Release of 99-P53449 Interactive Electronic Technical Manual (IETM) – SVD (EAD 16 OOC) | EA 15.2 | New
1010039 | #1008506 | Problem | IETM Style Guide update for "Accounting Management Troubleshooting - Normal Operation Procedure" | PI 16 | Ready for IRM Approval
1010027 | #377437 | Task | Feature 377437: Submit PDO for 98-P54141 ILS Gen2 Laptop | EA 15.3 | Done
1010011 | #243502 | Story | CM Release Work for EAD 16 OOC | EA 15.2 | Invalid | 0
1009991 | #354680 | Story | ATO Maintenance: Verify IA Remediation for Access Control and Password Complexity on Splunk Servers | EA 14.3 | Done | 1
1009987 | #396437 | Story | Feature 396437: Document the RCG build process and generate a baseline build on rcg_dev before it is decomissioned | EA 14.2 | Done | 2
1009986 | #396437 | Story | Feature 396437: Identify and document what is on rcg_dev (code, tools, versions, etc.) | EA 14.2 | Done | 1
1009935 | #342054 | Story | Feature 342054: Test Report, needed 45 days prior to FRCB. | PI 16 | New | 1
1009934 | #342054 | Story | Feature 342054: Complete System Operational Verification Test, SOVT, needed 45 days prior to FRCB (complete through CM Release) (Submit to LM by 7/28) | EA 15.2 | Done | 5
1009933 | #342054 | Story | Feature 342054: Complete BESEP (NRTP Sicily) and Submit to by <date> | EA 15.1 | Done | 1
1009932 | #342054 | Story | Feature 342054: Sicily Completion of Installation Design Plan IDP, needed 120 days prior to FRCB | EA 15.1 | Done | 1
1009930 | #318380 | Story | IETM Procedure: Feature demo the IETM changes for EAD 15 | EA 14.1 | Done | 1
1009929 | #318380 | Story | Feature 318380: IETM Procedure: Falcons Update per Style Guide and Incoporate into IETM and MTB | EA 14.1 | Done | 2 | #1009930
1009928 | #318380 | Story | IETM Procedure: Create instructions to use new FTP on Windows 10 MTC/AJM Laptop when performing AJM Repair and Replace | EA 14.1 | Done | 1 | #1009929
1009907 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtP | EA 14.1 | Done | 5
1009899 |  | Problem | IETM update to AIU Installation and AIU Removal procedures, to identify correct tools | Unassigned | Assessing
1009867 | #386935 | Task | Feature 386935: Submit initial STCD to customer and request feedback | EA 14.2 | Done
1009818 | #395174 | Story | Feature 395174: FRB Testing of the AIR DEHYDRATOR, ADH3-COM of PN = 17479 (AU), SN = 1293 (AU) | EA 14.2 | Done | 3
1009817 | #395174 | Story | Feature 395174: FRB Testing of the AIR DEHYDRATOR, ADH3-COM of PN = 17479 (SC), SN = 1337 | EA 14.2 | Done | 3
1009816 | #395174 | Story | Feature 395174: FRB Testing of the AIR DEHYDRATOR, ADH3-COM of PN = 17479, SN = 1178 and SN 1267 | EA 14.3 | Done | 3
1009808 | #378000 | Problem | Connected AWARE: SLE Alarm – AWARE failed to connect to SLE and alarm recovery procedure wiped out configuration parameters | EA 14.1 | Closed
1009632 | #379001 | Task | Re-apply Problem 1009622 Task for Deployment : Trouble ticket INC000004589736: WH- “RAF_ET_Alignment procedures document uses out of date satellite locations" updates needed for new CI ILS Laptop Gen 2 | Unassigned | New
1009631 | #379001 | Story | Re-write and Test Problem 1009622 Story : Trouble ticket INC000004589736: WH- “RAF_ET_Alignment procedures document uses out of date satellite locations" updates needed for new CI ILS Laptop Gen 2 | EA 14.2 | Done | 2
1009630 | #377437 | Story | Rebase and Test Problem 1009622 Story : Trouble ticket INC000004589736: WH- “RAF_ET_Alignment procedures document uses out of date satellite locations" updates needed for new CI ILS Laptop Gen 2 | EA 15.1 | Done | 2
1009622 | #395871 | Problem | Trouble ticket INC000004589736: WH- “RAF_ET_Alignment procedures document uses out of date satellite locations" updates needed for new CI ILS Laptop Gen 2 | EA 14.2 | Closed
1009583 |  | Problem | AWARE: Terminals could not proceed with OTAFT due to speed of AWARE scenarios | Unassigned | Assessing
1009581 | #378000 | Problem | AWARE: WH- awrsw101-wh-raf unable to login with emadmin or muos (failsafe) account | EA 14.1 | Closed
1009580 | #342054 | Problem | MUOSAT-MHAL: sle_cpp - connection to SLE refused to open after being open in previous scenarios | PI 16 | Implementing
1009578 | #378000 | Problem | Connected AWARE: SLE Alarm – AWARE failed to connect to SLE and alarm recovery procedure wiped out configuration parameters | EA 14.1 | Closed
1009548 | #1003390 | Story | Feature 1003390: Help measure MSL power at RBS | EA 14.4 | Done | 2
1009513 | #377408 | Problem | Typos/Administrative Corrections to SSG20_LinkDown_Recovery_Procedure.pdf | EA 14.3 | Closed
1009510 | #318430 | Story | Feature 318430 ETT Laptop - Feature Demo – Customer Demo Event | EA 14.1 | Done | 1
1009493 | #384036 | Story | Feature 384036: Update AAA\DNS to support the Nutanix integration in VLAB | EA 14.1 | Done | 1
1009491 | #386935 | Problem | Rebase MPC 14.27 into EAD16 baseline - Correct 5 KHz calibration bias. - Code Change needed only in RAF servers. | EA 14.3 | Closed
1009488 |  | Problem | Determine if metrics should be kept to track alarms at site for possible board failures | Unassigned | Assessing
1009458 | #1015911 | Story | Feature 1015911: Development and Test | PI 16 | New | 5
1009457 | #354174 | Story | Feature 354174: Begin Review of IETM Update for SPLUNK Update | EA 14.1 | Done | 2
1009456 | #1009453 | Story | Feature 1009453: Reproduce B2U Power Spike for Log Analysis - Systems | EA 15.4 | New | 3
1009455 | #1009453 | Story | Feature 1009453: Execute tests for DL power spike investigation (Lab team) | EA 15.2 | Done | 2
1009453 | #1016405 | Feature | Determine Cause of DL Power Spikes causing RNC Congestion | EA 15.4 | Implementing |  | #1017077
1009427 | #379001 | Task | Re-apply Problem 1006145 Task for Deployment : FEP SVD needs to be updated to include depot instructions for configuration for new part number dehydrator | Unassigned | New
1009426 | #1017680 | Story | Rebase and Test Problem 1006145 Story : FEP SVD needs to be updated to include depot instructions for configuration for new part number dehydrator | EA 15.1 | Done | 1
1009425 | #1016383 | Problem | Update Whitelist, and QuestDoor filters with additional alarms | PI 16 | Approved
1009291 | #318430 | Story | Quick Functional test of MTC /AJM and ETT Gen2 Laptops | EA 14.2 | Done | 1
1009268 |  | Problem | [MAINT] When group Tx override got denied, it could take up 2 minutes to be back a listener | Unassigned | Assessing
1009091 | #1001912 | Story | Feature 1001912: WF PWI burndown | EA 14.2 | Done | 3
1009066 | #384036 | Story | Feature 384036: Get ClearCase and ClearQuest Accounts to support NEDB | EA 14.1 | Done | 1
1009021 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Tom G. (14.1) | EA 14.1 | Done | 2
1009020 |  | Task | Parking Lot 103 - Critical Security Patching of Windows 10 and Server 2016/19 Nodes in RAN/RDE and SWIT | EA 14.4 | Done
1009019 |  | Task | Parking Lot 99 - buildforge1 Integrated Java Vulnerability | EA 15.4 | In Development
1009018 |  | Task | Parking Lot 98 - Upgrade DMZ Servers | EA 15.4 | In Development
1009017 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support | EA 14.1 | Done | 2
1009015 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support (Tom) | EA 14.1 | Done | 1
1009014 |  | Task | Parking Lot 107 - RCG-dev has 2 or 3 disks that are failing | EA 15.4 | In Development
1009013 |  | Task | Parking Lot 108 - Specs for RDE Windows Nodes ("ranframe"s) | EA 14.1 | Done
1009012 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support (Glen) | EA 14.1 | Done | 2
1009008 |  | Task | Parking Lot 109 - Create SecVars for Solaris and Linux Servers (BuildForge) | EA 15.2 | Done
1008998 | #378000 | Task | Feature 378000: Coordinate Final STCD Review Meeting (Internal) | EA 14.1 | Done
1008981 | #378000 | Story | Feature 378000: GSAM (AMP) Updates for AWARE O-Level Procedures | EA 14.1 | Done | 1
1008967 | #377437 | Story | Rebase and Test Problem 1008917 Story : WH- Manual RRT MATLAB code has out of date M50x associations. Need to associate M502 with PAC and M503 with CONUS | EA 15.2 | Done | 2
1008922 | #343920 | Task | Story 343920: CM Release of 99-P53449E - ILS - IETM (EAD 16) | PI 14 | Done
1008917 | #379001 | Problem | WH- Manual RRT MATLAB code has out of date M50x associations. Need to associate M502 with PAC and M503 with CONUS | EA 15.2 | Closed
1008840 | #381608 | Story | Feature 381608: Create the Site Functional Test Cases | EA 14.1 | Done | 1
1008818 | #379761 | Story | Feature 379761 FM Whitelist: MFR 1 write up | EA 14.3 | Done | 1
1008817 | #354871 | Story | Feature 354871: Integration and testing of NAVSOC OA Workstation upgrade (14.5) | EA 14.5 | Done | 3
1008816 | #378000 | Story | Feature 378000: AWARE for SC IETM Updates - Independent Test (Dry Runs) - Observer | EA 14.1 | Done | 8
1008804 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.4 | EA 14.4 | Done | 3
1008796 | #378000 | Problem | AWARE Alarm Recovery Procedures Refer to Accounts/Passwords that Do Not Exist at Site (Account Maintenance Plan) | EA 14.1 | Closed
1008793 | #378000 | Problem | Unable to Log Out User from AWARE VM | EA 14.1 | Closed
1008791 | #378000 | Problem | Typos/Administrative Errors in AWARE Alarm Recovery and IETM Procedures | EA 14.1 | Closed
1008737 | #390286 | Story | Feature 390286: Redlines for Account Maintenance Plan | EA 14.1 | Invalid | 0
1008736 | #381524 | Story | Feature 381524 PB: Create recovery procedure for new prov bridge faults | EA 14.4 | Done | 5 | #381528
1008734 | #386935 | Story | Feature 386935: Update IETM Procedure - Regular Maintenance Procedure for backing up Geo DB files. | EA 14.1 | Done | 2
1008724 | #381524 | Story | Feature 381524 PB: Support Fix Problem 381547 | EA 14.4 | Done | 2
1008721 | #381524 | Story | Feature 381524 PB: Support Fix Problem 381547 | EA 14.3 | Invalid | 0
1008719 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (14.5) | EA 14.5 | Done | 2
1008718 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (14.4) | EA 14.4 | Done | 2
1008715 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (14.3) | EA 14.3 | Done | 2
1008714 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (14.2) | EA 14.2 | Invalid | 0
1008713 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Marroquin (14.1) | EA 14.1 | Done | 2
1008712 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Chavez (14.5) | EA 14.5 | Done | 2
1008711 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Chavez (14.4) | EA 14.4 | Done | 2
1008710 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Chavez (14.3) | EA 14.3 | Done | 2
1008709 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Chavez (14.2) | EA 14.2 | Done | 2
1008707 | #396819 | Story | Lab - Maintain Labs - Bring up / Maintain WDE radio for PWI Burndown feature - Chavez (14.1) | EA 14.1 | Done | 2
1008697 | #384084 | Story | Feature 384084: Support Feature Demo – Customer Demo Event | EA 16.4 | New | 1
1008690 | #384084 | Task | Feature 384084: Create dev build for FM in VLAB (install included) | EA 14.3 | Done
1008689 | #384084 | Story | Feature 384084: Support Execute STCD Feature Integration and testing including STCD updates identified | EA 14.3 | Invalid | 0
1008685 | #384084 | Story | Feature 384084: Update rules files, integrate & test | EA 14.2 | Done | 2
1008681 | #384084 | Story | Feature 384084: Support create STCD and review with stakeholders | EA 14.2 | Done | 1
1008673 | #384084 | Story | Feature 384084: FM Topology - Perform Iterative Implementation, Integration, development Testing including updating design | EA 14.2 | Done | 2
1008663 | #384036 | Story | Feature 384036: Incorporate AAA Config into Nutanix SVD | EA 14.1 | Done | 3
1008653 | #388549 | Story | Feature 388549: Support ULX Hardware Design | EA 14.2 | Invalid | 0
1008646 | #395373 | Story | VMP: Support PMW-146 Review - 14.4 | EA 14.4 | Done | 3
1008645 | #395373 | Story | VMP: Continue Developing the Operational Scan Plan - 14.3 | EA 14.3 | Done | 3
1008644 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Section 14 - Integration and Test Strategy Continue from 14.1 [14.4] | EA 14.4 | Done | 3
1008643 | #395373 | Story | VMP: Development of an Operational Scan Plan- 14.1 | EA 14.1 | Done | 3
1008640 | #354680 | Story | Feature 354680 (Site): Verify SIPRNET access to search head in VLAB | EA 14.2 | Done | 2
1008639 | #1004171 | Story | Feature 1004171: Test group solution (14.3) | EA 14.4 | Done | 2
1008638 | #395373 | Story | Complete Scan Assessment Guidance document-Part 2a (Feature 395373 Cyber Sustainment Activities) | EA 14.5 | Invalid | 0
1008636 |  | Story | VMP: Complete Scan Assessment Guidance document (part 1) | Unassigned | Invalid | 0
1008635 | #1001912 | Story | Feature 1001912: WF PWI burndown - Yue-Chain | EA 14.3 | Done | 3
1008631 | #396819 | Story | Lab - Maintain Labs - Research/update test process documents, to include any CAR resolution | EA 14.3 | Invalid | 0
1008628 | #383110 | Feature | Complete Nutanix deployment | PI 15 | Rejected
1008626 | #395835 | Story | Support application review for DADMs applicability - 14.3 | EA 14.3 | Invalid | 0
1008625 | #1007536 | Story | Feature 1007536: Review and Rework 2-Factor PowerPoint Proposal | EA 14.4 | Done | 3
1008623 | #1007536 | Story | Feature 1007536: Review & Approve 2-factor PowerPoint Proposal | EA 14.4 | Done | 2
1008622 | #395835 | Story | Support application review for DADMs applicability - 14.1 | EA 14.1 | Done | 1
1008621 | #1007536 | Story | Feature 1007536: Review and Present 2-Factor PowerPoint Proposal | EA 14.4 | Done | 2 | #1007542 #1007543 #1007544
1008620 | #262134 | Feature | Lab – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Part B | EA 15.5 | Implementing
1008615 | #1004171 | Story | Feature 1004171: Create instrumented build for group prov fix scenarios | EA 14.2 | Done | 2
1008613 |  | Task | Feature 392743 ATO: submit PDO | EA 14.4 | Done
1008612 | #396819 | Story | Lab - Maintain Labs - Work MUOS test process document to resolve CAR 14.5 | EA 14.5 | Invalid | 0
1008611 | #1007536 | Story | Decompose Story 1007542, Story 1007544, and Story 1007543 | EA 14.2 | Done | 3 | #1007542 #1007543 #1007544
1008610 | #395373 | Story | Cyber Sustainment Activities PI 14 (Recurring) | EA 14.3 | Invalid | 0
1008609 | #392743 | Story | Feature 392743: Fix problem 354579 - part 4 | EA 14.2 | Done | 3 | #1008584
1008608 | #1006376 | Story | Feature 1006376: Implement review fixes | EA 14.3 | Invalid | 0
1008605 | #392743 | Story | Feature 392743: Fix problem 354579 - part 3 | EA 14.2 | Done | 2 | #1008609
1008600 | #395373 | Story | Generate DTA Process Document for MUOS | EA 14.2 | Done | 5
1008593 | #1001248 | Story | Feature 1001248 OTAP: IETM updates - ILS | EA 14.3 | Done | 1
1008592 | #1001248 | Story | Feature 1001248 OTAP: IETM updates | EA 14.3 | Done | 1
1008591 | #354174 | Story | Feature 354174 Splunk IETM: Feature demo prep | EA 14.3 | Done | 3
1008590 | #354174 | Story | Feature 354174 Splunk IETM: Dry runs - Joel | EA 14.2 | Done | 2
1008589 | #354174 | Story | Feature 354174 Splunk IETM: Dry runs | EA 14.2 | Done | 2
1008588 | #354174 | Story | Feature 354174 Splunk IETM: Test/Dry run procedure 313670 fix | EA 14.2 | Done | 2
1008587 | #354174 | Story | Feature 354174 Splunk IETM: Splunk HA IETM Review | EA 14.2 | Done | 1
1008586 | #354174 | Story | Feature 354174 Splunk IETM: Review fix for problem 313670 | EA 14.2 | Done | 1
1008585 | #392743 | Story | Feature 392743 ATO: Feature Demo – Customer Demo Event | EA 14.4 | Done | 1
1008584 | #392743 | Story | Feature 392743 ATO: demo prep | EA 14.3 | Done | 1 | #1008585
1008583 | #392743 | Story | Feature 392743 ATO: create STCD | EA 14.2 | Done | 1
1008582 | #392743 | Story | Feature 392743 ATO: MFR 1 write up | EA 14.2 | Done | 1
1008556 | #384036 | Story | Nutanix FRCB | EA 14.4 | Invalid | 0
1008555 | #390286 | Story | Feature 390286: Support MPC to Disable LLMNR and NetBIOS (Phase 1 of N) | EA 14.3 | Done | 5
1008553 | #384036 | Story | Nutanix alarm procedures testing | EA 14.3 | Invalid | 0
1008552 | #376446 | Task | Feature 376446: Cross-train IA posture improvement, final scans - Robert Stevens | EA 14.5 | Done
1008550 | #354680 | Story | Feature 354680 (Site): IA Posture Assessment - part 2 | EA 14.3 | Done | 3
1008549 | #354680 | Story | Feature 354680 (Site): Splunk HA review - Dustin | EA 14.4 | Done | 1
1008547 | #354680 | Story | Feature 354680 (Site): Splunk HA review - Ricardo | EA 14.4 | Done | 1
1008546 | #354680 | Story | Feature 354680 (Site): Splunk HA review - Katie | EA 14.5 | Done | 3
1008545 | #354680 | Story | Feature 354680 (Site): Splunk HA review - Joel | EA 14.4 | Done | 1
1008542 | #378000 | Story | Feature 378000: AWARE O-Level Procedure Updates - Independent Test (Dry Runs) | EA 14.1 | Done | 8
1008536 | #384136 | Story | Feature 384136: OBS HBSS- Review IA Related IETMs for Compliance (EA 14.3) | EA 14.3 | Done | 3
1008534 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: System Operational Verification Test, SOVT, Test Inputs for Feature - part 2 | EA 14.2 | Done | 3
1008533 | #384136 | Story | Feature 384136: MFR 3 – Review Design updates based on initial STIG finding Part 2 | EA 14.4 | Done | 3
1008532 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort (EA 14.4) | EA 14.4 | Done | 1
1008529 | #354680 | Story | Feature 354680 (Site): Scratch install of Splunk HA person 1 (SVD Redlines) | EA 14.2 | Done | 3
1008526 | #354646 | Story | MUOS Terminal Trade (Cyber Support) | EA 14.2 | Invalid | 0
1008525 | #354646 | Story | MUOS Terminal Trade (Cyber Support) | EA 14.1 | Done | 1
1008524 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Perform Iterative Implementation, Integration, and development.- part 3 | EA 14.3 | Done | 5
1008523 | #1007900 | Story | Feature 1007900: Verification for SVD Updates Second Story | PI 16 | New | 3
1008522 | #396835 | Story | Feature 396835: Incorporate Redlines and Finalize Gvt Property Inventory Report | EA 14.3 | Invalid | 0
1008521 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Shawn (14.1) | EA 14.1 | Done | 1
1008520 | #1008506 | Story | Feature 1008506: Initiate CM PDO Processing for all CI's | EA 16.5 | New | 1
1008519 | #1008506 | Story | Feature 1008506: Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1 | #1008520
1008518 | #1008506 | Story | Feature 1008506: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 16 | New | 2 | #1008519
1008517 | #1008506 | Story | Feature 1008506: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 1 | #1008519
1008516 | #1008506 | Story | Feature 1008506: Provide Development inputs to common documents | PI 16 | Invalid | 0 | #1008519
1008515 | #1008506 | Story | Feature 1008506: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 16 | New | 1
1008514 | #1008506 | Story | Feature 1008506: UX Research and Design Support (Change back to UX Team) | PI 16 | New | 3
1008513 | #1008506 | Story | Feature 1008506: Develop IETMs and Perform Development Testing | PI 16 | New | 3 | #1008519
1008512 | #1008506 | Story | Feature 1008506: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 16 | New | 1 | #1008519
1008511 | #1008506 | Story | Feature 1008506: Perform Iterative Implementation, Integration, development Testing including updating design | PI 16 | Invalid | 0 | #1008519
1008510 | #1008506 | Story | Feature 1008506: Provide Deployment Notes and Operator Impact Inputs - final | PI 16 | New | 1 | #1008519 #1021075
1008509 | #1008506 | Story | Feature 1008506: Create STCD and review with stakeholders | PI 16 | New | 3 | #1008517 #1008518 #1008511 #1008519
1008508 | #1008506 | Story | Feature 1008506: Document Initial capability specification and detailed design to start Implementation | PI 16 | Invalid | 0 | #1008509 #1008511
1008507 | #1008506 | Task | Feature 1008506: Hold Feature Review with SMEs | PI 16 | New
1008506 | #383110 | Feature | Troubleshooting & Recovery Procedures for Splunk HA | PI 16 - In Progress | Implementing
1008497 | #343920 | Task | Story 343920: CM Release of 98-P59412M NMS - NM - Provisioning - KeyMgmt – SVD (EAD 16) | PI 14 | Done
1008496 | #1000039 | Task | Story 1000039: Finish MPC and get approval | EA 14.2 | Done
1008494 | #396272 | Story | Feature 396272: Review UE instrumentation reports - EA 14.4 | EA 14.4 | Done | 2
1008493 | #1001636 | Story | Support Updating the Cyber IA Repository Database | EA 14.5 | Done | 1
1008491 | #381608 | Story | Feature 381608: Support STCD Execution | EA 14.1 | Done | 1
1008490 | #381608 | Story | Feature 381608: Support STCD Execution | EA 14.1 | Done | 1
1008488 | #381608 | Story | Feature 381608: Finish STCD Execution | EA 14.1 | Done | 2
1008486 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. Part 1 | EA 14.1 | Done | 5
1008482 | #395174 | Story | Feature 395174: SMDC Laptops Patches and Scans (Part 2) | EA 14.2 | Done | 1
1008481 | #392530 | Story | Cyber IA Patching - PI 14 (Recurring) - PI14.5 | Unassigned | Invalid | 0
1008480 | #395174 | Story | Feature 395174: SMDC Laptops Patches and Scans (Part 1) | EA 14.1 | Done | 1
1008478 | #392530 | Story | Cyber IA Patching - PI 14 (Recurring) - PI14.2 | EA 14.2 | Done | 1
1008477 | #392530 | Story | Cyber IA Patching - PI 14 (Recurring) - PI14.1 | EA 14.1 | Done | 3
1008476 | #392530 | Story | Cyber IA Patching - PI 14 (Recurring) - PI14.1 | EA 14.1 | Done | 1
1008475 | #353345 | Story | Feature 353345: Complete Customer Response Matrix (CRM)- Training Maintainer Refresher NW | EA 14.2 | Invalid | 0
1008473 |  | Problem | INC000004581199: NAVSOC HQ-OAS's ODTK Covariance message stopping AutoOD | Unassigned | Assessing
1008471 |  | Problem | INC000004581189: NAVSOC HQ-OAS Procedure for updating EOP type files | Unassigned | Assessing
1008466 | #1004171 | Story | Feature 1004171: Support Site Functional Testing in VLAB | EA 15.3 | Done | 1
1008465 | #318430 | Story | Feature 318430 ETT: PCR Verification | EA 14.1 | Done | 2
1008463 | #395871 | Story | Refresh PPA U2B External Interference System Parameters - implement MPC | EA 14.3 | Done | 2
1008462 | #318430 | Story | Feature 318430 ETT: Feature Demo – Customer Demo Event - ETT Laptop | EA 14.1 | Invalid | 0
1008460 | #395871 | Story | Refresh PPA U2B External Interference System Parameters - testing | EA 14.3 | Done | 1
1008456 | #1004171 | Story | Feature 1004171: Create instrumented build for group prov fix scenarios | EA 14.2 | Done | 2
1008455 | #384036 | Story | Feature 384036: Test Nutanix and Cisco Switch Deployment Plan to prevent outages (2) | EA 14.4 | Done | 2
1008454 | #1004171 | Story | Feature 1004171: Code walk through of solutions - Sang | EA 14.3 | Done | 1
1008453 | #290711 | Story | Feature 290711: AWARE SME Support (if needed) | EA 14.1 | Done | 1
1008452 | #318430 | Story | Feature 318430 ETT Laptop - Feature Demo – Customer Demo Support and STCD review | EA 14.1 | Done | 2
1008448 | #396272 | Story | Feature 396272: Review UE instrumentation reports - EA 14.1 | EA 14.1 | Done | 2
1008444 | #368860 | Story | Feature 368860 Cost Estimate ~ Waveform | EA 14.3 | Done | 1
1008443 | #368860 | Story | Feature: 368860 Cost Estimate ~ Waveform | EA 14.2 | Done | 1
1008409 | #1001636 | Story | 3) Determine which CAT1s in the new POAM spreadsheet are being addressed by Obsolescence | EA 14.1 | Done | 2
1008408 | #1001636 | Story | 2) Determine the CAT1s that have already been addressed by existing PWIs | EA 14.1 | Done | 3
1008407 | #395373 | Story | DADMS Compliance | EA 14.3 | Done | 3
1008406 | #395373 | Story | VMP: Support PMW Comment Resolution - 14.3 | EA 14.3 | Done | 3
1008405 | #386935 | Story | Feature 386935: Iterative STCD Development and Site Functional Plan | EA 14.4 | Done | 1
1008404 | #386935 | Story | Feature 386935: Iterative STCD Development and Site Functional Plan | EA 14.3 | Done | 1
1008403 | #386935 | Story | Feature 386935: Coordinate Final STCD Review Meeting (Internal) | EA 14.4 | Done | 1
1008402 | #386935 | Story | Feature 386935: Coordinate Intermediate STCD Review Meeting (Internal) | EA 14.3 | Done | 1
1008401 | #386935 | Story | Feature 386935: Coordinate Initial Test Planning (STCD) Meeting (Internal) | EA 14.2 | Done | 1
1008400 | #1002345 | Story | Feature 1002345: Coordinate Final STCD Review Meeting (Internal) | PI 16 | New | 1
1008399 | #1002345 | Story | Feature 1002345: Coordinate Intermediate STCD Review Meeting (Internal) | EA 15.2 | Done | 1
1008398 | #1002345 | Story | Feature 1002345: Coordinate Initial Test Planning (STCD) Meeting (Internal) | EA 14.3 | Done | 1
1008397 | #396002 | Story | Feature 396002: Train Zeta Technical Contract Coordinator | EA 14.1 | Done | 1
1008396 | #354680 | Story | Feature 354680 (Site): Add new Splunk HA hosts to GSKM | EA 14.3 | Done | 2
1008395 | #354680 | Task | Feature 354680 (Site): Obtain IA approval for Splunk HA | EA 14.1 | Invalid
1008394 | #354680 | Story | Feature 354680 Site: Splunk HA final lab testing: forwarder Failure/failovers | EA 14.3 | Done | 2
1008393 | #354680 | Story | Feature 354680 (Site): Splunk HA final SVD updates | EA 14.3 | Done | 2
1008392 | #380808 | Story | Feature 380808: Incorporate Splunk Redlines into the PKI Document | PI 16 | New | 1
1008391 | #354680 | Story | Feature 354680 (Site): Splunk HA PCR Verification | EA 14.5 | Done | 1
1008390 | #354680 | Story | Feature 354680 (Site): Backup/Archive CI review for Splunk HA | EA 14.2 | Done | 3
1008389 | #354680 | Story | Feature 354680 (Site): Splunk HA Review | EA 14.5 | Done | 3
1008388 | #354680 | Story | Feature 354680 (Site): Splunk HA- Begin RHEL CI review | EA 14.4 | Invalid | 0
1008387 | #354680 | Story | Feature 354680 (Site): Execute STCD: 1st full run of feature test | EA 14.3 | Done | 2
1008386 | #354680 | Story | Feature 354680 (Site): Complete Splunk HA STCD Development - Support | EA 14.3 | Invalid | 0
1008385 | #354680 | Story | Feature 354680 (Site): Complete Splunk HA STCD Development - Test Team | EA 14.3 | Done | 2
1008384 | #354680 | Story | Feature 354680 (Site): Splunk HA VLAB Performance Benchmark for STCD | EA 14.2 | Done | 2
1008382 | #354680 | Task | Feature 354680 (Site): QCOW VM File generation | EA 14.2 | Done
1008377 | #354680 | Story | Feature 354680 (Site): Continued Splunk HA STCD Development - Chris | EA 14.2 | Done | 2
1008376 | #354680 | Story | Feature 354680 (Site): Continued Splunk HA STCD Development - Art | EA 14.2 | Done | 3
1008375 | #354680 | Story | Feature 354680 (Site): Development Build Generation (Ready for VLAB) (QCOW file generation) | EA 14.2 | Done | 1
1008374 | #354680 | Task | Feature 354680 (Site): coordinate with Tools on Build script update/implementation & Testing | EA 14.1 | Done
1008373 | #354680 | Story | Feature 354680 (Site): Update ClearCase for Splunk HA | EA 14.2 | Done | 1
1008372 | #354680 | Story | Feature 354680 (Site): Complete Splunk HA SVD Draft (Ready for Official Hardware) following data migration | EA 14.2 | Done | 3
1008370 | #354680 | Story | Feature 354680 (Site): Scratch install of Splunk HA person 2: SVD Execution | EA 14.2 | Done | 3
1008369 | #354680 | Story | Feature 354680 (Site): Dry-run data migration plan in VLAB - TeamMember2 | EA 14.2 | Done | 1
1008363 | #383958 | Task | Feature 383958: Submit PDO for 98-P59422M – NMS – NM – SecretAppServer – SVD | EA 15.4 | New
1008335 | #386935 | Story | Feature 386935: SV Relo Phase 3 Closeout Testing | EA 14.1 | Done | 3
1008332 | #343920 | Task | Story 343920: CM Release of 99-P57051M - NMS - NM Common - GSAM (EAD 16) [aka Account Maintenance Plan] | PI 14 | New
1008280 | #377408 | Problem | Broken Link for jnxEventTrap Alarm Recovery in List Of COTS Alarms. | EA 14.3 | Closed
1008278 |  | Problem | Stop NFSmapid DNS queries from the MAS | Unassigned | Assessing
1008277 | #377408 | Problem | IETM Does Not Indicate SSG20s Can Only be Accessed from Legacy WS | EA 14.2 | Closed
1008274 | #393265 | Problem | Settings Not Provided for Tectia Login in the SSG20_LinkDown_Recovery_Procedure.pdf | EA 15.4 | Approved
1008269 |  | Problem | Permission Denied Errors when Executing Geolocation Services Verification Script | Unassigned | Assessing
1008265 | #388053 | Story | Design PPA Replacement | EA 14.1 | Done | 2
1008264 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Support AIM Team | EA 14.4 | Invalid | 0
1008263 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Support AIM Team | EA 14.3 | Invalid | 0
1008262 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Support AIM Team | EA 14.2 | Done | 1
1008261 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Support AIM Team | EA 14.1 | Done | 1
1008260 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Drawing Updates | EA 14.4 | Done | 1
1008259 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Drawing Updates | EA 14.3 | Invalid | 0
1008258 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Drawing Updates | EA 14.2 | Done | 1
1008257 | #1006376 | Story | Feature 1004171: Final Test Problem 1003393 | EA 15.3 | Invalid | 0
1008255 | #388549 | Story | Feature 388549: ULX Detailed Design - FM/Logging (Final Detailed Design Updates, Support Final Presentation)388549 | EA 14.4 | Done | 5
1008254 | #388549 | Story | Feature 388549: ULX Detailed Design - Monitor and Control (Define Connection to Data Storage, Manager, String Switchover, Component, Parameters, Returns) | EA 14.3 | Done | 5
1008253 | #388549 | Story | Feature 388549: ULX Detailed Design - Create BOM | EA 14.4 | Invalid | 0
1008252 | #388549 | Story | Feature 388549: ULX Detailed Design - Drawings, Part 2 of 2 | EA 14.4 | Invalid | 0
1008251 | #388549 | Story | Feature 388549: ULX Detailed Design - Drawings, Part 1 of 2 | EA 14.2 | Invalid | 0
1008250 | #388549 | Story | Feature 388549: ULX Detailed Design - Sparing Analysis | EA 14.2 | Invalid | 0
1008249 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support | EA 14.4 | Done | 3
1008248 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support | EA 14.4 | Done | 3
1008247 | #354680 | Task | Feature 354680 (Site): VLAB Coordination / Scheduling for HA integration and impact identification | EA 14.1 | Done
1008246 | #354680 | Story | Feature 354680 (Site): IA Patching and STIGs (RHEL) | EA 14.1 | Done | 5
1008245 | #354680 | Story | Feature 354680 (Site): Backup/Archive SVD updates for Splunk HA | EA 14.1 | Done | 1
1008244 | #354680 | Story | Feature 354680 (Site): Review PKI document updates for Splunk HA. Technical Review Only. Do not incorporated into EAD 16. | EA 14.3 | Done | 3
1008243 | #354680 | Story | Feature 354680 (Site): Review of Splunk HA updates to AMP document. Technical Review Only. Do not incorporated into EAD 16. | EA 14.3 | Done | 1
1008242 | #354646 | Story | MUOS Terminal Trade | EA 14.1 | Done | 2
1008241 | #354646 | Story | MUOS Terminal Trade | EA 14.3 | Invalid | 0
1008240 | #354646 | Story | MUOS Terminal Trade | EA 14.2 | Done | 3
1008239 | #354646 | Story | MUOS Terminal Trade | EA 14.1 | Done | 5
1008238 | #378964 | Task | Bernie Southerland PTO (EA 14.1 (2/3 - 2/7)) | EA 14.1 | Invalid
1008235 | #377408 | Problem | Correct Admin Typos in MUOS Geolocation Services — Verification IETM Procedure | EA 14.2 | Closed
1008234 | #393265 | Problem | Geolocation RF Tray Maintenance: Mini-Circuits SMA tool not present | EA 15.2 | Closed
1008231 | #1007536 | Story | Feature 1007536: Develop 2-Factor Power Point Proposal | EA 14.3 | Done | 5 | #1008623 #1008621 #1008625
1008230 | #395871 | Story | Feature 395871: TOFF front-end CRM TT support (Sally) 14.5 | EA 14.5 | Invalid | 0
1008229 | #395871 | Story | Feature 395871: TOFF front-end TT and MPC support (Sally) 14.3 | EA 14.3 | Done | 1
1008225 | #1008172 | Task | Feature 396308: TOFF PWI triage/assessment support (Chris T.) 14.5 | EA 14.5 | Done
1008224 | #1008171 | Task | Feature 396308: TOFF PWI triage/assessment support (Chris T.) 14.4 | EA 14.4 | Done
1008223 | #1008170 | Task | Feature 396308: TOFF PWI triage/assessment support (Chris T.) 14.3 | EA 14.3 | Done
1008222 | #1008172 | Task | Feature 396308: TOFF PWI triage/assessment support (Robert) 14.5 | EA 14.5 | Done
1008221 | #1008171 | Task | Feature 396308: TOFF PWI triage/assessment support (Robert) 14.4 | EA 14.4 | Done
1008220 | #1008170 | Task | Feature 396308: TOFF PWI triage/assessment support (Robert) 14.3 | EA 14.3 | Done
1008218 | #1008172 | Task | Feature 396308: TOFF PWI triage/assessment support (Shawn) 14.5 | EA 14.5 | Done
1008217 | #1008171 | Task | Feature 396308: TOFF PWI triage/assessment support (Shawn) 14.4 | EA 14.4 | Done
1008216 | #1008170 | Task | Feature 396308: TOFF PWI triage/assessment support (Shawn) 14.3 | EA 14.3 | Done
1008214 | #1008172 | Task | Feature 396308: TOFF PWI triage/assessment support (Mike M.) 14.5 | EA 14.5 | Done
1008213 | #1008171 | Task | Feature 396308: TOFF PWI triage/assessment support (Mike M.) 14.4 | EA 14.4 | Done
1008212 | #1008170 | Task | Feature 396308: TOFF PWI triage/assessment support (Mike M.) 14.3 | EA 14.3 | Done
1008209 | #354680 | Story | Feature 354680 (Site): HW/SW Map Document Review.Technical Review Only. Do not incorporated into EAD 16. | EA 14.3 | Done | 3
1008208 | #354680 | Story | Feature 354680 (Site): Splunk HA STCD Development (Ramp-up and development) - Art | EA 14.1 | Done | 5
1008207 | #354680 | Story | Feature 354680 (Site): SSL Configuration and Testing for Splunk | EA 14.1 | Done | 5
1008206 | #1008169 | Task | Feature 396308: TOFF PWI triage/assessment support (Chris T.) 14.2 | EA 14.2 | Done
1008203 | #1008169 | Task | Feature 396308: TOFF PWI triage/assessment support (Robert) 14.2 | EA 14.2 | Done
1008202 | #1008169 | Task | Feature 396308: TOFF PWI triage/assessment support (Shawn) 14.2 | EA 14.2 | Done
1008201 | #1008169 | Task | Feature 396308: TOFF PWI triage/assessment support (Mike M.) 14.2 | EA 14.2 | Done
1008199 | #1008168 | Task | Feature 396308: TOFF PWI triage/assessment support (Chris T.) 14.1 | EA 14.1 | Done
1008195 | #1008168 | Task | Feature 396308: TOFF PWI triage/assessment support (Robert) 14.1 | EA 14.1 | Done
1008194 | #1008168 | Task | Feature 396308: TOFF PWI triage/assessment support (Shawn) 14.1 | EA 14.1 | Done
1008193 | #1008168 | Task | Feature 396308: TOFF PWI triage/assessment support (Mike M.) 14.1 | EA 14.1 | Done
1008185 | #384036 | Story | Feature 384036:(SIEM SVD) update to support Nutanix and iLo data- Part 2 | EA 14.3 | Done | 3
1008180 |  | Problem | Geolocation RF Tray Maintenance: Wiring Diagrams included in Removal and Installation Procedures do not match cable tags at site | Unassigned | Assessing
1008177 | #396308 | Story | PI 14 SIC PWI Support - Assess Problem 1003195 - VLAB investigation of limit | EA 14.1 | Done | 1
1008172 | #396308 | Story | Feature 396308: TOFF PWI triage/assessment support 14.5 | EA 14.5 | Done | 1
1008171 | #396308 | Story | Feature 396308: TOFF PWI triage/assessment support 14.4 | EA 14.4 | Done | 1
1008170 | #396308 | Story | Feature 396308: TOFF PWI triage/assessment support 14.3 | EA 14.3 | Done | 1
1008169 | #396308 | Story | Feature 396308: TOFF PWI triage/assessment support 14.2 | EA 14.2 | Done | 1
1008168 | #396308 | Story | Feature 396308: TOFF PWI triage/assessment support 14.1 | EA 14.1 | Done | 1
1008143 | #395871 | Story | Feature 395871: WWTS front-end CRM TT support 14.5 | EA 14.5 | Invalid | 0
1008142 | #395871 | Story | Feature 395871: WWTS front-end CRM TT support (Bob) 14.4 | EA 14.4 | Invalid | 0
1008141 | #395871 | Story | Feature 395871: WWTS front-end CRM TT support (Bob) 14.3 | EA 14.3 | Done | 1
1008140 | #395871 | Story | Feature 395871: WWTS front-end CRM TT support (Bob) 14.2 | EA 14.2 | Done | 1
1008138 | #395871 | Story | Feature 395871: WWTS front-end CRM TT support (Bob) 14.1 | EA 14.1 | Done | 1
1008134 | #384036 | Story | Feature 384036: Update and Review the Nutanix SVD | EA 14.3 | Done | 2
1008118 | #1000847 | Story | Configure IIS on cwapp205 for MUOSRel migration | EA 14.1 | Done | 3
1008115 | #1006376 | Story | Feature 1006376: Review MAMA2 source code (for Ty) | EA 14.4 | Done | 2
1008110 | #381524 | Story | Feature 381524 PB: Fix Problem 381547 - Part 3 | EA 14.4 | Done | 3 | #381547
1008103 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - ILS Impacts Section | EA 15.1 | Done | 3
1008088 | #392743 | Story | Feature 392743 ATO: Provide Deployment Notes and Operator Impact Inputs | EA 14.3 | Done | 1
1008087 | #1016383 | Story | Feature 1016383: Whitelist: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 2
1008081 | #354174 | Story | Feature 354174 HA IETM: Placeholder for any missing procedures (IETM, troubleshooting, recovery) - part 4 | PI 14 | Invalid | 0
1008080 | #354174 | Story | Feature 354174 HA IETM: Placeholder for any missing procedures (IETM, troubleshooting, recovery) - part 3 | PI 14 | Invalid | 0
1008079 | #354174 | Story | Feature 354174 HA IETM: Placeholder for any missing procedures (IETM, troubleshooting, recovery) - part 2 | PI 14 | Invalid | 0
1008074 | #1015911 | Task | Feature 1015911: Submit PDO for RNC CI: 98-P53511T-GTS-RN-RNC-SVD | PI 16 | New
1008072 | #384036 | Story | Feature 384036:Create Nutanix Sizing model | EA 14.3 | Done | 3
1008071 | #384036 | Story | Feature 384036: Develop Nutanix and Cisco Switch Deployment Plan to prevent outages | EA 14.2 | Invalid | 0
1008069 | #387448 | Story | Generate Essential Documents Drawing Tree | EA 14.4 | Done | 1
1008068 | #387448 | Story | Generate Essential Documents Drawing Tree | EA 14.3 | Done | 1
1008067 | #387448 | Story | Generate Essential Documents Drawing Tree | EA 14.2 | Done | 1
1008066 | #387448 | Story | Update P2P Communication Call Flows | EA 14.5 | Done | 3
1008065 | #387448 | Story | Update P2P Communication Call Flows | EA 14.3 | Invalid | 0
1008064 | #387448 | Story | Update P2P Communication Call Flows | EA 14.2 | Done | 2
1008063 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort Part 3 | EA 14.3 | Done | 2
1008062 | #388053 | Story | Design PPA Replacement (Support) | EA 14.4 | Invalid | 0
1008061 | #388053 | Story | Design PPA Replacement | EA 14.3 | Done | 1
1008060 | #388053 | Story | Design PPA Replacement | EA 14.4 | Done | 5
1008059 | #388053 | Story | Design PPA Replacement | EA 14.3 | Done | 5
1008058 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SE) | EA 14.4 | Invalid | 0
1008057 | #387448 | Story | Update P2P Communication Call Flows | EA 14.5 | Done | 2
1008056 | #373090 | Story | Monthly Analysis and Reporting | EA 14.4 | Invalid | 0
1008055 | #343920 | Task | Story 343920: CM Release of 99-P57050M - NMS - NM Common PKI (EAD 16) | PI 14 | New
1008054 | #388053 | Story | Design FCAPS Replacement | PI 15 | Invalid | 0
1008053 | #388053 | Story | Design FCAPS Replacement | EA 14.4 | Done | 3
1008052 | #388053 | Story | Design FCAPS Replacement | EA 15.2 | Done | 5
1008051 | #379761 | Story | FM Whitelist updates for PI 14 (1st release): Identify Whitelist content (Systems) | EA 14.2 | Done | 1
1008050 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Architecture Lead | EA 14.4 | Done | 2
1008049 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtN | EA 14.4 | Done | 2
1008048 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ External Network (data, voice) | EA 14.4 | Done | 1
1008047 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Acquisition & Registration (AES) | EA 14.4 | Done | 1
1008046 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtP | EA 14.4 | Done | 1
1008045 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtP | EA 14.2 | Done | 2
1008043 | #368860 | Story | Feature 368860: Canada Cost Estimate ~ GDS | EA 14.3 | Done | 1
1008042 | #368860 | Story | Feature 368860: Canada Cost Estimate ~ GDS | EA 14.2 | Done | 1
1008041 | #368860 | Story | Feature: 368860 Cost Estimate ~ FCAPS | EA 14.4 | Invalid | 0
1008040 | #368860 | Story | Feature: 368860 Cost Estimate ~ FCAPS | EA 14.2 | Invalid | 0
1008039 | #368860 | Story | Feature: 368860 Cost Estimate ~ FCAPS | EA 14.1 | Done | 1
1008038 | #1007569 | Story | Feature 1007569: Technical Interchange Meeting (TIM) attendance 14.4 | EA 14.4 | Invalid | 0
1008037 | #1001636 | Story | 6) Create PWIs for Priority CAT1s (Part 1) | EA 14.3 | Done | 1
1008036 | #1007569 | Story | Feature 1007569: Technical Interchange Meeting (TIM) attendance 14.4 | EA 14.4 | Invalid | 0
1008035 | #395373 | Story | Support PMW During ATO Approval Process - 14.4 | EA 14.4 | Done | 1
1008034 | #395373 | Story | Support PMW During ATO Approval Process - 14.3 | EA 14.3 | Done | 1
1008033 | #395373 | Story | Support PMW During ATO Approval Process - 14.2 | EA 14.2 | Done | 1
1008032 | #1007569 | Story | Feature 1007569: Cyber support for enhanced alt-telemetry | EA 14.3 | Done | 1
1008028 | #395373 | Story | Polatis Switch Rework | EA 14.4 | Done | 1
1008026 | #395373 | Story | Develop Scan Assessment Guidance document-Part 1 (Feature 395373 Cyber Sustainment Activities) | EA 14.4 | Done | 3
1008025 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid
1008024 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1008023 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1008015 | #390286 | Story | Feature 390286: Verify GPO Changes in VLAB and Test | EA 14.3 | Done | 3
1008013 | #390286 | Story | Feature 390286: Apply Update to GPO in VLAB | EA 14.1 | Done | 1
1008003 | #396819 | Story | Feature 396819: TPM Resolve DB101 in VLAB | EA 14.3 | Done | 3
1007999 | #389549 | Story | Support PPA | EA 14.1 | Done | 3
1007991 |  | Problem | 98-P59401M RevP NM Backup and Archive (EAD-15) still has bogus instances that were removed during R2.1 Tech Refresh | Unassigned | Assessing
1007989 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Information Assurance Design - Continued from PI 14.4 [14.5] | EA 14.5 | Done | 2
1007988 | #385442 | Story | Feature 385442: Capabilities Specification - Information Assurance Design - Placeholder for ETI effort - IA - Continued from 14.3 [14.4] | EA 14.4 | Done | 2
1007987 | #385442 | Story | Feature 385442: Capabilities Specification - Information Assurance Design - Placeholder for ETI effort - IA - Continued from 14.2 [14.3] | EA 14.3 | Done | 2
1007976 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis - Waveform | EA 14.1 | Done | 1
1007933 | #1001912 | Story | Feature 1001912: WF PWI burndown - Leslie | EA 14.4 | Done | 3
1007932 | #1001912 | Story | Feature 1001912: WF PWI burndown - Leslie | EA 14.3 | Done | 2
1007931 | #1001912 | Story | Feature 1001912: WF PWI burndown - Leslie | EA 14.2 | Done | 2
1007930 | #1001912 | Story | Feature 1001912: WF PWI burndown - Leslie | EA 14.1 | Done | 2
1007929 | #377408 | Story | Feature 377408: Provide Deployment Notes and Operator Impact Inputs | EA 14.4 | Done | 1
1007928 | #1001912 | Story | Feature 1001912: WF PWI burndown - Ty | EA 14.1 | Done | 3
1007927 | #1001912 | Story | Feature 1001912: WF PWI burndown - Ty | EA 14.2 | Done | 2
1007926 | #1001912 | Story | Feature 1001912: WF PWI burndown - Ty | EA 14.3 | Done | 2
1007925 | #1001912 | Story | Feature 1001912: WF PWI burndown - Ty | EA 14.4 | Done | 2
1007924 | #1001912 | Story | Feature 1001912: WF PWI burndown - Sang | EA 14.4 | Done | 5
1007923 | #384036 | Story | Feature 384036: Upgrade V-Lab to Support Nutanix Solution | EA 14.5 | Invalid | 0
1007922 | #384036 | Story | Feature 384036: Upgrade V-Lab to Support Nutanix Solution | EA 14.5 | Invalid | 0
1007921 | #1001912 | Story | Feature 1001912: WF PWI burndown - Sang | EA 14.3 | Done | 5
1007920 | #384036 | Story | Feature 384036: Upgrade V-Lab to Support Nutanix Solution | EA 14.2 | Done | 1
1007919 | #1001912 | Story | Feature 1001912: WF PWI burndown - Sang | EA 14.2 | Done | 5
1007918 | #1001912 | Story | Feature 1001912: WF PWI burndown - Sang | EA 14.1 | Done | 5
1007917 | #1001912 | Story | Feature 1001912: WF PWI burndown - Loretta | EA 14.1 | Done | 3
1007916 | #1001912 | Story | Feature 1001912: WF PWI burndown - Loretta | EA 14.2 | Done | 3
1007915 | #1001912 | Story | Feature 1001912: WF PWI burndown - Loretta | EA 14.2 | Done | 3
1007914 | #1001912 | Story | Feature 1001912: WF PWI burndown - Loretta | EA 14.4 | Done | 5
1007909 | #1001912 | Story | Feature 1001912: WF PWI burndown - Hy | EA 14.4 | Done | 3
1007907 | #1001912 | Story | Feature 1001912: WF PWI burndown - Hy | EA 14.3 | Done | 2
1007906 | #1001912 | Story | Feature 1001912: WF PWI burndown - Hy | EA 14.2 | Done | 2
1007905 | #1001912 | Story | Feature 1001912: WF PWI burndown - Hy | EA 14.1 | Done | 2
1007904 | #1001912 | Story | Feature 1001912: WF PWI burndown | EA 14.3 | Done | 2
1007903 | #1001912 | Story | Feature 1001912: WF PWI burndown - Yue-Chain | EA 14.2 | Done | 3
1007902 | #1001912 | Story | Feature 1001912: WF PWI burndown | EA 14.2 | Done | 3
1007901 | #1001912 | Story | Feature 1001912: WF PWI burndown - Yue-Chain | EA 14.3 | Done | 3
1007900 | #384135 | Feature | OBS - HBSS: Prepare HBSS for Deployment to Site | PI 16 - In Progress | Implementing
1007899 | #1001912 | Story | Feature 1001912: WF PWI burndown - Anton | EA 14.4 | Done | 5
1007898 | #1001912 | Story | Feature 1001912: WF PWI burndown - Anton | EA 14.3 | Done | 5
1007897 | #1001912 | Story | Feature 1001912: WF PWI burndown - Anton | EA 14.2 | Done | 5
1007896 | #1001912 | Story | Feature 1001912: WF PWI burndown - Anton | EA 14.1 | Invalid | 0
1007895 | #1001912 | Story | Feature 1001912: WF PWI burndown - Tim | EA 14.1 | Done | 2
1007894 | #1001912 | Story | Feature 1001912: WF PWI burndown - Tim | EA 14.4 | Done | 5
1007893 | #1001912 | Story | Feature 1001912: WF PWI burndown - Tim | EA 14.3 | Done | 5
1007891 | #1001912 | Story | Feature 1001912: WF PWI burndown - Tim | EA 14.2 | Done | 3
1007890 | #1001912 | Story | Feature 1001912: WF PWI burndown - Tim | EA 14.1 | Invalid | 0
1007877 | #342054 | Story | Feature 342054:Redline verification and re-run for AWARE alignment procedure installation section | EA 15.5 | New | 3
1007875 | #384136 | Story | Feature 384136:Update based on redlines and configuration updates MUOS_IG_GS_Firewall_Network_SVD_98-P55755M Firewalls, LB, and Router, Switch to meet new IP address for ePO 200 and 201 | EA 14.3 | Done | 2
1007874 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.5 | EA 14.5 | Invalid | 0
1007873 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.5 | EA 14.5 | Invalid | 0
1007872 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.4 | EA 14.5 | Invalid | 0
1007871 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.4 | EA 14.5 | Invalid | 0
1007870 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.3 | EA 14.5 | Invalid | 0
1007869 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.3 | EA 14.4 | Invalid | 0
1007868 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.2 | EA 14.4 | Invalid | 0
1007867 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.2 | EA 14.4 | Invalid | 0
1007866 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.1 | EA 14.5 | Invalid | 0
1007865 |  | Story | Feature 1007569: ROM support (eval, creation, update, review, pricing 14.1 | EA 14.4 | Invalid | 0
1007864 | #1007569 | Story | Feature 1007569: Technical Interchange Meeting (TIM) attendance 14.2 | EA 14.2 | Done | 3
1007863 | #1007569 | Story | Feature 1007569: Technical Interchange Meeting (TIM) attendance 14.1 | EA 14.1 | Done | 3
1007862 |  | Story | Feature 1007569: SME tool support 14.5 | EA 14.5 | Invalid | 0
1007861 |  | Story | Feature 1007569: SME tool support 14.4 | EA 14.4 | Invalid | 0
1007860 |  | Story | Feature 1007569: SME tool support 14.3 | EA 14.3 | Invalid | 0
1007859 |  | Story | Feature 1007569: SME tool support 14.2 | EA 14.2 | Invalid | 0
1007858 |  | Story | Feature 1007569: SME tool support 14.1 | EA 14.1 | Invalid | 0
1007857 | #1007569 | Story | Feature 1007569: SME CONOPS support for enhanced alt-telemetry 14.5 | EA 14.5 | Done | 1
1007856 | #1007569 | Story | Feature 1007569: SME CONOPS support for enhanced alt-telemetry 14.4 | EA 14.4 | Invalid | 0
1007855 | #1007569 | Story | Feature 1007569: SME CONOPS support for enhanced alt-telemetry 14.3 | EA 14.3 | Invalid | 0
1007854 | #1007569 | Story | Feature 1007569: SME CONOPS support for enhanced alt-telemetry 14.2 | EA 14.2 | Done | 1
1007853 | #1007569 | Story | Feature 1007569: SME CONOPS support for enhanced alt-telemetry 14.1 | EA 14.1 | Done | 1
1007852 |  | Story | Feature 1007569: System Engineer support and IETM update plan 14.3 | EA 14.1 | Invalid | 0
1007851 |  | Story | Feature 1007569: System Engineer support and IETM update plan 14.2 | EA 14.1 | Invalid | 0
1007850 |  | Story | Feature 1007569: System Engineer support and IETM update plan 14.1 | EA 14.1 | Invalid | 0
1007849 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.5 | EA 14.5 | Done | 2
1007848 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.5 | EA 14.5 | Done | 2
1007847 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.5 | EA 14.5 | Done | 2
1007846 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.4 | EA 14.4 | Done | 2
1007845 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.4 | EA 14.4 | Done | 2
1007844 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.4 | EA 14.4 | Done | 3
1007843 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.3 | EA 14.3 | Done | 2
1007842 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.3 | EA 14.3 | Done | 2
1007841 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.3 | EA 14.3 | Done | 2
1007840 | #384136 | Story | Feature 384136:Update based on redlines and configuration updates: Firewall_Network_SVD_98-P55755M, Load Balancer LB_SVD_98-P55464M, Router_SVD_98-P55509M to incorporate updates to Nutanix Environment and the HBSS DMZ to SIPR | EA 14.2 | Done | 3
1007839 | #384136 | Story | Feature 384136: Cisco switch SVD configuration and review for Nutanix and HBSS | EA 14.2 | Done | 2
1007838 | #1006376 | Story | Feature 1006376: Review MAMA2 source code (for Katy) | EA 14.4 | Done | 1
1007837 | #1006376 | Story | Feature 1006376: Review MAMA2 source code (for Yu-Ling) | EA 14.4 | Done | 2
1007836 | #342054 | Story | Feature 342054: Build Spare RF Tray #2 for Connected AWARE SC | EA 15.3 | Done | 3
1007835 | #342054 | Story | Feature 342054: Build Spare RF Tray #1 for Connected AWARE SC | EA 14.2 | Done | 2
1007833 | #342054 | Story | Feature 342054: Build Spare RF Tray #1 for Connected AWARE SC | EA 15.3 | Done | 3
1007831 | #395174 | Story | Feature 395174: Analyze AIU; ANTENNA INTERFACE UNIT 21: SN TR46519365 for SR 1100783 / G3129 | EA 14.2 | Done | 1
1007830 | #395174 | Story | Feature 395174: Analyze AIU; ANTENNA INTERFACE UNIT 21: SN TR46519368 for SR 1099903 / G3128 | EA 14.2 | Done | 1
1007829 | #395174 | Story | Feature 395174: Analyze AIU; ANTENNA INTERFACE UNIT 21: SN TR46519363 for SR 1099870 / G3127 | EA 14.2 | Done | 1
1007828 | #395174 | Story | Feature 395174: Analyze AIU; ANTENNA INTERFACE UNIT 21: SN TR47409354 for SR 1093147 / G3095 | EA 14.1 | Done | 1
1007827 | #1000204 | Story | Release Regression - NMS Automation (xx.3) | EA 14.3 | Done | 1
1007826 |  | Problem | MUOSAT-MH: AWARE - Mobility timeouts can sometimes cause MultiHAL to hang | Unassigned | Assessing
1007824 | #384136 | Story | Feature 384136:Update MUOS_IG_GS_Network_ExtremeSwitch_SVD_98-P59856M Firewalls to meet new IP address for ePO 200 and 201 | EA 14.1 | Invalid | 0
1007821 | #1006376 | Story | Feature 1006376: Unit testing of MAMA2 cell selection functions | EA 14.3 | Done | 3
1007810 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Perform Iterative Implementation, Integration, and development.- part 4 | EA 14.4 | Done | 3
1007808 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Perform Iterative Implementation, Integration, and development.- part 2 | EA 14.2 | Done | 5
1007804 | #383168 | Story | Feature 383168 Completion of Base Electronic System Engineer Plan BESEP (needed 120 days prior to FRCB) | EA 14.1 | Done | 2
1007803 | #383168 | Story | Feature 383168 Generate Test Report, needed 45 days prior to FRCB. | EA 14.4 | Done | 3
1007802 | #383168 | Story | Feature 383168 Complete System Operational Verification Test, SOVT, needed 90 days prior to FRCB | EA 14.3 | Done | 2
1007801 | #383168 | Story | Feature 383168 Generate System Operational Verification Test, SOVT, Test Inputs for Feature | EA 14.3 | Done | 2 | #1007802
1007800 | #383168 | Story | Feature 383168 Create Redlines on Hardware Drawings Submitted for IDP (Template for HW/FRCB Deployable Feature) | EA 14.1 | Invalid | 0 | #1007798
1007799 | #383168 | Story | Feature 383168 Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | EA 14.1 | Invalid | 0 | #1007798
1007798 | #383168 | Story | Feature 383168 Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 120 days prior to FRCB; | EA 14.1 | Done | 3
1007797 | #383168 | Story | Feature 383168 Identify Logistics Considerations (non-IETM) for Site Power Changes for Nutanix | EA 14.4 | Done | 1
1007796 |  | Feature | <Feature xxx> HW/FRCB Template | Unassigned | Rejected
1007790 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 5 - Week 2 | EA 14.5 | Done | 2
1007789 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 4 - Week 2 | EA 14.4 | Done | 2
1007787 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 3 - Week 2 | EA 14.3 | Done | 2
1007784 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 2 - Week 2 | EA 14.2 | Done | 2
1007783 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 1 - Week 2 | EA 14.1 | Done | 2
1007780 | #342054 | Story | Feature 342054:Redline verification and re-run for AWARE alignment procedure installation section | EA 15.4 | New | 2
1007775 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 14.5 | Done | 3
1007773 |  | Problem | PPA User is incorrectly prevented from logging on to an application server. | Unassigned | Assessing
1007770 | #392743 | Story | Feature 392743: Fix problem 354579 - part 2 | EA 14.1 | Done | 5 | #1008605
1007769 | #392743 | Story | Feature 392743: Fix problem 354579 - part 1 | EA 14.1 | Done | 5
1007768 | #388053 | Story | Support design of PPA - (UX) part 3 | EA 14.3 | Done | 5
1007767 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems | EA 14.4 | Done | 3
1007766 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems | EA 14.3 | Done | 3
1007765 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems | EA 14.3 | Done | 3
1007764 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems | EA 14.2 | Done | 3
1007763 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems | EA 14.2 | Done | 3
1007762 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis | EA 14.1 | Done | 1
1007761 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis | EA 14.1 | Done | 1
1007760 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis | EA 14.1 | Done | 1
1007759 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis - Waveform | EA 14.2 | Invalid | 0
1007757 |  | Problem | Firewall reports WH aware servers sending messages to inf101-wh-nma on multiple ports. Policy does not support this activity. It looks like a network flood. | Unassigned | Assessing
1007753 | #1007536 | Story | Feature 1007536: Review 2-factor "Trade Study" - Feature Lead | EA 14.1 | Done | 2 | #1008231
1007751 | #1007536 | Story | Feature 1007536: Review 2-factor "Trade Study" - Developer #2 | EA 14.1 | Done | 2 | #1008231
1007748 | #1007536 | Story | Feature 1007536: Review 2-factor "Trade Study" - Developer #1 | EA 14.1 | Done | 2 | #1008231
1007743 | #279283 | Story | Lab - TXO Test Procedure Validation - CSCF/HSS - PM Board | EA 14.3 | Done | 1
1007742 | #279283 | Story | Lab - TXO Test Procedure Validation - CSCF/HSS - PMD Board | EA 14.3 | Done | 1
1007741 | #279283 | Story | Lab - TXO Test Procedure Validation - ATM- 4 Port OC-3 Board | EA 14.4 | Done | 1
1007740 | #279283 | Story | Lab - TXO Test Procedure Validation - SGSN - IBS7V3 Board | EA 14.2 | Done | 1
1007739 | #279283 | Story | Lab - TXO Test Procedure Validation - SGSN - GPBV3 Board | EA 14.1 | Done | 1
1007737 | #279283 | Story | Lab - TXO Test Procedure Validation - GGSN - 4 Port Ethernet Board | EA 14.4 | Done | 1
1007736 | #279283 | Story | Lab - TXO Test Procedure Validation - RNC - ET-M4 Board | EA 14.2 | Done | 1
1007735 | #279283 | Story | Lab - TXO Test Procedure Validation - SGSN - IBASV3 Board | EA 14.1 | Done | 1
1007734 | #395855 | Story | Feature 395855: Support Drwg Updates for Problem 321745 and Problem 1005849 | EA 14.2 | Done | 1
1007732 | #279283 | Story | Lab - TXO Test Procedure Validation - RBS - AIU Board | EA 14.1 | Done | 2
1007729 | #279283 | Story | Lab - TXO Test Procedure Validation - RBS - SCB3 Board | EA 14.2 | Done | 1
1007728 | #279283 | Story | Lab - TXO Test Procedure Validation- RBS - GPB51 Board | EA 14.1 | Done | 1
1007720 | #385856 | Story | Feature 385856: Create ROM and Notional Schedule - Hy | EA 14.1 | Done | 1
1007694 | #377437 | Story | Feature 377437 ETT: Update Gen2 Laptop SVD | EA 14.4 | Done | 3 | #1004266
1007683 | #385442 | Story | Feature 385442: Capabilities Design Specification and Detailed Design Documentation - Integration and Test Strategy [14.1] | EA 14.1 | Done | 2
1007628 | #1005740 | Story | Produce the Capability Spec document | EA 14.4 | Done | 3
1007627 | #1005740 | Story | Lead DSN GW Obs work | EA 14.4 | Done | 3
1007618 |  | Problem | I level reports OSS-RC Troubleshooting IETM needs adjustment in regards to FM Probe Restart | Unassigned | Assessing
1007607 | #385856 | Story | Feature 385856: Conversion to ACC - IA Support Part 2 Continued | EA 14.3 | Done | 1
1007606 | #385856 | Story | Feature 385856: Conversion to ACC - IA Support Part 2 Continued | EA 14.2 | Done | 1
1007605 | #384136 | Story | Feature 384136: PCR Verification for SVD Updates Second Story | EA 14.5 | Done | 1
1007604 | #385856 | Story | Feature 385856: ACC Test input Continued | EA 14.2 | Done | 1
1007603 | #384136 | Story | Feature 384136: PCR Verification for SVD Updates. | EA 14.4 | Done | 3
1007596 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.2 | EA 14.2 | Done | 1
1007595 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.2 | EA 14.2 | Done | 1
1007594 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.2 | EA 14.2 | Done | 1
1007593 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.1 | EA 14.1 | Done | 1
1007588 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.1 | EA 14.1 | Done | 1
1007587 | #1007569 | Story | Feature 1007569: SME support for enhanced alt-telemetry (attend reviews, update IETM plan, tool support, etc.) 14.1 | EA 14.1 | Done | 2
1007585 |  | Story | Feature 1007569: TD Kickoff - SME preparation and participation 14.1 | EA 14.1 | Invalid | 0
1007580 |  | Story | Feature 1007569: TD Kickoff - SME preparation and participation 14.1 | EA 14.1 | Invalid | 0
1007579 |  | Story | Feature 1007569: TD Kickoff - SME preparation and participation 14.1 | EA 14.1 | Invalid | 0
1007576 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 1 - Week 1 | EA 14.1 | Done | 5
1007569 | #243422 | Feature | TD 20-06: MUOS space support enhanced alternate telemetry (part 1 of 2) | EA 14.5 | Done
1007544 |  | Story | Feature 1007536: Design 2 Factor Authentication | Unassigned | Invalid | 0
1007543 | #1007536 | Story | Feature 1007536: Design 2 Factor Authentication | PI 15 | Invalid | 0
1007542 | #1007536 | Task | Feature 1007536: 2 Factor Authentication Plan for Capabilities Specification and CONOPS | EA 14.5 | Done
1007541 | #1001912 | Problem | Targeted cell search results do not contain enough information for the MAMA Request. | EA 15.1 | Closed
1007536 | #1004098 | Feature | WinOBS: Create a Development Concept/Architecture for 2-Factor Authentication (2-FA) | PI 16 - In Progress | Implementing
1007490 | #1004171 | Story | Feature 1004171: Code walk through of solutions - Bob | EA 14.3 | Done | 1
1007486 | #1004171 | Story | Feature 1004171: Code walk through of solutions - Yu-ling | EA 14.3 | Done | 2
1007473 | #385856 | Story | Feature 385856: Waveform Conversion to ACC - SME Continued | EA 14.2 | Done | 1
1007472 | #385856 | Story | Feature 385856: Waveform Conversion to ACC - HAIPE Continued | EA 14.2 | Done | 5
1007467 | #386935 | Story | Feature 386935: Geolocation - Evaluate options to transfer Ephemeris data to SIPRNET - Part 3 | EA 14.3 | Done | 1
1007466 | #386935 | Story | Feature 386935: Geolocation - Evaluate options to transfer Ephemeris data to SIPRNET - Part 2 | EA 14.2 | Done | 1
1007443 | #396819 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(14.5) | EA 14.5 | Done | 1
1007442 | #396819 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(14.4) | EA 14.4 | Done | 1
1007441 | #396819 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(14.3) | EA 14.3 | Done | 1
1007440 | #396819 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(14.2) | EA 14.2 | Done | 1
1007437 | #396819 | Story | Lab - Maintain Labs - RBS / RNC Network debug, recovery and repair - Reynolds(14.1) | EA 14.1 | Done | 1
1007435 | #384136 | Story | Feature 384136: OBS HBSS- Review IETMs for Style Guide Compliance (EA 14.5) | EA 14.5 | Done | 5
1007434 | #384136 | Story | Feature 384136: OBS HBSS- Review IETMs for Style Guide Compliance (EA 14.4) | EA 14.4 | Done | 8
1007433 | #384136 | Story | Feature 384136: OBS HBSS- Review IETMs for Style Guide Compliance (EA 14.3) | EA 14.3 | Done | 5
1007432 | #384136 | Story | Feature 384136: OBS HBSS- Review IETMs for Style Guide Compliance (EA 14.2) | EA 14.2 | Done | 5
1007431 | #1007900 | Story | Feature 1007900: Incorporation of IETM Updates and Integration Support for OBS - HBSS: Development, Integration, and Testing of Production HBSS Solution into VLab (EA 15.5) | PI 16 | New | 2
1007430 | #1007900 | Story | Feature 1007900: Incorporation of IETM Updates and Integration Support for OBS - HBSS: Development, Integration, and Testing of Production HBSS Solution into VLab (EA 15.4) | EA 15.4 | Implementing | 2
1007429 | #1007900 | Story | Feature 1007900: Incorporation of IETM Updates and Integration Support for OBS - HBSS | EA 15.3 | Done | 5
1007428 | #1007900 | Story | Feature 1007900: Incorporation of IETM Updates and Integration Support for OBS - HBSS: Development, Integration, and Testing of Production HBSS Solution into VLab (EA 15.2) | EA 15.2 | Done | 5
1007390 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Update RAF P2P Failure Rules - Sprint 4 | EA 14.4 | Invalid | 0
1007389 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Update RAF P2P Failure Rules - Sprint 3 | EA 14.4 | Invalid | 0
1007388 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Update RAF P2P Failure Rules - Sprint 2 | EA 14.5 | Done | 3
1007387 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Update RAF P2P Failure Rules - Sprint 1 | EA 14.4 | Done | 1
1007383 | #297335 | Story | RDE BuildForge - Complete test of Build Forge RNC Build (all 24 groups) | EA 15.1 | Done | 8
1007381 | #354174 | Story | Feature 354174 HA IETM: Placeholder for any missing procedures (IETM, troubleshooting, recovery) -part 1 | PI 14 | Invalid | 0
1007380 | #354174 | Story | Re-check Splunk HA procedure needs (IETM, troubleshooting, recovery) | PI 14 | Invalid | 0
1007360 | #395871 | Story | Feature 395871: PI 14 SA TT Support - cleanup of “stuck” profiles - part 2 MPC admin | EA 14.3 | Done | 2
1007357 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.3 | Done | 1
1007356 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.3 | Done | 1
1007355 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - BFDBN 509 01/1 FAN x 1 | EA 15.3 | Done | 1
1007354 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 1 | EA 15.4 | New | 1
1007353 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.4 | New | 1
1007352 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.2 | Done | 1
1007351 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.4 | New | 1
1007350 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.2 | Done | 1
1007349 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.2 | Done | 1
1007329 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid
1007328 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007327 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007318 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid
1007317 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007316 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007299 | #1004094 | Story | Feature 1004094: Support Common Design for use of Passwords and Credential Management (UX) | PI 17 | New | 1
1007298 | #1004094 | Story | Feature 1004094: Support Common Design for use of Passwords and Credential Management (UX) | PI 17 | New | 2
1007297 | #1004094 | Story | Feature 1004094: Determine HW/SW vendor for Credential Management | PI 17 | New | 5
1007296 | #1004094 | Story | Feature 1004094: Determine HW/SW vendor for Single Sign-on | PI 17 | New | 5
1007295 | #1007536 | Story | Feature 1007536: Determine HW/SW vendor for 2-factor | EA 14.5 | Done | 5 | #1011627
1007294 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation (John Herzberg, KinetX) | EA 14.4 | Done | 5
1007293 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIMs, Scenario Simulations Analysis & Documentation (John Herzberg, KinetX) | EA 14.3 | Done | 5
1007292 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation (John Herzberg, KinetX) | EA 14.2 | Done | 5
1007291 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation (John Herzberg, KinetX) | EA 14.1 | Done | 5
1007290 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (Larry Jordan, KinetX) | EA 14.4 | Done | 5
1007289 | #388549 | Story | Feature 388549: ULX Detailed Design - Update Sequence Diagrams, Connections to Data Store/Mgr, Switchover) | EA 14.3 | Done | 5
1007285 | #388549 | Story | Feature 388549: ULX Detailed Design - RF Processor (External Interfaces, Reqts, SOW for RINCON, Config, SA/FM, Test Pts, Test Plan) | EA 14.2 | Done | 5
1007284 | #388549 | Story | Feature 388549: ULX Detailed Design - FM/Logging (Systems Design, Component Diagrams, Intelligent Processing) & Channel Processor | EA 14.1 | Done | 5
1007283 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Tom Bowie, SME LOE) | EA 14.4 | Done | 1
1007282 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Tom Bowie, SME LOE) | EA 14.3 | Done | 1
1007270 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Tom Bowie, SME LOE) | EA 14.2 | Done | 1
1007269 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Tom Bowie, SME LOE) | EA 14.1 | Done | 1
1007262 | #1006376 | Story | Feature 1006376: Execute Tests - Part C | EA 15.3 | Done | 1
1007261 | #1006376 | Story | Feature 1006376: Execute Tests - Part B | EA 15.2 | Done | 2
1007260 | #1006376 | Story | Feature 1006376: Execute Tests - Part A | EA 15.1 | Done | 2 | #1007255
1007259 | #1006376 | Story | Feature 1006376: Monitor test logs - Part E | PI 15 | Invalid | 0
1007258 | #1006376 | Story | Feature 1006376: Monitor test logs - Part D | EA 15.4 | New | 3
1007257 | #1006376 | Story | Feature 1006376: Monitor test logs - Part C | EA 15.3 | Done | 1
1007256 | #1006376 | Story | Feature 1006376: Monitor test logs - Part B | EA 15.2 | Done | 1
1007255 | #1006376 | Story | Feature 1006376: Monitor test logs - Part A | EA 15.1 | Done | 1
1007254 | #1006376 | Story | Feature 1006376: Define test cases | EA 14.1 | Done | 2
1007250 |  | Problem | Update “NetMAC Monitor and Control System - Normal Operation Procedure” for style guide formatting | Unassigned | Triage
1007247 | #378000 | Problem | EAD14 Deployment: AWARE IETM Alarm summary does not match Netcool | EA 14.1 | Closed
1007246 | #342054 | Problem | MUOSAT-MH: AWARE - EAD14 Deployment - Common Group Key update caused AWARE failure | PI 16 | Implementing
1007245 |  | Problem | INC000004520973: NAVSOC HQ- Procedure updating for updating OAS SK scenario for relocated satellite | Unassigned | Assessing
1007243 |  | Problem | INC000004515469: NAVSOC HQ-OAS S-Band Thinning After Maneuvers | Unassigned | Assessing
1007242 |  | Problem | INC000004513895: NAVSOC HQ-OAS Variable For 30 day OD predictions | Unassigned | Assessing
1007234 |  | Problem | INC000004491712: NAVSOC HQ-OAS Not using correct thruster efficiency for relocation | Unassigned | Assessing
1007201 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RCG WH3 needs repair and restore | EA 14.1 | Done | 2
1007200 | #1007194 | Story | DSN GW: Develop Capability Design Document | PI 15 | Invalid | 0
1007199 | #1007194 | Story | DSN GW: Develop Capability Design Document | PI 15 | Invalid | 0
1007198 | #1007194 | Story | DSN GW: Develop Capability Design Document | PI 15 | Invalid | 0
1007194 | #216662 | Feature | OBS – DSN GW: Develop Capability Design Document | PI 15 - Candidate | Rejected
1007178 | #297335 | Story | Feature 297335: Developer Regression Test after transition | PI 14 | Invalid | 0
1007176 | #297335 | Story | Feature 297335: Developer verify RDE Developer Workstation (Solaris 10) | EA 14.5 | Done | 5
1007157 | #388549 | Story | Feature 388549: ULX Detailed Design - Monitor and Control (Systems Design, Component Diagrams, Sequence Diagrams | EA 14.2 | Done | 5
1007156 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (Scalability, Test Plan, Sequence Diagrams) | EA 14.3 | Done | 3
1007155 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (Photon Framework & uSvcs Detailed Design, FM/SA, Config, External Interfaces, Test Plan, Test Points) | EA 14.2 | Done | 3
1007139 | #378000 | Story | Feature 378000: Troubleshoot possible GCK issues after MPC implementation (if needed) | Unassigned | Invalid | 0
1007123 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. | EA 14.2 | Done | 5
1007118 | #379001 | Task | Re-apply Problem 390482 Task for Deployment : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid
1007117 | #379001 | Story | Re-write and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007116 | #379001 | Story | Rebase and Test Problem 390482 Story : JUNIT PWI MPC Rebase Automation Testing | Unassigned | Invalid | 0
1007107 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. Part 2 | EA 14.2 | Done | 8
1007106 | #392311 | Task | update MPC rebase to carry summary over to created workitems | Unassigned | Done
1007102 | #384036 | Story | Feature 384036: Update Nutanix Capability Design Document for Customer Review Meeting | EA 14.3 | Done | 3
1007101 | #384036 | Story | Feature 384036: Update CDD for Initial Customer Review Meeting | EA 14.1 | Done | 3
1007100 | #384036 | Story | Feature 384036: Prepare for Final Customer Review of Capability Design Document for Nutanix | EA 14.4 | Done | 2
1007099 | #384036 | Story | Feature 384036: Prepare for Initial Customer Review Meeting | EA 14.2 | Done | 3
1007092 | #384036 | Story | Feature 384036: SVD updates for Scripted OS installation | EA 14.2 | Done | 3
1007085 | #384036 | Story | Feature 384036: Pre-MFR 3 – Cyber Performs Final Cybersecurity Assessment for Scripted OS installation | EA 14.1 | Done | 3
1007066 | #379001 | Story | Rebase and Test Problem 1000411 Story: ETI Switchover Procedure Table 4 and Section 20 update | Unassigned | New | 2
1007061 | #1006376 | Story | Feature 1006376: Create Site validation plan | EA 15.1 | Done | 2
1007060 | #1006376 | Story | Feature 1006376: Create deployment notes and operational impacts | EA 15.4 | Implementing | 1
1007054 |  | Story | Review and perform the initial analysis of Capabilities Requirements and identify the list of changes for WF | PI 15 | Invalid | 0
1007053 |  | Story | Produce Test Documents | PI 15 | Invalid | 0
1007052 |  | Story | Finalize DSN GW design | PI 15 | Invalid | 0
1007051 | #396437 | Story | Update Documentation on Semaphore Usage to Pause CRON Jobs for Developer Audience | EA 14.2 | Done | 1
1007049 | #384136 | Story | Feature 384136: Update MUOS_IG_GS_NMS_NM_Security_GSKey_SVD_98-P59414M003 to update ePO 200 and 201 and remove 202 from this SVD | EA 14.3 | Done | 2 | #1007605
1007048 | #396415 | Story | Support Performance Evaluation of ABS iDeployIt | EA 14.4 | Invalid | 0
1007047 | #396415 | Story | HMS LOE Support for EA 14.5 | EA 14.5 | Done | 2
1007046 | #396415 | Story | HMS LOE Support for EA 14.4 | EA 14.4 | Done | 2
1007043 | #1005740 | Story | Produce the Capability Spec document | EA 14.4 | Invalid | 0
1007042 | #1005740 | Story | Produce the Capability Spec document | EA 14.3 | Done | 5
1007030 | #1006376 | Story | Feature 1006376: Implement review rework fixes | EA 14.4 | Done | 5 | #391361
1007029 | #1006376 | Story | Feature 1006376: Review MAMA2 source code (for Chad) | EA 14.4 | Done | 2
1007028 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. Part 3 | EA 14.3 | Done | 3
1007026 | #1006376 | Story | Feature 1006376: Implement fix for PWI 1006103 | EA 14.1 | Done | 2 | #1007029 #1007837 #1007838 #1008115
1007016 | #384036 | Story | Feature 384036: Define or update Nutanix Roles for RBAC and document in the Nutanix SVD | EA 14.1 | Done | 3
1007014 | #380808 | Story | Feature 384036: Install official Nutanix SW per the SVD in V-Lab | EA 15.1 | Invalid | 0
1007013 | #384036 | Story | Feature 384036: Install official Nutanix HW in SWIT lab | EA 14.2 | Done | 3
1007012 | #384036 | Story | Feature 384036: Document network in SWIT LAB | EA 14.1 | Done | 3
1007010 | #384036 | Story | Feature 384036: Deployment AAA/DNS for to support the Nutanix implementation | EA 14.3 | Done | 5
1007003 | #1000471 | Story | Implement Profile Portability: Waveform support of system integration | PI 17 | New | 8
1006996 | #380808 | Story | Feature 380808:VM backup procedure IETM development - Test IETM | PI 15 | Invalid | 0
1006994 | #380808 | Story | Feature 380808:VM backup procedure IETM development - Create IETM | PI 15 | Invalid | 0
1006992 | #384036 | Story | Feature 384036:VM backup procedure and policy development | EA 14.3 | Done | 3
1006982 | #384136 | Story | Feature 384136: MFR 3 – Develop Design updates based on initial STIG finding. | EA 14.3 | Done | 3
1006979 | #388076 | Story | Feature 388076: Do PWI work for Problem 347180 | EA 14.1 | Done | 1
1006978 | #388076 | Story | Feature 388076: Do PWI work for Problem 345802 | EA 14.1 | Done | 3
1006976 | #388076 | Story | Feature 388076: Do PWI work for Problem 345718 | EA 14.1 | Done | 3
1006975 | #388076 | Story | Feature 388076: Do PWI work for Problem 345715 | EA 14.3 | Done | 3
1006972 |  | Story | Feature 384136:Create configuration and SVD support MUOS_IG_GS_Network_LB_SVD_98-P55464M load balancer to incorporated updates to HBSS DMZ inside Nutanix Environment | EA 14.2 | Invalid | 0 | #1004857 #1007603
1006971 |  | Story | Feature 384136 OBS: Support the update to the MUOS_IG_GS_Network_Router_SVD_98-P55509M Routers rout203/204 and MUOS_IG_GS_Firewall_Network_SVD_98-P55755M to incorporated updated to DMZ with Nutanix | EA 14.1 | Invalid | 0 | #1004856 #1004858
1006970 | #343917 | Task | Story 343917: CM Release of 01-P53037E – SITE – MUOS ILS RAF Earth Terminal Test (ETT) Assembly (EAD 15) | EA 14.1 | Done
1006969 | #343917 | Task | Story 343917: CM Release of 01-P59548V – ILS – ILS LAPTOP GEN2 ASSEMBLY (EAD 15) | EA 14.1 | Done
1006955 | #379761 | Story | Feature 379761: Rebase Problem 1003754 - FM whitelist remove manpack radio link down alarms | EA 14.1 | Done | 1
1006953 | #379761 | Story | Feature 379761: Rebase Problem 1003717 - Update FM Whitelist for AHM_0007 and AHM_0009 | EA 14.2 | Done | 1
1006952 | #384136 | Story | Feature 384136: Rebuild ePO 5.10 to verify appendix A/B instructions and make redlines | EA 14.2 | Done | 2
1006951 |  | Story | Feature 342054: Closeout Review to rebase Gen1 and Gen2 Laptop CIs to incorporate SC site redlines | Unassigned | Invalid | 0
1006950 |  | Story | Feature 342054: Rebase Gen1 and Gen2 Laptop CIs to incorporate SC site redlines into the alignment procedure (Aidan) | Unassigned | Invalid | 0
1006949 |  | Story | Feature 342054: Rebase Gen1 and Gen2 Laptop CIs to incorporate SC site redlines into the alignment procedure (Nadolski) | Unassigned | Invalid | 0
1006948 | #1013259 | Story | Feature 1013259: Schedule coordination with Deployment Team for AWARE SC | PI 17 | New | 2
1006947 | #342054 | Story | Feature 342054: Create MPCs related to PWI 1009580 (EAD 14 release) | EA 14.3 | Done | 1
1006946 |  | Story | Feature 342054: MFT shipment prep (Comsec) and check status of remaing AWARE equipment | Unassigned | Invalid | 0
1006945 |  | Story | Feature 342054: Repeat the dry run of the AWARE alignment procedure installation section and AWARE Periodic Alignment section | Unassigned | Invalid | 0
1006944 |  | Story | Feature 342054: Repeat the dry run of the AWARE alignment procedure installation section and AWARE Periodic Alignment section | Unassigned | Invalid | 0
1006943 |  | Story | Feature 342054: Dry run and capture Redlines for AWARE alignment procedure installation section | Unassigned | Invalid | 0
1006942 | #342054 | Story | Feature 342054: Dry run and capture Redlines for AWARE alignment procedure installation section | EA 14.2 | Done | 1
1006941 |  | Story | Feature 342054: Define Equipment Deployment Plan | Unassigned | Invalid | 0
1006940 | #384136 | Story | Feature 384136: SVD Development to complete Appendix B and A for HBSS 5.10 ePO | EA 14.1 | Done | 5
1006939 | #1007900 | Story | Feature 1007900: Rebase mpc14.13 - Tectia Broker Service InstallAnywhere and SVD needs to be updated based on EAD14 deployment feedback | EA 15.2 | Done | 3
1006933 | #384036 | Story | Feature 384036: Test Nutanix and Cisco Switch Deployment Plan to prevent outages (1) | EA 14.5 | Invalid | 0
1006932 | #384036 | Story | Feature 384036: Develop Nutanix and Cisco Switch Deployment Plan to prevent outages | EA 14.2 | Done | 1
1006924 | #342054 | Story | Feature 342054: Travel paperwork back off date needed and work travel paperwork, training, etc. (Aidan) | PI 16 | New | 1
1006923 |  | Task | Feature 342054: Travel paperwork back off date needed and work travel paperwork, training, etc. (Konitzer) | Unassigned | Invalid
1006922 | #1013259 | Story | Feature 1013259: AWARE SC Travel paperwork back off date needed and work travel paperwork, training, etc. (Nadolski) | PI 17 | New | 2
1006921 | #342054 | Story | Feature 342054: Provide support to ILS (drawing releases, reviews) | Unassigned | Invalid | 0
1006920 |  | Story | Feature 342054: SC updates to AWARE SVD | Unassigned | Invalid | 0
1006917 | #342054 | Story | Feature 342054: Coordinate parts inventory/kitting | Unassigned | Invalid | 0
1006916 | #342054 | Story | Feature 342054: Calibrate AWARE RF tray SN003 | EA 14.4 | Done | 2
1006915 | #342054 | Task | Feature 342054: Obtain travel docs | EA 14.1 | Done
1006901 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Aidan) - Part 3 | PI 17 | New | 5
1006883 | #384036 | Story | Feature 384036: Create IETM Procedures for PM Data in PRISM GUI | EA 14.3 | Invalid | 0
1006882 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Aidan) - Part 2 | PI 17 | New | 5
1006881 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Engineer 2) - Part 3 | PI 17 | New | 5
1006880 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Engineer 2) - Part 2 | PI 17 | New | 5
1006879 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Hardware Installation - Part 2 | PI 17 | New | 5
1006877 | #384036 | Story | Feature 384036: PKI Deployment Plan | EA 14.4 | Done | 5
1006873 | #384036 | Story | Feature 384036: GSKM Updates | EA 14.3 | Done | 3 | #1006877
1006864 | #318430 | Story | AMP - Wrap-up common document updates for EAD 15 (Part 2 - Steve) | EA 14.1 | Done | 3
1006852 | #1006843 | Story | Determine Guard Update Process | EA 14.5 | Done | 5
1006851 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.4 | Done | 2
1006849 | #1006843 | Story | Determine Log/Data Files that Need to Pass Through Guard - SE | EA 14.5 | Done | 1
1006843 | #385420 | Feature | Define MUOS Guard Updates/Process for File Based Data | EA 14.5 | Done |  | #1007167
1006820 | #396415 | Story | Tools automation and metric Updates for EA 14.5 | EA 14.5 | Done | 2
1006819 | #396415 | Story | Tools automation and metric Updates for EA 14.4 | EA 14.4 | Done | 5
1006818 | #396415 | Story | Tools automation and metric Updates for EA 14.3 | EA 14.3 | Done | 5
1006817 | #396415 | Story | Tools automation and metric Updates for EA 14.2 | EA 14.2 | Done | 5
1006816 | #396415 | Story | Tools automation and Metric Updates for EA 14.1 | EA 14.1 | Done | 5
1006800 | #378000 | Story | Feature 378000: Support demo prep and Final demo - Ken | EA 14.1 | Done | 1
1006799 | #378000 | Story | Feature 378000: Support demo prep and Final demo | EA 14.1 | Done | 1
1006794 | #378000 | Story | Feature 378000: Demo Prep | EA 14.1 | Done | 2
1006792 | #388053 | Story | Feature 388053 PPA Obs: Support design of PPA - (SIC) part 3 | EA 14.3 | Done | 2
1006790 | #388053 | Story | Feature 388053 PPA Obs: Support design of PPA - (SIC) part 2 | EA 14.2 | Done | 2
1006787 | #1000471 | Story | Implement Profile Portability: Generate MUOS KMP Addendum | PI 17 | New | 8
1006780 | #396002 | Story | Geolocation - Evaluate options to transfer Ephemeris data to SIPRNET | EA 14.5 | Invalid | 0
1006763 | #342054 | Story | Feature 342054: Configure and test equipment going to site | PI 16 | New | 5
1006762 | #342054 | Story | Feature 342054: Burn-in time for the new radios to be deployed | EA 15.5 | New | 1
1006761 | #342054 | Story | Feature 342054: Move AWARE onto its own keyset to allow a compromise recovery | EA 14.1 | Done | 2
1006760 | #342054 | Story | Feature 342054: Move AWARE onto its own keyset to allow a compromise recovery | Unassigned | Invalid | 0
1006759 | #378000 | Story | Feature 378000: Troubleshoot USB adapter issue if Radio experiences a power loss (if needed) | Unassigned | Invalid | 0
1006758 | #378000 | Task | Feature 378000: Incorporate redlines for AWARE SVD (Problem 1003447) | EA 14.1 | Done
1006757 | #378000 | Story | Feature 378000: Fix Problem 1006756 - IETM Updates from AWARE EAD 14 Deployment | EA 14.1 | Done | 5
1006755 | #378000 | Story | Feature 378000: Fix Problem 1006754 - CGKey / compromise recovery scenario failures | Unassigned | Invalid | 0
1006750 | #378000 | Problem | AWARE Equipment Health down 6-8 minutes | EA 14.1 | Closed
1006741 | #1001912 | Story | Feature 1001912: MHAL: Adjust MultiHAL to work with WDE Group calls | EA 14.4 | Done | 8
1006730 | #395174 | Task | Feature 395174: TOFF - HW FRB Support EA 14.5 | EA 14.5 | Done
1006709 | #384136 | Story | Feature 384136: Perform STCD testing in VLAB by performing IETM, SVD and design instructions as developed by STCD (part 2 of 3) | EA 14.4 | Done | 3
1006708 | #384136 | Story | Feature 384136: Execute STCD Feature Integration and testing including STCD updates identified (part 2 of 2) | EA 14.2 | Done | 3
1006670 | #376446 | Story | Feature 376446: Regression Testing (MultiHAL) Pt.1 | EA 15.1 | Done | 3
1006669 | #376446 | Story | Feature 376446: Call Bank Specific Updates to MultiHAL | EA 15.1 | Done | 5
1006667 | #376446 | Story | Feature 376446: Regression Testing (MultiHAL) | EA 14.2 | Done | 3
1006654 | #376446 | Story | Feature 376446: Install and Configure AWARE Architecture on Second Server & Remaining VMs | EA 15.3 | Done | 5
1006622 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Finalize and Review document [15.2] | EA 15.2 | Done | 5
1006616 | #385442 | Story | Feature 385442: Capabilities Design Specification and Detailed Design Documentation - Deployment Strategy [14.2 ] | EA 14.2 | Done | 5
1006614 | #385442 | Story | Feature 385442: Capabilities Specification Documentation - Resource and Budget [15.1] | EA 15.1 | Done | 2
1006613 | #385442 | Story | Feature 385442: Capabilities Specification - Update Section 15&16 Development and Deployment Strategy - continued [14.4] | EA 14.4 | Done | 3
1006606 | #385442 | Story | Feature 385442:Capabilities Specification Documentation - Performance and Capacity [15.1] | EA 15.1 | Done | 3
1006605 | #385442 | Story | Feature 385442: Capabilities Specification Document section 8 System Level Management Design Concept [14.3] | EA 14.3 | Done | 5
1006604 | #385442 | Story | Feature 385442: Capabilities Specification - Interface Design, Risks and Constraints [14.4] | EA 14.4 | Done | 3
1006603 | #385442 | Story | Feature 385442: Capabilities Design Specification and Detailed Design Documentation - Information Assurance Design - Placeholder for ETI effort - IA [14.2] | EA 14.2 | Done | 2
1006598 | #385442 | Story | Feature 385442:Capabilities Specification - Problem Statement and Value Proposition [14.2] | EA 14.2 | Done | 2
1006597 | #385442 | Story | Feature 385442: Capabilities Specification - System Level Design Concept [14.4] | EA 14.4 | Done | 5
1006596 | #385442 | Story | Feature 38544:Capabilities Specification Documentation - Operational Concept and System Level Capability Objectives [14.3] | EA 14.3 | Done | 3
1006585 | #388053 | Story | Support design of PPA - (UX) part 4 | EA 14.4 | Done | 5
1006584 | #388053 | Story | Support design of PPA - (UX) part 5 | EA 14.5 | Done | 1
1006583 | #388053 | Story | Support design of PPA - (UX) part 2 | EA 14.2 | Done | 5
1006581 | #290711 | Story | Feature 290711: Implement PWIs | Unassigned | Invalid | 0
1006543 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - ROJ 208 452/1 PMD Printed Board Assembly x 2 | EA 14.3 | Done | 1
1006541 | #379221 | Story | Labs – TXO Ericsson – TEMP - Test Ericsson parts from second part of 2030 completion order - Additional Points required for the updated ordered list 25 points (2o Pts) | EA 14.3 | Invalid | 0
1006521 | #387448 | Story | Update P2P Communication Call Flows | EA 14.1 | Done | 2
1006519 | #388053 | Story | Design FCAPS Replacement | EA 14.1 | Done | 2
1006494 |  | Task | <Feature xxx> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid
1006493 |  | Task | <Feature xxx> Generate Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid
1006492 |  | Task | <Feature xxx> Complete System Operational Verification Test, SOVT, needed 90 days prior to FRCB | Unassigned | Invalid
1006491 |  | Task | <Feature xxx> Generate System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid |  | #1006492
1006490 |  | Task | <Feature xxx> Create Redlines on Hardware Drawings Submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid |  | #1006488
1006489 |  | Task | <Feature xxx> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid |  | #1006488
1006488 |  | Task | <Feature xxx> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 110 days prior to FRCB; | Unassigned | Invalid
1006487 |  | Task | <Feature xxx> Identify Logistics Considerations (non-IETM) (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid
1006482 | #378000 | Story | Feature 378000: Support to ILS Independent Testing of IETMs | EA 14.1 | Done | 3
1006480 | #378000 | Story | Feature 378000: Implement PWIs (1003161, 1004089, 1005797, 1006171, 1005794, 1006175) - from EAD 14 Informational MPCs | EA 14.1 | Done | 1
1006477 | #378000 | Story | Feature 378000: AWARE for SC IETM Updates - Independent Re-Test (if needed) | Unassigned | Invalid | 0
1006475 | #378000 | Story | Feature 378000: AWARE for SC IETM Updates - Re-work after independent testing (if needed) | Unassigned | Invalid | 0
1006474 | #378000 | Story | Feature 378000: AWARE for SC IETM Updates - Independent Test (Dry Runs) | EA 14.1 | Done | 5
1006471 |  | Feature | IMPLEMENTATION Investigate allowing ephemeris data available via DMZ to SIPRNET (need to create a deployment feature from template instead) | Unassigned | Rejected
1006461 | #1001912 | Problem | MILSTD: WF preserves the last known local mask when scanning is disabled | EA 15.1 | Closed
1006458 | #1006376 | Story | Build RNC for MAMA2 and Process ICM release | PI 14 | Invalid | 0
1006455 | #376446 | Story | Feature 376446: Update MultiHAL Web | EA 14.4 | Done | 3
1006454 | #376446 | Story | Feature 376446: IA Posture Improvement - Apply STIG Settings | EA 14.4 | Done | 3
1006453 | #376446 | Story | Call Bank Servers: IA Posture Improvement - Final Posture Assessment (Feature 376446) | EA 15.2 | Done | 2
1006452 | #386935 | Story | Feature 376446: IA Posture Improvement - AMS-GS Initial Assessment | EA 14.2 | Done | 2
1006450 | #376446 | Story | Feature 376446: Migrate current VMs to one server | EA 14.3 | Done | 1
1006447 | #376446 | Story | Feature 376446: Test PPP Driver | EA 14.4 | Done | 2
1006446 | #376446 | Story | Feature 376446: Develop PPP Driver/Configuration | EA 14.3 | Done | 5
1006438 | #1005343 | Task | Feature 1005343: Touch Point DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations (Apr 2020) | EA 14.5 | Done
1006437 | #1013452 | Story | Feature 1013452: Geo Ephemeris data push to SIPRNET - Update DMZ Firewalls | EA 15.2 | Done | 5
1006436 | #1013452 | Story | Feature 1013452: Geo Ephemeris data push to SIPRNET - Update Routers (may not be needed) | EA 15.4 | Invalid | 0
1006435 | #1013452 | Story | Feature 1013452: Geo Ephemeris data push to SIPRNET - Update DMZ Proxy load balancers (may not be needed) | EA 15.4 | Invalid | 0
1006418 | #1013452 | Story | Feature 1013452: Validate design for Geo Ephemeris data push to SIPRNET from UI server (Anil) | Unassigned | Invalid | 0
1006417 | #1013452 | Story | Feature 1013452: Validate design for Geo Ephemeris data push to SIPRNET from UI server (Keith) | EA 15.2 | Done | 2
1006416 | #1013452 | Story | Feature 1013452: Support Feature Demo Prep | PI 16 | New | 3
1006408 |  | Feature | Investigate allowing ephemeris data available via DMZ to SIPRNET | Unassigned | Rejected
1006376 | #340740 | Feature | MAMA2 Cleanup (including fix for PWI 1006103) | PI 16 - In Progress | Implementing
1006375 | #343917 | Task | Story 343917: CM Release of 98-P59858M - NMS - NM - Splunk - App- SVD (EAD 15) | EA 14.1 | Done
1006357 |  | Feature | Enhance and Optimize MUOS Build and Release Process Part 3 | PI 15 | Rejected
1006335 | #343917 | Task | Story 343917: CM Release of 99-P61689A – SEIT (EAD 15) [aka MUOS I-Level Procedures and Supporting Material] | EA 14.1 | Done
1006307 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (Sr RF Designer, Kevin Greenfield, KinetX) | EA 14.4 | Done | 5
1006306 | #388549 | Story | Feature 388549: ULX Detailed Design - Test Plan | EA 14.3 | Done | 5
1006305 | #388549 | Story | Feature 388549: ULX Detailed Design - Verification & Compliance Matrix, Channel Processor (Sequence Diagrams, Input to SA/FM, Config, Ext Interfaces, Test Plan) | EA 14.2 | Done | 5
1006303 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (FPGA, Kevin Greenfield, KinetX) | EA 14.4 | Done | 2
1006302 | #388549 | Story | Feature 388549: ULX Detailed Design - Preprocessor & RF Processor 9 Cleanup (ICD) (FPGA, Kevin Greenfield, KinetX) | EA 14.3 | Done | 2
1006301 | #388549 | Story | Feature 388549: ULX Detailed Design - Preprocessor, Reqts for AMS, Config, Test Pts, Ext. Interface, FM/SA, Test Plan (FPGA, Kevin Greenfield, KinetX) | EA 14.2 | Done | 2
1006300 | #388549 | Story | Feature 388549: ULX Detailed Design - Post Processor (Systems Design, ICD to RINCON, Ext Interfaces Document) | EA 14.1 | Done | 2
1006299 | #388549 | Story | Feature 388549: ULX Detailed Design - FM/Logging (Systems Design, Component Diagrams, Intelligent Processing) | EA 14.1 | Done | 5
1006298 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (Scalability, Test Plan, Sequence Diagrams, Conifguration) | EA 14.3 | Done | 3
1006297 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (Photon Framework & uSvcs Detailed Design, FM/SA, Config, External Interfaces, Test Plan, Test Points) | EA 14.2 | Done | 3
1006296 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (System Design, SW Architecture, Sequence Diagrams) | EA 14.1 | Done | 3
1006294 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support | EA 14.4 | Done | 5
1006293 | #388549 | Story | Feature 388549: ULX Detailed Design - ULX Manager (UI, Interfaces, Sequence Diagrams, Display Status, Configuration) | EA 14.3 | Done | 5
1006292 | #388549 | Story | Feature 388549: ULX Detailed Design - ULX Manager (Systems Design, Interfaces) | EA 14.2 | Done | 8
1006291 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (System Design, SW Architecture, Sequence Diagrams) | EA 14.1 | Done | 3
1006290 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support | EA 14.4 | Done | 8
1006289 | #388549 | Story | Feature 388549: ULX Detailed Design - Ext. Interfaces (Test Pts), Test Plans/Cases | EA 14.3 | Done | 8
1006288 | #388549 | Story | Feature 388549: ULX Detailed Design - RF Processor (External Interfaces, Reqts, SOW for RINCON, Config, SA/FM, Test Pts, Test Plan) | EA 14.2 | Done | 8
1006287 | #388549 | Story | Feature 388549: ULX Detailed Design - Post Processor (System Design, ICD to RINCON, Ext Interfaces Document) | EA 14.1 | Done | 8
1006286 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support | EA 14.4 | Done | 8
1006285 | #388549 | Story | Feature 388549: ULX Detailed Design - V&V Test Plan, Reqt Verification Matrix, Compliance Matrix) | EA 14.3 | Done | 8
1006284 | #388549 | Story | Feature 388549: ULX Detailed Design - Preprocessor (Reqts, Test Pts and Inputs for External Interface, FM/SA, Configuration, Test Plans) | EA 14.2 | Done | 8
1006283 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (Rich Nadolski) | EA 14.4 | Done | 2
1006281 | #388549 | Story | Feature 388549: ULX Detailed Design - ICD Support (Rich Nadolski) | EA 14.3 | Done | 2
1006280 | #388549 | Story | Feature 388549: ULX Detailed Design - AMS and RINCON ICD Support (Rich Nadolski) | EA 14.2 | Done | 2
1006278 | #388549 | Story | Feature 388549: ULX Detailed Design - AMS ICD Creation Support | EA 14.1 | Done | 2
1006275 | #388549 | Story | Feature 388549: ULX Detailed Design - Coordinate Final Report (Detailed Design, Deplyment & Support Costing) | EA 14.4 | Done | 2
1006274 | #388549 | Story | Feature 388549: ULX Detailed Design - Network Design, TO 9 BOE, Refine Subcontract Artifacts (SOW, Costing) | EA 14.3 | Done | 2
1006273 | #388549 | Story | Feature 388549: ULX Detailed Design - RINCON Subcontract (SOW, ICD, Costing) | EA 14.2 | Done | 2
1006272 | #388549 | Story | Feature 388549: ULX Detailed Design - Final Design Doc & Presentation Support (Cyber) | EA 14.4 | Done | 5
1006271 | #388549 | Story | Feature 388549: ULX Detailed Design - FCAPS & Design Oversight (Cyber) | EA 14.3 | Done | 5
1006270 | #388549 | Story | Feature 388549: ULX Detailed Design - FCAPS, Design Oversight (Cyber) | EA 14.2 | Done | 5
1006269 | #387276 | Story | Feature 387276: ULX SE Assessment - Final Document Delivery & Presentation Support | EA 14.5 | Done | 3
1006268 |  | Story | Feature 387276: ULX SE Assessment - Support (WWTS) 1 pt | EA 14.1 | Invalid | 0
1006267 | #387276 | Story | Feature 387276: ULX SE Assessment - Final Document Delivery & Presentation Support | EA 14.4 | Done | 2
1006266 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation | EA 14.3 | Done | 2
1006221 |  | Story | Build/prepare VLAB for integration of new DSN | PI 15 | Invalid | 0
1006220 |  | Story | Build/prepare VLAB for integration of new DSN | PI 15 | Invalid | 0
1006219 |  | Story | Build/prepare VLAB for integration of new DSN | PI 15 | Invalid | 0
1006218 |  | Story | Implement & component test UE/WF changes | PI 15 | Invalid | 0
1006217 |  | Story | Implement & component test UE/WF changes | PI 15 | Invalid | 0
1006216 |  | Story | Cisco equipment/General Consultation | PI 15 | Invalid | 0
1006215 |  | Story | Plan for (design) MAS setup/configuration for concurrent support of baseline DSN GW and new SBC | PI 15 | Invalid | 0
1006214 |  | Story | Assist with initial setup of the new DSN GW | PI 15 | Invalid | 0
1006213 |  | Story | Assist with initial setup of the new DSN GW | PI 15 | Invalid | 0
1006212 |  | Story | Implement & component test SBC configuration | PI 15 | Invalid | 0
1006211 |  | Story | Implement & component test SBC configuration | PI 15 | Invalid | 0
1006210 |  | Story | Design and implement a strategy for concurrent connectivity between MAS and both types of DSN GW | PI 15 | Invalid | 0
1006207 |  | Story | Implement & component test MAS changes | PI 15 | Invalid | 0
1006206 |  | Story | Implement & component test MAS changes | PI 15 | Invalid | 0
1006204 |  | Story | Perform the initial analysis of Capabilities Requirements and identify the list of changes for MAS + list of work items for SBC | PI 15 | Invalid | 0
1006203 |  | Story | DSN GW Obs/General Consultation | PI 15 | Invalid | 0
1006202 |  | Story | Produce Test Documents | PI 15 | Invalid | 0
1006201 |  | Story | Finalize DSN GW design | PI 15 | Invalid | 0
1006200 |  | Story | Finalize DSN GW design | PI 15 | Invalid | 0
1006199 |  | Story | Finalize DSN GW design | PI 15 | Invalid | 0
1006197 |  | Story | Lead DSN GW Obs work | PI 15 | Invalid | 0
1006196 |  | Story | Lead DSN GW Obs work | PI 15 | Invalid | 0
1006191 | #216662 | Feature | OBS - DSN GW: Develop Detailed System Design Artifacts | PI 16 - In Progress | Implementing
1006188 | #1005740 | Story | Feature 1005740: UE/WF Consultation | PI 14 | Invalid | 0
1006175 | #378000 | Problem | Connected AWARE: AWARE/MHAL not handling GCK Rekey | EA 14.1 | Closed
1006171 | #378000 | Problem | Connected AWARE: MyUTN USB Device failure | EA 14.1 | Closed
1006164 | #1005740 | Story | Plan for (design) lab setup for concurrent support of baseline DSN GW and new SBC | PI 14 | Invalid | 0
1006163 | #1005740 | Story | Plan for (design) lab setup for concurrent support of baseline DSN GW and new SBC | PI 14 | Invalid | 0
1006162 | #1005740 | Story | Develop expertise in the Cisco SBC product with focus on the platform/networking layer | PI 14 | Invalid | 0
1006161 | #1005740 | Story | Develop expertise in the Cisco SBC product with focus on the platform/networking layer | PI 14 | Invalid | 0
1006160 | #1005740 | Story | Synchronize work & planning w/TIS (OKAPI?) team | PI 14 | Invalid | 0
1006159 | #1005740 | Story | Feature 1005740: Cisco equipment/General Consultation | PI 14 | Invalid | 0
1006158 | #1005740 | Story | Develop expertise in the Cisco SBC product with focus on the SIP/SDP layer | PI 14 | Invalid | 0
1006157 | #1005740 | Story | Develop expertise in the Cisco SBC product with focus on the SIP/SDP layer | PI 14 | Invalid | 0
1006156 | #1005740 | Story | Update GTS artifacts for DSN GW Changes | PI 14 | Invalid | 0
1006155 | #1005740 | Story | Identify general approach for GTS evolution WRT | PI 14 | Invalid | 0
1006154 | #1005740 | Story | Identify general approach for GTS evolution WRT | PI 14 | Invalid | 0
1006153 | #1005740 | Story | Assist with MUOS Ground System changes for DSN GW | PI 14 | Invalid | 0
1006152 | #1005740 | Story | Synchronize work & planning w/TIS (OKAPI?) team | PI 14 | Invalid | 0
1006151 | #1005740 | Story | DSN GW Obs/General Consultation | PI 14 | Invalid | 0
1006150 | #1005740 | Story | Synchronize DSN GW work with TIS team | PI 14 | Invalid | 0
1006149 | #1005740 | Story | Produce the Capability Spec document | EA 14.2 | Done | 5
1006148 | #1005740 | Story | Produce the Capability Spec document | EA 14.1 | Done | 5
1006147 | #1005740 | Story | Lead DSN GW Obs work | EA 14.4 | Done | 1
1006146 | #1005740 | Story | Lead DSN GW Obs work | EA 14.2 | Done | 1
1006145 | #360140 | Problem | FEP SVD needs to be updated to include depot instructions for configuration for new part number dehydrator | EA 14.5 | Closed
1006135 | #1000471 | Story | Implement Profile Portability: Test load of initial UK keys provided by NSA | PI 17 | New | 3
1006134 | #1000471 | Story | Implement Profile Portability: Facilitate guard message changes and approvals | PI 17 | New | 13
1006133 | #1000471 | Story | Implement Profile Portability: Database changes (SQL Server) review | PI 17 | New | 3
1006132 | #1000471 | Story | Implement Profile Portability: ProvBridge review | PI 17 | New | 3
1006131 | #1000471 | Story | Implement Profile Portability: MGS Adapters review | PI 17 | New | 3
1006112 | #1000471 | Story | Implement Profile Portability: OTAP review | PI 17 | New | 3
1006111 | #1000471 | Story | Implement Profile Portability: KMS review | PI 17 | New | 3
1006103 | #1006376 | Problem | MAMA2: Rnh core dump during cell selection with 17 viable cells | EA 15.4 | Verifying
1006096 | #1000471 | Story | Implement Profile Portability: PPA review | PI 17 | New | 3
1006058 | #395855 | Story | Feature 395855: Deployment Notes and Operator Impact Inputs for PI 14 Parts Lists and Drawing Updates for EAD 16 | EA 14.5 | Done | 1
1005956 | #343917 | Task | Story 343917: CM Release of 69-P55756M INTERCONNECT DIAGRAM - ERS AWARE (EAD 15) | EA 14.1 | Done
1005943 | #343917 | Task | Story 343917: CM Release of 01-P55663M– ILS – ERS-AWARE Cabinet Assem (EAD 15) | EA 14.1 | Done
1005938 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Brian Kearney, SME LOE) | EA 14.4 | Done | 1
1005937 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Brian Kearney, SME LOE) | EA 14.3 | Done | 1
1005936 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Brian Kearney, SME LOE) | EA 14.2 | Done | 1
1005935 | #387276 | Story | Feature 387276: ULX SE Assessment - Attend Weekly TIMs, Final Report & Presentation Prep | EA 14.4 | Done | 2
1005921 |  | Task | Story 392938: CM Release of 98-P54107T – GEO – AMS-GS SVD for MPC14.x | EA 14.1 | In Development
1005919 | #1001263 | Story | Resolve problem 295002: KMS cannot parse error messages from OTAP | PI 16 | Invalid | 0
1005905 | #379001 | Task | Re-apply Problem 390482 Task for Deployment | Unassigned | Invalid
1005904 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1005903 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1005893 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1005892 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1005853 | #343920 | Task | Story 343920: CM Release of 53-P52819E – SITE – AC Power Distribution – AU (EAD 16) | EA 14.4 | Done
1005852 | #343920 | Task | Story 343920: CM Release of 01-P51661E, PCU CABINET - RAF, SCD (EAD 16) | EA 14.4 | Done
1005849 | #395855 | Problem | Feature 395855: Drawing Updates based on Redlines for in 53-P52819E – SITE – AC Power Distribution (EAD 16) | EA 14.2 | Closed
1005846 | #1004171 | Story | Feature 1004171: Monitor logs at sites once the EAD15 build containing traces is deployed | EA 15.5 | New | 1
1005843 |  | Problem | EAD14 Deployment: AWARE VM behavior | Unassigned | Assessing
1005838 | #1004094 | Story | Feature 1004094: Support Common Design for use of Passwords and Credential Management | PI 17 | New | 1
1005834 | #1004094 | Story | Feature 1004094: Review the system to determine need | PI 17 | New | 5
1005820 | #1008506 | Story | Implement - PWI 387434 - part 1 | EA 15.4 | New | 3
1005797 | #378000 | Problem | EAD14 Deployment: AWARE config file had wrong radio address | EA 14.1 | Closed
1005794 | #378000 | Problem | EAD14 Deployment: AWARE hostnames are incorrect in Netcool alarms | EA 14.1 | Closed
1005772 | #388053 | Story | Feature 388053: Support design of PPA (SE) | PI 14 | Invalid | 0
1005771 | #388549 | Story | Feature 388549: ULX Detailed Design - Create Development, Deployment & Support Costs for Contract Deliverable | EA 14.1 | Done | 2
1005770 | #388549 | Story | Feature 388549: ULX Detailed Design - Compliant to Support IATT, Patching/STIG Design, Design Oversight) (Kent Tang, Cyber) | EA 14.1 | Done | 5
1005746 |  | Story | Assist in the lab with SBC configuration, integration, test, and verification activities | PI 14 | Invalid | 0
1005745 |  | Story | Assist with MUOS Ground System changes for DSN GW | PI 14 | Invalid | 0
1005744 |  | Story | Assist with MUOS Ground System changes for DSN GW | PI 14 | Invalid | 0
1005743 |  | Story | Cisco equipment/General Consultation | PI 14 | Invalid | 0
1005742 |  | Story | DSN GW Obs/General Consultation | PI 14 | Invalid | 0
1005741 |  | Story | Lead DSN GW Obs work | PI 14 | Invalid | 0
1005740 | #216662 | Feature | OBS - DSN GW: Develop Capability Spec | EA 14.5 | Done
1005734 | #262145 | Feature | &amp;lt;Feature 1005717&amp;gt; MFR1 Template | PI 14 | Rejected
1005733 | #262145 | Feature | &lt;Feature 1005717&gt; MFR1 Template | PI 14 | Rejected
1005731 | #1005717 | Story | <Feature 1005717>: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
1005730 | #1005717 | Story | <Feature 1005717>- Prep and Perform Feature Demo – Customer Demo Event | PI 14 | Invalid | 0 | #1005731
1005729 | #1005717 | Story | <Feature 1005717>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 14 | Invalid | 0 | #1005730
1005728 | #1005717 | Story | <Feature 1005717>: Execute STCD Feature Integration and testing including STCD updates identified | PI 14 | Invalid | 0 | #1005730
1005727 | #1005717 | Story | <Feature 1005717>: Provide Development inputs to common documents | PI 14 | Invalid | 0 | #1005730
1005726 | #1005717 | Story | <Feature 1005717>: ILS Incorporation of IETM updates and integration support | PI 14 | Invalid | 0
1005725 | #1005717 | Story | <Feature 1005717> UX Research and Design Support | PI 14 | Invalid | 0
1005724 | #1005717 | Story | <Feature 1005717>: Develop IETMs and Perform Development Testing | PI 14 | Invalid | 0 | #1005730
1005723 | #1005717 | Story | <Feature 1005717>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 14 | Invalid | 0 | #1005730
1005722 | #1005717 | Story | <Feature 1005717>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 14 | Invalid | 0 | #1005730
1005721 | #1005717 | Story | <Feature 1005717>: Provide Deployment Notes and Operator Impact Inputs | PI 14 | Invalid | 0 | #1005730
1005720 | #1005717 | Story | <Feature 1005717>: Create STCD and review with stakeholders | PI 14 | Invalid | 0 | #1005730 #1005728 #1005722 #1005729
1005719 | #1005717 | Story | <Feature 1005717> Document Initial capability specification and detailed design to start Implementation | PI 14 | Invalid | 0 | #1005720 #1005722
1005718 | #1005717 | Task | <Feature 1005717> Hold Feature Review with SMEs | PI 14 | Invalid
1005717 | #262145 | Feature | <Feature 1005717> MFR1 Template | PI 14 | Rejected
1005649 | #1004171 | Problem | Modules not registering with CGNH | EA 15.4 | Verifying
1005643 |  | Problem | SSG20 access list needs updated to include new workstations | Unassigned | Assessing
1005640 | #1000471 | Story | Implement Profile Portability: Develop GUI prototypes | PI 17 | New | 5
1005617 | #1005321 | Story | Feature 1005321: Review & Compare Report from CSO | EA 15.2 | Done | 2
1005602 | #297335 | Story | RDE ClearCase - Manually Migrate ClearCase Data for Build related VOBs to RDE not addressed by MultiSite | EA 14.2 | Done | 3
1005593 | #377437 | Story | Feature 377437 ETT: Initiate PDO for Hardware/Software Map for ETT Laptop | EA 15.3 | Invalid | 0
1005592 | #377437 | Story | Feature 377437 ETT: Update Parts lists | Unassigned | Invalid | 0
1005591 |  | Task | Story 353837 Release PDO for 98-P53342 Simulation Framework (EAD 16 OOC) | EA 15.2 | Invalid
1005567 | #1002089 | Story | Feature 1002089: Update Refresher Training Materials | EA 14.3 | Invalid | 0
1005562 | #353256 | Story | Feature 353256: Complete International Site Visit Paperwork/Training (AU) - Trainer 2 | EA 14.1 | Invalid | 0
1005561 | #353134 | Story | Feature 353134: Complete International Site Visit Paperwork/Training (SC) - Trainer 2 | EA 14.1 | Done | 3
1005554 | #395871 | Story | Feature 395871: Labradors TT Support - EA 14.2 | EA 14.2 | Done | 2
1005552 | #395871 | Story | Feature 395871: Labradors TT Support - EA 14.1 | EA 14.1 | Invalid | 0
1005547 | #1001263 | Story | Feature 1001263 KMS: Rebase MPC for Problem 390411- KMS "setupImsis" method not correctly handling normal provisioning vs rekey | PI 16 | Invalid | 0
1005544 | #1001248 | Story | Feature 1001248: Implement Problem 390411- KMS "setupImsis" method not correctly handling normal provisioning vs rekey | EA 14.2 | Done | 1
1005529 | #383165 | Story | Feature 383165: Create CoCo Review for NME 8, 9 | EA 16.1 | New | 3
1005527 |  | Story | Feature 395871: Send out MPC for Problem 390411 | EA 14.1 | Invalid | 0
1005525 | #383165 | Story | Feature 383165: Create SCD of Server, Switches for NME 201 Rack for Nutanix | EA 14.5 | Done | 1
1005524 | #383165 | Story | Feature 383165: Begin CAD for the Revised Site Level Documentation | EA 14.5 | Done | 1
1005523 | #383165 | Story | Feature 383165: Create CoCo Review for the New Rack Documentation, Drawings, and Parts List for Nutanix | EA 16.1 | New | 1
1005511 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Unit Test Part 2 | EA 14.3 | Done | 3
1005510 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Unit Test Part 3 | EA 14.4 | Done | 3
1005509 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Unit Test Part 1 | EA 14.2 | Done | 3
1005504 | #378964 | Task | Sonia Montalvo-Johnson PTO (EA 14.1 (2/10)) | EA 14.1 | Invalid
1005503 | #378964 | Task | Sonia Montalvo-Johnson PTO (EA 14.1 (1/30 - 1/31)) | EA 14.1 | Done
1005502 | #379175 | Task | Sonia Montalvo-Johnson PTO (EA 14.1 (1/30 - 1/31)) | EA 14.1 | Done
1005501 | #379175 | Task | Sonia Montalvo-Johnson PTO (EA 14.1 (2/10)) | EA 14.1 | Invalid
1005500 | #379175 | Task | Craig Dixon PTO (EA 14.2 (2/13 - 2/17)) | EA 14.2 | Done
1005494 | #1013136 | Problem | During compromise common group key waveform got stuck | EA 16.1 | Close Pending
1005490 |  | Story | Feature 358656: ET Alarm Recovery Procedures IETM Style Guide Review and Dry Run (Part 2) | Unassigned | Invalid | 0
1005440 | #353256 | Story | Feature 353256: Travel from AU Site to PHX After Maintainer Refresher Training in AU (Trainer 1) | EA 16.3 | New | 3
1005434 | #341999 | Story | Feature 341999: Create Training Plan for Connected AWARE Training in SC (EAD 17) | PI 16 | New | 1
1005433 | #353256 | Story | Feature 353256: Complete International Site Visit Paperwork/Training (AU) - Trainer 1 | EA 14.1 | Invalid | 0
1005431 | #353134 | Task | Feature 353134: Create Training Plan for Refresher Training in SC | EA 14.1 | Done
1005416 | #1005403 | Task | Feature 1005403: Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in AU | EA 14.1 | Done
1005415 | #1005403 | Story | Feature 1005403: Present SOW Associated to 2020 Preventive Maintenance in AU | EA 14.3 | Done | 2
1005414 | #1005403 | Story | Feature 1005403: Prepare & Conduct PM Kickoff Meeting with Vendor (PM AU) | EA 16.3 | New | 1
1005412 | #1005403 | Story | Feature 1005403: Continue Oversight of Vendor Activities for 2020 Preventive Maintenance in AU | EA 16.5 | New | 1
1005411 | #1005403 | Story | Feature 1005403: Begin Oversight of Vendor Activities for 2020 Preventive Maintenance in AU | EA 16.4 | New | 1
1005410 | #1005403 | Task | Feature 1005403: Ship Supplies and Materials to Site for 2020 Preventive Maintenance in AU | EA 16.3 | New
1005409 | #1005403 | Story | Feature 1005403: Request Creation & Submission of PR & PO for Supplies and Materials Required for 2020 Preventive Maintenance in AU | EA 14.2 | Invalid | 0
1005408 | #1005403 | Story | Feature 1005403: Prepare, Review SOW Associated to 2020 Preventive Maintenance in AU | EA 14.2 | Done | 1
1005407 | #1005403 | Task | Feature 1005403: Create and Validate Plan for 2020 Preventive Maintenance Activities in AU | EA 14.2 | Done
1005406 | #1005403 | Task | Feature 1005403: Confirmation of Vendor, Access to Site, and Schedule of Activities for the 2020 Preventive Maintenance in AU | EA 14.2 | Done
1005405 | #1005403 | Story | Feature 1005403: Identification of Consumables Required for 2020 Preventive Maintenance in AU | EA 14.1 | Done | 1
1005404 | #1005403 | Story | Feature 1005403: Determine Corrective Actions Based Upon Trouble Tickets Received for 2020 Preventive Maintenance of AU | EA 14.4 | Done | 2
1005402 | #395174 | Story | Feature 395174: LAB Support for LBIP RU2B ASSEMBLY, PN = 01400018, SN = AL081409056. | EA 14.2 | Done | 2
1005396 | #395174 | Story | Feature 395174: FRB P/N 01-P51765E001, CHASSIS ASSEMBLY - WCDMA RF, S/N = 112. | EA 14.5 | Done | 1
1005392 |  | Task | Story 343920: CM Release of 98-P55616M – IA – SVD (EAD 16) March 2020 Update | PI 14 | Done
1005387 |  | Story | Feature Evaluation and Determination of Path Forward for GEO Removal ETISP Frame Sync Issue | PI 15 | Invalid | 0
1005382 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support | EA 14.4 | Done | 1
1005381 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support | EA 14.3 | Done | 1
1005380 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support | EA 14.2 | Done | 1
1005379 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support | EA 14.1 | Invalid | 0
1005375 |  | Story | Implement Problem 1004560 | EA 14.1 | Invalid | 0
1005361 |  | Story | Identify if CAT1 has been Resolved or Mitigated (13.6c) | Unassigned | Invalid | 0
1005359 |  | Story | Identify if CAT1 has been Resolved or Mitigated (13.4c) | Unassigned | Invalid | 0
1005358 |  | Story | Identify if CAT1 has been Resolved or Mitigated (13.4b) | Unassigned | Invalid | 0
1005348 | #1005343 | Story | Feature 1005343: Review DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations (Apr 2020) | EA 14.5 | Done | 5
1005347 | #1005343 | Story | Feature 1005343: Finalize DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations and Capture PMW Redlines Prior to Meeting (Mar 2020) | EA 14.4 | Done | 2
1005346 | #1005343 | Story | Feature 1005343: Review DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations and DMSMS WG Agenda Planning (Mar 2020) | EA 14.3 | Done | 8
1005345 | #1005343 | Story | Feature 1005343: Finalize DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations (Feb 2020) | EA 14.2 | Done | 1
1005344 | #1005343 | Story | Feature 1005343: Review DMSMS Tracker and Provide GD and PMW Supportability Impacts and Recommendations (Feb 2020) | EA 14.1 | Done | 5
1005343 | #262146 | Feature | DMSMS Tracker Submittal (CDRL A007)) | EA 14.5 | Done
1005341 | #1005321 | Task | Feature 1005321: Hold Kick-off Meeting | EA 14.5 | Done
1005340 | #1005321 | Story | Feature 1005321: Update Hardware Configuration Mapping for As-Built Drawing Package | EA 15.4 | Implementing | 2
1005339 | #1005321 | Story | Feature 1005321: Systemic Configuration Drawings; Consolidate and Complete Finalized Report | EA 16.1 | New | 2
1005338 | #1005321 | Story | Feature 1005321: Systemic Configuration Drawings; Identify and Confirm Draft Drawing Updates for all Sites | EA 15.3 | Done | 2
1005337 | #1005321 | Story | Feature 1005321: Complete Population of the Spreadsheet Created to Capture all the MUOS Servers Impacted by IA Patching with IA Patching Information | PI 14 | Invalid | 0
1005336 | #1005321 | Story | Feature 1005321: Review & Compare Report from CSO | EA 15.3 | Invalid | 0
1005335 | #1005321 | Story | Feature 1005321: Complete CSO Support for Systemic Configuration | EA 15.1 | Done | 2
1005334 | #1005321 | Story | Feature 1005321: Continue Populating the Spreadsheet Created to Capture all the MUOS Servers Impacted by IA Patching with IA Patching Information | PI 14 | Invalid | 0
1005333 | #1005321 | Story | Feature 1005321: Populate the Spreadsheet Created to Capture all the MUOS Servers Impacted by IA Patching with IA Patching Information | EA 15.3 | Done | 3
1005332 | #1005321 | Story | Feature 1005321: Create SVDs for the Systemic Configuration | EA 15.5 | New | 2
1005331 | #1005321 | Story | Feature 1005321: Create Service Requests (SRs) Spreadsheet for EAD 16 (for all Sites, Complete Package) | PI 15 | Invalid | 0
1005330 | #1005321 | Story | Feature 1005321: Create Service Requests (SRs) Spreadsheet for EAD 14 (for all Sites, Complete Package) - Document Process | EA 15.3 | Done | 5
1005329 | #1005321 | Story | Feature 1005321: Create Service Requests (SRs) Spreadsheet for EAD 14 (for all sites, Complete Package) - Document Process | PI 14 | Invalid | 0
1005328 | #1005321 | Story | Feature 1005321: Document Process for Accumulating Data for SRs, MPC, and SVD for the Software Delivered to Site | EA 16.1 | New | 5
1005327 | #1005321 | Story | Feature 1005321: CSO Support for Systemic Configuration | EA 15.2 | Done | 2
1005326 | #1005321 | Story | Feature 1005321: Update the Spreadsheet Capturing all the MUOS Servers Impacted by IA Patching | PI 15 | Invalid | 0
1005325 | #1005321 | Story | Feature 1005321: Update the Format Spreadsheet to Capture all MPCs for the Systemic Configuration | EA 15.5 | New | 2
1005324 | #1005321 | Story | Feature 1005321: Internal Review of Existing Documentation | PI 14 | Invalid | 0
1005323 | #1005321 | Story | Feature 1005321: Review the Process Flow of the Systemic Configuration Created in 2019 | PI 15 | Invalid | 0
1005321 | #262146 | Feature | Systemic Configuration (CDRL A015) | PI 16 - In Progress | Implementing
1005318 | #1002345 | Task | Feature 1002345: Submit PDO for 98-P55722M – GTS – SWITCH – HLR – SVD | PI 16 | New
1005306 | #378964 | Task | Mark Sederstrom PTO (EA 15.2 (4/30)) | EA 15.2 | Done
1005305 | #378964 | Task | Mark Sederstrom PTO (EA 15.2 (4/23)) | EA 15.2 | Invalid
1005304 | #378964 | Task | Mark Sederstrom PTO (EA 15.1 (4/16)) | EA 15.1 | Done
1005303 | #377408 | Problem | Feature 377408: FEP Controls and Indicators Procedure- System Reset button | EA 14.1 | Closed
1005302 | #378964 | Task | Mark Sederstrom PTO (EA 15.1 (4/9)) | EA 15.1 | Invalid
1005301 | #378964 | Task | Mark Sederstrom PTO (EA 14.5 (4/2)) | EA 14.5 | Done
1005300 |  | Problem | RCG Software Installation and Configuration Procedure (Radio_Cover_Generator_Server.pdf) | Unassigned | Assessing
1005299 | #378964 | Task | Mark Sederstrom PTO (EA 14.4 (3/19)) | EA 14.4 | Done
1005297 | #378964 | Task | Mark Sederstrom PTO (EA 14.3 (3/5)) | EA 14.3 | Done
1005292 | #378964 | Task | Mark Sederstrom PTO (EA 14/1 (2/20)) | EA 14.2 | Done
1005291 | #378964 | Task | Mark Sederstrom PTO (EA 14/1 (2/6)) | EA 14.1 | Done
1005286 | #1002381 | Story | Feature 1002381: Continue Creating Redlines Drawings for OBS - HLR: HW/FRCB for HLR Deployment | EA 14.5 | Done | 5
1005285 | #1002381 | Story | Feature 1002381: Continue Redlines on Hardware Drawings Submitted for IDP Associated with OBS - HLR: HW/FRCB for HLR Deployment | EA 14.3 | Done | 5
1005284 | #1002381 | Story | Feature 1002381: Begin Creation of Redlines on Hardware Drawings Submitted for IDP Associated with OBS - HLR: HW/FRCB for HLR Deployment | EA 14.2 | Done | 5
1005280 | #388053 | Story | Feature 388053 (PPA) - Design PPA Replacement (SIC) - part 4 | EA 14.4 | Done | 5
1005279 | #388053 | Story | Feature 388053 (PPA) - Design PPA Replacement (SIC) - part 3 | EA 14.3 | Done | 5
1005278 | #388053 | Story | Feature 388053 (PPA) - Design PPA Replacement (SIC) - part 2 | EA 14.2 | Done | 5
1005210 |  | Problem | Update IETM procedures to instruct operators of upper and lower boundaries for Broadcast Deactivation Date to prevent errors in Rekey and Group Comprimise | Unassigned | Assessing
1005175 | #386935 | Task | Rebase Story: Incorporate GEO UFO Table Updates as part of Relo Phase 3 activities into EAD16 baseline. | EA 14.3 | Done
1005169 | #386935 | Task | Rebase Story: Process GEO EAD14 Deployment Redlines MPC 14.10 into EAD16 baseline | EA 14.3 | Done
1004904 |  | Problem | Polatis Connections Reroute | Unassigned | Triage
1004868 | #384136 | Story | Feature 384136: Update MUOS_IG_GS_NMS_NM_OS_WindowsServer2012_SVD_98-P59852M003 to update to remove epo202 and 201 from document. | EA 14.3 | Done | 3
1004860 | #1007900 | Story | Feature 1007900: Update MUOS_IG_GS_GEO_SVD_98-P54107T003 to update host.all and host.deny for geo205 | PI 16 | New | 5
1004859 | #1000471 | Story | Implement Profile Portability: Migrate existing databases to new structure | PI 17 | New | 13
1004858 | #384136 | Story | Feature 384136 Update MUOS_IG_GS_Network_Router_SVD_98-P55509M Routers rout203/204 to incorporate updated to DMZ with Nutanix | EA 14.1 | Done | 2 | #1007603
1004857 | #384136 | Story | Feature 384136:Update MUOS_IG_GS_Network_LB_SVD_98-P55464M load balancer to incorporated updates to Nutanix Environment and the HBSS DMZ to SIPR | EA 14.1 | Done | 2
1004856 | #384136 | Story | Feature 384136:Update MUOS_IG_GS_Firewall_Network_SVD_98-P55755M Firewalls to meet new IP address for ePO 200 and 201 | EA 14.1 | Done | 2 | #1007603
1004855 | #1007900 | Story | Feature 1007900: Update MUOS_IG_GS_NMS_NM_Common_Tectia_SVD_98-P59813M003 to update ePO 200 and 201 remove 202 from this SVD | PI 16 | New | 5 | #1007605
1004854 | #1007900 | Story | Feature 1007900: Update MUOS_IG_IP_99-P57050M to update ePO 200 and 201 remove 202 from this SVD | PI 16 | New | 5 | #1007605
1004853 | #1000471 | Story | Implement Profile Portability: Implement and unit test ProvBridge changes | PI 17 | New | 5
1004852 | #1000471 | Story | Implement Profile Portability: Implement OTAP database changes | PI 17 | New | 3
1004851 | #1000471 | Story | Implement Profile Portability: Implement KMS database changes | PI 17 | New | 3
1004850 | #1000471 | Story | Implement Profile Portability: Implement PPA database changes | PI 17 | New | 3
1004849 |  | Story | Feature 384136: Update MUOS_IG_GS_NMS_NM_Common_SANSwitch_SVD_98-P59430M003 to remove ePO from this SVD | EA 14.5 | Done | 5
1004848 | #1007900 | Story | Feature 1007900: Update Updated NM RAID Array 98-P59436M003 to remove ePO from this server | EA 15.2 | Done | 5
1004847 | #1007900 | Story | Feature 1007900: Update HW/SW MAP 99-P59435M003 for updates to devices on Secret side to account for endpoint product updates. | EA 15.4 | Implementing | 5
1004824 | #1004094 | Story | Feature 1004094: Software/Hardware Needs Discussion for OBS: Develop Common Design for Use of Passwords and Credential Management | PI 14 | Invalid | 0
1004823 |  | Story | Feature 384136: Software/Hardware Needs Discussion for HBSS: Integration and Test Productio HBSS Solution in the VLab | PI 14 | Invalid | 0
1004822 | #384120 | Story | Feature 384120: Software/Hardware Needs Discussion for Implementation of VM Staging and Deployment Automation Solution in VLab | PI 14 | Invalid | 0
1004821 | #384036 | Story | Feature 384036: Create HW/SW Map for Cluster 200 (new CI) and Update NM_HW_SW Map | EA 14.4 | Done | 3
1004820 | #354680 | Story | Feature 354680: Software/Hardware Needs Discussion for SPLUNK HA | PI 14 | Invalid | 0
1004819 | #293338 | Story | Feature 293338: Software/Hardware Needs Discussion for SWIT Dev Env | PI 14 | Invalid | 0
1004818 | #376446 | Story | Feature 376446: Software/Hardware Needs Discussion for Call Bank Servers for Connected AWARE (Support of IATT) | Unassigned | Invalid | 0
1004816 | #342054 | Story | Feature 342054: Software/Hardware Needs Discussion for Deployment/Installation of Connected AWARE In SC | Unassigned | Invalid | 0
1004815 | #318430 | Story | Feature 318430: Software/Hardware Needs Discussion for Windows 10 Laptop for ETT | EA 14.1 | Invalid | 0
1004814 |  | Task | Story 343920: CM Release of 98-P54107T – GEO – AMS-GS SVD for MPC14.10 | EA 14.1 | In Development
1004801 |  | Problem | ocm11wh - Filesystem 'swap' mounted at '/var/run' is at 100% full: Recovery needs to be documented | Unassigned | Assessing
1004782 |  | Problem | rout201-wh-nma and rout202-wh-nma ports 1/1 offline | Unassigned | Assessing
1004759 |  | Problem | Remove geoc10x-xx-gcs entries from TCA ping in TPM | Unassigned | Assessing
1004738 | #384036 | Story | Feature 384036: Implement Automated Application installation using on Nutanix and RHEL per SVD (1) | EA 14.1 | Done | 5
1004716 | #1004702 | Story | Feature 1004702: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
1004715 | #1004702 | Story | Feature 1004702: Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #1004716
1004714 | #1004702 | Story | Feature 1004702: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #1004715
1004713 | #1004702 | Story | Feature 1004702: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #1004715
1004712 | #1004702 | Story | Feature 1004702: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #1004715
1004711 | #1004702 | Story | Feature 1004702: Incorporation of IETM Updates and Integration Support for High Priority AWARE Procedure Issues | Unassigned | Invalid | 0
1004710 | #1004702 | Story | Feature 1004702: Style Guide Review and Dry Runs of High Priority AWARE Procedure Issues | Unassigned | Invalid | 0
1004709 | #378000 | Story | Feature 378000: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #1004715
1004708 | #1004702 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #1004715
1004707 | #1004702 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #1004715
1004706 | #1004702 | Story | Feature 1004702: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #1004715
1004705 | #290711 | Story | Feature 290711: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #1004713 #1004715 #1004714 #1004707
1004704 | #1004702 | Story | Feature 1004702: IETM Updates | Unassigned | Invalid | 0 | #1004707 #1004705
1004703 | #1004702 | Task | Feature 1004702: Hold Feature Review with SMEs | Unassigned | Invalid
1004702 | #347073 | Feature | High Priority AWARE Procedure Issues | Unassigned | Rejected
1004700 | #376446 | Story | Feature 376446: Add Network Connectivity for 2 radios from H1186C | EA 15.2 | Done | 2
1004693 |  | Story | Feature 358656 SME Support | Unassigned | Invalid | 0
1004688 | #388053 | Story | Feature 388053 (PPA) - Design PPA Replacement (SIC) - part 1 | EA 14.1 | Done | 5
1004666 | #377437 | Story | Feature 377437 ETT: Feature Demo – Customer Demo Event - ETT Laptop | EA 15.3 | Done | 1 | #1004661
1004664 | #377437 | Story | Feature 377437 ETT: Initiate CM PDO Processing for all CI's (Gen 2 laptop, …) | EA 15.2 | Invalid | 0
1004663 | #377437 | Story | Feature 377437 ETT: Depot Build and Deliver ETT Laptops | Unassigned | Invalid | 0
1004662 | #377437 | Story | Feature 377437 ETT: Feature Demo - Customer Event Assistance | EA 15.3 | Done | 1
1004661 | #377437 | Story | Feature 377437 ETT: Update laptops for VLAB after demo passes. | EA 15.4 | New | 1
1004660 | #377437 | Story | Feature 377437 ETT Laptop - Feature Demo – Customer Demo Prep | EA 15.2 | Done | 3 | #1004666
1004659 | #377437 | Story | Feature 377437 ETT Laptop Feature Demo – Customer Demo Prep | EA 15.1 | Done | 3 | #1004666
1004649 | #377437 | Story | Feature 377437 ETT Laptop - Feature Demo – Customer Demo Prep | EA 15.2 | Done | 3 | #1004666
1004592 | #379001 | Story | Test and Rebase Story 1004590 to update the Windows Server 2012 CI SVD portion of this effort | Unassigned | New | 2
1004591 | #1007900 | Story | Test and Rebase Story 393061 to update the WIN10 Workstation CI SVD portion of this effort | PI 16 | New | 2
1004559 | #354174 | Story | Feature 354174 Splunk IETM: Part 2 - Engineering IETM Updates for Splunk HA - Joel | EA 14.1 | Done | 3
1004549 | #377437 | Story | Feature 377437 ETT: Initiate CM PDO Processing for all CIs | EA 15.3 | Done | 1
1004548 | #377437 | Task | Feature 377437 ETT: Initiate CM PDO Processing for parts lists | EA 15.1 | Invalid
1004546 | #377437 | Task | Feature 377437: Submit PDO for 99-P59552V Software to Hardware Mapping ILS Laptop GEN2 - ETT | EA 15.2 | Done
1004545 |  | Task | Story 353837 Release PDO for Account Maintenance Plan (EAD 17) | EA 15.2 | Invalid
1004543 | #377437 | Task | Feature 377437: CM Release of (Submit PDO for) 01-P53037 - ILS ETT Assembly Parts List (EAD 17) | EA 15.2 | Done
1004531 | #368860 | Story | Feature: 368860 Cost Estimate ~ IMS Lead | EA 14.4 | Done | 2
1004530 | #368860 | Story | Feature: 368860 Cost Estimate ~ IMS Lead | EA 14.3 | Done | 2
1004529 | #368860 | Story | Feature: 368860 Cost Estimate ~ IMS Lead | EA 14.2 | Done | 2
1004528 | #368860 | Story | Feature: 368860 Cost Estimate ~ IMS Lead | EA 14.1 | Done | 2
1004527 | #368860 | Story | Feature: 368860 Cost Estimate ~ SOW/PWS Lead | EA 14.4 | Done | 2
1004526 | #368860 | Story | Feature: 368860 Cost Estimate ~ SOW/PWS Lead | EA 14.3 | Done | 2
1004525 | #368860 | Story | Feature: 368860 Cost Estimate ~ SOW/PWS Lead | EA 14.2 | Done | 2
1004524 | #368860 | Story | Feature: 368860 Cost Estimate ~ SOW/PWS Lead | EA 14.1 | Done | 2
1004523 | #368860 | Story | Feature: 368860 Cost Estimate ~ COMSEC/Keys | EA 14.3 | Done | 2
1004522 | #368860 | Story | Feature: 368860 Cost Estimate ~ COMSEC/Keys | EA 14.2 | Done | 2
1004521 | #368860 | Story | Feature 368860: Cost Estimate for Canadian Foreign Military Sales Phase 1 | EA 14.2 | Done | 1
1004520 | #368860 | Story | Feature 368860: Continue Cost Estimate for Canadian Foreign Military Sales Phase 1 | EA 14.1 | Done | 2
1004518 | #368860 | Story | Feature: 368860 Cost Estimate ~ Test & Integration | EA 14.3 | Done | 2
1004517 | #368860 | Story | Feature: 368860 Cost Estimate ~ Test & Integration | EA 14.2 | Invalid | 0
1004516 | #368860 | Story | Feature: 368860 Cost Estimate ~ IA | EA 14.3 | Done | 2
1004515 | #368860 | Story | Feature: 368860 Cost Estimate ~ IA | EA 14.4 | Done | 2
1004514 | #368860 | Story | Feature:368860: Cost Estimate ~ Waveform | EA 14.1 | Done | 1
1004513 | #368860 | Story | Feature 368860: Canada Cost Estimate ~ GDS | EA 14.1 | Done | 1
1004511 | #368860 | Story | Feature: 368860 Cost Estimate - Canada GDS | EA 14.3 | Done | 1
1004510 | #368860 | Story | Feature 368860: Canadian FMS Planning Phase 1 - Cost Estimate ~ Core Network | EA 14.3 | Done | 5
1004506 | #368860 | Story | Feature: 368860 Cost Estimate ~ SA | EA 14.3 | Done | 1
1004505 | #368860 | Story | Feature: 368860 Cost Estimate ~ SA | EA 14.2 | Invalid | 0
1004504 | #368860 | Story | Feature: 368860 Cost Estimate ~ Provisioning & FCAPS | EA 14.2 | Done | 2
1004503 | #368860 | Story | Feature: 368860 Cost Estimate ~ Provisioning & FCAPS | EA 14.1 | Done | 2
1004502 | #368860 | Story | Feature: 368860 Cost Estimate ~ Teleport | EA 14.2 | Done | 1
1004501 | #368860 | Story | Feature: 368860 Cost Estimate ~ Teleport | EA 14.3 | Done | 1
1004499 | #368860 | Story | Feature: 368860 Cost Estimate ~ Teleport | EA 14.3 | Done | 1
1004497 | #368860 | Story | Feature: 368860 Cost Estimate ~ Teleport | EA 14.2 | Done | 1
1004495 | #368860 | Story | Feature: 368860 Cost Estimate ~ Cost Estimate Lead | EA 14.4 | Done | 1
1004494 | #368860 | Story | Feature: 368860 Cost Estimate ~ Cost Estimate Lead | EA 14.3 | Done | 1
1004493 | #368860 | Story | Feature: 368860 Cost Estimate ~ Cost Estimate Lead | EA 14.2 | Done | 2
1004492 | #368860 | Story | Feature: 368860 Cost Estimate ~ Cost Estimate Lead | EA 14.1 | Done | 1
1004489 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Test Strategy & Lab infrastructure | PI 14 | Invalid | 0
1004485 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Test Strategy & Lab infrastructure | EA 14.3 | Done | 1
1004484 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Test Strategy & Lab infrastructure | EA 14.2 | Done | 1
1004483 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Test Strategy & Lab infrastructure | EA 14.1 | Done | 1
1004481 | #368860 | Story | Feature 368860: High-Level System Architecture ~ UX/Training | EA 14.3 | Done | 1
1004479 | #368860 | Story | Feature 368860: High-Level System Architecture ~ ILS (training, doc) | EA 14.1 | Done | 1
1004478 | #368860 | Story | Feature 368860: High-Level System Architecture ~ ILS (training, doc, dwgs, sparing) for Canadian Foreign Military Sales Phase 1 | EA 14.1 | Done | 5
1004477 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Congestion Management | PI 14 | Invalid | 0
1004476 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Group / Key Mgmnt | EA 14.1 | Done | 2
1004473 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ COMSEC framework/Traffic Segregation | PI 14 | Invalid | 0
1004472 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ COMSEC framework/Traffic Segregation | EA 14.2 | Done | 5
1004468 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ IA | EA 14.4 | Done | 2
1004467 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ IA | EA 14.3 | Done | 2
1004465 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ IA | EA 14.2 | Done | 2
1004462 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ IA | EA 14.1 | Done | 2
1004461 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.4 | Invalid | 0
1004458 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.2 | Invalid | 0
1004456 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.3 | Done | 2
1004455 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.2 | Done | 2
1004454 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ SA (Splunk, reports) | EA 14.1 | Done | 2
1004451 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ FCAPS | EA 14.3 | Done | 1
1004449 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ FCAPS | EA 14.4 | Done | 1
1004448 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Provisioning | EA 14.4 | Done | 2
1004447 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Provisioning | EA 14.3 | Done | 2
1004445 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Provisioning | EA 14.2 | Done | 3
1004444 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Provisioning | EA 14.1 | Done | 1
1004442 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ External Network (data, voice) | EA 14.2 | Done | 1
1004441 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtN | EA 14.3 | Done | 3
1004439 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtN | EA 14.2 | Done | 3
1004438 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtP | EA 14.3 | Done | 2
1004436 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ PtP | EA 14.1 | Done | 1
1004434 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Acquisition & Registration (AES) | EA 14.2 | Done | 1
1004432 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Architecture Lead | EA 14.4 | Done | 3
1004431 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Architecture Lead | EA 14.3 | Done | 1
1004430 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Architecture Lead | EA 14.2 | Done | 3
1004429 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Architecture Lead | EA 14.1 | Done | 5
1004425 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Coordination Lead | EA 14.4 | Done | 1
1004424 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Coordination Lead | EA 14.3 | Done | 1
1004423 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Coordination Lead | EA 14.2 | Done | 1
1004421 | #368860 | Story | Feature: 368860 High-Level System Architecture ~ Coordination Lead | EA 14.1 | Done | 1
1004359 | #1004171 | Story | Feature 1004171: Create the Deployment Notes and Operator impacts | EA 15.1 | Done | 1
1004358 | #381608 | Story | Feature 381608: Create the Deployment Notes and Operator impacts | EA 14.1 | Done | 1
1004314 | #332951 | Story | Feature 332951: UX/ILS Support for RBS Alarm Recovery Procedures (15.1) | EA 15.1 | Done | 2
1004308 | #332951 | Story | Feature 332951: Lab Support of RBS IETM Updates (15.2) | EA 15.1 | Done | 2
1004266 | #377437 | Story | Feature 377437 ETT: PCR Verification (All) | EA 14.4 | Done | 3 | #1004660 #1004659 #1004649
1004265 | #377437 | Story | Feature 377437 ETT: IA final Posture Assessment | Unassigned | Invalid | 0
1004264 | #377437 | Story | Feature 377437 ETT: Create final image | Unassigned | Invalid | 0
1004263 | #377437 | Story | Feature 377437 ETT: Review DADMS status | Unassigned | Invalid | 0
1004262 | #377437 | Story | Feature 377437 ETT: Integration Test updates | EA 14.4 | Done | 3 | #1004662
1004260 | #377437 | Story | Feature 377437 ETT: Install SF on Win 10 with new version of MySQL and Apache | Unassigned | Invalid | 0
1004259 | #377437 | Story | Feature 377437 ETT: Fix issues found during IA Patching and STIGs Assessment Part 1 | Unassigned | Invalid | 0
1004258 | #377437 | Story | Feature 377437 ETT: support IA Patching and STIGs Assessment | Unassigned | Invalid | 0
1004257 | #377437 | Story | Feature 377437 ETT: IA Posture Assessment MFR 3 CAP document support | Unassigned | Invalid | 0
1004256 | #377437 | Story | Feature 377437 ETT: Update Hardware/Software Map for ETT Laptop | EA 15.1 | Done | 3 | #1017833
1004251 | #377437 | Story | Feature 377437 ETT: Rebuild the ETT Laptop image with the new SF | Unassigned | Invalid | 0
1004249 | #377437 | Story | Feature 377437 ETT: Harden MariaDB and document the procedure. | Unassigned | Invalid | 0
1004248 | #377437 | Story | Feature 377437 ETT: Get the SimulationFramework set up properly in ClearQuest / ClearCase to build. (Tools) | EA 14.1 | Done | 3
1004247 | #377437 | Story | Feature 377437 ETT: Get the SimulationFramework set up properly in ClearQuest / ClearCase to build. (Developer) | EA 14.1 | Done | 1
1004246 | #377437 | Story | Feature 377437 ETT: Test the new RF Alignment Tool | EA 14.4 | Done | 3 | #377441 #377438 #1004266
1004245 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Code Updates Part 2 | EA 14.2 | Done | 5 | #1007694 #1004244 #1005511
1004244 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Code Updates Part 3 | EA 14.3 | Done | 5 | #1007694 #1005510 #1004246
1004243 | #377437 | Story | Feature 377437 ETT: Update the component of the SimFramework - Code Updates Part 1 | EA 14.1 | Done | 5 | #1007694 #1004245 #1005509
1004241 | #377437 | Story | Feature 377437 ETT: Migrate the actual database to MariaDB making changes to the schema as needed to make it work with the newer DB software. | Unassigned | Invalid | 0
1004240 | #1004171 | Story | Feature 1004171: Create the Site Functional Test Case | EA 15.1 | Done | 1
1004239 | #377437 | Story | Feature 377437 ETT: Upgrade the DB software and document the procedure | Unassigned | Invalid | 0
1004238 | #381608 | Story | Feature 381608: Initiate CM PDO Processing for all CI's | EA 14.1 | Done | 1
1004230 | #1004171 | Story | Feature Demo - Customer Demo Event - Feature 1004171: | EA 16.1 | New | 1
1004171 | #381600 | Feature | Implement Group Provisioning Change | PI 16 - In Progress | Implementing
1004170 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Testing | EA 14.4 | Done | 1
1004168 | #1001248 | Story | Feature 1001248 OTAP: Update Profile Portability Call Flows | EA 14.3 | Done | 2
1004167 | #387448 | Story | Incorporate Core Document Redlines into Baseline | EA 14.2 | Done | 2
1004166 | #387448 | Story | Incorporate CAI Redlines into Baseline | EA 14.5 | Done | 1
1004165 | #387448 | Story | Update P2P Communication Call Flows | EA 14.1 | Done | 1
1004164 | #387448 | Story | Generate Essential Documents Drawing Tree | EA 14.1 | Done | 2
1004140 | #1002606 | Story | Feature 1002606: SME support of Build RCG | PI 17 | New | 3
1004139 | #1002606 | Story | Feature 1002606: Build RCG | PI 17 | New | 8
1004133 | #343915 | Task | Story 343915: CM Release of 98-P55479M - GTS - RN - ETI - ETT - SVD (EAD 14 OOC) | EA 14.1 | Done
1004123 | #1002345 | Story | Feature 1002345: Incorporation of IETM Updates and support Tester Execution - HW Drawings for HLR/AuC HW & SW | PI 16 | New | 3
1004096 | #1004094 | Story | Feature 1004094: Support Common Design for use of Passwords and Credential Management (UX) | PI 17 | New | 2
1004095 | #1004094 | Story | Feature 1004094: Support Common Design for use of Passwords and Credential Management | PI 17 | New | 5
1004094 | #1004098 | Feature | OBS: Develop Common Design for use of Passwords and Credential Management | PI 17 | Analyzing
1004091 | #1002345 | Story | Feature 1002345: Update HP HLR/AuC SVD | PI 16 | New | 5
1004089 | #378000 | Problem | EAD14 Deployment - AWARE Softphone manual startup script had to be moved | EA 14.1 | Closed
1004027 |  | Task | Story 393213: CM Release of 98-P53557T - GTS - RN - RCG Server - SVD (EAD 17) | Unassigned | New
1004016 | #393265 | Problem | Update IETM Schedule of Routine Procedures for On-Orbit Operations to include password maintenance | EA 15.4 | Approved
1003914 | #392058 | Problem | Feature 392058: IETM Recovery procedure incorrect for ETI_11xx and ETI_7101 | EA 15.1 | Closed
1003897 | #383958 | Story | Feature 383958 Bulk SAR: PPA Implementation, Integration, development Testing including updating design - part 5 | PI 15 | Invalid | 0
1003896 | #383958 | Story | Feature 383958 Bulk SAR: PPA Implementation, Integration, development Testing including updating design - part 4 | EA 15.2 | Done | 8
1003895 | #383958 | Story | Feature 383958 Bulk SAR: PPA Implementation, Integration, development Testing including updating design - part 3 | EA 15.1 | Done | 8
1003894 | #383958 | Story | Feature 383958 Bulk SAR: PPA Implementation, Integration, development Testing including updating design - part 2 | EA 14.4 | Done | 3
1003893 |  | Story | Feature 392743 ATO: Restore host after STIG issue in SWIT - part 2 | PI 14 | Invalid | 0
1003891 | #378964 | Task | Cecilia Reynolds PTO (EA 14.4 (3/17)) | EA 14.4 | Done
1003864 | #1014387 | Problem | EAD14 Deployment: Prism ETISP SVD Redlines | EA 15.3 | Closed
1003755 | #378000 | Problem | EAD14 Deployment: IETM changes identified during EAD14 AWARE deployment | EA 14.1 | Closed
1003754 | #379761 | Problem | FM whitelist remove manpack radio link down alarms | EA 14.4 | Closed
1003728 | #354871 | Story | Feature 354871: Development of NAVSOC OA Workstation upgrade (14.5) | EA 14.5 | Done | 2
1003727 | #354871 | Story | Feature 354871: Development of NAVSOC OA Workstation upgrade (14.4) | EA 14.4 | Done | 1
1003726 | #354871 | Story | Feature 354871: Development of NAVSOC OA Workstation upgrade (14.3) | EA 14.3 | Done | 1
1003724 | #354871 | Story | Feature 354871: Development of NAVSOC OA Workstation upgrade (14.2) | EA 14.2 | Done | 2
1003723 | #354871 | Story | Feature 354871: Development of NAVSOC OA Workstation upgrade (14.1) | EA 14.1 | Done | 3
1003719 |  | Problem | Update RT Logic password expiration impacts in the Account Maintenance Plan | PI 17 | Approved
1003717 | #379761 | Problem | Update FM Whitelist for AHM_0007 and AHM_0009 | EA 14.4 | Closed
1003635 |  | Task | Story XXXXXX: ICM Release of 99-P53449E - ILS - IETM (EAD 16) | PI 14 | Invalid
1003609 | #386935 | Problem | GEO EAD14 deployment: UFO-1 results have a low yield. | EA 14.3 | Closed
1003585 | #354680 | Story | Feature 354680 (Site): Formal Update of GS Key Mgt | PI 14 | Invalid | 0
1003583 | #354680 | Story | Feature 354680: Update of Parts List for Implementation of SPLUNK HA | EA 14.4 | Invalid | 0
1003582 | #354680 | Story | Feature 354680 (Site): Formal Update of HW/SW Map | EA 14.1 | Done | 2
1003581 | #354680 | Story | Feature 354680 (Site): Formal Update of PKI - part 1 | EA 14.1 | Done | 3
1003574 | #363573 | Story | Analysis of Troubleshooting Approach - SIC | PI 17 | New | 3
1003569 |  | Problem | RNC group owner receives an unexpected inactivity timeout message from listener after the call has been released | Unassigned | Assessing
1003480 | #1002381 | Story | Feature 1002381: Evaluate Thermal Analysis for HLR/AuC Cabinet | EA 14.5 | Done | 2
1003461 | #1003452 | Task | Feature 1003452: Brown, Paul (EA 14.4) | EA 14.4 | Invalid
1003460 | #1003452 | Task | Feature 1003452: Brown, Paul (EA 14.3) | EA 14.3 | Invalid
1003459 | #1003452 | Task | Feature 1003452: Brown, Paul (EA 14.2) | EA 14.2 | Invalid
1003453 | #1003452 | Task | Feature 1003452: Brown, Paul (EA 14.1) | EA 14.1 | Invalid
1003447 | #378000 | Problem | EAD14 Deployment: Redlines to AWARE SVD | EA 14.1 | Closed
1003402 |  | Story | Feature 1003390: IA Support Part 2 | Unassigned | Invalid | 0
1003401 |  | Story | Feature 1003390: IA Support Part 1 | Unassigned | Invalid | 0
1003396 | #378000 | Problem | AWARE PKI update | EA 14.1 | Closed
1003393 | #1006376 | Problem | Non-optimal list of cells being generated in the MAMA2 Response for non-group based cell selection | EA 15.4 | Verifying
1003372 | #384136 | Story | Feature 384136: Update NME Windows 10 SVD 98-P59860M for IP/Gateway/DNS changes for HBSS Remote Console | EA 14.2 | Done | 3 | #1007603
1003368 | #343918 | Task | Story 343918: CM Release of 01-P59554V – ILS – Laptop, MTCAJM GEN 2 Assembly | EA 14.1 | Done
1003364 | #343918 | Task | Story 343918: CM Release of PL01-P59554V – ILS – Laptop, MTCAJM GEN 2 Assembly - Parts List | EA 14.1 | Done
1003357 | #343918 | Task | Story 343918: CM Release of PL01-P53003E001 – ILS – RAF Install NW | EA 14.1 | Done
1003354 | #343918 | Task | Story 343918: CM Release of PL01-P53004E001 – ILS – RAF Install AU | EA 14.1 | Done
1003353 |  | Story | Placeholder Story | PI 15 | Invalid | 0
1003352 |  | Story | Placeholder Story | PI 14 | Invalid | 0
1003351 |  | Problem | Firewall reports ranimgmt-sc-1 sending messages to fcu101-au on port 8081. Policy does not support this activity. It looks like a network flood. | Unassigned | Assessing
1003266 | #378964 | Task | Amelia Watt PTO (EA 14.2 (2/14)) | EA 14.2 | Done
1003264 | #1013259 | Story | Feature 1013259: Prepare 3 AWARE Radios for Shipment to Sicily | PI 17 | New | 3
1003263 | #342054 | Story | Feature 342054: Configure AWARE Hardware in Depot | PI 16 | New | 2
1003161 | #378000 | Problem | Connected AWARE: Update muos Database Password script failed to update files | EA 14.1 | Closed
1003137 | #354871 | Story | Feature 354871: Working with Vendor (ADS) to resolve issues preventing the NAVSOC OA Workstation upgrade (14.5) | EA 14.5 | Done | 1
1003135 | #354871 | Story | Feature 354871: Working with Vendor (ADS) to resolve issues preventing the NAVSOC OA Workstation upgrade (14.4) | EA 14.4 | Done | 1
1003133 | #354871 | Story | Feature 354871: Working with Vendor (ADS) to resolve issues preventing the NAVSOC OA Workstation upgrade (14.3) | EA 14.3 | Done | 1
1003131 | #354871 | Story | Feature 354871: Working with Vendor (ADS) to resolve issues preventing the NAVSOC OA Workstation upgrade (14.2) | EA 14.2 | Done | 1
1003128 | #354871 | Story | Feature 354871: Working with Vendor (ADS) to resolve issues preventing the NAVSOC OA Workstation upgrade (14.1) | EA 14.1 | Done | 1
1003105 | #392743 | Story | Feature 392743 ATO: MFR 1 CAP | EA 14.1 | Invalid | 0
1003103 | #388195 | Story | Feature 388195: Cyber SE Support | PI 14 | Invalid | 0
1003102 | #384084 | Story | Feature 384084: Cyber SE Support | EA 14.2 | Invalid | 0
1003101 | #354680 | Story | Feature 354680 (Site): Cyber SE Support | PI 14 | Invalid | 0
1003035 | #1001912 | Story | Feature 1001912:WF Burndown part 3 | PI 14 | Invalid | 0
1003034 | #1001912 | Story | Feature 1001912:WF Burn down part 2 | PI 14 | Invalid | 0
1003031 | #1001912 | Story | Feature 1001912: WF Burn down part 1 | PI 14 | Invalid | 0
1003026 | #1001912 | Story | Feature 1001912: Hold demo and feature closeout | PI 15 | Invalid | 0
1003014 | #241246 | Task | <Feature xxx>: Verify xyz common document redlines | Unassigned | Invalid |  | #241249
1003004 | #342054 | Story | I-Level Procedures - Wrap-up common document updates for EAD 18 | PI 16 | New | 1
1003003 | #380808 | Story | CSCI - Wrap-up common document updates for EAD 18 and Submit PDO (EA 16.x) | PI 16 | New | 1
1003001 | #380808 | Story | HW/SW Mapping - Wrap-up common document updates for EAD 18 | PI 16 | Invalid | 0
1003000 | #380808 | Story | PKI - Wrap-up common document updates for EAD 18 | PI 16 | New | 2
1002999 | #342054 | Story | NEDB - Wrap-up common document updates for EAD 18 | PI 16 | New | 1
1002998 | #342054 | Story | AMP - Wrap-up common document updates for EAD 18 | PI 16 | New | 1
1002997 | #1000575 | Story | I-Level Procedures - Wrap-up common document updates for EAD 17 | PI 15 | Invalid | 0
1002996 | #1000575 | Story | CSCI - Wrap-up common document updates for EAD 17 | PI 15 | Invalid | 0
1002995 |  | Story | Functional Block Diagram - Wrap-up common document updates for EAD 17 and submit PDO | Unassigned | Invalid | 0
1002994 |  | Story | HW/SW Mapping - Wrap-up common document updates for EAD 17 and submit PDO (EA 15.4) | Unassigned | Invalid | 0
1002993 | #1000575 | Story | PKI - Wrap-up common document updates for EAD 17 | PI 15 | Invalid | 0
1002992 | #1000575 | Story | NEDB - Wrap-up common document updates for EAD 17 | PI 15 | Invalid | 0
1002991 | #377437 | Story | AMP - Wrap-up common document updates for EAD 17 and submit PDO (EA 15.3) | EA 15.3 | Done | 1 | #1020009
1002990 | #1000574 | Story | I-Level Procedures - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002989 | #1000574 | Story | CSCI - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002988 | #1000574 | Story | Functional Block Diagram - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002987 | #1000574 | Story | HW/SW Mapping - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002986 | #1000574 | Story | PKI - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002985 | #1000574 | Story | NEDB - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002984 | #1000574 | Story | AMP - Wrap-up common document updates for EAD 16 | PI 14 | Invalid | 0
1002961 | #379001 | Task | Re-apply Problem 390482 Task for Deployment | Unassigned | Invalid
1002960 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1002959 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1002926 | #386935 | Problem | Geo Deployment: Fix UFO1 Entries in GUI Search display | EA 14.3 | Closed
1002892 | #353256 | Story | Feature 353256: Conduct Maintainer Refresher Training in AU (Trainer 2) (Days 4-5) | EA 16.3 | New | 2
1002890 | #353256 | Story | Feature 353256: Conduct Maintainer Refresher Training in AU (Trainer 1) (Days 4-5) | EA 16.3 | New | 2
1002886 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Hardware Installation - Part 1 | PI 17 | New | 5
1002885 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Aidan) - Part 1 | PI 17 | New | 5
1002884 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE Software Installation (Engineer 2) - Part 1 | PI 17 | New | 5
1002883 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE RF alignment | PI 17 | New | 2
1002874 | #393391 | Story | Feature 393391: Perform Iterative Implementation, Integration, development Testing including updating design (part 2 of 2) | PI 16 | New | 3
1002832 | #1002477 | Story | Feature 1002477: Training Department Incorporation of CRM Updates into CBT Product | EA 15.1 | Done | 5
1002831 | #1002477 | Story | Feature 1002477: Review Update CBT | EA 15.3 | Done | 3
1002830 | #1002477 | Story | Feature 1002477: Cleanup and Replace the T500GT Lesson with T400XR Lesson | EA 15.2 | Done | 1
1002819 | #1002477 | Story | Feature 1002477: Obtain New Graphics for the NMS Splunk Operations & MUOS SA App Lessons (Part 1) | EA 15.1 | Done | 3
1002800 | #363573 | Story | Analysis of Troubleshooting Approach - TOFF | PI 17 | New | 3
1002799 | #363573 | Story | Analysis of Troubleshooting Approach -UX: Support/Define Up Front Research Question/Metrics | PI 17 | New | 2
1002798 | #363573 | Story | Analysis of Troubleshooting Approach - SE | PI 17 | New | 8
1002767 | #379001 | Task | Re-apply Problem 387316 Task for Deployment | Unassigned | Invalid
1002766 | #379001 | Story | Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
1002765 | #379001 | Story | Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
1002757 | #383110 | Story | Feature xxxxxx: Fix Problem 319351 | Unassigned | New | 8
1002756 | #383110 | Story | Feature xxxxxx: Fix Problem 319759 | Unassigned | New | 2
1002755 | #383110 | Story | Feature xxxxxx: Fix Problem 355347 - part 2 | Unassigned | New | 5
1002754 | #383110 | Story | Feature xxxxxx: Fix Problem 355347 - part 1 | Unassigned | New | 8
1002724 |  | Problem | IETM Provisioning Troubleshooting Guide | Unassigned | Assessing
1002718 | #379001 | Task | Re-apply Problem 390482 Task for Deployment | Unassigned | Invalid
1002717 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1002716 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1002686 |  | Task | Re-apply Problem 390482 Task for Deployment | Unassigned | Invalid
1002685 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1002684 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1002678 | #379001 | Task | Re-apply Problem 390482 Task for Deployment | Unassigned | Invalid
1002677 | #379001 | Story | Re-write and Test Problem 390482 Story | Unassigned | Invalid | 0
1002676 | #379001 | Story | Rebase and Test Problem 390482 Story | Unassigned | Invalid | 0
1002642 | #1002621 | Story | Define changes to Debug and Trace Level Logging | Unassigned | New | 8
1002641 | #1002621 | Story | Define changes to Debug and Trace Level Logging | Unassigned | New | 8
1002640 | #1002621 | Story | Define changes to Debug and Trace Level Logging | Unassigned | New | 8
1002637 | #1002606 | Story | Feature 1002606: Implement changes to Info Level Logging | PI 17 | New | 8
1002636 | #1002606 | Story | Define changes to Info Level Logging | PI 17 | New | 8
1002635 | #1002621 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
1002634 | #1002621 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | New | 1 | #1002635
1002633 | #1002621 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #1002634
1002632 | #1002621 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #1002634
1002631 | #1002621 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | New | 0 | #1002634
1002630 | #1002621 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | New | 1
1002629 | #1002621 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | New | 3
1002628 | #1002621 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | New | 3 | #1002634
1002627 | #1002621 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | New | 1 | #1002634
1002626 | #1002621 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #1002634
1002625 | #1002621 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #1002634
1002624 | #1002621 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | New | 3 | #1002634 #1002626 #1002632 #1002633
1002623 | #1002621 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #1002624 #1002626
1002622 | #1002621 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | New
1002621 | #381595 | Feature | RCG Logging Debug-Trace Level Updates | PI 17 | Analyzing
1002620 | #1002606 | Story | Feature 1002606: Initiate CM PDO Processing for all CI's | PI 17 | New | 1
1002619 | #1002606 | Story | Feature 1002606: Prep and Perform Feature Demo – Customer Demo Event | PI 17 | New | 1 | #1002620
1002618 | #1002606 | Story | Feature 1002606: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 17 | New | 2 | #1002619
1002617 | #1002606 | Story | Feature 1002606: Execute STCD Feature Integration and testing including STCD updates identified | PI 17 | New | 20 | #1002619
1002616 | #1002606 | Story | Feature 1002606: Update and review SVD | PI 17 | New | 3 | #1002619
1002615 | #1002606 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
1002614 | #1002606 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
1002613 | #1002606 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #1002619
1002612 | #1002606 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #1002619
1002611 | #1002606 | Story | Feature 1002606: Perform Iterative Implementation, Integration, development Testing including updating design | PI 17 | New | 8 | #1002619
1002610 | #1002606 | Story | Feature 1002606: Provide Deployment Notes and Operator Impact Inputs | PI 17 | New | 1 | #1002619
1002609 | #1002606 | Story | Feature 1002606: Create STCD and review with stakeholders | PI 17 | New | 3 | #1002618 #1002619 #1002611 #1002617
1002608 | #1002606 | Story | Feature 1002606: Document Initial capability specification and detailed design to start Implementation | PI 17 | New | 8 | #1002609 #1002611
1002607 | #1002606 | Task | Feature 1002606: Hold Feature Review with SMEs | PI 17 | New
1002606 | #381595 | Feature | RCG Logging Info Level Update | PI 17 | Approved
1002596 | #379001 | Task | Re-apply Problem 387316 Task for Deployment | Unassigned | Invalid
1002595 | #379001 | Story | Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
1002583 | #243505 | Feature | Tools Team Support / LOE for SDE/ODE Environment in PI 15 | EA 15.5 | Implementing
1002548 | #396437 | Story | Implement Direct NAS RDE Backup | EA 14.3 | Done | 3
1002533 | #381524 | Task | Feature 381524: Submit PDO for 98-P59815M - NMS - NM - ProvBridge - SVD | EA 15.4 | New
1002530 | #343920 | Task | Story 343920: CM Release of MUOS_IG_GS_NMS_NM_Provisioning_OTAP_SVD_98-P59419M (EAD 16) | PI 14 | Done
1002512 | #395174 | Story | Feature 395174: Monitor NW De-Ice Furnace ET3 Issue | EA 14.2 | Invalid | 0
1002491 | #1000707 | Feature | OBS - HLR: Complete and Release As-Built documentation for HLR Solution | Unassigned | Rejected
1002486 | #1000707 | Feature | OBS - HLR: Complete and Release ILS Documentation for HLR Solution | PI 16 | Rejected
1002477 | #262146 | Feature | Incorporate CRM comments into the Training Conduct Support Package (A013) | EA 15.3 | Done
1002428 | #1013259 | Story | Support Deployment of HLR at NW | PI 17 | New | 13
1002425 | #1013259 | Story | Support Deployment of HLR at WH | PI 17 | New | 13
1002424 | #1002345 | Story | Feature 1002345: Support HP integration and Validation into VLab (Week 1) | PI 16 | New | 5
1002419 | #1002381 | Story | Feature 1002381: Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 120 days prior to FRCB; | EA 15.4 | Implementing | 3
1002418 | #1002381 | Story | Feature 1002381: Completion of Base Electronic System Engineer Plan BESEP (needed 120 days prior to FRCB) | EA 15.1 | Done | 2
1002416 | #1002381 | Story | Feature 1002381: Identify Logistics Considerations for OBS - HLR: HW/FRCB for HLR Deployment (non-IETM) | EA 14.3 | Done | 1
1002415 | #1002381 | Story | Feature 1002381: Define Power Consumption Changes for IDP Associated with OBS - HLR: HW/FRCB for HLR Deployment | EA 14.4 | Done | 0
1002413 | #1002381 | Story | Feature 1002381: CoCo Review of Finalized Drawings for IDP Associated with OBS - HLR: HW/FRCB for HLR Deployment | EA 14.5 | Invalid | 0
1002412 | #1002381 | Story | Feature 1002381: Generate Test Report, needed 45 days prior to FRCB. | PI 16 | New | 3
1002411 | #1002381 | Story | Feature 1002381: Complete System Operational Verification Test, SOVT, needed 90 days prior to FRCB | EA 15.3 | Done | 5
1002410 | #1002381 | Story | Feature 1002381: Generate System Operational Verification Test, SOVT, Test Inputs for Feature, needed 90 days before FRCB | EA 15.2 | Done | 5
1002401 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Sprint 5 | EA 14.5 | Invalid | 0
1002381 | #1000707 | Feature | OBS - HLR: HW/FRCB for HLR Deployment | PI 16 - In Progress | Implementing
1002363 | #1002345 | Story | Feature 1002345: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
1002362 | #1002345 | Story | Feature 1002345: Prep and Perform Feature Demo – Customer Demo Event | PI 16 | New | 1 | #1002363
1002361 | #1002345 | Story | Feature 1002345: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.2 | Done | 1 | #1002362
1002360 | #1002345 | Story | Feature 1002345: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 5 | #1002362
1002359 | #1002345 | Story | Feature 1002345: Provide Development inputs to AMP common document | PI 16 | New | 1 | #1002362
1002358 | #1002345 | Story | Feature 1002345: MFR 3 – CSE Completes Final CAP | PI 16 | New | 5 | #1002362
1002357 | #1002345 | Story | Feature 1002345: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 16 | New | 3 | #1002358 #1002362
1002356 | #1002345 | Story | Feature 1002345: Style Guide, Dry Run of IETM Updates and Integration Support for HLR/AuC HW & SW | PI 16 | New | 2
1002355 | #1002345 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
1002354 | #1002345 | Story | Feature 1002345: Develop IETMs and Perform Development Testing | PI 16 | New | 2 | #1002362 #1002356 #1004123
1002353 | #1002345 | Story | Feature 1002345: MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | PI 16 | New | 5 | #1002357
1002352 | #1002345 | Story | Feature 1002345: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | PI 16 | New | 1 | #1002353
1002351 | #1002345 | Story | Feature 1002345: MFR 3 – CSE Performs initial Cybersecurity Assessment | PI 16 | New | 5 | #1002352
1002350 | #1002345 | Story | Feature 1002345: Update and execute ATP in VLAB | EA 14.4 | Done | 8 | #1002351 #1002362
1002349 | #1002345 | Story | Feature 1002345: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 1 | #1002362
1002348 | #1002345 | Story | Feature 1002345: Iterative STCD Development and Site Functional Plan (replicate per sprint) | EA 14.3 | Done | 3 | #1002360 #1002350 #1002361 #1002362
1002347 |  | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 14 | Invalid | 0 | #1002350 #1002349 #1002348
1002346 | #1002345 | Task | Feature 1002345: Hold Feature Review with SMEs | EA 14.3 | Done
1002345 | #1000707 | Feature | OBS - HLR: Upgrade HP HLR/AuC HW & SW | PI 16 - In Progress | Implementing |  | #1002425 #1002428
1002344 | #354680 | Task | Feature 354680 (SITE): Rebase SPLUNK Enterprise Timestamp Issue (Problem 1001538) | EA 14.1 | Done
1002246 | #386935 | Problem | Geo Deployment: Discrepancies noted in the following rpm package file names when performing a query | EA 14.3 | Closed
1002127 | #297335 | Story | Import CC VOB Tags to RDEwin region | EA 14.5 | Done | 2
1002094 | #1002089 | Story | Feature 1002089: Support SC Training | EA 14.2 | Done | 3
1002091 | #1002089 | Story | Feature 1002089: Update Refresher Training Materials with Comments/Lessons Learned from SC | EA 14.5 | Invalid | 0
1002089 | #262146 | Feature | Update Refresher Training Materials to Include Redlines from WH and SC Refresher Training Events | EA 14.3 | Done
1002060 |  | Story | Identify if CAT1 has been Resolved or Mitigated (13.5) | Unassigned | Invalid | 0
1002041 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Sprint 3 | EA 14.5 | Invalid | 0
1002040 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Sprint 4 | EA 14.4 | Done | 1
1002038 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Sprint 2 | EA 14.2 | Invalid | 0
1002037 | #1002036 | Story | TD 19-10 Service Management Additional Tasks - Sprint 1 | EA 14.5 | Invalid | 0
1002036 | #245569 | Feature | TD 19-10 Service Management Additional Tasks - respond to questions from ATT | EA 14.5 | Done
1001945 | #395174 | Story | Feature 395174: TOFF - HW FRB Support EA 14.4 | EA 14.4 | Done | 2
1001943 | #395174 | Task | Feature 395174: TOFF - HW FRB Support EA 14.3 | EA 14.3 | Invalid
1001941 | #395174 | Story | Feature 395174: TOFF - HW FRB Support EA 14.2 | EA 14.2 | Done | 2
1001935 | #395174 | Story | Feature 395174: TOFF - HW FRB Support EA 14.1 | EA 14.1 | Done | 2
1001932 | #393391 | Task | Feature 393391: Submit PDO for 98-P53544T - GTS - SWITCH - HSS -SVD | PI 16 | New
1001926 | #297335 | Story | Coordinate with IT to perform CQ Database Final Cutover Activities | EA 15.1 | Done | 3
1001924 | #297335 | Story | Create remaining RDE Windows 2012 VMs using the completed UserSvcsTemplate (1 to 2 VMs) | EA 14.2 | Done | 2
1001922 | #297335 | Story | Complete the configuration of UserSvcBase VM Template | EA 14.2 | Done | 3
1001921 | #297335 | Story | Create /Update remaining RDE Workstation VMs based on the previously validated RDE Developer Workstation- (8 VMs) | EA 14.1 | Done | 5
1001920 | #297335 | Story | Resolve Issues found in RDE Developer Workstation (Solaris 10) | EA 15.1 | Done | 5
1001913 | #1001912 | Story | Feature 1001912: Cyber Support for WF PWI Burnoff | PI 14 | Invalid | 0
1001912 | #245573 | Feature | WF PWI Burn down - Group | EA 15.1 | Done
1001905 |  | Story | Fix Problem 387255 | PI 14 | Invalid | 0
1001826 | #1007900 | Problem | Monitor ePolicy Orchestrator – Normal Operation Procedure for step 2.2.9.4 should be the same as 2.2.9.5 | PI 16 | Approved
1001675 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.5 | EA 14.5 | Done | 3
1001674 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.3 | EA 14.3 | Done | 3
1001673 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 14.1 | EA 14.1 | Done | 3
1001671 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 15.5 | EA 15.5 | New | 1
1001670 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 15.4 | EA 15.3 | Done | 1
1001669 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 15.3 | EA 15.3 | Done | 3
1001668 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 15.2 | EA 15.2 | Done | 1
1001667 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 15.1 | EA 15.1 | Done | 1
1001664 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 14.5 | EA 14.5 | Done | 1
1001663 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 14.4 | EA 14.4 | Done | 1
1001661 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 14.3 | EA 14.3 | Done | 1
1001659 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 14.2 | EA 14.2 | Done | 1
1001658 | #372921 | Story | Support RMF IATT effort for call banks (Systems) - 14.1 | EA 14.1 | Done | 1
1001652 |  | Story | Determine Method of Deployment for CAT1s | Unassigned | Invalid | 0
1001649 | #1001636 | Story | 7) Create PWIs for Priority CAT1s (Part 2) | EA 14.4 | Done | 1
1001646 | #1001636 | Story | 4) Determine Priority Order for Open CAT1s | EA 14.2 | Done | 1
1001644 | #1001636 | Story | 5) Load new POAM into the IA Repository database in the SEL. | EA 14.5 | Invalid | 0
1001642 | #1001636 | Story | 8) Work with PMW to disposition resolved/mitigated CAT1s | EA 14.5 | Invalid | 0
1001640 |  | Story | Identify if CAT1 has been Resolved or Mitigated (13.4a) | Unassigned | Invalid | 0
1001636 | #245560 | Feature | Cyber: CAT1 Mitigation and Burndown | EA 14.5 | Done
1001611 |  | Problem | MUOSAT-SP: SoftPhone does not report specific error codes back to automation for some vague failures | Unassigned | Assessing
1001609 |  | Story | Feature 393396: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
1001608 |  | Story | Feature 393396: Prep and Perform Feature Demo – Customer Demo Event | PI 15 | Invalid | 0 | #1001609
1001607 |  | Story | Feature 393396: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 15 | Invalid | 0 | #1001608
1001606 |  | Story | Feature 393396: Execute STCD Feature Integration and testing including STCD updates identified | PI 15 | Invalid | 0 | #1001608
1001605 |  | Story | Feature 393396: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1001608
1001604 |  | Story | Feature 393396: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 15 | Invalid | 0
1001603 |  | Story | Feature 393396: UX Research and Design Support (Change back to UX Team) | PI 15 | Invalid | 0
1001602 |  | Story | Feature 393396: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1001608
1001601 |  | Story | Feature 393396: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 15 | Invalid | 0 | #1001608
1001600 |  | Story | Feature 393396: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 | Invalid | 0 | #1001608
1001599 |  | Story | Feature 393396: Provide Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0 | #1001608
1001598 |  | Story | Feature 393396: Create STCD and review with stakeholders | PI 15 | Invalid | 0 | #1001606 #1001608 #1001607 #1001600
1001597 |  | Story | Feature 393396: Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #1001598 #1001600
1001596 |  | Task | Feature 393396: Hold Feature Review with SMEs | PI 15 | Invalid
1001595 |  | Feature | <Feature xxx> MFR1 Template | PI 15 | Rejected
1001592 | #393391 | Story | Feature 393391: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
1001591 | #393391 | Story | Feature 393391: Prep and Perform Feature Demo Ð Customer Demo Event | PI 16 | New | 1 | #1001592
1001590 | #393391 | Story | Feature 393391: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 16 | New | 2 | #1001591
1001589 | #393391 | Story | Feature 393391: Execute STCD Feature Integration and testing including STCD updates identified | PI 16 | New | 3 | #1001591
1001588 | #393391 | Story | Feature 393391: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1001591
1001587 | #393391 | Story | Feature 393391: IETM - Remove CSCF/HSS Disk Maintenance from NMS Routine Procedures | PI 16 | New | 1
1001586 | #393391 | Story | Feature 393391: UX Research and Design Support (Change back to UX Team) | PI 15 | Invalid | 0
1001585 | #393391 | Story | Feature 393391: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1001591
1001584 | #393391 | Story | Feature 393391: MFR 1 Ð Dev Team Performs Cybersecurity Assessment | PI 16 | New | 1 | #1001591
1001583 | #393391 | Story | Feature 393391: Perform Iterative Implementation, Integration, development Testing including updating design (part 1 of 2) | PI 16 | New | 3 | #1001591
1001582 | #393391 | Story | Feature 393391: Provide Deployment Notes and Operator Impact Inputs | PI 16 | New | 1 | #1001591
1001581 | #393391 | Story | Feature 393391: Create STCD and review with stakeholders | PI 16 | New | 3 | #1001583 #1001589 #1001590 #1001591
1001580 | #393391 | Story | Feature 393391: Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #1001583 #1001581
1001579 | #393391 | Task | Feature 393391: Hold Feature Review with SMEs | PI 16 | Done
1001578 |  | Feature | <Feature xxx> MFR1 Template | PI 14 | Rejected
1001571 |  | Problem | MAS whitelisted alarms and recovery procedures need systemic look in order for O-Level to be able to react when actually needed. | Unassigned | Assessing
1001530 |  | Problem | ACAS Scan of EMA11 produced Splunk indication of Provisioning outage | Unassigned | Triage
1001502 |  | Task | Story TBD: CM Release of 98-P61659A – GTS – RN – ETI Test Tool SVD (EAD N/A) | Unassigned | New
1001499 | #383165 | Story | Feature 383165: Finalize New Rack Documentation, Drawings & Parts Lists (01-P59866M NME 201 CABINET ASSEMBLY - NMS) | PI 14 | Invalid | 0
1001453 | #343920 | Task | Story 343920: CM Release of 98-P54107T – GEO – AMS-GS SVD for MPC14.2 | PI 14 | Done
1001404 | #385856 | Story | Feature 385856: Conversion to ACC - TACLANE - Checkout New GEM One Software & Remote TACLANE Upgrade | EA 14.2 | Done | 5
1001373 | #1000254 | Story | Identify approach to Development process using GIT | PI 17 | New | 2
1001367 | #1000254 | Story | Identify approach to VLAB Delivery of build artifacts | PI 17 | New | 2
1001366 | #1000254 | Story | Identify the plan for Build Process interaction with GIT source code | PI 17 | New | 5
1001363 | #1000254 | Story | Identify the GitLab REPO structure for Dev & Release Projects | PI 17 | New | 5
1001362 | #1000254 | Story | Identify GIT Workflow(s) to be adopted | PI 17 | New | 5
1001338 | #396002 | Story | Feature 396002: TOFF PI 14 Technical Support - EA 14.5 | EA 14.5 | Done | 1
1001336 | #396002 | Story | Feature 396002: TOFF PI 14 Technical Support - EA 14.4 | EA 14.4 | Done | 1
1001334 | #396002 | Story | Feature 396002: TOFF PI 14 Technical Support - EA 14.3 | EA 14.3 | Done | 1
1001333 | #396002 | Story | Feature 396002: TOFF PI 14 Technical Support - EA 14.2 | EA 14.2 | Done | 1
1001329 | #396002 | Story | Feature 396002: TOFF PI 14 Technical Support - EA 14.1 | EA 14.1 | Done | 1
1001262 | #1001248 | Story | Feature 1001248 OTAP: Initiate CM PDO Processing for all CI's | EA 14.5 | Done | 1
1001261 | #1001248 | Story | Feature 1001248 OTAP: Prep and Perform Feature Demo – Customer Demo Event | EA 14.5 | Done | 1 | #1001262
1001260 | #1001248 | Story | Feature 1001248 OTAP: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 14.4 | Done | 1 | #1001261
1001259 | #1001248 | Story | Feature 1001248 OTAP: Execute STCD Feature Integration and testing including STCD updates identified | EA 14.4 | Done | 1 | #1001261
1001258 | #1001248 | Story | Feature 1001248 OTAP: Provide Development inputs to common documents | PI 14 | Invalid | 0 | #1001261
1001257 | #1001248 | Story | Feature 1001248: Incorporation of IETM Updates and Integration Support for OTAP Issues Due to Intermittent Locks on Caller Records | PI 14 | Invalid | 0
1001256 | #1001248 | Story | Feature 1001248 OTAP: UX Research and Design Support | PI 14 | Invalid | 0
1001255 | #1001248 | Story | Feature 1001248 OTAP: Develop IETMs and Perform Development Testing | PI 14 | Invalid | 0 | #1001261
1001254 | #1001248 | Story | Feature 1001248 OTAP: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 14.3 | Done | 1 | #1001261
1001253 | #1001248 | Story | Feature 1001248 OTAP: Fix Problem 387255 Perform Iterative Implementation, Integration, and development.- part 1 | EA 14.1 | Done | 5 | #1001261
1001252 | #1001248 | Story | Feature 1001248 OTAP: Provide Deployment Notes and Operator Impact Inputs | EA 14.2 | Done | 1 | #1001261
1001251 | #1001248 | Story | Feature 1001248 OTAP: Create STCD outline and review with stakeholders | EA 14.1 | Done | 2 | #1001261 #1001260 #1001253 #1001259
1001250 | #1001248 | Story | Feature 1001248 OTAP: Document Initial capability specification and detailed design to start Implementation | PI 14 | Invalid | 0 | #1001253 #1001251
1001249 | #1001248 | Task | Feature 1001248 OTAP: Hold Feature Review with SMEs | EA 14.1 | Done
1001248 | #395610 | Feature | OTAP issues due to intermittent locks on caller records | EA 14.5 | Done
1001247 | #1001248 | Story | Fix Problem 387279 : No feedback provided to PPA operator for updates to Terminal Profile Defaults system configuration parameters | EA 14.2 | Done | 1
1001089 | #1000254 | Story | Build Prototype CI for CM Release | PI 17 | New | 3
1001088 | #1000254 | Story | Build Prototype CI for VLab Install | PI 17 | New | 3
1001087 | #1000254 | Story | Test Out GitLab Issue and Linkage to RTC | PI 17 | New | 3
1001086 | #1000254 | Story | Test out checkout check in | PI 17 | New | 3
1001085 | #1000254 | Story | Test out branching/ merging | PI 17 | New | 3
1001084 | #1000254 | Story | Migrate Prototype CI from ClearCase to GitLab | PI 17 | New | 3
1001083 | #1000254 | Story | Create a RAN ICM Release Flow Diagram | PI 17 | New | 1
1001081 | #1000254 | Story | Update GitLab Scripts/ Tool to Support ICM Release Requirements | PI 17 | New | 3
1001080 | #1000254 | Story | Identify Requirements for ICM Release | PI 17 | New | 3
1001079 | #1000254 | Story | Setup GitLab CM System on Development Server | PI 17 | New | 3
1001078 | #1000254 | Story | Create a SDE/ODE Build Flow Diagram | PI 17 | New | 1
1001075 | #1001062 | Story | Lock and Obsolete old/unused UCM Projects in ClearCase (RDE) | EA 15.2 | Done | 1
1001067 |  | Story | Lock and Decommission ERIC CC Region VOBs | PI 15 | Invalid | 0
1001066 | #1001062 | Story | Lock and Decommission RAN CC & Eric Region VOBs | EA 15.2 | Done | 1
1001064 | #1001062 | Story | Add RDE Crmregister information to Tools Info page in Sharepoint | EA 15.1 | Done | 1
1001062 | #243505 | Feature | RAN Dev Env (RDE) Post Transition Cleanup | EA 15.5 | Implementing
1001059 | #1001062 | Story | Update Sharepoint Tools page with RDE crmregister info | PI 15 | Invalid | 0
1001058 | #297335 | Story | Complete the split of User /home directories from /home in the RAN vs /home in RDE | EA 14.1 | Done | 3
1001057 | #297335 | Story | Migrate any necessary BuildForge jobs from RAN/RANDBS to RDE/RDEDBS | EA 15.2 | Done | 5 | #334396
1001056 | #1020744 | Story | RAN Issue- Investigate and fix error relating to creating baselines for RBS product build | EA 16.3 | New | 3
1001051 | #1000847 | Story | Update Documentation on MUOSRel | EA 14.3 | Done | 1
1001050 | #1000847 | Story | Test and Resolve Build Actions on MUOSRel | EA 14.2 | Done | 2
1001049 | #1000847 | Story | Test and Resolve Developer Actions on MUOSRel | EA 14.2 | Done | 2
1001047 | #1000847 | Story | Migrate MUOSRel Application | EA 14.3 | Done | 1
1001042 | #396437 | Story | Tools Team Support / LOE for RAN/RDE for EA 14.3 | EA 14.3 | Invalid | 0
1001041 | #396437 | Story | Tools Team Support / LOE for RAN/RDE for EA 14.5 | EA 14.5 | Done | 3
1001040 | #396437 | Story | Tools Team Support / LOE for RAN/RDE for EA 14.4 | EA 14.4 | Invalid | 0
1001039 | #396437 | Story | Tools Team Support / LOE for RAN/RDE for EA 14.2 | EA 14.2 | Invalid | 0
1001038 | #396437 | Story | Tools Team Support / LOE for RAN/RDE for EA 14.1 | EA 14.1 | Invalid | 0
1001036 | #396415 | Story | LOE for SDE/ODE for EA 14.5 | EA 14.5 | Done | 3
1001035 | #396415 | Story | LOE for SDE/ODE for EA 14.4 | EA 14.4 | Done | 5
1001034 | #396415 | Story | LOE for SDE/ODE for EA 14.3 | EA 14.3 | Done | 5
1001033 | #396415 | Story | LOE for SDE/ODE for EA 14.2 | EA 14.2 | Done | 5
1001032 | #396415 | Story | LOE for SDE/ODE for EA 14.1 | EA 14.1 | Done | 5
1001028 | #293338 | Story | Tools Team support of Developer testing and acceptance of Virtualized Developer Workstations (SWIT) | EA 14.5 | Done | 5
1001026 | #293338 | Story | Developer Support for SWIT VM Template- MUOS Specific SW Installations (JBoss, Tectia) | EA 14.2 | Done | 2
1000995 | #1013136 | Problem | [MAINT] PrevClockFrequencyErrorEstimatePPM needs to set to ZERO when FPGA fails to lock on when using PrevClockFrequencyErrorEstimatePPM of non-zero | EA 16.1 | Close Pending
1000956 | #379001 | Story | Rebase Problem 388765 - SFRE script needed for ETI switchover procedure | Unassigned | New | 1
1000920 | #1000902 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
1000919 | #1000902 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | PI 15 | Invalid | 0 | #1000920
1000918 | #1000902 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 15 | Invalid | 0 | #1000919
1000917 | #1000902 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | PI 15 | Invalid | 0 | #1000919
1000916 | #1000902 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1000919
1000915 | #1000902 | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP (Change back to Cyber) | PI 15 | Invalid | 0 | #1000919
1000914 | #1000902 | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 15 | Invalid | 0 | #1000919 #1000915
1000913 | #1000902 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 15 | Invalid | 0
1000912 | #1000902 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 15 | Invalid | 0
1000911 | #1000902 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1000919
1000910 | #1000902 | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | PI 15 | Invalid | 0 | #1000914
1000909 | #1000902 | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | PI 15 | Invalid | 0 | #1000910
1000908 | #1000902 | Story | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | PI 15 | Invalid | 0 | #1000909
1000907 | #1000902 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 | Invalid | 0 | #1000919 #1000908
1000906 | #1000902 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0 | #1000919
1000905 | #1000902 | Story | <Feature xxx>: Create STCD and review with stakeholders | PI 15 | Invalid | 0 | #1000918 #1000919 #1000907 #1000917
1000904 | #1000902 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #1000907 #1000906 #1000905
1000903 | #1000902 | Task | <Feature xxx> Hold Feature Review with SMEs | PI 15 | Invalid
1000902 |  | Feature | <Feature xxx> MFR3 Template | PI 15 | Rejected
1000901 | #1000884 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
1000900 | #1000884 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #1000893
1000899 | #1000884 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #395544 #1000893
1000898 | #1000884 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #1000893
1000897 | #1000884 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #1000893
1000896 | #1000884 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #1000893
1000895 | #1000884 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #1000893
1000894 | #1000884 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #1000893 #1000899 #1000897 #1000896
1000893 | #1000884 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #1000892
1000892 | #1000884 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
1000891 | #1000884 | Story | <Feature xxx>: MFR 2 – Cyber Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0
1000890 | #1000884 | Story | <Feature xxx>: MFR 2 – Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0
1000889 | #1000884 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves ACAS Scan Findings | Unassigned | Invalid | 0
1000888 | #1000884 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves Final ACAS Scan Findings | Unassigned | Invalid | 0
1000887 | #1000884 | Story | <Feature xxx>: MFR 2 – Cyber Completes Final CAP | Unassigned | Invalid | 0
1000886 | #1000884 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
1000885 | #1000884 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #1000895 #1000899 #1000894
1000884 |  | Feature | <Feature xxx> MFR2 Template | Unassigned | Rejected
1000883 | #1000884 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
1000880 | #1000866 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
1000879 | #1000866 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | PI 15 | Invalid | 0 | #1000880
1000878 | #1000866 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 15 | Invalid | 0 | #1000879
1000877 | #1000866 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | PI 15 | Invalid | 0 | #1000879
1000876 | #1000866 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #1000879
1000875 | #1000866 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 15 | Invalid | 0
1000874 | #1000866 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 15 | Invalid | 0
1000873 | #1000866 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #1000879
1000872 | #1000866 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 15 | Invalid | 0 | #1000879
1000871 | #1000866 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 | Invalid | 0 | #1000879
1000870 | #1000866 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0 | #1000879
1000869 | #1000866 | Story | <Feature xxx>: Create STCD and review with stakeholders | PI 15 | Invalid | 0 | #1000871 #1000877 #1000878 #1000879
1000868 | #1000866 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #1000871 #1000869
1000867 | #1000866 | Task | <Feature xxx> Hold Feature Review with SMEs | PI 15 | Invalid
1000866 |  | Feature | <Feature xxx> MFR1 Template | PI 15 | Rejected
1000853 | #293338 | Story | Develop SWIT VM Template | EA 14.2 | Done | 5 | #342802
1000852 | #293338 | Story | Obtain SW Licenses Needed for SWIT | EA 14.2 | Done | 2
1000847 | #243505 | Feature | Update MUOSRel App68 | EA 14.3 | Done
1000802 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Front Fan Tray (1), Routing Engine Board (RE) (1) and Rear Fan Tray (1) 3 parts total | EA 14.3 | Invalid | 0
1000801 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - BFBBN 101 01/1 FAN (1) and BFD 509 08/4 FAN (1) 2 parts total | EA 15.3 | Done | 1
1000800 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - BFDBN 509 01/1 FAN x 1 | EA 15.3 | Done | 1
1000799 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 15.5 | New | 1
1000798 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 15.5 | New | 1
1000797 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 14.3 | Done | 1
1000796 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 14.3 | Done | 1
1000795 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 14.3 | Done | 1
1000794 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 14.3 | Done | 1
1000793 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - GPB53, 1GHZ, 1GB/1.5-2GB x 1 | EA 14.1 | Invalid | 0
1000792 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - BKV 301 487/1 FAN UNIT x 2 | EA 15.3 | Done | 1
1000791 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - PEBV3 POWER & ETHERNET x 2 | EA 14.5 | Invalid | 0
1000790 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - PEBV3 POWER & ETHERNET x 1 | EA 14.5 | Invalid | 0
1000789 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBTEV3 4XT1/E1 x 2 | EA 15.5 | New | 1
1000788 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBTEV3 4XT1/E1 x 2 | EA 15.3 | Done | 1
1000787 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBTEV3 4XT1/E1 x 2 | EA 15.3 | Done | 1
1000786 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBTEV3 4XT1/E1 x 2 | EA 14.5 | Invalid | 0
1000785 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBTEV3 4XT1/E1 x 1 | EA 15.3 | Done | 1
1000784 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 14.2 | Done | 1
1000783 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 14.2 | Done | 1
1000782 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 14.3 | Done | 1
1000781 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 15.5 | New | 1
1000780 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 15.5 | New | 1
1000779 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 15.5 | New | 1
1000778 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBS7V3 SS7 x 2 | EA 14.4 | Invalid | 0
1000777 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000776 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.4 | Implementing | 1
1000775 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.4 | Implementing | 1
1000774 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.4 | Done | 1
1000773 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000772 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000771 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000770 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000769 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - IBASV3B ATM SMF x 2 | EA 15.2 | Done | 1
1000768 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.1 | Done | 1
1000767 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.2 | Done | 1
1000766 | #1008620 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 15.4 | New | 1
1000765 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.5 | Done | 1
1000764 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.5 | Done | 1
1000763 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.5 | Done | 1
1000762 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.5 | Done | 1
1000761 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.4 | Done | 1
1000760 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.5 | Done | 1
1000759 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.4 | Done | 1
1000758 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.4 | Done | 1
1000757 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.4 | Done | 1
1000756 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.4 | Done | 1
1000755 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - AIU Board x 2 | EA 14.1 | Done | 1
1000754 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Managing the boards in the v-lab, coordinating swapping/down time and monitor automation | EA 14.5 | Done | 1
1000753 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Managing the boards in the v-lab, coordinating swapping/down time and monitor automation | EA 14.4 | Done | 1
1000752 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Managing the boards in the v-lab, coordinating swapping/down time and monitor automation | EA 14.5 | Done | 1
1000751 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Managing the boards in the v-lab, coordinating swapping/down time and monitor automation | EA 14.2 | Done | 1
1000750 | #379221 | Story | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Managing the boards in the v-lab, coordinating swapping/down time and monitor automation | EA 14.3 | Done | 1
1000749 | #379001 | Story | Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
1000642 | #396002 | Story | Feature 396002: SA PI 13 Technical Support - create Splunk – Infra CI setup docs - Ken | EA 14.5 | Done | 1
1000542 | #1000471 | Story | Implement Profile Portability: Implement, review, and unit test Waveform changes | PI 17 | New | 13
1000541 | #1000471 | Story | Implement Profile Portability: SME support | PI 17 | New | 13
1000536 | #1000471 | Story | Implement Profile Portability: Systems Support | PI 17 | New | 8
1000534 | #1000471 | Story | Implement Profile Portability: Implement and unit test MGS Adapters changes | PI 17 | New | 8
1000533 | #1000471 | Story | Implement Profile Portability: Implement and unit test OTAP changes | PI 17 | New | 13
1000529 | #1000471 | Story | Implement Profile Portability: Implement and unit test KMS changes | PI 17 | New | 20
1000528 | #1000471 | Story | Implement Profile Portability: Implement and unit test PPA changes | PI 17 | New | 13
1000489 | #1000471 | Story | Implement Profile Portability: Initiate CM PDO Processing for all CI's | PI 17 | New | 1
1000488 | #1000471 | Story | Implement Profile Portability: Prep and Perform Feature Demo – Customer Demo Event | PI 17 | Invalid | 0 | #1000489
1000487 | #1000471 | Story | Implement Profile Portability: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 17 | New | 3 | #1000488
1000486 | #1000471 | Story | Implement Profile Portability: Execute STCD Feature Integration and testing including STCD updates identified | PI 17 | New | 20 | #1000488
1000485 | #1000471 | Story | Implement Profile Portability: Provide Development inputs to common documents | PI 17 | New | 3 | #1000488
1000484 | #1000471 | Story | Implement Profile Portability: MFR 3 – CSE Completes Final CAP | PI 17 | New | 5 | #1000488
1000483 | #1000471 | Story | Implement Profile Portability: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 17 | New | 3 | #1000484 #1000488
1000482 | #1000471 | Story | Implement Profile Portability: ILS Incorporation of IETM updates and integration support | PI 17 | New | 1
1000481 | #1000471 | Story | Implement Profile Portability: UX Research and Design Support | PI 17 | New | 3
1000480 | #1000471 | Story | Implement Profile Portability: Develop IETMs and Perform Development Testing | PI 17 | New | 8 | #1000488
1000479 | #1000471 | Story | Implement Profile Portability: MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | PI 17 | New | 5 | #1000483
1000478 | #1000471 | Story | Implement Profile Portability: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | PI 17 | New | 1 | #1000479
1000477 | #1000471 | Story | Implement Profile Portability: MFR 3 – CSE Performs initial Cybersecurity Assessment | PI 17 | New | 5 | #1000478
1000476 | #1000471 | Story | Implement Profile Portability: Perform Iterative Implementation, Integration, development Testing including updating design | PI 17 | Invalid | 0 | #1000488 #1000477
1000475 | #1000471 | Story | Implement Profile Portability: Provide Deployment Notes and Operator Impact Inputs | PI 17 | New | 1 | #1000488
1000474 | #1000471 | Story | Implement Profile Portability: Create STCD and review with stakeholders | PI 17 | New | 5 | #1000488 #1000476 #1000486 #1000487
1000473 | #1000471 | Story | Implement Profile Portability: Update Capability Spec and Capability Design Document as needed | PI 17 | New | 3 | #1000474 #1000476 #1000475
1000472 | #1000471 | Task | Implement Profile Portability: Hold Feature Review with SMEs | PI 17 | New
1000471 | #219578 | Feature | Implement Profile Portability | PI 17 | Analyzing
1000415 |  | Feature | OBS - TPM: Develop Design for PPA | Unassigned | Rejected
1000404 |  | Problem | INC000004414276: NAVSOC HQ-Checking momentum adjusts in OAS relocation phase 1 procedure | Unassigned | Assessing
1000403 |  | Problem | INC000004414275: NAVSOC HQ-Intrusion reports for relocation | Unassigned | Assessing
1000325 | #395871 | Story | Feature 395871: Okapi Trouble Ticket Support - 14.4 | EA 14.4 | Done | 1
1000324 | #395871 | Story | Feature 395871: Okapi Trouble Ticket Support - 14.3 | EA 14.3 | Done | 1
1000323 | #395871 | Story | Feature 395871: Okapi Trouble Ticket Support - 14.2 | EA 14.2 | Done | 1
1000322 | #395871 | Story | Feature 395871: Okapi Trouble Ticket Support - 14.1 | EA 14.1 | Done | 1
1000321 | #395871 | Story | Feature 395871: Trouble Ticket Support - 14.4 | EA 14.4 | Done | 1
1000320 | #395871 | Story | Feature 395871: Trouble Ticket Support - 14.3 | EA 14.3 | Done | 1
1000319 | #395871 | Story | Feature 395871: Trouble Ticket Support - 14.2 | EA 14.2 | Done | 1
1000318 | #395871 | Story | Feature 395871: Trouble Ticket Support - 14.2 - Invalidate (Duplicate) | Unassigned | Invalid | 0
1000317 | #395871 | Story | Feature 395871: Trouble Ticket Support - 14.1 | EA 14.1 | Invalid | 0
1000316 | #396308 | Story | Feature 396308: Okapi PWI Triage/Assessment Support EA 14.4 | EA 14.4 | Done | 1
1000315 | #396308 | Story | Feature 396308: Okapi PWI Triage/Assessment Support EA 14.3 | EA 14.3 | Done | 1
1000313 | #396308 | Story | Feature 396308: Okapi PWI Triage/Assessment Support EA 14.2 | EA 14.2 | Done | 1
1000312 | #396308 | Story | Feature 396308: Okapi PWI Triage/Assessment Support EA 14.1 | EA 14.1 | Done | 1
1000309 | #396308 | Story | Feature 396308: PWI Triage/Assessment Support EA 14.4 (LOE) | EA 14.4 | Done | 1
1000308 | #396308 | Story | Feature 396308: PWI Triage/Assessment Support EA 14.3 (LOE) | EA 14.3 | Done | 1
1000307 | #396308 | Story | Feature 396308: PWI Triage/Assessment Support EA 14.2 (LOE) | EA 14.2 | Done | 1
1000306 | #396308 | Story | Feature 396308: PWI Triage/Assessment Support EA 14.1 (LOE) | EA 14.1 | Invalid | 0
1000305 | #396710 | Story | Feature 396710: Update List of Custom Alarms and Alarm Procedures (part 2) | Unassigned | New | 8
1000304 | #396710 | Story | Feature 396710: Deployment Notes and Operator Impact Inputs | Unassigned | New | 3
1000303 | #396710 | Story | Feature 396710: ET/ETISP Alarm Recovery Review for Style Guide Compliance | Unassigned | New | 20
1000302 | #396710 | Story | Feature 396710: Test and Verify Updated List of Custom Alarms and Alarm Procedures | Unassigned | New | 20
1000301 | #396710 | Story | Feature 396710: Update List of Custom Alarms and Alarm Procedures (part 1) | Unassigned | New | 20
1000300 | #396710 | Story | Feature 396710: IETM Alarm Recovery Procedures - Update PDF's and IETM proper | Unassigned | New | 13
1000299 | #396710 | Story | Feature 396710: Prep For and Execute Feature Demo Customer Demo Event | Unassigned | New | 5
1000286 | #395871 | Story | Feature 395871: Laptops Trouble Ticket Support - 14.5 | EA 14.5 | Done | 1
1000285 | #395871 | Story | Feature 395871: Laptops Trouble Ticket Support - 14.4 | EA 14.4 | Done | 1
1000284 | #395871 | Story | Feature 395871: Laptops Trouble Ticket Support - 14.3 | EA 14.3 | Done | 1
1000283 | #395871 | Story | Feature 395871: Laptops Trouble Ticket Support - 14.2 | EA 14.2 | Done | 1
1000282 | #395871 | Story | Feature 395871: Laptops Trouble Ticket Support - 14.1 | EA 14.1 | Done | 1
1000281 | #396308 | Story | Feature 396308: Laptops PWI Triage/Assessment Support - 14.5 | PI 14 - Candidate | Invalid | 0
1000280 | #396308 | Story | Feature 396308: Laptops PWI Triage/Assessment Support - 14.4 | PI 14 - Candidate | Invalid | 0
1000279 | #396308 | Story | Feature 396308: Laptops PWI Triage/Assessment Support - 14.3 | PI 14 - Candidate | Invalid | 0
1000278 | #396308 | Story | Feature 396308: Laptops PWI Triage/Assessment Support - 14.2 | PI 14 - Candidate | Invalid | 0
1000276 | #396308 | Story | Feature 396308: Laptops PWI Triage/Assessment Support - 14.1 | PI 14 - Candidate | Invalid | 0
1000268 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.5 | Done | 1
1000267 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.4 | Done | 1
1000266 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.3 | Done | 1
1000265 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.2 | Done | 1
1000264 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.1 | Done | 1
1000262 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.4 | Done | 1
1000261 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.5 | Done | 1
1000260 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.3 | Invalid | 0
1000258 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.2 | Done | 1
1000257 | #396308 | Story | Feature 396308: WWTS PWI Triage/Assessment Support | EA 14.1 | Done | 3
1000254 | #243505 | Feature | Trade Study and Prototype New Source Code repository and build tools | PI 17 | Analyzing
1000249 | #1000204 | Story | Release Regression - NMS Automation (xx.5) | EA 14.5 | Done | 1
1000248 | #1000204 | Story | Release Regression - NMS Automation (xx.4) | EA 14.4 | Done | 5
1000247 | #1000204 | Story | Release Regression - NMS Automation (xx.3) | EA 14.3 | Done | 5
1000246 | #1000204 | Story | Release Regression - NMS Automation (xx.2) | EA 14.2 | Done | 5
1000245 | #1000204 | Story | Release Regression - NMS Automation (xx.1) | EA 14.1 | Done | 5
1000244 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 14.5 | Done | 3
1000243 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 14.4 | Done | 5
1000242 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 14.3 | Done | 5
1000241 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 14.2 | Done | 5
1000240 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 14.1 | Done | 2
1000239 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.5) | EA 14.5 | Done | 2
1000238 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.4) | EA 14.4 | Done | 5
1000237 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.3) | EA 14.3 | Done | 5
1000236 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.2) | EA 14.2 | Done | 5
1000235 | #1000204 | Story | Release Regression - Manual Regression Test Run/Automate (xx.1) | EA 14.1 | Done | 5
1000234 | #1000204 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.5) | EA 14.5 | Done | 1
1000233 | #1000204 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.4) | EA 14.4 | Done | 1
1000232 | #1000204 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.3) | EA 14.3 | Done | 1
1000231 | #1000204 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.2) | EA 14.2 | Done | 1
1000230 | #1000204 | Story | Release Regression - Lab SW Versioning via NodeConfig (xx.1) | EA 14.1 | Done | 1
1000229 | #1000204 | Story | Release Regression - EAD15 Regression Test Selection (xx.1) | EA 14.1 | Done | 2
1000228 | #1000204 | Story | Release Regression - Call Automation (14.5) | EA 14.5 | Done | 1
1000227 | #1000204 | Story | Release Regression - Call Automation (14.4) | EA 14.4 | Done | 1
1000226 | #1000204 | Story | Release Regression - Call Automation (14.3) | EA 14.3 | Done | 1
1000225 | #1000204 | Story | Release Regression - Call Automation (xx.2) | EA 14.2 | Done | 1
1000224 | #1000204 | Story | Release Regression - Call Automation (xx.1) | EA 14.1 | Done | 1
1000223 | #1000204 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.5) | EA 14.5 | Done | 2
1000222 | #1000204 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.4) | EA 14.4 | Done | 2
1000221 | #1000204 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.3) | EA 14.3 | Done | 2
1000220 | #1000204 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.2) | EA 14.2 | Done | 2
1000219 | #1000204 | Story | Auto - RFR Regression - Test script bug fixes and maintenance (xx.1) | EA 14.1 | Done | 3
1000204 | #262134 | Feature | Release Regression - EAD 16 Regression Testing (PI14) | EA 14.5 | Done
1000186 | #341999 | Story | Feature 341999: Connected AWARE Training SC - Complete Customer Response Matrix (CRM) | PI 16 | New | 1
1000185 | #341999 | Story | Feature 341999: Conduct Connected AWARE Training in SC | PI 16 | New | 1
1000182 | #341999 | Story | Feature 353345: Travel to/from Site to Conduct Connected AWARE Training at SC | PI 14 | Invalid | 0
1000163 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (14.5) | EA 14.5 | Invalid | 0
1000162 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (14.4) | EA 14.4 | Invalid | 0
1000161 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (14.3) | EA 14.3 | Invalid | 0
1000160 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (14.2) | EA 14.2 | Invalid | 0
1000159 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Mark C (14.1) | EA 14.1 | Invalid | 0
1000158 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (14.5) | EA 14.5 | Done | 1
1000157 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (14.4) | EA 14.4 | Done | 3
1000156 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (14.3) | EA 14.3 | Done | 3
1000155 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (14.2) | EA 14.2 | Done | 3
1000154 | #396819 | Story | Lab - Maintain WDEs - Debug, recovery, repair, RF calibration, and IULAN - Brian (14.1) | EA 14.1 | Done | 3
1000153 | #396819 | Story | Feature 396819: Lab - Maintain OTA Call Banks - SME Support - Loretta (14.5) | EA 14.5 | Done | 1
1000152 | #396819 | Story | Feature 396819: Lab - Maintain OTA Call Banks - SME Support - Loretta (14.3) | EA 14.3 | Done | 1
1000151 | #396819 | Story | Feature 396819: Lab - Maintain OTA Call Banks - SME Support - Loretta (14.1) | EA 14.1 | Done | 1
1000150 | #396819 | Story | Lab - Maintain OTA Call Banks - Carl (14.5) | EA 14.5 | Done | 3
1000149 | #396819 | Story | Lab - Maintain OTA Call Banks - Carl (14.4) | EA 14.4 | Done | 5
1000148 | #396819 | Story | Lab - Maintain OTA Call Banks - Carl (14.3) | EA 14.3 | Done | 5
1000147 | #396819 | Story | Lab - Maintain OTA Call Banks - Carl (14.2) | EA 14.2 | Done | 5
1000146 | #396819 | Story | Lab - Maintain OTA Call Banks - Carl (14.1) | EA 14.1 | Done | 5
1000145 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (14.5) | EA 14.5 | Done | 1
1000144 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (14.4) | EA 14.4 | Done | 2
1000143 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (14.3) | EA 14.3 | Done | 2
1000142 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (14.2) | EA 14.2 | Done | 2
1000141 | #396819 | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (14.1) | EA 14.1 | Done | 2
1000140 | #396819 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (14.5) | EA 14.5 | Done | 3
1000139 | #396819 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (14.4) | EA 14.4 | Done | 5
1000138 | #396819 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (14.3) | EA 14.3 | Done | 3
1000137 | #396819 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (14.2) | EA 14.2 | Done | 3
1000136 | #396819 | Story | Lab - Maintain Labs - Technician including lab maintenance, installs and repairs - Val (14.1) | EA 14.1 | Done | 3
1000135 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.5) | EA 14.5 | Done | 3
1000134 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.4) | EA 14.4 | Done | 3
1000133 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.3) | EA 14.3 | Done | 3
1000132 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.2) | EA 14.2 | Done | 3
1000131 | #396819 | Story | Lab - Maintain Labs - Technician 2 including lab maintenance, installs and repairs - Beth (14.1) | EA 14.1 | Done | 3
1000130 | #396819 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (14.5) | EA 14.5 | Done | 2
1000129 | #396819 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (14.4) | EA 14.4 | Done | 2
1000128 | #396819 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (14.3) | EA 14.3 | Done | 2
1000127 | #396819 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (14.2) | EA 14.2 | Done | 2
1000126 | #396819 | Story | Lab - Maintain Labs - Support - Provide NMS and Provisioning Support for SSCPAC Testing - Havis (14.1) | EA 14.1 | Done | 2
1000125 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (14.5) | EA 14.5 | Done | 0
1000124 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (14.4) | EA 14.4 | Done | 2
1000123 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (14.3) | EA 14.3 | Done | 2
1000122 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (14.2) | EA 14.2 | Done | 2
1000121 | #396819 | Story | Lab - Maintain Labs - RF, WCTB, WILMAs outage debug, recovery and repair - Glen (14.1) | EA 14.1 | Done | 2
1000120 | #396819 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (14.5) | EA 14.5 | Done | 2
1000119 | #396819 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (14.4) | EA 14.4 | Done | 2
1000118 | #396819 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (14.3) | EA 14.3 | Done | 2
1000117 | #396819 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (14.2) | EA 14.2 | Done | 2
1000116 | #396819 | Story | Lab - Maintain Labs - RF maintenance and problem resolution (non-WDE radio work) - Brian (14.1) | EA 14.1 | Done | 2
1000115 | #396819 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (14.5) | EA 14.5 | Done | 1
1000114 | #396819 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (14.4) | EA 14.4 | Done | 1
1000113 | #396819 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (14.3) | EA 14.3 | Done | 1
1000112 | #396819 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (14.2) | EA 14.2 | Done | 1
1000111 | #396819 | Story | Lab - Maintain Labs - RBS/RNC Health Checks (14.1) | EA 14.1 | Done | 1
1000110 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (14.5) | EA 14.5 | Done | 1
1000109 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (14.4) | EA 14.4 | Done | 1
1000108 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Brian (14.3) | EA 14.3 | Done | 1
1000107 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (14.2) | EA 14.2 | Done | 1
1000106 | #396819 | Story | Feature 396819: Lab - Maintain Labs - RAN outage debug, recovery, repair and Maintenance - Katy (14.1) | EA 14.1 | Done | 1
1000105 | #396819 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (14.5) | EA 14.5 | Done | 1
1000104 | #396819 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (14.4) | EA 14.4 | Done | 1
1000103 | #396819 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (14.3) | EA 14.3 | Done | 1
1000102 | #396819 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (14.2) | EA 14.2 | Done | 1
1000101 | #396819 | Story | Lab - Maintain Labs - PRC 155 repairs and status - Tim (14.1) | EA 14.1 | Done | 1
1000100 | #396819 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - ??? (14.1) | EA 14.5 | Done | 2
1000099 | #396819 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - ??? (14.5) | EA 14.4 | Done | 2
1000098 | #396819 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - ??? (14.4) | EA 14.3 | Done | 2
1000097 | #396819 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - ??? (14.3) | EA 14.2 | Done | 2
1000096 | #396819 | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - ??? (14.2) | EA 14.1 | Done | 2
1000095 | #396819 | Story | Lab - Maintain Labs - NMS SME Support - Colin (14.5) | EA 14.5 | Done | 1
1000094 | #396819 | Story | Lab - Maintain Labs - NMS SME Support - Colin (14.4) | EA 14.4 | Done | 1
1000093 | #396819 | Story | Lab - Maintain Labs - NMS SME Support - Colin (14.3) | EA 14.3 | Done | 1
1000092 | #396819 | Story | Lab - Maintain Labs - NMS SME Support - Colin (14.2) | EA 14.2 | Done | 1
1000091 | #396819 | Story | Lab - Maintain Labs - NMS SME Support - Colin (14.1) | EA 14.1 | Done | 1
1000090 | #396819 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (14.5) | EA 14.5 | Done | 2
1000089 | #396819 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (14.4) | EA 14.4 | Done | 5
1000088 | #396819 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (14.3) | EA 14.3 | Done | 5
1000087 | #396819 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (14.2) | EA 14.2 | Done | 2
1000086 | #396819 | Story | Lab - Maintain Labs - Labs Scheduling and Maintenance - Havis (14.1) | EA 14.1 | Done | 5
1000085 | #396819 | Story | Feature 396819: Lab - Maintain Labs - Lab Floor Plan Updates (PI-14) | EA 14.5 | Invalid | 0
1000084 | #396819 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (14.5) | EA 14.5 | Done | 3
1000083 | #396819 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (14.4) | EA 14.4 | Done | 5
1000082 | #396819 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (14.3) | EA 14.3 | Done | 5
1000081 | #396819 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (14.2) | EA 14.2 | Done | 5
1000080 | #396819 | Story | Lab - Maintain Labs - Facility Management, security, GFE, calibration, test equipment repairs - Tim (14.1) | EA 14.1 | Done | 5
1000079 | #396819 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (14.5) | EA 14.5 | Done | 1
1000078 | #396819 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (14.4) | EA 14.4 | Done | 1
1000077 | #396819 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (14.3) | EA 14.3 | Done | 1
1000076 | #396819 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (14.2) | EA 14.2 | Done | 1
1000075 | #396819 | Story | Lab - Maintain Labs - Core Network debug, recovery and repair - Dave (14.1) | EA 14.1 | Done | 1
1000066 |  | Problem | Add "Persistent Clock Error" field to WDS Appendix E, Last Known State table. | Unassigned | Assessing
1000064 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.5 | Done | 1
1000063 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.3 | Invalid | 0
1000062 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.1 | Invalid | 0
1000061 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.5 | Done | 1
1000060 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.4 | Done | 1
1000059 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.3 | Done | 1
1000057 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support 14.2 | EA 14.2 | Done | 1
1000056 | #395871 | Story | Feature 395871: WWTS Trouble Ticket Support | EA 14.1 | Done | 1
1000052 | #1000037 | Story | Feature 1000037: Create PDO to Release SLA/TPS Report to PMW | EA 14.1 | Invalid | 0
1000044 | #396002 | Story | Feature 396002: PI 13 Technical Support | EA 14.5 | Done | 1
1000041 | #396002 | Story | Feature 396002: PI 13 Technical Support | EA 14.4 | Done | 1
1000040 | #396002 | Story | Feature 396002: PI 13 Technical Support | Unassigned | Invalid | 0
1000039 | #396002 | Story | Feature 396002: PI 13 Technical Support | EA 14.2 | Done | 1
1000038 | #396002 | Story | Feature 396002: PI 13 Technical Support | EA 14.1 | Done | 1
396968 |  | Problem | PM is not always recovering from temporary network outages | Unassigned | Assessing
396926 |  | Problem | WCDMA CPICH ratio errors following B2U beacon level alignment | Unassigned | Triage
396916 | #395871 | Story | Feature 395871: MAGIC TT Support - EA 14.5 | EA 14.5 | Done | 2
396915 | #395871 | Story | Feature 395871: MAGIC TT Support - INC000004707387, INC000004709806, INC000004712183, INC000004712743 (Valverde) | EA 14.4 | Done | 1
396914 | #395871 | Story | Feature 395871: MAGIC TT Support - INC000004634236 (NW-DSN GATEWAY LOSS OF SYNC CONDITION) | EA 14.3 | Done | 1
396913 | #395871 | Story | Feature 395871: MAGIC TT Support - EA 14.2 | EA 14.2 | Done | 2
396912 | #395871 | Story | Feature 395871: MAGIC TT Support - EA 14.1 | EA 14.1 | Done | 2
396909 | #396308 | Story | Feature 396308: MAGIC PWI Triage/Assessment Support - EA 14.5 | EA 14.5 | Done | 2
396908 | #396308 | Story | Feature 396308: MAGIC PWI Triage/Assessment Support - EA 14.4 | EA 14.4 | Done | 2
396907 | #396308 | Story | Feature 396308: MAGIC PWI Triage/Assessment Support - EA 14.3 | EA 14.3 | Done | 2
396906 | #396308 | Story | Feature 396308: MAGIC PWI Triage/Assessment Support - EA 14.2 | EA 14.2 | Done | 2
396905 | #396308 | Story | Feature 396308: MAGIC PWI Triage/Assessment Support - EA 14.1 | EA 14.1 | Done | 2
396902 | #396885 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
396901 | #396885 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #396894
396900 | #396885 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #396894
396899 | #396885 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #396894
396898 | #396885 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #396894
396897 | #396885 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #396894
396896 | #396885 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #396894
396895 | #396885 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #396900 #396894 #396898 #396897
396894 | #396885 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #396893
396893 | #396885 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
396892 | #396885 | Story | <Feature xxx>: MFR 2 – Cyber Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0
396891 | #396885 | Story | <Feature xxx>: MFR 2 – Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0
396890 | #396885 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves ACAS Scan Findings | Unassigned | Invalid | 0
396889 | #396885 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves Final ACAS Scan Findings | Unassigned | Invalid | 0
396888 | #396885 | Story | <Feature xxx>: MFR 2 – Cyber Completes Final CAP | Unassigned | Invalid | 0
396887 | #396885 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
396886 | #396885 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #396900 #396895 #396896
396885 |  | Feature | <Feature xxx> MFR2 Template | Unassigned | Rejected
396884 | #396885 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
396857 |  | Problem | Update VLAB DMZ Firewall to allow ePO Console Web Access from SECRET NMF Windows 10 Workstations | Unassigned | Assessing
396841 | #396835 | Task | Feature 396835: Create PDO to Release CDRL A006 Government Property Inventory Report to CM | EA 14.3 | Invalid
396840 | #396835 | Story | Feature 396835: Incorporate Redlines and Finalize the Government Property Inventory Report | EA 14.3 | Done | 3
396839 | #396835 | Story | Feature 396835: Review and Redline the New Government Property Inventory Report | EA 14.1 | Done | 2
396838 | #396835 | Story | Feature 396835: Create the New Government Property Inventory Report | EA 14.2 | Done | 5
396835 | #262146 | Feature | Government Property Inventory Report (CDRL A006) | EA 14.3 | Done
396833 | #380291 | Story | Lab - Maintain Labs - Upgrade workstation 111/211 to Windows 10 - Sally (13.2) | Unassigned | Invalid | 0
396819 | #262134 | Feature | Lab - Maintain Labs for Integration, Testing and Test Events with minimal down time (PI-14) | EA 14.5 | Done
396814 | #343920 | Task | Story 343920: CM Release of 98-P59422M – NMS – NM – SecretAppServer – SVD (EAD 16) | PI 14 | Done
396800 | #396770 | Task | Feature 396770: Create PDO to Release CDRL A005 Warranty Performance Report to PMW | EA 14.1 | Done
396799 | #396770 | Story | Feature 396770: Incorporate Redlines and Finalize the Warranty Performance Report | EA 14.1 | Done | 1
396770 | #262146 | Feature | Warranty Performance Report (CDRL A005) | EA 14.1 | Done
396712 | #216364 | Feature | Add/update IETM alarm recovery procedures for CORE/GIS alarms [Non-O-Level] | Unassigned | Draft
396710 | #216364 | Feature | ETI Add/update IETM alarm recovery procedures for ETI/ETISP alarms (part 4 of 4 [Non-O-Level] | Unassigned | Analyzing
396703 | #395688 | Story | May 2020 IA Patch Deployment (Part 2) | EA 15.3 | Invalid | 0
396697 |  | Problem | Account Maintenance Plan: Procedure typo 5.336.2 Password change instructions 1.d.ii step 2 command should be “use ipworks” | Unassigned | Assessing
396683 | #396669 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
396682 | #396669 | Story | Feature Demo – Customer Demo Event - Feature 396669 INSPECTION | EA 15.4 | New | 1 | #396683
396681 | #396669 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 15 | Invalid | 0 | #396682
396680 | #396669 | Story | Feature 396669: Execute STCD Feature Integration and testing including STCD updates identified | EA 15.3 | Invalid | 0 | #396682
396679 | #396669 | Story | <Feature xxx>: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #396682
396678 | #396669 | Story | Feature 396669: UX IETM Support for Alarm Recovery Procedures for RCG Alarms (15.4) | EA 15.4 | New | 1
396677 | #396669 | Story | Feature 396669: UX IETM Support for Alarm Recovery Procedures for RCG Alarms (15.1) | EA 15.1 | Done | 1
396676 | #1015603 | Story | <Feature 396669>: Develop IETM <TBD> and Perform Development Testing | PI 16 - Candidate | Invalid | 0 | #396682
396675 | #396669 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 15 | Invalid | 0 | #396682
396674 | #396669 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | PI 15 | Invalid | 0 | #396682
396673 | #396669 | Story | Feature 396669: Provide Deployment Notes and Operator Impact Inputs | EA 15.4 | New | 1 | #396682
396672 | #396669 | Story | Feature 396669: Create STCD and review with stakeholders and start test execution | EA 15.2 | Done | 2 | #396681 #396682 #396680 #396674
396671 | #396669 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | PI 15 | Invalid | 0 | #396672 #396674
396670 | #396669 | Task | Feature 396669: Hold Feature Review with SMEs | EA 15.1 | Invalid
396669 | #216364 | Feature | Add/update IETM alarm recovery procedures for RCG alarms Part 2 | EA 15.4 | Implementing
396663 | #262146 | Feature | Assess Training Needs and Plan Training for Development During PI 14 (Recurring) | EA 14.5 | Done
396662 | #396655 | Task | Feature xxxxxx: Upload Demo Documentation and Demo Status Workbook for Analysis Demo of the Coordinate and Complete Non-Feature IETM Content for EAD xx (Analysis Demo) | Unassigned | Invalid
396661 | #396655 | Story | Feature Demo – Customer Demo Event - Feature xxxxxx | Unassigned | Invalid | 0
396660 | #396655 | Story | Feature xxxxxx: IETM Admin Updates part 1 of 5 (EA xx.1) | Unassigned | Invalid | 0
396659 | #396655 | Story | Feature xxxxxx: IETM Admin Updates part 2 of 5 (EA xx.2) | Unassigned | Invalid | 0
396658 | #396655 | Story | Feature xxxxxx: IETM Admin Updates part 3 of 5 (EA xx.3) | Unassigned | Invalid | 0
396657 | #396655 | Story | Feature xxxxxx: IETM Admin Updates part 4 of 5 (EA xx.4) | Unassigned | Invalid | 0
396656 | #396655 | Story | Feature xxxxxx: IETM Admin Updates part 5 of 5 (EA xx.5) | Unassigned | Invalid | 0
396655 | #262146 | Feature | Coordinate and Complete Non-Feature IETM Content for EAD xx (Recurring) | Unassigned | Rejected
396647 | #395897 | Story | Database IAVA Intake - 15.5 | Unassigned | Invalid | 0
396646 |  | Story | Database IAVA Intake - 15.4 | Unassigned | Invalid | 0
396643 | #395897 | Story | Database IAVA Intake - 15.3 | Unassigned | Invalid | 0
396642 |  | Story | Database IAVA Intake - 15.2 | Unassigned | Invalid | 0
396641 | #395897 | Story | Database IAVA Intake - 15.1 | Unassigned | Invalid | 0
396640 | #395373 | Story | Database IAVA Intake - 14.5 | EA 14.5 | Done | 1
396639 | #395373 | Story | Database IAVA Intake - 14.4 | EA 14.4 | Invalid | 0
396638 | #395373 | Story | Database IAVA Intake - 14.3 | EA 14.3 | Done | 1
396636 | #395373 | Story | Database IAVA Intake - 14.2 | EA 14.2 | Done | 1
396635 | #395373 | Story | Database IAVA Intake - 14.1 | EA 14.1 | Done | 1
396519 | #396508 | Story | Feature 396508: Complete Customer Response Matrix (CRM) - Training EAD 15 [Deliver Training] | EA 15.5 | New | 1
396518 | #396508 | Story | Feature 396508: Deliver Training at SMDC - Training EAD 15 [Deliver Training] | EA 14.4 | Invalid | 0
396517 | #396508 | Story | Feature 396508: Deliver Training at NCTAMS - Training EAD 15 [Deliver Training] | EA 15.5 | New | 3
396516 | #396508 | Story | Feature 396508: Finalize, Print, and Ship Materials - Training EAD 15 [Create Training] | EA 15.4 | New | 1
396515 | #396508 | Task | Feature 396508: Incorporate Comments from Internal Review - Training EAD 15 [Create Training] | EA 14.5 | Invalid
396514 | #396508 | Story | Feature 396508: SysEng SME Review EAD 15 Training Materials | EA 14.4 | Invalid | 0
396513 | #396508 | Story | Feature 396508: SA SME Review of Training EAD 15 Training Materials | EA 14.2 | Invalid | 0
396512 | #396508 | Story | Feature 396508: Create Training Materials - Training EAD 15 [Create Training] | EA 14.2 | Done | 1
396511 | #396508 | Story | Feature 396508: Create Draft Training Plan - Training EAD 15 [Training Plan] | EA 14.2 | Done | 1
396510 | #396508 | Task | Feature 396508: Hold Operator Impact meeting + Action Items - Training EAD 15 [Op Impacts] | EA 14.2 | Done
396509 | #396508 | Story | Feature 396508: Finalize Op Impact Briefing Slides - Training EAD 15 [Op Impacts] | EA 14.1 | Done | 1
396508 | #262146 | Feature | Deliver EAD 15 Training | EA 15.5 | Implementing
396506 | #396492 | Story | Feature 396492: Initiate CM PDO Processing for all CI's | EA 14.1 | Done | 1
396505 | #396492 | Story | Feature 396492: Prep and Perform Feature Demo – Customer Demo Event | EA 14.1 | Done | 2 | #396506
396501 | #396492 | Story | Feature 396492: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | PI 14 | Invalid | 0
396496 | #396492 | Story | Feature 396492: Provide Deployment Notes and Operator Impact Inputs | EA 14.1 | Done | 1 | #396505
396492 | #395610 | Feature | Address ProvBridge to HLR timeout during terminal provisioning | EA 14.1 | Done
396478 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (part 5 of 8) | EA 15.3 | Done | 3
396437 | #243505 | Feature | Tools Team Support / LOE for RAN/RDE Environment in PI 14 | EA 14.5 | Done
396415 | #243505 | Feature | Tools Team Support / LOE for SDE/ODE Environment in PI 14 | EA 14.5 | Done
396382 | #396308 | Story | Feature 396308: PI 14 SA PWI Support - EA 14.5 | EA 14.5 | Done | 1
396381 | #396308 | Story | Feature 396308: PI 14 SA PWI Support - EA 14.4 | EA 14.4 | Done | 2
396380 | #396308 | Story | Feature 396308: PI 14 SA PWI Support - EA 14.3 | EA 14.3 | Done | 2
396379 | #396308 | Story | Feature 396308: PI 14 SA PWI Support - EA 14.2 | EA 14.2 | Done | 2
396378 | #396308 | Story | Feature 396308: PI 14 SA PWI Support - EA 14.1 | EA 14.1 | Done | 2
396377 | #395871 | Story | Feature 395871: PI 14 SA TT Support - EA 14.5 | EA 14.5 | Done | 1
396375 | #395871 | Story | Feature 395871: PI 14 SA TT Support - EA 14.4 | EA 14.4 | Done | 2
396373 | #395871 | Story | Feature 395871: PI 14 SA TT Support - EA 14.3 | EA 14.3 | Done | 2
396372 | #395871 | Story | Feature 395871: PI 14 SA TT Support - cleanup of “stuck” profiles - part 1 | EA 14.2 | Done | 3
396370 | #395871 | Story | Feature 395871: PI 14 SA TT Support - EA 14.1 (SQL Server - manual profile check) | EA 14.1 | Done | 2
396365 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support - 14.5 | EA 14.5 | Done | 0
396364 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support - 14.4 | EA 14.4 | Done | 2
396363 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support - 14.3 | EA 14.3 | Done | 2
396362 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support - 14.2 | EA 14.2 | Done | 2
396361 | #396308 | Story | Feature 396308: CSE PWI Triage/Assessment Support - 14.1 | EA 14.1 | Done | 2
396334 | #396308 | Story | Feature 396308: Falcons PWI Triage/Assessment Support EA 14.5 | EA 14.5 | Done | 1
396333 | #396308 | Story | Feature 396308: Falcons PWI Triage/Assessment Support EA 14.4 | EA 14.4 | Done | 1
396332 | #396308 | Story | Feature 396308: Falcons PWI Triage/Assessment Support EA 14.3 | EA 14.3 | Done | 1
396331 | #396308 | Story | Feature 396308: Falcons PWI Triage/Assessment Support EA 14.2 | EA 14.2 | Done | 1
396330 | #396308 | Story | Feature 396308: Falcons PWI Triage/Assessment Support EA 14.1 | EA 14.1 | Done | 1
396329 | #396308 | Story | Feature 396308: Octopi PWI Triage/Assessment Support EA 14.5 | EA 14.5 | Done | 1
396328 | #396308 | Story | Feature 396308: Octopi PWI Triage/Assessment Support EA 14.4 | EA 14.4 | Done | 1
396327 | #396308 | Story | Feature 396308: Octopi PWI Triage/Assessment Support EA 14.3 | EA 14.3 | Done | 1
396326 | #396308 | Story | Feature 396308: Octopi PWI Triage/Assessment Support EA 14.2 | EA 14.2 | Done | 1
396325 | #396308 | Story | Feature 396308: Octopi PWI Triage/Assessment Support EA 14.1 | EA 14.1 | Done | 1
396309 | #243395 | Feature | PI 14 Agile Teams Trouble Ticket Support (Recurring) | PI 14 - Candidate | Rejected
396308 | #243395 | Feature | PI 14 PWI Triage/Assessment Support (Recurring) | EA 14.5 | Done
396305 | #396272 | Story | Firewall Health Check and capture metrics - EA 14.5 | EA 14.5 | Done | 1
396304 | #396272 | Story | Firewall Health Check and capture metrics - EA 14.4 | EA 14.4 | Done | 1
396303 | #396272 | Story | Firewall Health Check and capture metrics - EA 14.3 | EA 14.3 | Invalid | 0
396302 | #396272 | Story | Firewall Health Check and capture metrics - EA 14.2 | EA 14.2 | Done | 1
396301 | #396272 | Story | Firewall Health Check and capture metrics - EA 14.1 | EA 14.1 | Done | 1
396299 | #396272 | Story | Create Sprint Review RAN Report - EA 14.5 | EA 14.5 | Invalid | 0
396298 | #396272 | Story | Create Sprint Review RAN Report - EA 14.4 | EA 14.4 | Invalid | 0
396297 | #396272 | Story | Create Sprint Review RAN Report - EA 14.3 | EA 14.3 | Invalid | 0
396296 | #396272 | Story | Create Sprint Review RAN Report - EA 14.2 | EA 14.2 | Invalid | 0
396295 | #396272 | Story | Create Sprint Review RAN Report - EA 14.1 | EA 14.1 | Invalid | 0
396293 | #396272 | Task | TFDU Health Check and Report incidents - EA 14.5 | EA 14.5 | Done
396292 | #396272 | Task | TFDU Health Check and Report incidents - EA 14.4 | EA 14.4 | Done
396291 | #396272 | Task | TFDU Health Check and Report incidents - EA 14.3 | EA 14.3 | Done
396290 | #396272 | Task | TFDU Health Check and Report incidents - EA 14.2 | EA 14.2 | Done
396289 | #396272 | Task | TFDU Health Check and Report incidents - EA 14.1 | EA 14.1 | Done
396287 | #396272 | Story | Report P-sync Levels - EA 14.4 | EA 14.4 | Invalid | 0
396286 | #396272 | Story | Report P-sync Levels - EA 14.2 | EA 14.2 | Invalid | 0
396284 | #396272 | Story | Daily Call Bank Health Check and Incident Capture for TOFF Metrics - EA 14.5 | EA 14.5 | Invalid | 0
396283 | #396272 | Story | Daily Call Bank Health Check and Incident Capture for TOFF Metrics - EA 14.4 | EA 14.4 | Invalid | 0
396282 | #396272 | Story | Daily Call Bank Health Check and Incident Capture for TOFF Metrics - EA 14.3 | EA 14.3 | Invalid | 0
396281 | #396272 | Story | Daily Call Bank Health Check and Incident Capture for TOFF Metrics - EA 14.2 | EA 14.2 | Invalid | 0
396280 | #396272 | Story | Daily Call Bank Health Check and Incident Capture for TOFF Metrics - EA 14.1 | EA 14.1 | Invalid | 0
396278 | #396272 | Story | Feature 396272: Daily RAN Ground Health Check and Incident Capture for TOFF Metrics - EA 14.5 | EA 14.5 | Done | 1
396277 | #396272 | Story | Feature 396272: Daily RAN Ground Health Check and Incident Capture for TOFF Metrics - EA 14.4 | EA 14.4 | Done | 1
396276 | #396272 | Story | Feature 396272: Daily RAN Ground Health Check and Incident Capture for TOFF Metrics - EA 14.3 | EA 14.3 | Done | 1
396275 | #396272 | Story | Feature 396272: Daily RAN Ground Health Check and Incident Capture for TOFF Metrics - EA 14.2 | EA 14.2 | Done | 1
396274 | #396272 | Story | Feature 396272: Daily RAN Ground Health Check and Incident Capture for TOFF Metrics - EA 14.1 | EA 14.1 | Done | 1
396272 | #245575 | Feature | Capture & Communicate TOFF Metrics (Recurring) | EA 14.5 | Done
396262 | #396002 | Story | Feature 396002: SIC PI 14 Technical Support - EA 14.4 | EA 14.4 | Invalid | 0
396261 | #396002 | Story | Feature 396002: SIC PI 14 Technical Support - EA 14.3 | EA 14.3 | Invalid | 0
396260 | #396002 | Story | Feature 396002: SIC PI 14 Technical Support - EA 14.2 | EA 14.2 | Done | 1
396259 | #396002 | Story | Feature 396002: SIC PI 14 Technical Support - EA 14.1 | EA 14.1 | Invalid | 0
396253 | #396248 | Story | Feature 396248: Update CRM Database Entries for EA 14.5 | EA 14.5 | Done | 2
396252 | #396248 | Story | Feature 396248: Update CRM Database Entries for EA 14.4 | EA 14.4 | Done | 2
396251 | #396248 | Story | Feature 396248: Update CRM Database Entries for EA 14.3 | EA 14.3 | Done | 2
396250 | #396248 | Story | Feature 396248: Update CRM Database Entries for EA 14.2 | EA 14.2 | Done | 2
396249 | #396248 | Story | Feature 396248: Update CRM Database Entries for EA 14.1 & Produce CSO CDM Report through EAD 14 | EA 14.1 | Done | 2
396248 | #262146 | Feature | PI 14 Maintain CRM Database (Recurring) | EA 14.5 | Done
396242 | #395871 | Story | Feature 395871: WWTS Waveform Analysis and Issue Support (5) | EA 14.5 | Done | 1
396241 | #395871 | Story | Feature 395871: Waveform Analysis and Issue Support (4) | EA 14.4 | Done | 1
396240 | #395871 | Story | Feature 395871: WWTS Waveform Analysis and Issue Support (3) | EA 14.3 | Done | 1
396239 | #395871 | Story | Feature 395871: WWTS Waveform Analysis and Issue Support (2) | EA 14.2 | Done | 1
396238 | #395871 | Story | Feature 395871: WWTS Waveform Analysis and Issue Support (1) | EA 14.1 | Done | 1
396237 | #395871 | Task | Feature 395871: TOFF LOE TT Support - EA 14.5 | EA 14.5 | Done
396236 | #395871 | Task | Feature 395871: TOFF LOE TT Support - EA 14.4 | EA 14.4 | Done
396235 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.3 | EA 14.3 | Done | 1
396234 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.2 | EA 14.2 | Done | 1
396233 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.1 | EA 14.1 | Done | 1
396232 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.5 | EA 14.5 | Done | 3
396231 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.4 | EA 14.4 | Done | 3
396230 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.3 | EA 14.3 | Done | 5
396229 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.2 | EA 14.2 | Done | 5
396228 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.1 | EA 14.1 | Done | 5
396227 | #395871 | Task | Feature 395871: TOFF LOE TT Support - EA 14.5 | EA 14.5 | Done
396226 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.4 | EA 14.4 | Done | 2
396225 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.3 | EA 14.3 | Done | 5
396224 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.2 | EA 14.2 | Done | 2
396223 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.1 | EA 14.1 | Done | 3
396222 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396221 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396220 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396219 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396218 | #395871 | Story | Feature 395871: TOFF LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396217 | #395871 | Story | Feature 395871: WWTS Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.5 | EA 14.5 | Invalid | 0
396216 | #395871 | Story | Feature 395871: WWTS Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.4 | EA 14.4 | Invalid | 0
396215 | #395871 | Story | Feature 395871: WWTS Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.3 | EA 14.3 | Invalid | 0
396214 | #395871 | Story | Feature 395871: WWTS Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.2 | EA 14.2 | Invalid | 0
396213 | #395871 | Story | Feature 395871: WWTS Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.1 | EA 14.1 | Invalid | 0
396212 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.5 | EA 14.5 | Done | 1
396211 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.4 | EA 14.4 | Done | 3
396210 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.3 | EA 14.3 | Done | 1
396209 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.2 | EA 14.2 | Done | 3
396208 | #395871 | Story | Feature 395871: TOFF LOE - TT Support - EA 14.1 | EA 14.1 | Done | 3
396207 | #395871 | Story | Feature 395871: TOFF LOE - Site Support and PWI generation - EA 14.5 | EA 14.5 | Done | 1
396206 | #395871 | Story | Feature 395871: TOFF LOE - Site Support and PWI generation - EA 14.4 | EA 14.4 | Done | 1
396205 | #395871 | Story | Feature 395871: TOFF LOE - Site Support and PWI generation - EA 14.3 | EA 14.3 | Done | 1
396204 | #395871 | Story | Feature 395871: TOFF LOE - Site Support and PWI generation - EA 14.2 | EA 14.2 | Done | 1
396203 | #395871 | Story | Feature 395871: TOFF LOE - Site Support and PWI generation - EA 14.1 | EA 14.1 | Done | 1
396202 | #395871 | Story | Feature 395871: TOFF LOE - MPC Support - EA 14.5 | EA 14.5 | Done | 1
396201 | #395871 | Story | Feature 395871: TOFF LOE - MPC Support - EA 14.4 | EA 14.4 | Done | 1
396200 | #395871 | Story | Feature 395871: TOFF LOE - MPC Support - EA 14.3 | EA 14.3 | Done | 1
396199 | #395871 | Story | Feature 395871: TOFF LOE - MPC Support - EA 14.2 | EA 14.2 | Done | 2
396198 | #395871 | Story | Feature 395871: TOFF LOE - MPC Support - EA 14.1 | EA 14.1 | Done | 2
396197 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.5 | EA 14.5 | Done | 1
396196 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.4 | EA 14.4 | Done | 1
396195 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.3 | EA 14.3 | Done | 1
396194 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.2 | EA 14.2 | Done | 2
396193 | #395871 | Story | Feature 395871: TOFF LOE - FRB Support - EA 14.1 | EA 14.1 | Done | 2
396192 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396191 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396190 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396189 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396188 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396187 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396186 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396185 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396184 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396183 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396182 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396181 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396180 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396179 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396178 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396177 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396176 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396175 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396174 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396173 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396172 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.5 | EA 14.5 | Invalid | 0
396171 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.4 | EA 14.4 | Invalid | 0
396170 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.3 | EA 14.3 | Invalid | 0
396169 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.2 | EA 14.2 | Invalid | 0
396168 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.1 | EA 14.1 | Invalid | 0
396167 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396166 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396165 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396164 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396163 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396162 |  | Story | LOE - Site Support and PWI generation - EA 14.5 | EA 14.5 | Invalid | 0
396161 |  | Story | LOE - Site Support and PWI generation - EA 14.4 | EA 14.4 | Invalid | 0
396160 |  | Story | LOE - Site Support and PWI generation - EA 14.3 | EA 14.3 | Invalid | 0
396159 |  | Story | LOE - Site Support and PWI generation - EA 14.2 | EA 14.2 | Invalid | 0
396158 |  | Story | LOE - Site Support and PWI generation - EA 14.1 | EA 14.1 | Invalid | 0
396157 |  | Story | LOE - MPC Support - EA 14.5 | EA 14.5 | Invalid | 0
396156 |  | Story | LOE - MPC Support - EA 14.4 | EA 14.4 | Invalid | 0
396155 |  | Story | LOE - MPC Support - EA 14.3 | EA 14.3 | Invalid | 0
396154 |  | Story | LOE - MPC Support - EA 14.2 | EA 14.2 | Invalid | 0
396153 |  | Story | LOE - MPC Support - EA 14.1 | EA 14.1 | Invalid | 0
396152 |  | Story | LOE - FRB Support - EA 14.5 | EA 14.5 | Invalid | 0
396151 |  | Story | LOE - FRB Support - EA 14.4 | EA 14.4 | Invalid | 0
396150 |  | Story | LOE - FRB Support - EA 14.3 | EA 14.3 | Invalid | 0
396149 |  | Story | LOE - FRB Support - EA 14.2 | EA 14.2 | Invalid | 0
396148 |  | Story | LOE - FRB Support - EA 14.1 | EA 14.1 | Invalid | 0
396147 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396146 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396145 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396144 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396143 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396142 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396141 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396140 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396139 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396138 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396137 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396136 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396135 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396134 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396133 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396132 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396131 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396130 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396129 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396128 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396127 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.5 | EA 14.5 | Invalid | 0
396126 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.4 | EA 14.4 | Invalid | 0
396125 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.3 | EA 14.3 | Invalid | 0
396124 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.2 | EA 14.2 | Invalid | 0
396123 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.1 | EA 14.1 | Invalid | 0
396122 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396121 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396120 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396119 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396118 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396117 |  | Story | LOE - Site Support and PWI generation - EA 14.5 | EA 14.5 | Invalid | 0
396116 |  | Story | LOE - Site Support and PWI generation - EA 14.4 | EA 14.4 | Invalid | 0
396115 |  | Story | LOE - Site Support and PWI generation - EA 14.3 | EA 14.3 | Invalid | 0
396114 |  | Story | LOE - Site Support and PWI generation - EA 14.2 | EA 14.2 | Invalid | 0
396113 |  | Story | LOE - Site Support and PWI generation - EA 14.1 | EA 14.1 | Invalid | 0
396112 |  | Story | LOE - MPC Support - EA 14.5 | EA 14.5 | Invalid | 0
396111 |  | Story | LOE - MPC Support - EA 14.4 | EA 14.4 | Invalid | 0
396110 |  | Story | LOE - MPC Support - EA 14.3 | EA 14.3 | Invalid | 0
396109 |  | Story | LOE - MPC Support - EA 14.2 | EA 14.2 | Invalid | 0
396108 |  | Story | LOE - MPC Support - EA 14.1 | EA 14.1 | Invalid | 0
396107 |  | Story | LOE - FRB Support - EA 14.5 | EA 14.5 | Invalid | 0
396106 |  | Story | LOE - FRB Support - EA 14.4 | EA 14.4 | Invalid | 0
396105 |  | Story | LOE - FRB Support - EA 14.3 | EA 14.3 | Invalid | 0
396104 |  | Story | LOE - FRB Support - EA 14.2 | EA 14.2 | Invalid | 0
396103 |  | Story | LOE - FRB Support - EA 14.1 | EA 14.1 | Invalid | 0
396102 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396101 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396100 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396099 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396098 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396097 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396096 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396095 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396094 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396093 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396092 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396091 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396090 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396089 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396088 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396087 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396086 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396085 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396084 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396083 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396082 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.5 | EA 14.5 | Invalid | 0
396081 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.4 | EA 14.4 | Invalid | 0
396080 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.3 | EA 14.3 | Invalid | 0
396079 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.2 | EA 14.2 | Invalid | 0
396078 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.1 | EA 14.1 | Invalid | 0
396077 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396076 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396075 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396074 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396073 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396072 |  | Story | LOE - Site Support and PWI generation - EA 14.5 | EA 14.5 | Invalid | 0
396071 |  | Story | LOE - Site Support and PWI generation - EA 14.4 | EA 14.4 | Invalid | 0
396070 |  | Story | LOE - Site Support and PWI generation - EA 14.3 | EA 14.3 | Invalid | 0
396069 |  | Story | LOE - Site Support and PWI generation - EA 14.2 | EA 14.2 | Invalid | 0
396068 |  | Story | LOE - Site Support and PWI generation - EA 14.1 | EA 14.1 | Invalid | 0
396067 |  | Story | LOE - MPC Support - EA 14.5 | EA 14.5 | Invalid | 0
396066 |  | Story | LOE - MPC Support - EA 14.4 | EA 14.4 | Invalid | 0
396065 |  | Story | LOE - MPC Support - EA 14.3 | EA 14.3 | Invalid | 0
396064 |  | Story | LOE - MPC Support - EA 14.2 | EA 14.2 | Invalid | 0
396063 |  | Story | LOE - MPC Support - EA 14.1 | EA 14.1 | Invalid | 0
396062 |  | Story | LOE - FRB Support - EA 14.5 | EA 14.5 | Invalid | 0
396061 |  | Story | LOE - FRB Support - EA 14.4 | EA 14.4 | Invalid | 0
396060 |  | Story | LOE - FRB Support - EA 14.3 | EA 14.3 | Invalid | 0
396059 |  | Story | LOE - FRB Support - EA 14.2 | EA 14.2 | Invalid | 0
396058 |  | Story | LOE - FRB Support - EA 14.1 | EA 14.1 | Invalid | 0
396054 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396053 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396052 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396051 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396050 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396049 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396048 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396047 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396046 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396045 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396044 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396043 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396042 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396041 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396040 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396039 |  | Story | LOE TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396038 |  | Story | LOE TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396037 |  | Story | LOE TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396036 |  | Story | LOE TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396035 |  | Story | LOE TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396034 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.5 | EA 14.5 | Invalid | 0
396033 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.4 | EA 14.4 | Invalid | 0
396032 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.3 | EA 14.3 | Invalid | 0
396031 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.2 | EA 14.2 | Invalid | 0
396030 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 14.1 | EA 14.1 | Invalid | 0
396029 |  | Story | LOE - TT Support - EA 14.5 | EA 14.5 | Invalid | 0
396028 |  | Story | LOE - TT Support - EA 14.4 | EA 14.4 | Invalid | 0
396027 |  | Story | LOE - TT Support - EA 14.3 | EA 14.3 | Invalid | 0
396026 |  | Story | LOE - TT Support - EA 14.2 | EA 14.2 | Invalid | 0
396025 |  | Story | LOE - TT Support - EA 14.1 | EA 14.1 | Invalid | 0
396024 |  | Story | LOE - Site Support and PWI generation - EA 14.5 | EA 14.5 | Invalid | 0
396023 |  | Story | LOE - Site Support and PWI generation - EA 14.4 | EA 14.4 | Invalid | 0
396022 |  | Story | LOE - Site Support and PWI generation - EA 14.3 | EA 14.3 | Invalid | 0
396021 |  | Story | LOE - Site Support and PWI generation - EA 14.2 | EA 14.2 | Invalid | 0
396020 |  | Story | LOE - Site Support and PWI generation - EA 14.1 | EA 14.1 | Invalid | 0
396019 |  | Story | LOE - MPC Support - EA 14.5 | EA 14.5 | Invalid | 0
396018 |  | Story | LOE - MPC Support - EA 14.4 | EA 14.4 | Invalid | 0
396017 |  | Story | LOE - MPC Support - EA 14.3 | EA 14.3 | Invalid | 0
396016 |  | Story | LOE - MPC Support - EA 14.2 | EA 14.2 | Invalid | 0
396015 |  | Story | LOE - MPC Support - EA 14.1 | EA 14.1 | Invalid | 0
396014 |  | Story | LOE - FRB Support - EA 14.5 | EA 14.5 | Invalid | 0
396013 |  | Story | LOE - FRB Support - EA 14.4 | EA 14.4 | Invalid | 0
396012 |  | Story | LOE - FRB Support - EA 14.3 | EA 14.3 | Invalid | 0
396011 |  | Story | LOE - FRB Support - EA 14.2 | EA 14.2 | Invalid | 0
396010 |  | Story | LOE - FRB Support - EA 14.1 | EA 14.1 | Invalid | 0
396008 | #396002 | Story | Feature 396002: MAGIC PI 14 Technical Support - EA 14.5 | EA 14.5 | Done | 1
396007 | #396002 | Story | Feature 396002: MAGIC PI 14 Technical Support - EA 14.4 | EA 14.4 | Done | 1
396006 | #396002 | Story | Feature 396002: MAGIC PI 14 Technical Support - EA 14.3 | EA 14.3 | Invalid | 0
396005 | #396002 | Story | Feature 396002: MAGIC PI 14 Technical Support - EA 14.2 | EA 14.2 | Done | 1
396004 | #396002 | Story | Feature 396002: MAGIC PI 14 Technical Support - EA 14.1 | EA 14.1 | Done | 1
396002 | #243395 | Feature | PI 14 Technical Support (Recurring) | EA 14.5 | Done
396001 | #243395 | Feature | Deployment and on-site support of OSS-RC for PI16 | PI 16 | Approved
395992 | #395897 | Story | Update RMF artifact (e.g., RAR, POAM) based on monthly site scans - 15.4 | Unassigned | Invalid | 0
395990 | #395897 | Story | Update RMF artifact (e.g., RAR, POAM) based on monthly site scans - 15.2 | Unassigned | Invalid | 0
395989 |  | Story | June Updates to IA Repository | Unassigned | Invalid | 0
395988 | #395897 | Story | May Updates to IA Repository | Unassigned | Invalid | 0
395987 | #395897 | Story | April Updates to IA Repository | Unassigned | Invalid | 0
395983 |  | Story | Support Code Collaborator Reviews - 15.5 | Unassigned | Invalid | 0
395982 |  | Story | Support Code Collaborator Reviews - 15.4 | Unassigned | Invalid | 0
395981 |  | Story | Support Code Collaborator Reviews - 15.3 | Unassigned | Invalid | 0
395980 |  | Story | Support Code Collaborator Reviews - 15.2 | Unassigned | Invalid | 0
395979 |  | Story | Support Code Collaborator Reviews - 15.1 | Unassigned | Invalid | 0
395962 |  | Problem | O-Level unable to complete Monthly maintenance procedure "Clean up Planned Areas" | Unassigned | Assessing
395926 | #395855 | Story | Feature Demo – Customer Demo Event - Feature 395855: PI 14 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 14.5 | Done | 1
395925 | #395855 | Task | Feature 395855: Upload Demo Documentation to GD & LM Site for PI 14 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 14.4 | Done |  | #395926
395924 |  | Task | Feature 395855: Create PDO to Release Parts List/Drawings (Part 5) (EA xx.x) | PI 14 | Invalid
395923 |  | Story | Feature 395855: Create CoCo Review for xyz Parts List/Drawings (Part 5) (EA xx.x) | Unassigned | Invalid | 0
395922 | #395855 | Story | Feature xxxxxx: Parts List Updates for EA xx.x | Unassigned | Invalid | 0
395920 |  | Story | Feature xxxxxx: Drawing Updates for EA xx.x | Unassigned | Invalid | 0
395919 | #395855 | Task | Feature 395855: Create PDO to Release Parts List/Drawings | EA 14.4 | Done |  | #395925
395918 | #395855 | Story | Feature 395855: Create CoCo Review for ETT Modifications | EA 14.4 | Done | 1 | #395919
395917 | #395855 | Story | Feature 395855: Parts List Updates for EA 14.4 (Nutanix holder) | PI 15 | Invalid | 0 | #395918
395916 | #395855 | Story | Feature 395855: Drawing Updates for EA 14.4 Resolve Problem 1015116 (ETT Modification) | EA 14.4 | Done | 1 | #395918
395905 | #395897 | Story | IAVA Intake - 15.5 | EA 15.5 | New | 2
395904 | #395897 | Story | IAVA Intake - 15.4 | EA 15.4 | Implementing | 2
395903 | #395897 | Story | IAVA Intake - 15.3 | EA 15.3 | Done | 2
395902 | #395897 | Story | IAVA Intake - 15.2 | EA 15.2 | Done | 2
395901 | #395897 | Story | IAVA Intake - 15.1 | EA 15.1 | Done | 2
395897 | #245560 | Feature | Cyber: RMF Continuous Monitoring - PI 15 (Recurring) | EA 15.5 | Implementing
395895 | #395853 | Story | MFR EAD 17 Support - Continuing Support | EA 15.3 | Done | 2
395894 | #395853 | Story | Update SP Supplement for EAD 17.0 Content | EA 15.5 | New | 3
395893 | #395853 | Story | Update and review with customer MFR for EAD 17.0 | EA 15.5 | New | 3
395891 | #395853 | Story | Update ACAS Scan Limitations White Paper - EAD 17 | EA 15.5 | New | 1
395886 | #395853 | Story | Support EAD-18 Due Diligence Cyber Assessments | EA 15.3 | Done | 3
395884 | #395853 | Story | Generate and review with customer MFR for EAD 17.0 (Part 1) | EA 15.4 | Implementing | 1
395881 | #395853 | Story | Support application review for DADMs applicability - 15.5 | EA 15.5 | New | 1
395880 | #395853 | Story | Support application review for DADMs applicability - 15.4 | EA 15.4 | Implementing | 1
395878 | #395853 | Story | Support application review for DADMs applicability - 15.3 | EA 15.3 | Done | 1
395877 | #395853 | Story | Support application review for DADMs applicability - 15.2 | EA 15.2 | Done | 1
395876 | #395853 | Story | Support application review for DADMs applicability - 15.1 | EA 15.1 | Done | 1
395871 | #245568 | Feature | Identify, Report, Prioritize, and Support to Incidents & Trouble Tickets (Recurring) | EA 14.5 | Done
395867 | #395855 | Task | Feature 395855: Create PDO to Release Parts List/Drawings (Part 3) EA 14.3 | EA 14.3 | Invalid |  | #395925
395866 | #395855 | Story | Feature 395855: Create CoCo Review for 01-P51661E and 53-P52819E_Rev E for AU Drawings (Part 3) EA 14.3 | EA 14.3 | Done | 1 | #395867
395865 | #395855 | Story | Feature 395855: Parts List Updates for EA 14.3 (Nutanix) | EA 14.3 | Done | 1 | #395866
395864 | #383165 | Story | Feature 383165: Drawing Updates for EA 14.3 - NME 201/202 ICD & Wahiawa SF/NMF ICD Redlines and WIP Version | EA 14.2 | Done | 3 | #395866
395863 | #395855 | Task | Feature 395855: Create PDO to Release Parts List/Drawings (Part 2) EA 14.2 | EA 14.2 | Invalid |  | #395925
395862 | #395855 | Story | Feature 395855: Create CoCo Review for xyz Parts List/Drawings (Part 2) EA 14.2 | EA 14.2 | Invalid | 0 | #395863
395861 | #395855 | Story | Feature 395855: Parts List Updates for EA 14.2 | EA 14.2 | Invalid | 0 | #395862
395860 | #395855 | Story | Feature 395855: Drawing Updates for EA 14.2 - Resolves Problem 321745 and Problem 1005849 | EA 14.2 | Done | 1 | #395862
395859 | #395855 | Task | Feature 395855: Create PDO to Release Finalized Drawings for IDP Associated with OBS - HLR: HW/FRCB for HLR Deployment | EA 14.5 | Invalid
395858 | #395855 | Story | Feature 395855: Create CoCo Review for xyz Parts List/Drawings (Part 1) EA 14.1 | EA 14.1 | Invalid | 0 | #395859
395857 | #395855 | Story | Feature 395855: Parts List Updates for EA 14.1 | EA 14.1 | Invalid | 0 | #395858
395856 | #395855 | Story | Feature 395855: Drawing Updates for EA 14.1 | EA 14.1 | Invalid | 0 | #395858
395855 | #262146 | Feature | PI 14 Parts List and Drawing Updates/Modifications Discovered within IA Patching or Outside Standard Features (Recurring) | EA 15.1 | Done
395853 | #245560 | Feature | Cyber: MFR Deployment Support - PI 15 (Recurring) | EA 15.5 | Implementing
395852 |  | Story | Update and review with customer MFR for EAD 16.0 | Unassigned | Invalid | 0
395850 |  | Story | Update ACAS Scan Limitations White Paper - EAD 16 | Unassigned | Invalid | 0
395848 |  | Story | Review and analyze scan data for EAD 16.0 MFR | Unassigned | Invalid | 0
395847 | #353345 | Story | Feature 353345: Familiarize Trainer with Maintainer Refresher Training in WH | EA 14.1 | Invalid | 0
395846 | #395835 | Story | Generate and review with customer MFR for EAD 16.0 | EA 14.5 | Done | 2
395844 |  | Story | MFR EAD 16 Support - Continuing Support | Unassigned | Invalid | 0
395843 | #395835 | Story | Update SP Supplement for EAD 16.0 Content | EA 14.5 | Done | 1
395841 |  | Story | Support application review for DADMs applicability - 14.5 | Unassigned | Invalid | 0
395839 | #395835 | Story | Support application review for DADMs applicability - 14.4 | EA 14.4 | Done | 1
395838 |  | Story | Support application review for DADMs applicability - 14.3 | Unassigned | Invalid | 0
395837 | #395835 | Story | Support application review for DADMs applicability - 14.2 | EA 14.2 | Done | 1
395836 |  | Story | Support application review for DADMs applicability - 14.1 | Unassigned | Invalid | 0
395835 | #245560 | Feature | Cyber MFR Support - PI 14 (Recurring) | EA 14.5 | Done
395771 | #353134 | Story | Feature 353134: Conduct Maintainer Refresher Training in SC (Trainer 2) | EA 16.5 | New | 3
395770 | #353134 | Story | Feature 353134: Travel to Site to Conduct Maintainer Refresher Training in SC (Trainer 2) | EA 16.5 | New | 2
395769 | #353345 | Story | Feature 353345: Conduct Refresher Training in WH (Trainer 2) | EA 14.1 | Done | 3
395768 | #353345 | Story | Feature 353345: Travel to Site to Conduct Refresher Training at WH (Trainer 2) | EA 14.1 | Done | 2
395727 | #353256 | Story | Feature 353256: Travel to Site to Conduct Maintainer Refresher Training in AU (Trainer 2) | EA 16.2 | New | 2
395726 | #353256 | Story | Feature 353256: Conduct Maintainer Refresher Training in AU (Trainer 2) (Days 1-3) | EA 16.2 | New | 3
395713 | #395688 | Story | Updated HW SW Map for May Patch deployment Part A | EA 15.1 | Done | 2
395712 | #395688 | Story | Release status report with metrics spreadsheet for May Deployment Part B | EA 15.4 | Invalid | 0
395710 |  | Story | Scan and review the patch findings from the site and SWIT and VLAB | Unassigned | Invalid | 0
395709 | #395688 | Story | Complete SWIT testing for May and June Patches Part B | EA 15.5 | New | 3
395707 | #395688 | Story | Download May and June patches, and update patching script Part B | EA 15.5 | Invalid | 0
395705 |  | Story | Support patch release | Unassigned | Invalid | 0
395704 | #395688 | Story | Complete SWIT Testing for May Deployment | EA 15.1 | Done | 5 | #1020149
395703 | #395688 | Story | Cross-training (Kirk D): Create patch bundle, measure/sign and formally release to CM with final script, download bundle to protected laptop | EA 15.2 | Done | 3
395701 | #395688 | Story | Update Node Config for IA patches Part A | EA 15.5 | New | 1
395700 |  | Story | Update Patch SVD for all impacted systems to include any configurations changes and hostname list and MPC | Unassigned | Invalid | 0
395699 | #395688 | Story | Validate May and July Patches in SWIT/Vlab vs Site Part B | EA 15.5 | New | 2
395698 | #395688 | Story | Scan and review the patch findings from the site and SWIT and VLAB Part A | EA 15.4 | Implementing | 2
395697 |  | Problem | [MAINT] Request DTI testing with fading channels | Unassigned | Assessing
395696 | #395688 | Story | July 2020 Patch Deployment - Develop and finalize candidate patch target list Part B | EA 15.4 | New | 3
395695 | #395688 | Story | Update Patch SVDs for with redlines from site and misc cleanup Part A | EA 15.3 | Invalid | 0
395694 | #395688 | Story | Update IA-Server-patch-tracker spreadsheet in Clear Case w/patch bundle installed | EA 15.3 | Invalid | 0
395693 |  | Story | Release status report with metrics spreadsheet | Unassigned | Invalid | 0
395692 | #395688 | Story | Dry Run May 2020 IA Patch Deployment Part A | EA 15.3 | Done | 3
395690 |  | Story | Complete SWIT testing | Unassigned | Invalid | 0
395689 |  | Story | Download patches, and update patching script | Unassigned | Invalid | 0
395688 | #245560 | Feature | Cyber: TO3 IA Patching - PI 15 (Recurring) | EA 15.5 | Implementing
395686 |  | Task | Chris Curtis - OOP Reminder: 11/29-29 Thanksgiving and 12/23-1/3 Christmas | Unassigned | Invalid
395684 |  | Task | Gerald Vaughn. OOP reminder: | PI 16 | New
395660 | #378000 | Problem | Minor comment errors in WH AWARE Cell lists | EA 14.1 | Closed
395614 | #218902 | Story | Deployment team SME input to identify differences between the VLAB and Site - SME Input | PI 16 | New | 2
395613 | #218902 | Story | Analyze the RAN to identify differences between the VLAB and Site - SME Input | PI 16 | New | 2
395612 | #218902 | Story | Lab - VLab Like Site - Analyze NMS and Situational Awareness to identify differences - SME Input | PI 16 | New | 2
395611 | #218902 | Story | Analyze Core/GIS to identify differences between the VLAB and Site - SME Input | PI 16 | New | 2
395556 | #395538 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
395555 | #395538 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | New | 1 | #395556
395554 | #395538 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #395555
395553 | #395538 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #395555
395552 | #395538 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | New | 0 | #395555
395551 |  | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP (Change back to Cyber) | Unassigned | Invalid | 0
395550 |  | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0
395549 | #395538 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | New | 1
395548 | #395538 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | New | 3
395547 | #395538 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | New | 3 | #395555
395546 |  | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0
395545 |  | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0
395544 |  | Story | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0
395543 | #395538 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #395555
395542 | #395538 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #395555
395541 | #395538 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | New | 3 | #395554 #395543 #395555 #395553
395540 | #395538 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #395542 #395541 #395543
395539 | #395538 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | New
395538 |  | Feature | <Feature xxx> MFR2 Template | Unassigned | Draft
395463 | #369623 | Story | Support of GPS Trade Study | Unassigned | Invalid | 0
395433 | #1006817 | Task | Complete Feature Burnup | EA 14.2 | Done
395425 | #392530 | Story | Updated HW SW Map for March Patch deployment | EA 14.3 | Done | 3
395424 | #392530 | Story | Release status report with metrics spreadsheet for March Deployment | EA 14.3 | Done | 2
395423 | #392530 | Story | Scan and review the patch findings from the site and SWIT and VLAB | EA 14.4 | Done | 3
395422 | #392530 | Story | Complete SWIT testing For March Patches | EA 14.5 | Done | 2
395421 | #392530 | Story | Download patches, and update patching script | EA 14.5 | Invalid | 0
395420 | #392530 | Story | Support patch release | EA 14.1 | Invalid | 0
395418 | #392530 | Story | Complete February SWIT Testing, and complete VLAB test for March Deployment | EA 14.2 | Done | 3
395417 | #392530 | Story | Create patch bundle, measure/sign and formally release to CM with final script, download bundle to protected laptop | EA 14.2 | Done | 3
395416 | #392530 | Story | Update Node Config for IA patches | EA 14.2 | Done | 1
395415 |  | Story | Update Patch SVD for all impacted systems to include any configurations changes and hostname list and MPC | Unassigned | Invalid | 0
395414 | #392530 | Story | Validate May Deployment Patches in SWIT/Vlab vs Site | EA 14.5 | Done | 2
395413 |  | Story | Scan and review the patch findings from the site and SWIT and VLAB | Unassigned | Invalid | 0
395412 | #392530 | Story | May 2020 Patch Deployment - Develop and finalize candidate patch target list | EA 14.4 | Done | 3
395411 | #392530 | Story | Update Patch SVDs for with redlines from site and misc cleanup | EA 14.4 | Done | 2
395410 | #392530 | Story | Update IA-Server-patch-tracker spreadsheet in Clear Case w/patch bundle installed | EA 14.2 | Done | 3
395409 |  | Story | Release status report with metrics spreadsheet | Unassigned | Invalid | 0
395407 | #392530 | Story | March 2020 IA Patch Deployment | EA 14.3 | Done | 5
395395 | #395835 | Story | Update RMF artifact (e.g., RAR, POAM) based on monthly site scans - 14.4 | EA 14.4 | Invalid | 0
395394 |  | Story | Update RMF artifact (e.g., RAR, POAM) based on monthly site scans - 14.2 | Unassigned | Invalid | 0
395388 | #395373 | Story | March Updates to IA Repository | EA 14.5 | Done | 2
395387 | #395373 | Story | February Updates to IA Repository | EA 14.3 | Done | 2
395386 | #395373 | Story | January Updates to IA Repository | EA 14.1 | Done | 2
395385 | #395373 | Story | Support Code Collaborator Reviews - 14.5 | EA 14.5 | Done | 1
395384 | #395373 | Story | Support Code Collaborator Reviews - 14.4 | EA 14.4 | Done | 1
395383 | #395373 | Story | Support Code Collaborator Reviews - 14.3 | EA 14.3 | Done | 1
395382 | #395373 | Story | Support Code Collaborator Reviews - 14.2 | EA 14.2 | Done | 1
395381 | #395373 | Story | Support Code Collaborator Reviews - 14.1 | EA 14.1 | Done | 1
395380 | #395373 | Story | IAVA Intake - 14.5 | EA 14.5 | Done | 2
395379 | #395373 | Story | IAVA Intake - 14.4 | EA 14.4 | Done | 2
395378 | #395373 | Story | IAVA Intake - 14.3 | EA 14.3 | Done | 2
395377 | #395373 | Story | IAVA Intake - 14.2 | EA 14.2 | Done | 2
395376 | #395373 | Story | IAVA Intake - 14.1 | EA 14.1 | Done | 2
395373 | #245560 | Feature | Cyber Sustainment Activities - PI 14 (Recurring) | EA 14.5 | Done
395370 | #1001912 | Problem | Waveform hangs when an RRC message arrives for a parent RRC process. | EA 15.1 | Closed
395356 |  | Problem | Waveform locks up when mobility is triggered by locking the current cell. | Unassigned | Assessing
395355 |  | Problem | CAI and Waveform are not in agreement on the RAU bit in the MAMA Response message. | Unassigned | Assessing
395352 |  | Problem | OOS after GSLN after Mobility during Group Idle mobility testing. | Unassigned | Assessing
395338 |  | Story | Lab - Polatis Switch Replacement - Perform lab integration and test (Tom) | Unassigned | Invalid | 0
395336 |  | Story | Lab - Polatis Switch Replacement - Perform lab integration and test (Glen) | Unassigned | Invalid | 0
395329 | #395538 | Story | <Feature xxx>: MFR 2 – Cyber Completes Final CAP | Unassigned | New | 5
395328 | #395538 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves Final ACAS Scan Findings | Unassigned | New | 3
395326 | #395538 | Story | <Feature xxx>: MFR 2 – Dev Team Resolves ACAS Scan Findings | Unassigned | New | 3
395325 | #395538 | Story | <Feature xxx>: MFR 2 – Dev Team Supports Initial Cybersecurity Assessment | Unassigned | New | 1
395324 | #395538 | Story | <Feature xxx>: MFR 2 – Cyber Performs initial Cybersecurity Assessment | Unassigned | New | 5
395246 | #378000 | Problem | 98-P55510M SVD - deficiencies in knowing what is installed on what and gives path to media that are in the RHEL SVD. DEPOT WILL HAVE ISSUES INSTALLING | EA 14.1 | Closed
395205 |  | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab (20+ boards) | PI 14 | Invalid | 0
395198 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | PI 14 | Invalid | 0
395197 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.5 | EA 14.5 | Done | 1
395196 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.4 | EA 14.4 | Done | 1
395195 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.3 | EA 14.3 | Done | 1
395194 | #395114 | Story | Feature 395114 : Evaluation of HW FRB Support EA 14.2 to Evaluate the GEO Removal in VLab ETISP Frame Sync Loss Issue | EA 15.5 | New | 1
395193 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.1 for 1536_MHZ_CLOCK_DISTRIBUTION_CARD, PN = WS/CSYNC-0/0, SN = 1000056 | EA 14.1 | Done | 1
395192 |  | Story | <Feature XXXXXX>: Logistics HW FRB Support EA XX.X | PI 14 | Invalid | 0
395191 | #395174 | Story | Feature 395174: Logistics HW FRB Support EA 14.5 | EA 14.5 | Done | 5
395190 | #395174 | Story | Feature 395174: Logistics HW FRB Support EA 14.4 | EA 14.4 | Done | 5
395189 | #395174 | Story | Feature 395174: Logistics HW FRB Support EA 14.3 | EA 14.3 | Done | 5
395188 | #395174 | Story | Feature 395174: Logistics HW FRB Support EA 14.2 | EA 14.2 | Done | 5
395187 | #395174 | Story | Feature 395174: Logistics HW FRB Support EA 14.1 | EA 14.1 | Done | 5
395186 |  | Story | <Feature XXXXXX>: Lab - Verify Field or Site Declared Failures in the Lab (EA XX.X) | PI 14 | Invalid | 0
395185 | #395174 | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab EA 14.5 | EA 14.5 | Done | 1
395184 | #395174 | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab EA 14.4 | EA 14.4 | Invalid | 0
395183 | #395174 | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab EA 14.3 | EA 14.3 | Done | 1
395182 | #395174 | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab EA 14.2 | EA 14.2 | Invalid | 0
395181 | #395174 | Story | Feature 395174: Lab - Verify Field or Site Declared Failures in the Lab EA 14.1 | EA 14.1 | Done | 1
395180 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | PI 14 | Invalid | 0
395179 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.5 | EA 14.5 | Done | 1
395178 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.4 | EA 14.4 | Done | 1
395177 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.3 | EA 14.3 | Invalid | 0
395176 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.2 to Evaluate the GEO Removal in VLab ETISP Frame Sync Loss Issue | EA 14.3 | Done | 1
395175 | #395174 | Story | Feature 395174: Evaluation of HW FRB Support EA 14.1 for 1536_MHZ_CLOCK_DISTRIBUTION_CARD, PN = WS/CSYNC-0/0, SN = 1000056 | EA 14.1 | Done | 1
395174 | #262146 | Feature | PI 14 HW FRB Support (Recurring) | EA 14.5 | Done
395139 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | Unassigned | Invalid | 0
395138 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.5 | EA 15.5 | New | 1
395137 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.4 | EA 15.4 | Implementing | 1
395136 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.3 | EA 15.3 | Done | 1
395135 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.2 | EA 15.2 | Done | 1
395134 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.1 | EA 15.1 | Done | 1
395133 |  | Story | <Feature XXXXXX>: Logistics HW FRB Support EA 13.7 | Unassigned | Invalid | 0
395132 |  | Story | <Feature XXXXXX>: Logistics HW FRB Support EA XX.X | Unassigned | Invalid | 0
395131 | #395114 | Story | Feature 395114: Logistics HW FRB Support EA 15.5 | EA 15.5 | New | 3
395130 | #395114 | Story | Feature 395114: Logistics HW FRB Support EA 15.4 | EA 15.4 | Implementing | 3
395129 | #395114 | Story | Feature 395114: Logistics HW FRB Support EA 15.3 | EA 15.3 | Done | 5
395128 | #395114 | Story | Feature 395114: Logistics HW FRB Support EA 15.2 | EA 15.2 | Done | 5
395127 | #395114 | Story | Feature 395114: Logistics HW FRB Support EA 15.1 | EA 15.1 | Done | 5
395126 |  | Story | <Feature XXXXXX>: Lab - Verify Field or Site Declared Failures in the Lab (EA XX.X) | Unassigned | Invalid | 0
395125 | #395114 | Story | Feature 395114: Lab - Verify Field or Site Declared Failures in the Lab EA 15.5 | EA 15.5 | New | 1
395124 | #395114 | Story | Feature 395114: Lab - Verify Field or Site Declared Failures in the Lab EA 15.4 | EA 15.4 | New | 1
395123 | #395114 | Story | Feature 395114: Lab - Verify Field or Site Declared Failures in the Lab EA 15.3 | EA 15.3 | Done | 1
395122 | #395114 | Story | Feature 395114: Lab - Verify Field or Site Declared Failures in the Lab EA 15.2 | EA 15.2 | Done | 1
395121 | #395114 | Story | Feature 395114: Lab - Verify Field or Site Declared Failures in the Lab EA 15.1 | EA 15.1 | Done | 1
395120 |  | Story | <Feature XXXXXX>: Evaluation of HW FRB Support (EA XX.X) | Unassigned | Invalid | 0
395119 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.5 | EA 15.5 | New | 1
395118 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.4 | EA 15.4 | Implementing | 1
395117 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.3 | EA 15.3 | Done | 1
395116 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.2 | EA 15.2 | Done | 1
395115 | #395114 | Story | Feature 395114: Evaluation of HW FRB Support EA 15.1 | EA 15.1 | Done | 1
395114 | #262146 | Feature | PI 15 HW FRB Support (CDRL A008) (Recurring) | EA 15.5 | Implementing
395002 |  | Problem | MAINT: WF reported Incorrect MobilityTriggerState in MAMA2 message | Unassigned | Assessing
394979 | #383958 | Story | Ability to download an Excel spreadsheet template - Part 2 | EA 14.2 | Done | 2
394978 | #383958 | Story | Ability to download an Excel spreadsheet template - Part 1 | EA 14.1 | Done | 2
394971 | #396492 | Story | Feature 396492: Verify fix of Problem 390392 | EA 14.1 | Done | 1
394965 | #378000 | Problem | AWARE - VM becomes unusable during MHAL archiving | EA 14.1 | Closed
394963 |  | Problem | AWARE - Fault Notifier must be throttled to send messages 2 seconds apart | Unassigned | Assessing
394949 |  | Problem | When MHAL restarts, MHAL restarts the radios or radios take too long to restart | Unassigned | Assessing
394948 | #378000 | Problem | Splunk is moving between the unknown and executing state when there is loss of communication to the power supply. | EA 14.1 | Closed
394931 |  | Problem | RNC P2P_CDR trace for Mobility Request CDR duplicates 5 lines for single cell/beam scenario (log print only issue) | Unassigned | Assessing
394050 |  | Problem | Splunk index uses reserrved words (e.g. "tag" ) as field labels that can't be searched. | Unassigned | Assessing
393957 | #354871 | Story | Feature 354871: IETM updates (OAS Hardware Overview) OA Workstation upgrade | EA 15.1 | Done | 3
393950 | #354871 | Story | Feature 354871: IETM updates (Using the Safemode desktop) OA Workstation upgrade | EA 15.2 | Done | 3 | #354939
393891 | #393793 | Story | Feature 393793: Conclude next investigative phase, make further recommendations addressing MAS Registrar Out-of-Sync (OOS) causes | EA 14.5 | Done | 2
393833 |  | Problem | Runaway “SNMPP” process on the IASS firewalls | Unassigned | Assessing
393801 | #393793 | Story | Feature 393793: Investigate site logs to address MAS Registrar Out-of-Sync (OOS) causes - 14.3 | EA 14.3 | Invalid | 0
393799 | #393793 | Story | Feature 393793: Investigate site logs to address MAS Registrar Out-of-Sync (OOS) causes - 14.5 | EA 14.5 | Done | 2
393793 | #389645 | Feature | MAS: Investigate MAS Registrar Out-of-Sync causes | EA 14.5 | Done
393770 |  | Story | CM Release Work for EAD 17 Documents | PI 15 | Invalid | 0
393769 | #243502 | Story | CM Release Work for EAD 17 OOC | EA 15.5 | New | 1
393686 | #380808 | Task | Feature 380808: Submit PDO for 99-P57050M - NMS - NM Common PKI | PI 16 | New
393655 |  | Feature | Cyber Sustainment Activities (PI 14) | Unassigned | Rejected
393654 |  | Feature | Cyber EAD 16 MFR Support (Recurring) | Unassigned | Rejected
393642 | #1013136 | Problem | Invalid CR object in OTA-FT Update Request message when no keysets are provisioned | EA 16.1 | Implementing
393525 | #393517 | Story | Feature 393517: Automate GEO ground status configuration values | Unassigned | Invalid | 0
393524 | #393517 | Story | Feature 393517: Automate ETISP state change and services restart | Unassigned | Invalid | 0
393522 | #393517 | Story | Feature 393517: Automate ERS RF switch configuration | Unassigned | Invalid | 0
393521 | #393517 | Story | Feature 393517: Automate GEO Configuration | Unassigned | Invalid | 0
393520 | #393517 | Story | Feature 393517: Automate Polatis optical switch configuration | Unassigned | Invalid | 0
393519 | #393517 | Story | Feature 393517: Automate verification that a RRT has been received by the ETISP and calculated SFRE is good | Unassigned | Invalid | 0
393496 |  | Problem | MAINT: Unknown 1.pst entry will cause waveform to fail to launch | Unassigned | Assessing
393489 | #378964 | Task | Mark Sederstrom PTO (EA 15.4 (5/21 - 5/22)) | EA 15.4 | Done
393488 | #378964 | Task | Mark Sederstrom PTO (EA 15.3 (5/7 - 5/8)) | EA 15.3 | Done
393487 | #378964 | Task | Mark Sederstrom PTO (EA 15.2 (4/23 - 4/24)) | EA 15.2 | Done
393486 | #378964 | Task | Mark Sederstrom PTO (EA 15.1 (4/9 - 4/10)) | EA 15.1 | Done
393485 | #378964 | Task | Mark Sederstrom PTO (EA 14.5 (3/26 - 3/27)) | EA 14.5 | Done
393484 | #378964 | Task | Mark Sederstrom PTO (EA 14.4 (3/12 - 3/13)) | EA 14.4 | Done
393483 | #378964 | Task | Mark Sederstrom PTO (EA 14.3 (2/27 - 2/28)) | EA 14.3 | Done
393482 | #378964 | Task | Mark Sederstrom PTO (EA 14.2 (2/13 - 2/14)) | EA 14.2 | Done
393481 | #378964 | Task | Mark Sederstrom PTO (EA 14.1 (1/30 - 1/31)) | EA 14.1 | Done
393467 | #366348 | Story | Lab - Polatis Switch Replacement - Create Deployment Notes, Operator Impact Inputs, and provide input on training (Tom) | Unassigned | Invalid | 0
393432 | #393356 | Feature | Automate bi-monthly manual task : Automate AMS-GS Security Log Collection | Unassigned | Rejected
393426 | #393356 | Feature | Automate weekly manual task : Check DSN GW and reset ports and channels | PI 15 | Rejected
393423 |  | Problem | Vendor: uphy_api_scheduler causing radio lock up | Unassigned | Assessing
393397 | #393356 | Feature | Automate weekly manual task : Check disk space on RCG Server | PI 17 | Draft
393396 | #393356 | Feature | Automate weekly manual task: HSS Routine Maintenance | PI 15 | Rejected
393391 | #393356 | Feature | Automate weekly manual task: CN CSA - CSCF/HSS Disk Space Maintenance | PI 16 | Approved
393360 | #393356 | Feature | Automate bi-weekly manual task : Manage Firewall Disk space | PI 15 | Rejected
393348 |  | Problem | RNC: Activate PDP Context Reject message during C0 (requested-traffic-class-not-available) | Unassigned | Assessing
393346 |  | Problem | Eggplant Automation found scenario where new version of Frequency Profiles can't be saved. | Unassigned | Assessing
393272 | #393265 | Task | Feature 393265: Upload Demo Documentation and Demo Status Workbook for Analysis Demo of the Coordinate and Complete Non-Feature IETM Content for EAD 17 (Analysis Demo) | EA 15.3 | Done
393271 | #393265 | Story | Feature Demo – Customer Demo Event - Feature 393265: Coordinate and Complete Admin IETM Work - ANALYSIS | EA 15.4 | Implementing | 1
393270 |  | Story | Feature 393265: IETM Admin Updates part 1 of 5 (EA 17.1) | PI 15 | Invalid | 0
393269 |  | Story | Feature 393265: IETM Admin Updates part 2 of 5 (EA 17.2) | PI 15 | Invalid | 0
393268 |  | Story | Feature 393265: IETM Admin Updates part 3 of 5 (EA 17.3) | PI 15 | Invalid | 0
393267 |  | Story | Feature 393265: IETM Admin Updates part 4 of 5 (EA 17.4) | PI 15 | Invalid | 0
393266 |  | Story | Feature 393265: IETM Admin Updates part 5 of 5 (EA 17.5) | PI 15 | Invalid | 0
393265 | #262146 | Feature | Coordinate and Complete Non-Feature IETM Content for EAD 17 (Recurring) | EA 15.4 | Implementing
393262 |  | Problem | xsf files for Extreme Switch 450/450A in S/W Installation Instruction are mixed up | Unassigned | Assessing
393260 | #381608 | Story | Feature Demo – Customer Demo Event - Feature 381608: Prep and Hold Feature Demo | EA 14.1 | Done | 1
393257 | #378000 | Problem | SPLUNK Group Status partial outage this weekend for ~16 hours due to AWARE | EA 14.1 | Closed
393252 |  | Problem | OAS Zero Velocity Momentum Adjusts | Unassigned | Assessing
393251 |  | Problem | OAS Unable to remove momentum dumps using maneuver planning application | Unassigned | Assessing
393249 |  | Problem | OAS Filter Tuning | Unassigned | Assessing
393219 |  | Problem | 99-P55760M Software to Hardware Mapping ERS-AWARE - missing SVD/TPS 98-P54199T NM AV/HIDS HBSS instance for awr101-wh-raf | Unassigned | Assessing
393214 |  | Task | Story 393213: CM Release of 99-P53449E - ILS - IETM (EAD 17) | PI 15 | Invalid
393213 | #243502 | Story | Non-Feature PDOs for EAD 17 | EA 16.2 (archived) | New | 1
393106 |  | Problem | NSA finding: Wrong EF Handle table used in in methods umtsAdapter_WriteUmtsProvisioningTransparentEfs() and umtsAdapter_WriteUmtsProvisioningCyclicAndLinearEfs(). | Unassigned | Assessing
393051 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
393021 | #386935 | Problem | Typo in Zeta EGS SVD RPM List | EA 14.4 | Closed
392975 | #386935 | Problem | Rebase Problem 392974 - No convergence for geos below 300 MHz | EA 14.3 | Closed
392922 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
392921 | #343914 | Task | Story 343914: CM Release of 01-P59186M – SEIT – MUOS General Purpose Workstation, SCD (EAD 14) | EA 14.1 | Done
392902 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
392790 | #343918 | Task | Story 343918: CM Release of 99-P53447E – New CDRL – ILS – FRACAS (EAD 15 OOC) (Rev GF - February 2020 Release) | PI 14 - In Progress | Done
392789 | #343918 | Task | Story 343918: CM Release of 99-P53447E – New CDRL – ILS – FRACAS (EAD 15 OOC) (Rev GE - January 2020 Release) | Unassigned | Done
392788 | #343918 | Task | Story 343918: CM Release of 99-P53447E – New CDRL – ILS – FRACAS (EAD 15 OOC) (Rev GA - December Release) | Unassigned | Done
392787 | #343918 | Task | Story 343918: CM Release of 99-P53447E – CDRL A217 – ILS – FRACAS (EAD 15 OOC) (Rev GA - November Release) | Unassigned | Done
392783 | #343920 | Task | Story 343920: CM Release of 98-P59403M - NMS - NM Common - GenericUnixSTIG (EAD 16) | PI 14 | Done
392767 | #392743 | Story | Feature 392743 ATO: Execute Generic STIG SVD | EA 14.4 | Done | 1
392743 | #216552 | Feature | High Dev Risk - ATO Generic Unix STIG SVD Findings - (Solaris) | EA 14.4 | Done
392710 | #378000 | Problem | Aware does not recover if Radio experiences a power loss | EA 14.1 | Closed
392699 | #388076 | Story | Feature 388076: Finish the group PWIs and work in this feature | PI 14 | Invalid | 0
392688 |  | Problem | IETM Updates for Range Rate File Duration | Unassigned | Assessing
392644 | #388913 | Story | Feature 388913: ULX SME Support | Unassigned | Invalid | 0
392627 | #388913 | Story | Feature 388913: Clarify interfaces and specifications (Engineer 1) | Unassigned | Invalid | 0
392567 | #383883 | Story | Feature 383883: EAD 14 Geo on-site support (Anil) | Unassigned | Invalid | 0
392561 | #1004171 | Story | Feature 1004171: Update design docs | EA 14.3 | Done | 1
392560 | #1004171 | Story | Feature 1004171: Assist with Feature Demo | EA 16.1 | New | 1
392557 | #1004171 | Story | Feature 1004171: Support group solution testing (14.3) | EA 14.3 | Done | 1
392556 | #1004171 | Story | Feature 1004171: Support group solution testing (14.3) | EA 14.3 | Done | 1
392555 | #1004171 | Story | Feature 1004171: Support group solution testing (14.2) | EA 14.2 | Done | 2
392554 | #1004171 | Story | Feature 1004171: Support group solution testing (14.2) | EA 14.2 | Done | 2
392553 | #1004171 | Story | Feature 1004171: Test group solution (14.2) | EA 14.2 | Done | 3
392552 | #1004171 | Story | Feature 1004171: Test group solution (14.2) | EA 14.2 | Done | 2
392551 | #1004171 | Story | Feature 1004171: Test group solution (14.3) | EA 14.3 | Done | 1
392550 | #1004171 | Story | Feature 1004171: Test group solution with instrumented build | EA 14.3 | Done | 2
392549 | #1004171 | Story | Feature 1004171: Integrate and Test group solution (14.3) | EA 14.3 | Done | 3
392546 | #1004171 | Story | Feature 1004171: Code walk through of solutions - Chad | EA 14.3 | Done | 2
392530 | #245560 | Feature | Cyber IA Patching - PI 14 (Recurring) | EA 14.5 | Done
392526 | #257560 | Story | Feature 257560: Update AWARE Design Documentation FCAPS IDD | EA 14.2 | Done | 3
392524 | #257560 | Story | Feature 257560: Update AWARE Design Documentation FCAPS IDD | EA 14.3 | Done | 1
392523 | #257560 | Story | Feature 257560: Update AWARE Design Documentation - Aware X5 Design Doc - part 3 | EA 14.3 | Done | 2
392521 | #257560 | Story | Feature 257560: Update AWARE Design Documentation - Aware X5 Design Doc - part 2 | EA 14.2 | Done | 3
392502 | #384036 | Story | Feature 384036: MFR 3 – CSE Completes Final CAP | EA 14.3 | Invalid | 0
392482 | #371222 | Story | Feature 371222: ADI/EMI/PRISM Support - RR Integration (Part 5) | Unassigned | Invalid | 0
392467 | #384036 | Story | Feature 384036: Create Nutanix environment in SWIT LAB | EA 14.2 | Done | 3
392393 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 2 of 2) | EA 15.4 | Invalid | 0
392388 | #1011295 | Problem | Feature 1011295: Additional GEO Removal in Vlab Resolved ETISP Frame Sync Loss Issues | EA 15.5 | Implementing
392384 | #354871 | Story | Feature 354871: MFR 3 - Dev Team Resolves ACAS Scan and STIG Findings Part 2 of 2 | EA 16.2 | New | 2
392379 | #384036 | Story | Feature 384036: Nutanix FM alarm whitelist | EA 14.1 | Done | 2
392318 | #262145 | Story | Establish new process for Deployment Meeting to Replace Deployment and Release Notes | PI 14 | Invalid | 0
392315 | #1000254 | Story | Work with IT to obtain migration plan for new Dev Ops CM and Build System | PI 17 | New | 2
392314 | #1000254 | Story | Select CI for new CM and Build System Prototype | PI 17 | New | 1
392313 | #1000254 | Story | Research and Train on New Build Tools | PI 17 | New | 3
392312 | #1000254 | Story | Research and Train on New CM Tools | PI 17 | New | 3
392303 | #354680 | Story | Feature 354680 (Site): Create Splunk HA SVD Draft (1st draft for dry-runs) - TeamMember2 | EA 14.1 | Done | 3
392302 | #354680 | Story | Feature 354680 (Site): Create Splunk HA SVD Draft (1st draft for dry-runs) - TeamMember1 | EA 14.1 | Done | 5
392268 | #380808 | Task | Feature 380808: Submit PDO for 98-P59856M - Network - ExtremeSwitch - SVD | PI 16 | New
392266 | #343917 | Task | Story 343917: CM Release of 63-P53199T - ILS - Functional Block Diagram (EAD 15) | EA 14.1 | Done
392263 | #343917 | Task | Story 343917: CM Release of 99-P53198T - NMS - NM Common - NEDB (EAD 15) | EA 14.1 | Done
392229 |  | Problem | MUOSAT-MHAL: Increase Reliability and Usage of UTN Devices | Unassigned | Assessing
392226 | #342163 | Story | Complete TACLANE Redlines CoCo Review | EA 15.1 | Done | 2
392225 | #342163 | Story | Fix Problem 353654: IETM - Backup HAIPE- Normal Operation Procedure Refers to a Section in GEM One User Manual that Does Not Exist | EA 15.1 | Done | 1
392224 | #342163 | Story | Fix Problem 352636: IETM - GEM One content in Security Management needs to be updated and verified in the lab | EA 15.1 | Done | 1
392223 | #342163 | Task | Fix Problem 352633: IETM - GEM One steps do not belong in NMF Power Up procedure | EA 15.1 | Done
392222 | #342163 | Task | Fix Problem 352632: IETM - Current HAIPE G Clock Maintenance steps require local update; should use GEM One | EA 15.2 | Done
392221 | #342163 | Task | Fix Problem 352630: IETM - Instructions for checking for HAIPE Faults and FFVS expiration are missing from HAIPE Management procedure | EA 15.2 | Done
392188 | #392170 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
392187 | #392170 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #392188
392186 | #392170 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #392187
392185 | #392170 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #392187
392184 | #392170 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #392187
392183 | #392170 | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP (Change back to Cyber) | Unassigned | Invalid | 0 | #392187
392182 | #392170 | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #392187 #392183
392181 | #392170 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to Falcons) | Unassigned | Invalid | 0
392180 | #392170 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
392179 | #392170 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #392187
392178 | #392170 | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #392182
392177 | #392170 | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #392178
392176 | #392170 | Story | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #392177
392175 | #392170 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #392187 #392176
392174 | #392170 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #392187
392173 | #392170 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #392187 #392185 #392186 #392175
392172 | #392170 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #392173 #392175 #392174
392171 | #392170 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
392170 |  | Feature | <Feature xxx> MFR3 Template | Unassigned | Rejected
392158 | #385442 | Story | Feature 385442: Architecture, Design, and Execution Plan - Network Design (Proof of Concept and Prototype Design)[15.1] | EA 15.1 | Done | 3
392157 | #385442 | Story | Feature 385442: Architecture, Design, and Execution Plan - Network Design (Physical Design Create and Review) [14.3] | EA 14.3 | Done | 3
392151 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | EA 14.4 | Done | 2
392150 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | EA 14.2 | Done | 2
392149 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | EA 14.1 | Done | 1
392132 | #385442 | Story | Feature 385442: Architecture, Design, and Execution Plan - Network Design (Functional Design Create and Review) [14.2] | EA 14.2 | Done | 5
392075 | #388076 | Story | Feature 388076: Final regression test of WF PWIs in this increment | EA 14.3 | Done | 3
392068 | #392058 | Story | Feature 392058: Deployment Notes and Operator Impact Inputs | EA 16.1 | New | 1
392067 |  | Story | Feature 392058: ET/ETISP Alarm Recovery Review for Style Guide Compliance Part 1 | Unassigned | Invalid | 0
392066 | #392058 | Story | Feature 392058: Test and Verify Updated List of Custom Alarms and Alarm Procedures (part 1) | EA 15.3 | Done | 5
392065 | #392058 | Story | Feature 392058: Develop/create IETM Procedures for ERS - Alarm history investigation and detailed analysis | EA 15.1 | Done | 2
392064 | #392058 | Story | Feature 392058: ETI IETM Alarm Recovery Procedures - Update PDF's and IETM proper | EA 15.4 | Done | 5
392063 | #392058 | Story | Feature 392058: Prepare and Execute Feature Demo - Customer Demo Event | EA 16.1 | New | 2
392058 | #216364 | Feature | TO-4: ETI Alarms: Add/Update IETM Alarm Recovery Procedures (Part 2 of 4) [Non-O-Level] | PI 16 - In Progress | Implementing
392038 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation | EA 14.2 | Done | 8
392037 | #387276 | Story | Feature 387276: ULX SE Assessment - Complete Scenarios, Analysis of Simulations, Report | EA 14.1 | Done | 8
392036 |  | Story | Feature 387276: ULX SE Assessment - Support (WWTS) 5 pts | EA 14.2 | Invalid | 0
392035 |  | Story | Feature 387276: ULX SE Assessment - Support (WWTS) - 3 pts | EA 14.3 | Invalid | 0
392032 | #387276 | Story | Feature 387276: ULX SE Assessment - Attend Weekly TIMs, Final Report & Presentation Prep | EA 14.2 | Done | 2
392026 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation | EA 14.1 | Done | 3
391932 | #385856 | Story | Feature 385856: ACC Test input | EA 14.1 | Done | 1
391924 |  | Story | RTC Automation -- automate the building and deploying of the RTC services using Jenkins | Unassigned | Invalid | 0
391922 |  | Story | RTC Automation -- Automate the invalidation of groups of related stories/tasks/features | Unassigned | Invalid | 0
391916 | #1004171 | Story | Feature 1004171: Execute the STCD against the RNC build for final verification | EA 15.3 | Done | 5
391911 |  | Story | RTC automation -- automate retrieval of RTC workitem types, Planned For, Filed Against, Target Deployment | Unassigned | Invalid | 0
391821 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
391818 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
391813 | #343914 | Task | Story 343914: CM Release of 99-P48072V – SEIT – System Operational Verification Test (SOVT) for MUOSv1.1.22.0 (EAD 14), 2nd Release needed prior to 10/28/2019 | Unassigned | Invalid
391812 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | EA 14.4 | Done | 3
391775 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391772 | #297335 | Story | Validate RAN MUOS custom script Issues | EA 14.4 | Done | 3
391770 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391765 | #1020744 | Story | Compile Load Modules for the Remaining RAN CI's part 1 | EA 16.1 | New | 5
391721 | #384036 | Story | Feature 384036: IETM develop procedures for VMs | EA 14.1 | Done | 2
391720 | #384036 | Story | Feature 384036: IETM develop procedures for NME201 and NME202 | EA 14.3 | Done | 3
391719 | #384036 | Story | Feature 384036: IETM develop procedures for Cisco 10 GIG Switch | EA 14.2 | Done | 2
391709 | #384036 | Story | Feature 384036: Build NME201 (for Nutanix) in H1125 South and connect to SWIT LAB | EA 14.2 | Done | 2
391706 | #384036 | Story | Feature 384036: Update New Cisco Switch CI to to support Nutanix infrastructure (2) | EA 14.2 | Invalid | 0
391705 | #384036 | Story | Feature 384036: Implement STIGs and final configuration for Cisco Switch | EA 14.3 | Done | 3
391703 | #384036 | Story | Feature 384036: Update New Cisco Switch CI to to support Nutanix infrastructure (1) | EA 14.1 | Done | 3
391697 | #384036 | Story | Feature 384036: review and deliver 98-P55755M_GS_Firewall_Network_SVD.doc and config changes | EA 14.1 | Invalid | 0
391679 | #384036 | Story | Feature 384036: complete reviews and deliver Extreme Switch CI to to support Nutanix Changes | EA 14.4 | Done | 3
391678 | #384036 | Story | Feature 384036: complete SVD migration instructions and configs for ExtremeSwitch, Firewall, load balancer and Router | EA 14.1 | Done | 1
391661 | #384036 | Story | Feature 384036: review and deliver CI 98-P59410M_F5BIG_IP_SVD.doc | EA 14.1 | Invalid | 0
391655 |  | Story | Feature 384036: Juniper SVD updates to support Nutanix environment (2) | PI 14 | Invalid | 0
391606 |  | Story | Feature 318430 ETT: Final integration/debug of updated SF | Unassigned | Invalid | 0
391582 |  | Story | Feature 384120: Update AAA SVD for Automation servers | Unassigned | Invalid | 0
391579 |  | Story | Feature 384120: Develop AAA and Password/PKI mgt plan for MUOS moving forward, including automation | Unassigned | Invalid | 0
391563 | #380808 | Story | Implement Problem 389378 | PI 16 | New | 3
391551 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391541 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391536 | #385856 | Story | Feature 385856: Conversion to ACC - IETM Placeholder | EA 14.2 | Invalid | 0
391520 | #385856 | Story | Feature 385856: Create ROM and Notional Schedule - Fernando | EA 14.3 | Done | 1
391519 | #385856 | Story | Feature 385856: Create ROM and Notional Schedule - Anton | EA 14.2 | Done | 2
391518 | #385856 | Story | Feature 385856: Create ROM and Notional Schedule - Ty | EA 14.3 | Done | 2
391517 | #385856 | Story | Feature 385856: Create ROM and Notional Schedule - Hy | EA 14.2 | Done | 2
391512 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. Part 1 | EA 14.1 | Done | 5
391509 | #384036 | Story | Feature 384036: Create redlines for 98-P59434M_NM_CSCI_SVD.doc for Nutanix Hardware | EA 14.2 | Done | 1
391507 | #384036 | Story | Feature 384036: Update 98-P59434M_NM_CSCI_SVD.doc | EA 14.3 | Done | 2
391506 | #380808 | Story | Feature 380808: Build and Deliver 99-P59435M_NM_HW_SW_Mapping.doc for Nutanix Hardware | PI 16 | New | 1
391502 | #354871 | Story | Feature 354871: MFR 3 Ð CSE Performs initial Cybersecurity Assessment (part 2 of 2) | EA 16.2 | New | 3
391485 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391476 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
391472 | #354871 | Story | Feature 354871: MFR 3 Ð Dev Team Resolves Final ACAS Scan and STIG Findings | EA 16.3 | New | 3
391465 | #384036 | Story | Feature 384036:(SIEM SVD) update to support Nutanix and iLo data- Part 1 | EA 14.2 | Done | 5
391460 | #354680 | Story | Feature 354680 (Site): VM updates for Splunk HA | PI 14 | Invalid | 0
391459 | #354680 | Story | Feature 354680 (Site): Splunk HA VLAB integration Testing | EA 14.2 | Done | 2
391458 | #354680 | Story | Feature 354680 (Site): Splunk HA VLAB Data Migration - TeamMember3 | EA 14.2 | Done | 1
391457 | #354680 | Story | Feature 354680 (Site): Update patches/STIGs based on initial scan (Splunk HA) (Final RHEL image ready) | EA 14.2 | Done | 3
391456 | #384036 | Story | Feature 384036:(NEDB 99-P53198T.xls) Updates for the NEDB for the Nutanix hardware | EA 14.2 | Done | 1 | #1011899
391455 | #354680 | Story | Feature 354680 (Site): Splunk HA VLAB Data Migration - TeamMember1 | EA 14.2 | Done | 1
391449 | #343914 | Task | Story 343914: CM Release of PL01-P53569E001 – NME 9 Cabinet Assembly - NMA, Parts List (EAD 14) | PI 14 | Done
391448 | #343914 | Task | Story 343914: CM Release of PL01-P53578E001 – NME 8 Cabinet Assembly - NMA, Parts List (EAD 14) | PI 14 | Done
391393 | #354871 | Story | Feature 354871: MFR 3 Ð CSE Completes Final CAP (Change back to Cyber Security Engineering) - EAD 17.x | EA 16.1 | New | 5 | #391397
391361 | #1004171 | Story | Feature 1004171: Build the RNC for testing | EA 15.2 | Done | 5 | #1017268
391353 | #384036 | Story | Feature 384036: Develop Procedures to Display PM Data in PRISM GUI | EA 14.3 | Done | 3
391338 | #384036 | Story | Feature 384036:(AMP Document) Document all local accounts and how to maintain | EA 14.3 | Done | 5
391293 |  | Story | Feature 384036:(Nutanix SVD) Document how to install and Configure the Nutanix system on a new Cluster | Unassigned | Invalid | 0
391274 |  | Story | Feature 384036: Document what Recovery procedures need to be defined for the Nutanix system in the IETM | Unassigned | Invalid | 0
391273 | #384036 | Story | Feature 384036: Investigate of the Nutanix Alert Recovery Procedures Testing | EA 14.2 | Done | 8
391271 |  | Task | Story 343920: CM Release of 99-P57050M - NMS - NM Common PKI (EAD 16) | Unassigned | Invalid
391233 | #386935 | Story | Feature 386935: EAD16 MPC from EAD14 Site Deployment Redlines | EA 14.2 | Done | 1
391224 | #386935 | Story | Feature 386935: GEO EAD17 - Redline and Finalize Ephemeris Design Document | EA 14.4 | Done | 2
391189 |  | Problem | IETM: "Recover From a Failed AutoOD - Normal Operation Procedure" procedure needs a step to run the OAS to MUS ephemeris task | Unassigned | Assessing
391187 |  | Problem | Telem check will fail to process maneuver telemetry properly when there is an OD failure where OD only predicts out ephemeris for a couple days and a couple days have elapsed since the failure | Unassigned | Assessing
391183 | #392743 | Story | Feature 392743 ATO: Fix Problem 354579 - Update SVD to include verification steps & review | EA 14.3 | Done | 3
391181 |  | Problem | Telemetry check warnings for intrusions in OAS not matching telemetry when they're not needed | Unassigned | Assessing
391179 |  | Problem | Many of the momentum adjusts on S-band (generally for M503), the OAS telemetry acceration history files fail to generated properly. | Unassigned | Assessing
391177 |  | Problem | Ue goes OOS when targeting the strongest cell during a mobility event. | Unassigned | Assessing
391127 | #384036 | Story | Feature 384036: Juniper provide Red Line configurations for initial V-LAB testing | EA 14.1 | Invalid | 0
391012 | #342054 | Task | Feature 342054: Submit PDO for 99-P48077V - SEIT - MUOSv1.1.26.0 (EAD-18) AWARE Connected - Sicily Test Report | PI 16 | New
391002 | #354871 | Story | Feature 354871: Review SVD for OA Workstation | EA 15.2 | Invalid | 0
390993 | #1013136 | Problem | MAMA 2: SIB TIMER EXPIRED while walking the MAMA 2 cell response list. | EA 16.1 | Close Pending
390944 | #245572 | Feature | Automate the PKI deployment | Unassigned | Draft
390942 |  | Problem | IETM needs instruction to restart OAS every week due to ADS recommendation from TT INC000002341449 | Unassigned | Assessing
390922 |  | Problem | Need to investigate OSE_HEAP_EHEAP_EXHAUSTED Core dumps; which was cause of group outage | Unassigned | Assessing
390916 | #354871 | Story | Feature 354871: Review SVD for OA Workstation (part 1 of 2) | EA 15.5 | New | 1
390895 | #354680 | Story | Feature 354680 Site: Support patch & STIGs based on scan results | EA 14.2 | Done | 1
390834 |  | Problem | Vendor: MCaiSecure throws coverFail errors. | Unassigned | Assessing
390831 | #343914 | Task | Story 343914: CM Release of 99-P61687A – Security Plan (SP) Supplement – MUOS (EAD 14) | EA 14.1 | Done
390808 |  | Task | Jessica OOP reminder: | Unassigned | Invalid
390807 |  | Task | Katie OOP reminder: | Unassigned | New
390806 |  | Task | Dustin OOP reminder: | Unassigned | New
390804 |  | Task | Colin OOP reminder: | Unassigned | New
390801 |  | Task | Ken OOP reminder: | Unassigned | New
390800 |  | Task | Ricardo OOP reminder | Unassigned | New
390799 |  | Task | Chris OOP reminder: | Unassigned | New
390798 |  | Task | Khai OOP reminder: | Unassigned | New
390797 |  | Task | Craig OOP reminder | Unassigned | Invalid
390795 |  | Task | Mark OOP reminder: 7/13-7/17 (Training) | PI 16 | Invalid
390758 |  | Problem | Remove references to the "etnbe" laptop host names from the system (SIEM) | Unassigned | Assessing
390729 |  | Task | Martin OOP reminder: | Unassigned | New
390727 |  | Task | Art OOP reminder: | Unassigned | Invalid
390721 |  | Task | Max OOP reminder: | Unassigned | Invalid
390704 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390702 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390700 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390695 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390691 |  | Task | Alex OOP reminder: | Unassigned | Invalid
390661 |  | Problem | [MAINT] UE Instrumentation: AsNasActivity reported incorrect for PTP Service in Splunk | Unassigned | Assessing
390656 |  | Problem | [Harris] deadlock when AP1 state failed during cell search/measurement | Unassigned | Assessing
390611 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390607 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390604 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
390597 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
390472 |  | Problem | MAMA 2: Trigger "mobility to next cell" instead of going OOS on some OOS triggers. | Unassigned | Assessing
390444 |  | Story | Migrate Existing Development Projects to New Project Structure (This is linked directly to item 4 and may be done concurrently) | PI 14 | Invalid | 0
390441 | #1022632 | Feature | Enhance and Optimize MUOS Build and Release Process Part 2 | PI 17 | Implementing
390418 |  | Problem | "no buffer space" error on Analysis Engine when performing aggregate plan analysis | Unassigned | Assessing
390411 | #1001248 | Problem | KMS "setupImsis" method not correctly handling normal provisioning vs rekey | EA 14.3 | Closed
390401 | #387276 | Story | Feature 387276: ULX SE Assessment - Attend Weekly TIMs, Final Report & Presentation Prep | EA 14.1 | Done | 2
390400 | #387276 | Story | Feature 387276: ULX SE Assessment - Scenario Creation, Analysis & Results Support (Brian Kearney, SME LOE) | EA 14.1 | Done | 1
390398 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation ) | EA 14.2 | Done | 2
390392 | #396492 | Problem | ProvBridge to HLR timeout during terminal provisioning | EA 14.1 | Closed
390386 | #243505 | Feature | Update Process and Tools so that future SVD Updates get accounted for in TPS license evaluations | PI 14 | Rejected
390355 | #1019230 | Problem | Ue Instrumentation: Group talker reports as "listener" after configuring receiving leg. It should report as "talker". | PI 17 | Approved
390317 | #297335 | Story | Regression Test after transition | EA 14.5 | Done | 2
390316 | #297335 | Story | Regression Test prior to transition | EA 14.4 | Done | 2
390299 | #385856 | Story | Feature 385856: Conversion to ACC - Capability Spec Review/Redline Support | EA 14.4 | Done | 2
390294 | #385442 | Story | Feature 385442: Architecture, design, and Execution Plan (IA) [14] | PI 14 | Invalid | 0
390286 | #216552 | Feature | Cyber BlueSheets | EA 14.5 | Done
390239 | #1007900 | Story | Feature 1007900: Monitor and document HIPS and MAC exceptions identified during development of HBSS on both High and low sides. | EA 15.4 | Implementing | 2
390238 | #384136 | Story | Feature 384136: Monitor and document HIPS and MAC exceptions identified during development of HBSS on both High and low sides. Sprint 2 | EA 14.2 | Done | 2
390237 | #384136 | Story | Feature 384136: Monitor and document HIPS and MAC exceptions identified during development of HBSS on both High and low sides. Sprint 4 | EA 14.4 | Done | 2
390232 | #384136 | Story | Feature 384136: Develop IETM procedures based on list of identified IETM updates. Part 2 | EA 14.2 | Done | 5
390119 | #384136 | Story | Feature 384136: Develop FCAP Solutions for SIEM | EA 14.3 | Done | 5
390110 |  | Task | Story 393213: CM Release of 98-P59858M of NM Splunk Application SVD (EAD 17) | PI 15 | Invalid
390108 | #384153 | Story | Finalize Design TPM Replacement Phase 2- Researcher [Wireframe Development] | Unassigned | New | 2
390107 | #384153 | Story | Finalize Design TPM Replacement Phase 2- Designer [Wireframe Development] | Unassigned | New | 2
390106 | #384153 | Story | Generate Report for TPM Replacement Phase 2 User Interviews [Report User Event] | Unassigned | New | 2
390105 | #384153 | Story | Interview Users for TPM Replacement Phase 2 [Conduct User Event] | Unassigned | New | 3
390104 | #384153 | Story | Create Research Plan and Needed Materials for TPM Replacement Phase 2 [Plan User Event] | Unassigned | New | 2
390103 | #384153 | Story | Design Round 2 TPM Replacement Phase 2- Researcher [Wireframe Development] | Unassigned | New | 3
390102 | #384153 | Story | Design Round 2 TPM Replacement Phase 2- Designer [Wireframe Development] | Unassigned | New | 3
390101 | #384153 | Story | Design Round 1 TPM Replacement Phase 2- Researcher [Wireframe Development] | Unassigned | New | 3
390100 | #384153 | Story | Design Round 1 TPM Replacement Phase 2- Designer [Wireframe Development] | Unassigned | New | 3
390099 | #384153 | Story | Prep and Conduct User Interviews TPM Replacement Phase 2 [Perform Focused User Research] | Unassigned | New | 2
390098 | #380808 | Task | Feature 380808: Submit PDO for 98-P59859M - NMS - NM - Splunk - Infra - SVD | PI 16 | New
390097 |  | Task | Story 1011568: CM Release of 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD (EAD 18) | PI 15 | Invalid
390080 | #1007900 | Story | Feature 1007900: OBS HBSS- IETM Updates | EA 15.1 | Done | 5 | #384145
390076 |  | Task | Story 343920: CM Release of 98-P59815M - NMS - NM - ProvBridge - SVD (EAD 16) | PI 14 | Invalid
390074 | #1011441 | Task | Feature 1011441: Submit PDO for 99-P53426E – ILS – MUOS Ground Systems Level of Repair Analysis (LORA) | EA 16.2 | New
390060 | #318430 | Story | Feature 318430 ETT: Build laptops for VLAB after demo passes. | EA 14.2 | Done | 3
390026 | #342054 | Task | Feature 342054: Submit PDO for 99-P61689A – SEIT [aka MUOS I-Level Procedures and Supporting Material] | PI 16 | New
390025 |  | Task | Story 390018: CM Release of 98-P55479M - GTS - RN - ETI - ETT - SVD (EAD 17) | PI 15 | Invalid
390024 |  | Task | Story 390018: CM Release of 99-P53449E - ILS - IETM (EAD 17) | PI 15 | Invalid
390023 |  | Task | Story 343920: CM Release of 98-P59861M - NMS - NM - Common - ETI - SVD (EAD 16) | PI 14 | Invalid
390022 |  | Task | Story 343920: CM Release of 98-P55613M - GTS - RN - ET - SVD (EAD 16) | PI 14 | Invalid
390020 |  | Task | Story 343920: CM Release of 98-P55479M - GTS - RN - ETI - ETT - SVD (EAD 16) | PI 14 | Invalid
390019 | #358656 | Task | Feature 358656: Submit PDO for 99-P53449E - ILS - IETM | EA 16.1 | New
390018 |  | Story | INVALID: CM Release Work for EAD 17 | PI 15 | Invalid | 0
390016 | #343920 | Task | Story 343920: CM Release of 98-P54107T – GEO – AMS-GS SVD (EAD 16) | PI 14 | Done
390010 | #380808 | Task | Feature 380808: Submit PDO for 98-P59428M - NMS - NM - Security - SIEM - SVD | PI 16 | New
390009 |  | Task | Story 343917: CM Release of 98-P54191T - NMS - NM - FCAP - FaultMgmt - SVD (EAD 15) | Unassigned | Invalid
390008 |  | Task | Story 343920: CM Release of 98-P55755M - Firewall - Network - SVD (EAD 16) | Unassigned | Invalid
389969 | #389965 | Story | Update CMDB to reflect MUOS | PI 16 | Invalid | 0
389956 | #389941 | Story | Installation and Validation of GFI-CMDB - SE support | PI 16 | Invalid | 0
389936 | #389930 | Story | Installation and Validation of SM components and capabilities - Obsolescence support | PI 15 | Invalid | 0
389934 | #389930 | Story | Installation and Validation of SM components and capabilities - SE support | PI 15 | Invalid | 0
389922 | #379001 | Story | Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389887 | #384136 | Story | Feature 384136: SVD Development and Test Support EA14.4 | EA 14.4 | Done | 2
389886 | #384136 | Story | Feature 384136: IETM Development and Unit Test Support for SNMP Traps | EA 14.4 | Done | 3
389884 | #384136 | Story | Feature 384136: SVD Development and Test Support EA14.3 part 2 | EA 14.3 | Done | 3
389882 | #384136 | Story | Feature 384136: SVD Development and Test Support EA14.3 Part 1 | EA 14.3 | Done | 3
389881 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
389879 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
389877 |  | Story | JUNIT SUMMARY | Unassigned | Invalid | 0
389849 |  | Task | CM Release of 99-P53449E - ILS - IETM (EAD 15) | Unassigned | Invalid
389832 | #380808 | Story | Feature 380808: Update Functional Block Diagram | PI 16 | New | 3
389828 | #1007900 | Story | Feature 1007900: Update EAD 18 Account Management Plan | EA 15.2 | Done | 5
389813 | #384136 | Story | Feature 384136: Continued STCD Development, Testing of Migration of ePO 200 to Nutanix and importing ePO201 into Nutanix provide redlines to development team. | EA 14.1 | Done | 5 | #389882
389805 | #1002583 | Story | Develop Plan for first.last migration | EA 15.2 | Done | 3
389796 | #384136 | Story | Feature 384136: MFR 3 – Develop Design updates based on initial STIG finding Part 2 | EA 14.4 | Done | 5
389794 | #384136 | Story | Feature 384136: Support Review and test of IETM procedures based on development of IETM Procedures | EA 14.4 | Done | 3
389789 | #1007900 | Story | Feature 1007900: Document and Release Capability Design Document | EA 15.4 | Implementing | 2
389788 | #384136 | Story | Feature 384136: Document capability specification and detailed design Post Implementation | EA 14.4 | Done | 3
389746 | #387276 | Story | Feature 387276: ULX System Assessment Support | Unassigned | Invalid | 0
389745 | #387276 | Story | Feature 387276: ULX SE Assessment - Attend Weekly TIMs, Final Report & Presentation Prep | EA 14.3 | Done | 2
389715 | #1007900 | Problem | Feature 1007900: Analysis of HBSS ePO issues from trouble ticket | EA 15.3 | Closed
389692 | #343917 | Task | Story 343917: CM Release of 98-P54188T - NMS - NM - Security - AAA - SVD (EAD 15) | EA 14.1 | Done
389681 | #387276 | Story | Feature 387276: ULX SE Assessment - Weekly TIM's, Scenario Simulations Analysis & Documentation | EA 14.3 | Done | 8
389656 | #388195 | Story | Feature 388195: Install the Virtualized PM Universal Forwarder VM | PI 14 | Invalid | 0
389654 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort Part 4 | EA 14.4 | Done | 2
389650 | #388195 | Story | Feature 388195: Set-up Network Communication between Splunk, Nutanix, HBSS, and VM Automation - Perform Iterative Implementation, Integration, development Testing including updating design | PI 14 | Invalid | 0
389647 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort (EA 14.3 - part 1 of 2) | EA 14.3 | Done | 3
389561 | #243502 | Story | CM Release Work for EAD 16 Documents | EA 15.4 | New | 1
389549 | #388154 | Feature | OBS - PPA: Create a Development Concept/Architecture for PPA Replacement | EA 14.2 | Done
389475 | #343917 | Task | Story 343917: CM Release of RNC CI: 98-P53511T-GTS-RN-RNC-SVD (EAD 15) | EA 14.1 | Done
389452 | #354680 | Story | Feature 354680 (Site): Splunk HA Integration / performance testing | EA 14.2 | Done | 2 | #354682
389451 | #354680 | Story | Feature 354680 (Site): Splunk HA STCD Development (Ramp-up and development) - Chris | EA 14.1 | Done | 2 | #354682
389429 |  | Problem | Firewall (primarily Australia) is denying inter-apn routing between APN05 to APN05 at AU, NW and WH sites starting with the ISAKMP messaging | Unassigned | Assessing
389401 |  | Task | Problem 387316 | Unassigned | Invalid
389400 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389378 | #380808 | Problem | Remove references to the "etnbe" laptop host names from the NEDB; find other references and create PWIs | PI 16 | Approved
389376 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389364 |  | Task | Problem 387316 | Unassigned | Invalid
389363 |  | Story | JUNIT Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
389362 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389347 |  | Task | Problem 387316 | Unassigned | Invalid
389346 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389344 |  | Story | JUNIT Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
389343 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389342 |  | Story | JUNIT Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
389341 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389340 |  | Story | JUNIT Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
389339 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
389288 | #377408 | Story | Feature 377362: Resolve Problem 381247 PKI Expiration Spreadsheet in IETM | EA 14.2 | Done | 5
389252 | #383165 | Story | Feature 383165: Update the MUOS System Drawing Tree | EA 14.1 | Done | 3
389249 | #383165 | Story | Feature 383165:Complete Redlines for Ancillary Cabinets (8, 9, 14, 15) | EA 14.1 | Done | 3
389247 | #383165 | Story | Feature 383165: Design and Documentation of New Rack Documentation, Drawings, and Parts List for Nutanix | EA 14.1 | Done | 2
389241 | #383165 | Story | Feature 383165: Gather & Submit Redlined Documents to Support FRCB Submittal for Nutanix | EA 15.4 | Implementing | 1
389160 |  | Problem | Firewall (primarily Northwest) denying inter-apn routing between APN11 to APN12 at NW and WH sites starting with the ISAKMP messaging | Unassigned | Assessing
389110 |  | Problem | Update IETM Alarm Procedures with TPM References | Unassigned | Assessing
388996 |  | Task | Story 343885: CM Release of 98-P54107T – GEO – AMS-GS SVD **MPC EAD13.xx Information **** | EA 14.1 | In Development
388793 |  | Problem | Functional Block Diagram Updates | Unassigned | Assessing
388653 | #384036 | Story | Feature 384036: Juniper SVD updates to support Nutanix environment (1) | EA 14.1 | Invalid | 0
388555 | #388549 | Story | Feature 388549: ULX Detailed Design - Channel Processor (System Design, SW Architecture, Sequence Diagrams) | EA 14.1 | Done | 8
388554 | #388549 | Story | Feature 388549: ULX Detailed Design - Preprocessor (System Design, Redundancy, AMS ICD) | EA 14.1 | Done | 5
388553 | #388549 | Story | Feature 388549: ULX Detailed Design - Preprocessor (System Design, Redundancy, AMS ICD) | EA 14.1 | Done | 8
388549 | #370101 | Feature | TD 19-15: Create ULX Detailed Design | EA 14.5 | Done
388548 | #354174 | Story | Feature 354174 Splunk IETM: Splunk HA Review IETMs | EA 14.2 | Done | 1
388542 |  | Problem | MAMA2: The expiration of the SIB_TIMER causes OOS. UE should move to the next cell in the MAMA2 list instead. | Unassigned | Assessing
388535 |  | Problem | Vendor: OOS after Multiservice Congestion Occurs | Unassigned | Assessing
388534 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort Part 3 | EA 14.2 | Done | 5
388530 |  | Problem | Evaluate and Update IETM - HPA Acceptance Procedure & HPA Degas Procedure to include body overcurrent fault test | Unassigned | Assessing
388511 | #388497 | Story | Feature 388497: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
388503 | #388497 | Story | Feature 388497: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #388510 #1001940
388478 | #383165 | Story | Feature 383165 Completion of Base Electronic System Engineer Plan BESEP (needed 120 days prior to FRCB) | EA 15.4 | Implementing | 3
388477 | #383165 | Story | Feature 383165 Generate Test Report, needed 45 days prior to FRCB. | EA 16.5 | New | 3
388476 | #383165 | Story | Feature 383165 Complete System Operational Verification Test, SOVT, needed 90 days prior to FRCB | EA 16.3 | New | 5
388475 | #383165 | Story | Feature 383165 Generate System Operational Verification Test, SOVT, Test Inputs for Feature | EA 16.2 | New | 5 | #388476
388474 | #383165 | Story | Feature 383165: Create Redlines on Hardware Drawings Submitted for IDP | EA 14.4 | Invalid | 0 | #388472
388473 | #383165 | Story | Feature 383165: Define Power Consumption Changes for IDP | EA 15.1 | Done | 1 | #388472
388472 | #383165 | Story | Feature 383165 Work on Installation Design Plan IDP (red lines Hardware drawings submitted(red lines Hardware drawings submitted), needed 120 days prior to FRCB; | EA 15.4 | Implementing | 5
388471 | #383165 | Story | Feature 383165: Begin Identification of Logistics Considerations (non-IETM) for Nutanix Deployment | EA 15.1 | Done | 1
388470 |  | Feature | <Feature xxx> HW/FRCB Template | Unassigned | Rejected
388338 | #383170 | Story | Feature 383170: Create Draft Training Plan - Nutanix [Training Plan] | PI 14 | Invalid | 0
388337 | #383170 | Story | Feature 383170: Create Training Materials - Nutanix [Create Training] | PI 14 | Invalid | 0
388336 | #383170 | Story | Feature 383170: AWARE SME Review of Nutanix Training Materials | PI 14 | Invalid | 0
388335 | #383170 | Story | Feature 383170: SysEng SME Review Nutanix Training Materials | PI 14 | Invalid | 0
388334 | #383170 | Task | Feature 383170: Finalize, Print, and Ship Materials - Nutanix [Create Training] | PI 14 | Invalid
388333 | #383170 | Story | Feature 383170: Deliver Training at NCTAMS - Nutanix [Deliver Training] | PI 14 | Invalid | 0
388332 | #383170 | Story | Feature 383170: Complete Customer Response Matrix (CRM) - Nutanix [Deliver Training] | PI 14 | Invalid | 0
388279 |  | Problem | INC000004326041: NAVSOC HQ-OAS Planned Failover procedure corrections | Unassigned | Assessing
388274 |  | Problem | INC000004283233: NAVSOC HQ-Recovery from ODs during maneuvers | Unassigned | Assessing
388267 |  | Problem | INC000004283280: NAVSOC HQ-Telemetry check doesn't check telemetry if the previous telemetry task failed | Unassigned | Assessing
388264 |  | Problem | INC000004283331: NAVSOC HQ-EWSK and not just relocation for thruster efficiency solving fix | Unassigned | Assessing
388261 |  | Problem | INC000004283330: NAVSOC HQ-24 hr max duration requirement for recovery ODs | Unassigned | Assessing
388257 |  | Problem | INC000004283134: NAVSOC HQ-Procedure for configuring a different satellite for Ka-Band | Unassigned | Assessing
388209 | #388195 | Story | Feature 388195: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
388208 | #388195 | Story | Feature 388195:- Prep and Perform Feature Demo – Customer Demo Event | PI 14 | Invalid | 0 | #388209
388207 | #388195 | Story | Feature 388195: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 14 | Invalid | 0 | #388208
388206 | #388195 | Story | Feature 388195: Execute STCD Feature Integration and testing including STCD updates identified | PI 14 | Invalid | 0 | #388208
388205 | #388195 | Story | Feature 388195: Update SVD | PI 14 | Invalid | 0 | #388208
388204 | #388195 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | PI 14 | Invalid | 0
388203 | #388195 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | PI 14 | Invalid | 0
388202 | #388195 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | PI 14 | Invalid | 0 | #388208
388201 | #388195 | Story | Feature 388195: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 14 | Invalid | 0 | #388208
388199 | #388195 | Story | Feature 388195: Provide Deployment Notes and Operator Impact Inputs | PI 14 | Invalid | 0 | #388208
388198 | #388195 | Story | Feature 388195: Create STCD outline and review with stakeholders | PI 14 | Invalid | 0 | #388206 #388208 #388207
388196 | #388195 | Task | Feature 388195: Hold Feature Recap Review with SMEs | PI 14 | Invalid
388158 | #388053 | Story | Design PPA Replacement | EA 14.2 | Done | 5
388157 | #388053 | Story | Support design of PPA - part 1 | EA 14.1 | Done | 5
388156 | #388053 | Story | Feature 388053 PPA Obs: Support design of PPA - (SIC) part 1 | EA 14.1 | Done | 3
388155 | #388053 | Story | Support design of PPA | EA 14.4 | Done | 5
388122 |  | Task | RNC Decoder Support | Unassigned | Invalid
388077 | #382898 | Story | Test new radios with call bank automation | PI 14 | Invalid | 0
388076 | #245573 | Feature | WF PWI Burn down | EA 14.3 | Done
388075 | #382898 | Story | Prepare for Taunton Maintanence Trip | PI 14 | Invalid | 0
388074 | #382898 | Story | Identify and pull radios to go to Taunton | PI 14 | Invalid | 0
388073 | #382898 | Task | Determine if antenna movement is needed and cross train | PI 14 | Invalid
388072 | #382898 | Story | Prepare HW for shipment to Taunton | PI 14 | Invalid | 0
388071 | #382898 | Story | Travel and work in Taunton | PI 14 | Invalid | 0
388053 | #388154 | Feature | OBS - PPA: Develop System Design for PPA Replacement | EA 15.4 | Implementing
388026 | #388004 | Story | Feature 388004: TD0202-18-13 Unclass GDS Analysis - Waveform | EA 14.2 | Invalid | 0
388021 | #388004 | Story | TD 19-18 Unclass GDS Analysis - Systems (Part 3) | EA 14.1 | Done | 5
388006 |  | Story | JUNIT Re-write and Test Problem 387316 Story | Unassigned | Invalid | 0
388005 |  | Story | JUNIT Rebase and Test Problem 387316 Story | Unassigned | Invalid | 0
388004 | #249368 | Feature | TD 19-18 Unclass GDS Analysis | EA 14.4 | Done
387886 | #390441 | Story | Perform Cutover from Exiting Development Projects to New Project Structure | PI 17 | New | 1
387885 | #390441 | Story | Migrate Existing Development Projects to New Project Structure (This is linked directly to item 4 and may be done concurrently) | PI 17 | New | 3
387884 | #390441 | Story | Update ClearQuest to Support UCM Project Enhancements (EADs and OOCs) (ODE) | PI 17 | New | 5
387883 | #390441 | Story | Update BuildForge to Support UCM Project Enhancements (EADs and OOCs) | PI 17 | New | 5
387793 | #382059 | Story | Feature 382059: Implement first set of prioritized System Document baseline updates - SME support for WF/RAN | Unassigned | Invalid | 0
387591 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Engineering IETM Development - ETI | PI 14 | Invalid | 0
387579 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Review for Style Guide Compliance and Dry Run- SA | PI 14 | Invalid | 0
387578 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Review for Style Guide Compliance and Dry Run- Systems | PI 14 | Invalid | 0
387577 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Review for Style Guide Compliance and Dry Run- AMS-GS_AWARE | PI 14 | Invalid | 0
387470 | #382059 | Story | Implement first set of prioritized System Document baseline updates - SME support for AAA/DNS | Unassigned | Invalid | 0
387468 | #382059 | Story | Feature 382059: Implement first set of prioritized System Document baseline updates - SME support for Custom Code | Unassigned | Invalid | 0
387466 | #382059 | Story | Feature 382059: Implement First Set of Prioritized System Document Baseline Updates - SME support for ILS | Unassigned | Invalid | 0
387465 | #382059 | Story | Implement first set of prioritized System Document baseline updates - SME support for KMS | Unassigned | Invalid | 0
387462 | #382059 | Story | Implement first set of prioritized System Document baseline updates - SME support for PPA | Unassigned | Invalid | 0
387461 | #382059 | Story | Implement first set of prioritized System Document baseline updates - SME support for PPA | Unassigned | Invalid | 0
387452 | #381997 | Feature | Implement updates towards establishment of MUOS Core System Documentation baseline | PI 16 - Candidate | Approved
387448 | #381997 | Feature | Implement updates towards establishment of MUOS Esential System Documentation Baseline | EA 15.4 | Implementing
387446 | #381997 | Feature | Implement updates towards establishment of MUOS Essential System Documentation baseline | EA 15.5 | Implementing
387434 | #1008506 | Problem | Procedure to recover KVM display when it disappears on KVM with Version 6 of FW does not exist | EA 15.4 | Approved
387371 | #384136 | Story | Feature 384136: Update AAA SVD 98-P54188T003 for DNS changes for HBSS High Side | EA 14.1 | Done | 5 | #1007603
387369 |  | Story | Feature 384120: Connect to AAA for Domain Password | Unassigned | Invalid | 0
387323 | #371080 | Story | Generate Dashboard Coding Standard Document | PI 15 | Invalid | 0
387322 | #371080 | Story | Define Process to Receive/Load ARSTRAT Dashboard in VLAB | PI 15 | Invalid | 0
387321 | #371080 | Story | Add Transfer of ARSTRAT Dashboard TT/PWIs to Problem Resolution Process | PI 15 | Invalid | 0
387311 | #387307 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
387310 | #387307 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #387311
387309 | #387307 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
387308 | #387307 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #387309
387279 | #1001248 | Problem | No feedback provided to PPA operator for updates to Terminal Profile Defaults system configuration parameters | EA 14.3 | Closed
387278 | #387276 | Story | Feature 387276: ULX SE Assessment - Final Document Delivery & Presentation Support | EA 14.4 | Done | 8
387277 | #387276 | Story | Feature 387276: ULX SE Assessment - Final Document Delivery & Presentation Support | EA 14.5 | Done | 2
387276 | #370101 | Feature | TD 20-05: ULX System Assessment | EA 14.5 | Done
387255 | #1001248 | Problem | OTAP issues due to intermittent locks on caller records | EA 14.5 | Closed
387252 |  | Story | Feature 384120: Systems SME Support | Unassigned | Invalid | 0
387249 | #384153 | Story | Feature 384153: Systems SME Support | Unassigned | New | 3
387236 | #384136 | Story | Feature 384136: Lab team Infrastructure Support - NUTANIX | EA 14.1 | Done | 3 | #390232
387231 | #1007900 | Story | Feature 1007900: MFR 3 – CSE Completes Final CAP (Change back to Cyber Security Engineering) | PI 16 | New | 5 | #387230
387230 | #1007900 | Story | Feature 1007900: MFR 3 – Dev Team Resolves Additional STIG or SCAN Findings | EA 15.1 | Done | 5
387225 | #387207 | Story | Feature 387207: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
387224 | #387207 | Story | Feature 387207- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #387225
387223 | #387207 | Story | Feature 387207: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #387224
387222 | #387207 | Story | Feature 387207: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #387224
387221 | #387207 | Story | Feature 387207: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #387224
387220 | #387207 | Story | Feature 387207: MFR 3 – CSE Completes Final CAP (Change back to Cyber Security Engineering) | Unassigned | Invalid | 0 | #387224
387219 | #387207 | Story | Feature 387207: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #387220 #387224
387218 | #387207 | Story | Feature 387207: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | Unassigned | Invalid | 0
387216 | #387207 | Story | Feature 387207: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #387224
387215 | #387207 | Story | Feature 387207:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #387219
387214 | #387207 | Story | Feature 387207: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #387215
387213 | #387207 | Story | Feature 387207: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #387214
387212 | #387207 | Story | Feature 387207: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #387213 #387224
387211 | #387207 | Story | Feature 387207: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #387224
387210 | #387207 | Story | Feature 387207: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #387224 #387222 #387223 #387212
387209 | #387207 | Story | Feature 387207 Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #387211 #387212 #387210
387081 | #356968 | Story | OBS - AWARE & Call Banks: Transition Plan to Clustered Architecture VM environment | PI 16 | New | 5
387080 | #356968 | Story | OBS - AWARE & Call Banks: Transition Plan to Clustered Architecture VM environment | PI 16 | New | 5
387079 | #356968 | Story | OBS - AWARE & Call Banks: Transition Plan to Clustered Architecture VM environment | PI 16 | New | 5
387073 | #290711 | Story | Feature 290711: SE AWARE Deployment support | Unassigned | Invalid | 0
387069 | #392058 | Story | Feature 392058: MPC Rebase for NetMAC GUI update | EA 15.1 | Done | 1
387050 |  | Feature | Address site deployment impacts to NM AAA 98-P54188T SVD | Unassigned | Rejected
387044 | #387036 | Story | <Feature xxx> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0
387043 | #387036 | Story | <Feature xxx> Generate Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
387042 | #387036 | Story | <Feature xxx> Complete System Operational Verification Test, SOVT, needed 90 days prior to FRCB | Unassigned | Invalid | 0
387041 | #387036 | Story | <Feature xxx> Generate System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #387042
387040 | #387036 | Story | <Feature xxx> Create Redlines on Hardware Drawings Submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #387038
387039 | #387036 | Story | <Feature xxx> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #387038
387038 | #387036 | Story | <Feature xxx> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 110 days prior to FRCB; | Unassigned | Invalid | 0
387037 | #387036 | Story | <Feature xxx> Identify Logistics Considerations (non-IETM) (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0
387036 |  | Feature | <Feature xxx> HW/FRCB Template | Unassigned | Rejected
387022 | #382059 | Story | Replicate core design documents from CM to the document tree | Unassigned | Invalid | 0
387019 | #382059 | Story | System design documents: Define process for document format conversion | Unassigned | Invalid | 0
386950 | #386935 | Story | Feature 386935: MUOS Geolocation Support/Maintenance EAD 16: GEO SVD updates, Incorporate EAD14 Deployment Redlines (Part 1) | EA 14.3 | Done | 3
386949 | #386935 | Story | Feature 386935: Initiate CM PDO Processing for all CI's | EA 14.4 | Done | 1
386948 | #386935 | Story | Feature 386935- Prep and Perform Feature Demo – Customer Demo Event | EA 14.4 | Done | 1 | #386949
386947 |  | Story | Feature 386935: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0
386946 | #386935 | Story | Feature 386935: Agile Team Test (PCR Verification & Test) | EA 14.4 | Done | 2 | #386948
386945 | #386935 | Story | Feature 386935: Provide Development inputs to <xyz> common document | Unassigned | Invalid | 0 | #386948
386944 | #386935 | Task | Feature 386935: Incorporation of User Manual and IETM Updates and Integration Support for MUOS Geolocation Support, Maintenance Zeta EAD 15 | EA 14.4 | Done
386943 | #386935 | Story | Feature 386935: UX Review of Zeta User Manual | EA 14.2 | Done | 1
386942 | #386935 | Story | Feature 386935: Engineering Review of Zeta User Manual | EA 14.3 | Done | 2 | #386948
386941 | #386935 | Story | Feature 386935: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 14.2 | Invalid | 0 | #386948
386940 | #386935 | Story | Feature 386935: Install & Unit Test Zeta Delivery | EA 14.2 | Done | 5 | #386948
386939 | #386935 | Story | Feature 386935: Provide Deployment Notes and Operator Impact Inputs | EA 14.4 | Done | 1 | #386948
386938 | #386935 | Story | Feature 386935: Iterative STCD Development and Site Functional Plan | EA 14.2 | Done | 3 | #386946 #386940 #386948
386937 | #386935 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #386940 #386938
386936 | #386935 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
386935 | #338100 | Feature | MUOS Geolocation Support, Maintenance Zeta EAD 16 | EA 14.4 | Done
386928 | #383958 | Story | Bulk Planning SAR Input Enhancement: Integration testing | PI 15 | Invalid | 0
386890 |  | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0
386887 | #379001 | Story | Rebase and Test Problem xxx Story | Unassigned | New | 2
386882 | #384168 | Story | Feature 384168: Systems cradle to grave oversight and review of feature (IA) | Unassigned | New | 1
386857 | #386853 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
386856 | #386853 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #386857
386855 | #386853 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
386854 | #386853 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #386855
386853 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
386849 | #383110 | Feature | OBS - HW: Complete and Release As-Design documentation for Nutanix Solution | PI 15 | Rejected
385956 |  | Story | Integrate NMS with AWARE: Demo 1 - SA Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
385905 | #354680 | Story | Feature 354680 (Site): Splunk HA final lab testing: SSL Comm issues | EA 14.3 | Invalid | 0
385901 | #354680 | Story | Feature 354680 (Site): AAA/Domain account for SPLUNK (maybe) | EA 14.5 | Invalid | 0
385900 | #354680 | Story | Feature 354680 (Site): Formal update for network devices | EA 14.1 | Done | 1
385899 | #354680 | Story | Feature 354680 (Site): Feature Demo prep: Dry run STCD | EA 14.4 | Done | 1
385892 | #385856 | Story | Feature 385856: Conversion to ACC - ILS | Unassigned | Invalid | 0
385890 | #385856 | Story | Feature 385856: ROM for Conversion to ACC | EA 14.2 | Invalid | 0
385888 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort Part 3 | EA 14.1 | Done | 5
385887 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort (EA 14.2) | EA 14.2 | Done | 2
385886 | #385856 | Story | Feature 385856: Conversion to ACC - Systems Effort Continued | EA 14.1 | Done | 5
385883 | #385856 | Story | Feature 385856: Conversion to ACC - IA Support Part 2 | EA 14.1 | Done | 1
385881 | #385856 | Story | Feature 385856: Conversion to ACC - Capability Spec Writeup for Ground System (Part 2) | EA 14.3 | Done | 3
385880 | #385856 | Story | Feature 385856: Conversion to ACC - TACLANE - Create Notional GEM One/TACLANE Schedule & ROM | EA 14.3 | Done | 5
385877 | #385856 | Story | Feature 385856: Waveform Conversion to ACC - RSS/CIL Analysis Part 2 | EA 14.1 | Done | 5
385875 | #382898 | Story | Install Redhat image and update for Call Banks (Taunton) | PI 14 | Invalid | 0
385874 | #385856 | Story | Feature 385856: Waveform Conversion to ACC - WF SME Part 2 | EA 14.1 | Done | 2
385869 | #385856 | Story | Feature 385856: Waveform Conversion to ACC - HAIPE Part 1 | EA 14.1 | Done | 8
385856 | #367849 | Feature | TD 20-04 MUOS Conversion to Advanced Cryptographic Capability (ACC) | EA 14.4 | Done
385666 |  | Story | Complete SWIT testing | Unassigned | Invalid | 0
385665 |  | Story | Download patches, and update patching script | Unassigned | Invalid | 0
385643 | #384084 | Story | Feature 384084: Netcool Correlations - Perform Iterative Implementation, Integration, development Testing including updating design - part 3 | EA 14.3 | Done | 5
385641 | #384036 | Story | Feature 384036: Upgrade V-Lab to Support Nutanix Solution | EA 14.1 | Done | 3
385633 | #1016383 | Story | Add Nutanix alarms/events to white list | PI 16 | New | 1
385632 | #216351 | Feature | FM Whitelist updates for PI 15: Update whitelist and filter logic | EA 15.4 | Done
385605 | #376446 | Story | Feature 376446: MAGIC Team handoff to Lab Support Team | EA 15.4 | Implementing | 3
385604 | #376446 | Story | Feature 376446: MAGIC Team handoff to Lab Support Team | PI 16 | New | 1
385603 | #376446 | Story | Call Bank Servers: IA Posture Improvement - Posture Assessment (Feature 376446) | EA 14.3 | Done | 3
385602 | #376446 | Story | Feature 376446: Call Bank IATT (Linux) Cyber Support | EA 14.4 | Done | 1
385601 | #376446 | Story | Feature 376446: Configure and Test AWARE Architecture on Radio Pair | EA 15.2 | Done | 5
385600 | #376446 | Story | Feature 376446: Install AWARE Architecture for Call Banks | EA 14.2 | Done | 2
385599 | #376446 | Story | Feature 376446: Update Ruby & Update MultiHAL to use new Ruby version | EA 14.1 | Done | 5
385598 | #376446 | Story | Feature 376446: Configure Linux for PPP access to MOXA | EA 14.4 | Done | 3
385570 | #343917 | Task | Story 343917: CM Release of 99-P53442E – ILS – MUOS ALTERNATE PARTS LIST (EAD 15) | EA 14.1 | Done
385455 | #257560 | Story | Feature 257560: Update AWARE Design Documentation FCAPS IDD | EA 14.2 | Done | 2
385454 | #257560 | Story | Feature 257560: Update AWARE Design Documentation - MHAL SWDD | EA 14.2 | Done | 5
385453 | #257560 | Story | Feature 257560: Update AWARE Design Documentation - Aware X5 Design Doc | EA 14.1 | Done | 3
385452 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | EA 14.1 | Done | 1
385451 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | Unassigned | Invalid | 0
385449 | #384084 | Story | Feature 384084: Support for VM Dev Environment Faults | PI 14 | Invalid | 0
385448 | #384084 | Story | Feature 384084: Support for HBSS Faults | PI 14 | Invalid | 0
385447 | #384084 | Story | Feature 384084: Support for Nutanix Faults Define Severity/ Type for SNMP alarms for Nutanix | EA 14.1 | Done | 5
385444 | #385442 | Story | Feature 385442: Architecture, design, and Execution Plan (Finalize Network Designs) [14.4] | EA 14.4 | Done | 2
385442 | #385438 | Feature | OBS - NET: Determine Network Architecture and Design of the MUOS Ground System and Develop an Execution Plan | EA 16.1 | Implementing
385441 | #383165 | Task | Feature 383165: Support FRCB Package Creation (Release Management) | EA 16.1 | New
385409 |  | Story | Placeholder | Unassigned | Invalid | 0
385407 |  | Story | Placeholder | Unassigned | Invalid | 0
385406 |  | Story | Placeholder | Unassigned | Invalid | 0
385192 | #385178 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
385191 | #385178 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #385192
385190 | #385178 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #385191
385189 | #385178 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #385191
385188 | #385178 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #385191
385187 | #385178 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | Unassigned | Invalid | 0
385186 | #385178 | Story | <Feature xxx> UX Research and Design Support (Change back to UX Team) | Unassigned | Invalid | 0
385185 | #385178 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #385191
385184 | #385178 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #385191
385183 | #385178 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #385191
385182 | #385178 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #385191
385181 | #385178 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #385190 #385191 #385189 #385183
385180 | #385178 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #385183 #385181
385179 | #385178 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
385178 |  | Feature | <Feature xxx> MFR1 Template | Unassigned | Rejected
385163 |  | Task | AWARE & MHAL Going Connected: Interim Demo 1 - System Test, STCD development and Demo Prep - (Combined INTERIM Demo for Features 290638, 285527) | Unassigned | Invalid
385129 | #385111 | Story | <Feature 385111>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
385128 | #385111 | Story | <Feature 385111>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #385129
385127 | #385111 | Story | <Feature 385111>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #385128
385126 | #385111 | Story | <Feature 385111>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #385128
385125 | #385111 | Story | <Feature 385111>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #385128
385124 | #385111 | Story | <Feature 385111>: MFR 3 – CSE Completes Final CAP | Unassigned | Invalid | 0 | #385128
385123 | #385111 | Story | <Feature 385111>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #385124 #385128
385122 | #385111 | Story | <Feature 385111>: ILS Incorporation of IETM updates and integration support | Unassigned | Invalid | 0
385121 | #385111 | Story | <Feature 385111> UX Research and Design Support (Change back to UX team) | Unassigned | Invalid | 0
385120 | #385111 | Story | <Feature 385111>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #385128
385119 | #385111 | Story | <Feature 385111>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #385123
385118 | #385111 | Story | <Feature 385111>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #385119
385117 | #385111 | Story | <Feature 385111>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #385118
385116 | #385111 | Story | <Feature 385111>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #385128 #385117
385115 | #385111 | Story | <Feature 385111>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #385128
385114 | #385111 | Story | <Feature 385111>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #385128 #385127 #385116 #385126
385113 | #385111 | Story | <Feature 385111> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #385114 #385116 #385115
385112 | #385111 | Task | <Feature 385111> Hold Feature Review with SMEs | Unassigned | Invalid
385076 | #382932 | Story | Cell Status Placeholder | Unassigned | Invalid | 0
385075 | #382932 | Story | Pie Chart Placeholder | Unassigned | Invalid | 0
385074 | #384943 | Story | SA Placeholders | Unassigned | New | 20
384952 | #384943 | Story | Feature 384943: Incorporation of IETM Updates and Integration Support for Expansion of Instrumentation Status in SA Dashboards | Unassigned | New | 1
384823 |  | Problem | Vendor: Array out of bounds when NSAPI is 15. | Unassigned | Assessing
384673 | #355228 | Story | RF Alignment Site # 3 (Relocation): Travel Prep - Engineer 2 | Unassigned | Invalid | 0
384599 | #1001062 | Story | Upgrade RDE & ERC & BKP VOBs to schema 80 (Do Not upgrade schema for VOBs replicated to ODE) | EA 15.4 | Implementing | 5
384597 | #297335 | Story | Change Mastership of VOBs from ERIC to ERC | EA 14.5 | Done | 3 | #384596 #390317
384596 | #297335 | Story | Change Mastership of VOBs from RAN to RDE | EA 14.5 | Done | 5 | #390317
384477 | #1002583 | Story | User Identification accounts for GDMS domain (renaming) | EA 15.5 | New | 5
384439 | #384430 | Story | <Feature 384430>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #384447
384429 |  | Problem | VENDOR: Fatal error 0x02000128 occurs when two RSSI messages are sent. | Unassigned | Assessing
384411 |  | Problem | In the VLab, we cannot logon to the following firewalls using a Domain Radius Account. The following FIREWALLS have been identified to have this problem: nwiassfw1, nwtisfw1, hqiascfw1, hqiascfw2, auiasrfw1 | Unassigned | Assessing
384271 | #384233 | Story | Feature 384233: Systems cradle to grave oversight and review of feature | Unassigned | Invalid | 0
384267 |  | Story | Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
384266 | #384233 | Story | Feature 384233: Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
384263 | #384233 | Story | Feature 384233: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0
384261 | #384233 | Story | Feature 384233: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0
384260 | #384233 | Story | Feature 384233: Provide Development inputs to common documents | Unassigned | Invalid | 0
384243 | #384233 | Story | Feature 384233: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | Unassigned | Invalid | 0
384242 | #384233 | Story | Feature 384233: UX Research and Design Support (change back to UX team) | Unassigned | Invalid | 0
384241 | #384233 | Story | Feature 384233: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0
384240 | #384084 | Story | Feature 384084: MFR 1 – Dev Team Performs Cybersecurity Assessment | EA 14.2 | Done | 1
384239 | #384233 | Story | Feature 384233: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0
384238 | #384233 | Story | Feature 384233: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
384237 | #384233 | Story | Feature 384233: Create STCD and review with stakeholders | Unassigned | Invalid | 0
384236 | #384233 | Story | Feature 384233: Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0
384233 | #384135 | Feature | OBS - HBSS: Analyze, Design, and Implement changes to FM System (Netcool) for HBSS Solution | Unassigned | Rejected
384182 | #384168 | Story | Feature 384168: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
384181 | #384168 | Story | Feature 384168: Prep and Perform Feature Demo  Customer Demo Event | Unassigned | New | 1 | #384182
384180 | #384168 | Story | Feature 384168: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #384181
384179 | #384168 | Story | Feature 384168: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #384181
384178 | #384168 | Story | Feature 384168: Provide Development inputs to common documents | Unassigned | New | 0 | #384181
384177 | #384168 | Story | Feature 384168: Incorporation of IETM Updates and Integration Support | Unassigned | New | 1
384176 | #384168 | Story | Feature 384168: UX Research and Design Support | Unassigned | New | 3
384175 | #384168 | Story | Feature 384168: Develop IETMs and Perform Development Testing | Unassigned | New | 3 | #384181
384174 | #384168 | Story | Feature 384168: MFR 1  Dev Team Performs Cybersecurity Assessment | Unassigned | New | 1 | #384181
384173 | #384168 | Story | Feature 384168: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #384181
384172 | #384168 | Story | Feature 384168: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #384181
384171 | #384168 | Story | Feature 384168: Create STCD and review with stakeholders | Unassigned | New | 3 | #384181 #384179 #384180 #384173
384170 | #384168 | Story | Feature 384168: Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #384173 #384171
384169 | #384168 | Task | Feature 384168: Hold Feature Review with SMEs | Unassigned | New
384167 | #384153 | Story | Feature 384153: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
384166 | #384153 | Story | Feature 384153: Prep and Perform Feature Demo – Customer Demo Event | Unassigned | New | 1 | #384167
384165 | #384153 | Story | Feature 384153: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #384166
384164 | #384153 | Story | Feature 384153: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #384166
384163 | #384153 | Story | Feature 384153: Provide Development inputs to common documents | Unassigned | New | 0 | #384166
384162 | #384153 | Story | Feature 384153: Incorporation of IETM Updates and Integration Support | Unassigned | Invalid | 0
384161 | #384153 | Story | TPM Replacement Phase 2- UX Document Gathering/Material Review [Perform Initial User Research] | Unassigned | New | 2
384160 | #384153 | Story | Feature 384153: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #384166
384159 | #384153 | Story | Feature 384153: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | New | 1 | #384166
384158 | #384153 | Story | Feature 384153: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #384166
384157 | #384153 | Story | Feature 384153: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #384166
384156 | #384153 | Story | Feature 384153: Create STCD and review with stakeholders | Unassigned | New | 3 | #384164 #384158 #384165 #384166
384155 | #384153 | Story | Feature 384153: Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #384156 #384158
384154 | #384153 | Task | Feature 384153: Hold Feature Review with SMEs | Unassigned | New
384150 | #1007900 | Story | Feature 1007900: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
384149 | #1007900 | Story | Feature 1007900: Prep For Demo – Customer Demo Event | PI 16 | New | 5 | #384150 #1012619
384148 | #1007900 | Story | Feature 1007900: Review the HBSS SOVT Inputs and get customer stakeholder approval | EA 16.2 | New | 2 | #384149 #388475
384147 | #384136 | Story | Feature 384136: Execute STCD Feature Integration and testing including STCD updates identified (part 1 of 2) | EA 14.2 | Done | 5 | #384149 #389884
384146 | #1007900 | Story | Feature 1007900: Update NEDB | PI 16 | New | 1 | #384149
384145 | #1007900 | Story | Feature 1007900: Incorporation of IETM Updates and Integration Support for OBS - HBSS: | PI 16 | New | 2 | #389794
384144 | #384136 | Story | Feature 384136: OBS HBSS- Review IETMs for Style Guide Compliance (EA 14.1) | EA 14.1 | Done | 5 | #390080
384142 |  | Story | Feature 384136: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #384149
384141 | #384136 | Story | Feature 384136: Perform STCD testing in VLAB by performing IETM, SVD and design instructions as developed by STCD (part 1 of 3) | EA 14.3 | Done | 5 | #384149
384140 | #1007900 | Story | Feature 1007900: Provide Deployment Notes and Operator Impact Inputs | EA 15.3 | Done | 2 | #384149
384138 | #384136 | Story | Feature 384136: HBSS IETM Dry Run Support | EA 14.3 | Done | 2 | #384139 #384141
384136 | #384135 | Feature | OBS - HBSS: Integrate and test production HBSS solution into VLab | EA 14.5 | Done |  | #1007900
384132 | #384120 | Story | Feature 384120: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #384133
384119 |  | Task | OBS - VM: Develop, Integrate, and Test VM Environment Solution in VLab | Unassigned | Invalid
384104 |  | Feature | <Feature xxx> MFR1 Template | Unassigned | Rejected
384098 | #384084 | Story | Feature 384084: Initiate CM PDO Processing for all CI's | EA 16.4 | New | 1
384097 | #384084 | Story | Feature Demo – Customer Demo Event - Feature 384084 | EA 16.4 | New | 2 | #384098
384096 | #384084 | Story | Feature 384084: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 14 | Invalid | 0 | #384097
384095 | #384084 | Story | Feature 384084: Execute STCD Feature Integration and testing including STCD updates identified (part 1 of 2) | EA 14.3 | Done | 3 | #384097
384094 | #384084 | Story | Feature 384084: Update rules files, integrate & test | EA 14.3 | Done | 2 | #384097
384093 | #384084 | Story | Feature 384084: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | PI 14 | Invalid | 0
384092 | #384084 | Story | Feature 384084: Obs Nutanix FM Changes- Update Alarm Summaries/Event IDs to Provide Meaningful Text to Operators | EA 14.2 | Done | 1
384091 | #384084 | Story | Feature 384084: Develop IETMs and Perform Development Testing | PI 14 | Invalid | 0 | #384097
384090 | #384233 | Story | Feature 384233: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #384097
384089 | #384084 | Story | Feature 384084: FM Topology - Perform Iterative Implementation, Integration, development Testing including updating design | EA 14.1 | Done | 3 | #384097
384088 | #384084 | Story | Feature 384084: Provide Deployment Notes and Operator Impact Inputs | EA 14.5 | Done | 1 | #384097
384087 | #384084 | Story | Feature 384084: Create STCD and review with stakeholders | EA 14.2 | Done | 3
384086 | #384084 | Story | Feature 384084: initial Review/Rework FM | EA 14.5 | Done | 3
384085 | #384084 | Task | Feature 384084: Hold Feature Review with SMEs | PI 14 | Done
384084 | #383110 | Feature | OBS - HW: Design and Implement changes to FM System (Netcool) for Nutanix HW and Application VMs | PI 16 - In Progress | Implementing
384083 |  | Story | Feature 383168: Design System Needs for Site Upgrade for Nutanix Deployment | PI 14 | Invalid | 0
384074 | #383110 | Feature | OBS - HW: Create training package for Nutanix Solution | PI 15 | Rejected
384073 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
384071 | #384036 | Story | Feature 384036: Update 99-P59435M_NM_HW_SW_Mapping.doc for Nutanix Hardware | EA 14.2 | Done | 5
384069 | #384036 | Story | Feature 384036: MFR 3 – CSE Completes Final CAP | EA 14.2 | Done | 2 | #384042
384067 | #384036 | Story | Feature 384036: Prep and Perform Feature Demo – Customer Demo Event | EA 14.4 | Invalid | 0
384066 | #380808 | Story | Feature 380808: Load baseline and execute STCD in the VLab | EA 15.3 | Done | 5
384059 |  | Story | Feature 384036: Create set of recovery procedures for Nutanix (1) | Unassigned | Invalid | 0
384044 | #1008628 | Story | Feature 384036: Provide Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0
384036 | #383110 | Feature | OBS - HW: Integrate Nutanix HW/SW Design into VLab | EA 14.5 | Done |  | #380808
384007 | #383110 | Feature | OBS - HW: Regression Test Nutanix Solution with VM Applications, IA Refresh, and Release | PI 15 | Rejected
384006 |  | Feature | Create complete set of operation, recovery, maintenance procedures, and Task Analysis Updates for Nutanix solution | Unassigned | Rejected
383976 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Execute STCD Feature Integration and testing including STCD updates identified | EA 15.5 | New | 1 | #383960
383975 | #383958 | Story | Bulk Planning SAR Input Enhancement: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | PI 15 | Invalid | 0 | #383960 #383961
383974 | #383958 | Story | Feature 383958:Bulk Planning SAR Input Enhancement: Provide Development inputs to common documents | PI 15 | Invalid | 0 | #383960
383973 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | EA 15.3 | Done | 1 | #383960
383971 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement IETM Review for Style Guide Compliance | EA 15.1 | Done | 2 | #1019316
383970 | #383958 | Story | Feature 383958: Incorporation of IETM Updates and Integration Support for Bulk Planning SAR Input Enhancement | EA 15.3 | Done | 1
383969 | #383958 | Story | Bulk Planning SAR Input Enhancement: MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | PI 15 | Invalid | 0 | #383975
383968 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Create STCD and review with stakeholders | EA 15.2 | Done | 2 | #383966 #383976 #383973 #383960
383967 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Initiate CM PDO Processing for all CI's | EA 15.4 | New | 1
383966 | #383958 | Story | Feature 383958 Bulk SAR: PPA Implementation, Integration, development Testing including updating design - part 1 | EA 14.3 | Done | 1 | #383964 #383960
383965 | #383958 | Story | Bulk Planning SAR Input Enhancement: Document Initial capability specification and detailed design to start Implementation | PI 14 | Invalid | 0 | #383968 #383963 #383966
383964 | #383958 | Story | Bulk Planning SAR Input Enhancement: MFR 3 – CSE Performs initial Cybersecurity Assessment | PI 15 | Invalid | 0 | #383959
383963 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Provide Deployment Notes and Operator Impact Inputs | EA 15.1 | Done | 1 | #383960
383962 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: Develop IETMs and Perform Development Testing | EA 15.1 | Done | 3 | #383960 #383970
383961 | #383958 | Story | Feature 383958: Bulk Planning SAR Input Enhancement: MFR 1 – IA Posture Assessment | EA 15.1 | Done | 2 | #383960
383960 | #383958 | Story | Feature Demo – Customer Demo Event: Feature 383958: Bulk Planning SAR Input Enhancement | EA 15.4 | New | 1 | #383967
383959 | #383958 | Story | Bulk Planning SAR Input Enhancement: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | PI 15 | Invalid | 0 | #383969
383958 | #385201 | Feature | Bulk Planning SAR Input Enhancement | EA 15.4 | Implementing
383926 | #383908 | Story | Feature 383908: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #383910
383925 | #383908 | Story | Feature 383908: MFR 3  Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | New | 3 | #383911 #383910
383924 | #383908 | Story | Feature 383908: Provide Development inputs to common documents | Unassigned | New | 0 | #383910
383923 | #383908 | Story | Feature 383908: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #383910
383922 | #383908 | Task | Feature 383908: Hold Feature Review with SMEs | Unassigned | New
383921 | #383908 | Story | Feature 383908: UX Research and Design Support | Unassigned | New | 3
383920 | #383908 | Story | Feature 383908: Incorporation of IETM Updates and Integration Support for MFR3 Template | Unassigned | New | 1
383919 | #383908 | Story | Feature 383908: MFR 3  Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | New | 5 | #383925
383918 | #383908 | Story | Feature 383908: Create STCD and review with stakeholders | Unassigned | New | 3 | #383910 #383923 #383916 #383926
383917 | #383908 | Story | Feature 383908: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
383916 | #383908 | Story | Feature 383908: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #383910 #383914
383915 | #383908 | Story | Feature 383908: Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #383916 #383913 #383918
383914 | #383908 | Story | Feature 383908: MFR 3  CSE Performs initial Cybersecurity Assessment | Unassigned | New | 5 | #383909
383913 | #383908 | Story | Feature 383908: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #383910
383912 | #383908 | Story | Feature 383908: Develop IETMs and Perform Development Testing | Unassigned | New | 3 | #383910
383911 | #383908 | Story | Feature 383908: MFR 3  CSE Completes Final CAP (Change back to Cyber Security Engineering) | Unassigned | New | 5 | #383910
383910 | #383908 | Story | Feature 383908: Prep and Perform Feature Demo  Customer Demo Event | Unassigned | New | 1 | #383917
383909 | #383908 | Story | Feature 383908: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | New | 1 | #383919
383908 |  | Feature | <Feature xxx> MFR3 Template | Unassigned | Draft
383900 | #364632 | Story | Feature 364632: Initiate CM PDO Processing for all CI's | PI 17 | New | 1
383899 | #364632 | Story | Feature 364632: Prep and Perform Feature Demo – Customer Demo Event | PI 17 | New | 1 | #383900
383898 | #364632 | Story | Feature 364632: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | PI 17 | New | 2 | #383899
383897 | #364632 | Story | Feature 364632: Execute STCD Feature Integration and testing including STCD updates identified | PI 17 | New | 0 | #383899
383896 | #364632 | Story | Feature 364632: Provide Development inputs to common documents | PI 17 | New | 0 | #383899
383895 | #364632 | Story | Feature 364632: ILS Incorporation of IETM updates and integration support (Change back to IETM-Training) | PI 15 | Invalid | 0
383894 | #364632 | Story | Feature 364632: UX Research and Design Support (change back to UX team) | PI 15 | Invalid | 0
383893 | #364632 | Story | Feature 364632: Develop IETMs and Perform Development Testing | PI 15 | Invalid | 0 | #383899
383892 | #364632 | Story | Feature 364632: MFR 1 – Dev Team Performs Cybersecurity Assessment | PI 17 | New | 1 | #383899
383891 | #364632 | Story | Feature 364632: Perform Iterative Implementation, Integration, development Testing including updating design | PI 17 | New | 0 | #383899
383890 | #364632 | Story | Feature 364632: Provide Deployment Notes and Operator Impact Inputs | PI 17 | New | 1 | #383899
383889 | #364632 | Story | Feature 364632: Create STCD and review with stakeholders | PI 15 | Invalid | 0 | #383899 #383898 #383897 #383891
383888 | #364632 | Story | Feature 364632: Document Initial capability specification and detailed design to start Implementation | PI 17 | New | 0 | #383889 #383891
383887 | #364632 | Task | Feature 364632: Hold Feature Review with SMEs | PI 17 | New
383826 | #383812 | Story | Feature 383812: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
383825 | #383812 | Story | Feature 383812: Prep and Perform Feature Demo  Customer Demo Event | Unassigned | Invalid | 0 | #383826
383824 | #383812 | Story | Feature 383812: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #383825
383823 | #383812 | Story | Feature 383812: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #383825
383822 | #383812 | Story | Feature 383812: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #383825
383821 | #383812 | Story | Feature 383812: Incorporation of IETM Updates and Integration Support | Unassigned | Invalid | 0
383820 | #383812 | Story | Feature 383812: UX Research and Design Support | Unassigned | Invalid | 0
383819 | #383812 | Story | Feature 383812: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #383825
383818 | #383812 | Story | Feature 383812: MFR 1  Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #383825
383817 | #383812 | Story | Feature 383812: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #383825
383816 | #383812 | Story | Feature 383812: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #383825
383815 | #383812 | Story | Feature 383812: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #383824 #383817 #383823 #383825
383814 | #383812 | Story | Feature 383812: Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #383817 #383815
383813 | #383812 | Task | Feature 383812: Hold Feature Review with SMEs | Unassigned | Invalid
383648 | #383640 | Story | Feature 383640: Evaluation of HW FRB Support (EA 13.7) | Unassigned | Invalid | 0
383647 | #383640 | Story | Feature 383640: Evaluation of HW FRB Support (EA 13.6) | Unassigned | Invalid | 0
383645 |  | Story | Feature 366838: Continued Evaluation for HW FRB: Initial Assessment - WCDMA VME ASSEMBLY – ETISP, PN = 01-P51759E002, SN = 114 | Unassigned | Invalid | 0
383608 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #383595
383606 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
383605 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
383604 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #383595
383603 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #383595
383601 |  | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #383595
383599 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #383596
383598 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #383595
383597 |  | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #383601
383596 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #383595
383594 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #383599 #383592
383593 |  | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #383595
383592 |  | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #383585
383591 |  | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #383595
383590 |  | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0 | #383595
383589 |  | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #383595
383588 |  | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #383589
383587 |  | Story | <Feature yyy> Create red lines Hardware drawings submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #383584
383586 |  | Story | <Feature yyy> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #383584
383585 |  | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #383591
383584 |  | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #383595
383554 |  | Problem | VENDOR: "break" missing in case statement. | Unassigned | Assessing
383474 |  | Problem | SCS: During Prepass need to load default XML files to insure correct settings | Unassigned | Assessing
383383 |  | Story | Feature 383332: MAGIC PI 13 Technical Support - EA 13.7 | Unassigned | Invalid | 0
383278 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0 | #383295
383248 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
383246 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
383242 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
383208 | #1007900 | Problem | Feature 1007900: EAD-13 Deployment: HBSS changes to allow Asset Maintenance Move task | EA 15.3 | Closed
383202 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
383193 | #383180 | Story | Feature 383180: UX Research and Design Support | Unassigned | Invalid | 0
383192 | #383180 | Story | Feature 383180: Incorporation of IETM Updates and Integration Support for ETI Switchover Procedure Workaround for Critical FOUO TPM Functions per FRB 2019-13 | Unassigned | Invalid | 0
383170 | #262146 | Feature | OBS - HW: Create Training to support Initial Nutanix Deployment | PI 14 | Rejected
383168 | #383110 | Feature | OBS - HW: FRCB for Site Power Changes for Nutanix Deployment | EA 14.5 | Done
383167 |  | Task | OBS - HW: Analyze, Design, and Implement changes to FM System (Netcool) for Nutanix System | Unassigned | Invalid
383166 |  | Task | OBS - HW: Create initial set of operation, recovery, and maintenance procedures for Nutanix solution | Unassigned | New
383165 | #383110 | Feature | OBS - HW: Create Drawings and FRCB Package for Nutanix Deployment | PI 16 - In Progress | Implementing
383164 |  | Task | OBS - HW: Integrate Nutanix HW/SW design into VLab in production form | Unassigned | New
383159 | #383141 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #383143
383158 | #383141 | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #383144 #383143
383154 | #383141 | Story | <Feature xxx> UX Research and Design Support | Unassigned | Invalid | 0
383153 | #383141 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support | Unassigned | Invalid | 0
383152 | #383141 | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #383158
383151 | #383141 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #383143 #383159 #383149 #383156
383150 | #383141 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0 | #383143
383149 | #383141 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #383143 #383147
383148 | #383141 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #383151 #383146 #383149
383147 | #383141 | Story | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #383142
383146 | #383141 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #383143
383145 | #383141 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #383143
383144 | #383141 | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP | Unassigned | Invalid | 0 | #383143
383143 | #383141 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
383142 | #383141 | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #383152
383141 |  | Feature | <Feature xxx> Template | Unassigned | Rejected
383114 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
383075 | #381524 | Story | Feature 381524 PB: Fix Problem 381547 - Part 2 | EA 14.3 | Done | 2 | #1008110
383074 | #381524 | Story | Feature 381524: Fix Problem 381547 - Part 1 | EA 14.2 | Done | 3 | #383075
383012 | #382879 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | New | 2 | #382882
383008 | #382879 | Story | <Feature xxx>: UX Research and Design Support (change back to UX team) | Unassigned | New | 3
383005 | #382879 | Story | <Feature xxx>:ILS Incorporation of IETM Updates and Integration Support (Change back to Falcons) | Unassigned | New | 1
383003 | #382879 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | New | 0 | #382882
383002 |  | Task | SA Support: Analyze Problem 378289 (Jitter Causing Bad SA Reporting) | Unassigned | Invalid
383000 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382997 | #382879 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | New | 3 | #382751 #382866 #382882 #383012
382950 | #382932 | Story | Feature 382932: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #382934
382949 | #382932 | Story | Feature 382932: MFR 3  Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #382935 #382934
382948 | #382932 | Story | Feature 382932: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #382934
382947 | #382932 | Story | Feature 382932: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #382934
382946 | #382932 | Task | Feature 382932: Hold Feature Review with SMEs | Unassigned | Invalid
382945 | #382932 | Story | Feature 382932: UX Research and Design Support | Unassigned | Invalid | 0
382944 | #382932 | Story | Feature 382932: Incorporation of IETM Updates and Integration for Support Implement Replacement of Dashboard Pie-Charts | Unassigned | Invalid | 0
382943 | #382932 | Story | Feature 382932: MFR 3  Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #382949
382942 | #382932 | Story | Feature 382932: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #382940 #382950 #382947 #382934
382941 | #382932 | Story | Feature 382932: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0 | #382934
382940 | #382932 | Story | Feature 382932: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #382934 #382938
382939 | #382932 | Story | Feature 382932: Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #382937 #382940 #382942
382938 | #382932 | Story | Feature 382932:  Cyber Performs Cybersecurity Assessment | Unassigned | Invalid | 0 | #382933
382937 | #382932 | Story | Feature 382932: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #382934
382936 | #382932 | Story | Feature 382932: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #382934
382935 | #382932 | Story | Feature 382932: MFR 3  CSE Completes Final CAP | Unassigned | Invalid | 0 | #382934
382934 | #382932 | Story | Feature 382932: Prep and Perform Feature Demo  Customer Demo Event | Unassigned | Invalid | 0
382933 | #382932 | Story | Feature 382932: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #382943
382927 | #384943 | Story | Investigate Instrumentation Dashboard Status - SA | Unassigned | New | 5
382926 | #384943 | Story | Investigate Instrumentation Dashboard Status - UX | Unassigned | New | 5
382925 | #384943 | Story | Investigate Instrumentation Dashboard Status - SE | Unassigned | New | 5
382924 | #384943 | Story | Investigate Instrumentation Dashboard Status - SE | Unassigned | New | 5
382923 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382922 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382921 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382920 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382895 | #278830 | Feature | TD19-10: PI 13/14 Support of ADI/EMI/PRISM Integration | EA 14.5 | Done
382890 | #382879 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
382888 | #382879 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | New | 3 | #382882
382887 | #382879 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #382882
382886 | #382879 | Story | <Feature xxx>: Document Initial capability specification and detailed design to start Implementation | Unassigned | New | 0 | #382997 #382866 #382887
382883 | #382879 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | New | 1 | #382882
382882 | #382879 | Story | <Feature xxx>: Prep and Perform Feature Demo – Customer Demo Event | Unassigned | New | 1 | #382890
382879 |  | Feature | <Feature xxx> MFR1 Template | Unassigned | Draft
382871 | #382879 | Task | <Feature xxx>: Hold Feature Review with SMEs | Unassigned | New
382866 | #382879 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | New | 0 | #382882
382854 | #382839 | Story | Feature xxxxxx: Complete Customer Response Matrix (CRM) - Training EAD xx [Deliver Training] | Unassigned | Invalid | 0
382853 | #382839 | Story | Feature xxxxxx: Deliver Training at ARSTRAT - Training EAD xx [Deliver Training] | Unassigned | Invalid | 0
382852 | #382839 | Story | Feature xxxxxx: Deliver Training at NCTAMS - Training EAD xx [Deliver Training] | Unassigned | Invalid | 0
382851 | #382839 | Task | Feature xxxxxx: Finalize, Print, and Ship Materials - Training EAD xx [Create Training] | Unassigned | Invalid
382850 | #382839 | Task | Feature xxxxxx: Incorporate Comments from Internal Review - Training EAD xx [Create Training] | Unassigned | Invalid
382849 | #382839 | Story | Feature xxxxxx: SysEng SME Review EAD xx Training Materials | Unassigned | Invalid | 0
382848 | #382839 | Story | Feature xxxxxx: SA SME Review of Training EAD xx Training Materials | Unassigned | Invalid | 0
382847 | #382839 | Story | Feature xxxxxx: Create Training Materials - Training EAD xx [Create Training] | Unassigned | Invalid | 0
382846 | #382839 | Story | Feature xxxxxx: Create Draft Training Plan - Training EAD xx [Training Plan] | Unassigned | Invalid | 0
382845 | #382839 | Story | Feature xxxxxx: Hold Operator Impact meeting + Action Items - Training EAD xx [Op Impacts] | Unassigned | Invalid | 0
382844 | #382839 | Story | Feature xxxxxx: Finalize Op Impact Briefing Slides - Training EAD xx [Op Impacts] | Unassigned | Invalid | 0
382839 | #262146 | Feature | Deliver EAD XX Training | Unassigned | Rejected
382838 | #396663 | Story | Feature 396663: JDTA Redlines Associated with PI 14/EAD 16 [Task Analysis] | EA 14.5 | Done | 1
382837 | #396663 | Story | Feature 396663: Release Notes/Feature Demos Sprint 14.5 [Assess Training Needs] | EA 14.5 | Done | 1
382836 | #396663 | Story | Feature 396663: Release Notes/Feature Demos Sprint 14.4 [Assess Training Needs] | EA 14.4 | Done | 1
382835 | #396663 | Story | Feature 396663: Release Notes 14.3 [Assess Training Needs] | EA 14.3 | Done | 1
382834 | #396663 | Task | Feature 396663: Release Notes/Feature Demos Sprint 14.2 [Assess Training Needs] | EA 14.2 | Done
382833 | #396663 | Story | Feature 396663: Release Notes/Feature Demos Sprint 14.1 [Assess Training Needs] | EA 14.1 | Done | 1
382832 | #262146 | Feature | Assess Training Needs and Plan Training for Development During PI xx (Recurring) | Unassigned | Rejected
382751 | #382879 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | New | 0 | #382882
382750 |  | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #382735
382749 | #382732 | Story | <Feature xxx>: Provide Development inputs to <xyz> common document | Unassigned | Invalid | 0 | #382734
382748 | #382732 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #382734
382746 | #382732 | Story | <Feature xxx> UX Research and Design Support | Unassigned | Invalid | 0
382744 | #382732 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support | Unassigned | Invalid | 0
382743 |  | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #382750
382742 | #382732 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #382734 #382740 #382748
382741 | #382732 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0 | #382734
382740 | #382732 | Story | <Feature 382740>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #382734
382739 | #382732 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #382742 #382737 #382740
382738 | #382732 | Story | <Feature xxx>: MFR 1 – Dev Team Performs Cybersecurity Assessment | Unassigned | Invalid | 0
382737 | #382732 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #382734
382736 | #382732 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #382734
382735 |  | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP | Unassigned | Invalid | 0
382734 | #382732 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
382733 |  | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #382743
382732 |  | Feature | <Feature xxx> MFR1 Template | Unassigned | Rejected
382693 | #354680 | Story | Feature 354680 (Site): Define file structure (app versus deployment binaries) | EA 14.1 | Done | 1
382643 |  | Problem | There are many -127 value cells in the MAMA Request | Unassigned | Assessing
382567 | #382568 | Story | MUOS feature automation testing xxx | Unassigned | Invalid | 0
382463 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382460 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
382359 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures - Deployment Notes and Operator Impact Inputs (Part 2 of N) | PI 14 | Invalid | 0
382357 | #380660 | Story | Feature 380660: Update Whitelist vs Alarm Recovery Analysis and create increment report [Engineering Docs] | EA 14.5 | Invalid | 0
382355 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures - Customer Demo Event | PI 14 | Invalid | 0
382354 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: IETM Considerations checklist | PI 14 | Invalid | 0
382353 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 14 | Invalid | 0
382350 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures - IETM Development and Integration Updates | PI 14 | Invalid | 0
382348 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Interim Demo | PI 14 | Invalid | 0
382347 | #380660 | Story | Feature 380660: Updated Whitelist vs Alarm Recovery Analysis and Create Report [Engineering Docs] (Part 1) | PI 14 | Invalid | 0
382345 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures - Deployment Notes and Operator Impact Inputs (Part 1 of N) | PI 14 | Invalid | 0
382343 | #380660 | Story | Feature 380660: PI 14 Alarm Recovery Procedures - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 14 | Invalid | 0
382340 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Review for Style Guide Compliance and Dry Run- TOFF | PI 14 | Invalid | 0
382315 | #378406 | Task | Story 343885: CM Release of 98-P54107T – GEO – AMS-GS SVD **MPC EAD13.06_Sept_UFO_Table_Update**** | EA 14.1 | Done
382275 | #354174 | Story | Feature 354174 Splunk IETM: Fix Problem 313670 | EA 14.1 | Done | 5
382265 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Engineering IETM Development - Systems | PI 14 | Invalid | 0
382263 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Review for Style Guide Compliance and Dry Run- WF/RAN | PI 14 | Invalid | 0
382261 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Engineering IETM Development - AMS-GS_AWARE | PI 14 | Invalid | 0
382260 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Engineering IETM Development - TOFF | PI 14 | Invalid | 0
382256 | #380660 | Story | Feature 380660: PI 14 Whitelist Alarm Recovery Procedures: Engineering IETM Development - WF/RAN | PI 14 | Invalid | 0 | #382263
382253 |  | Problem | OAS setup.exe can't log into raid if the OA is already logged in | Unassigned | Assessing
382251 | #354871 | Problem | OAS system log and OAS log doesn't store enough data for delayed recovery | EA 15.5 | Approved
382250 | #354871 | Problem | The database prunes to only 2 days worth of synchronization data | EA 15.5 | Approved
382248 | #354871 | Problem | Synchronize sites restore is too early to grab latest OD | EA 15.5 | Approved
382149 | #382134 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382136
382148 | #382134 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382147 | #382134 | Story | Feature 382134: UX IETM Development and Integration Updates for Design Document Update | Unassigned | Invalid | 0
382146 | #382134 | Story | Feature 382134: IETM Development and Integration Updates for Design Document Update | Unassigned | Invalid | 0
382145 | #382134 | Story | Feature 382134: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #382136
382144 | #382134 | Story | Feature 382134: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #382136
382143 | #382134 | Story | Feature 382134: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
382142 | #382134 | Story | Feature 382134: IETM Update for Design Document Update | Unassigned | Invalid | 0 | #382136
382141 | #382134 | Story | Feature 382134: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #382136
382140 | #382134 | Story | Feature 382134: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #382137
382139 | #382134 | Story | Feature 382134: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #382136
382138 | #382134 | Story | Feature 382134: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #382142
382137 | #382134 | Story | Feature 382134: IA Posture Assessment | Unassigned | Invalid | 0 | #382136
382136 | #382134 | Story | Feature 382134: Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #382143
382135 | #382134 | Story | Feature 382134: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #382140
382134 | #381997 | Feature | Complete establishment of MUOS Core System Documentation baseline | PI 17 | Analyzing
382129 | #382114 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382116
382128 | #382114 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382127 | #382114 | Story | Feature 382114: UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
382126 | #382114 | Story | Feature 382114: IETM Development and Integration Updates | PI 15 | Invalid | 0
382125 | #382114 | Story | Feature 382114: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #382116
382124 | #382114 | Story | Feature 382114: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #382116
382123 | #382114 | Story | Feature 382114: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
382122 | #382114 | Story | Feature 382114: IETM Update for Transfer non-CM Design Documents to Repository | PI 15 | Invalid | 0 | #382116
382121 | #382114 | Story | Feature 382114: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #382116
382120 | #382114 | Story | Feature 382114: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #382117
382119 | #382114 | Story | Feature 382114: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #382116
382118 | #382114 | Story | Feature 382114: Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #382122
382117 | #382114 | Story | Feature 382114: IA Posture Assessment | PI 15 | Invalid | 0 | #382116
382116 | #382114 | Story | Feature 382114: Customer Demo Event - Feature 382114 | PI 15 | Invalid | 0 | #382123
382115 | #382114 | Story | Feature 382114: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #382120
382114 | #381999 | Feature | Transfer non-CM Design Documents to Repository | PI 15 | Rejected
382111 | #382096 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382098
382110 | #382096 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382109 | #382096 | Story | Feature 382096: UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
382108 | #382096 | Story | Feature 382096: IETM Development and Integration Updates | PI 15 | Invalid | 0
382107 | #382096 | Story | Feature 382096: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #382098
382106 | #382096 | Story | Feature 382096: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #382098
382105 | #382096 | Story | Feature 382096: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
382104 | #382096 | Story | Feature 382096: IETM Update for Convert/transfer FrameMaker CM Design Documents to Repository | PI 15 | Invalid | 0 | #382098
382103 | #382096 | Story | Feature 382096: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #382098
382102 | #382096 | Story | Feature 382096: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #382099
382101 | #382096 | Story | Feature 382096: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #382098
382100 | #382096 | Story | Feature 382096: Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #382104
382099 | #382096 | Story | Feature 382096: IA Posture Assessment | PI 15 | Invalid | 0 | #382098
382098 | #382096 | Story | Feature 382096: Customer Demo Event - <Feature xxx> | PI 15 | Invalid | 0 | #382105
382097 | #382096 | Story | Feature 382096: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #382102
382096 | #381997 | Feature | Convert/transfer FrameMaker CM Design Documents to Repository | PI 15 | Rejected
382092 | #382077 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382079
382091 | #382077 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382090 | #382077 | Story | Feature 382077: UX IETM Development and Integration Updates | PI 15 | Invalid | 0
382089 | #382077 | Story | Feature 382077: IETM Development and Integration Updates | PI 15 | Invalid | 0
382088 | #382077 | Story | Feature 382077: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #382079
382087 | #382077 | Story | Feature 382077: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #382079
382086 | #382077 | Story | Feature 382077: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
382085 | #382077 | Story | Feature 382077: IETM Update for Replicate CM Design Documents to Repository | PI 15 | Invalid | 0 | #382079
382084 | #382077 | Story | Feature 382077: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #382079
382083 | #382077 | Story | Feature 382077: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #382080
382082 | #382077 | Story | Feature 382077: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #382079
382081 | #382077 | Story | Feature 382077: Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #382085
382080 | #382077 | Story | Feature 382077: IA Posture Assessment | PI 15 | Invalid | 0 | #382079
382079 | #382077 | Story | Feature 382077: Customer Demo Event - <Feature xxx> | PI 15 | Invalid | 0 | #382086
382078 | #382077 | Story | Feature 382077: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #382083
382077 | #381997 | Feature | Replicate CM Design Documents to Repository | PI 15 | Rejected
382074 | #382059 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382061
382073 | #382059 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382072 | #382059 | Story | Feature 382059: UX IETM Development and Integration Updates | Unassigned | Invalid | 0
382071 | #382059 | Story | Feature 382059: IETM Development and Integration Updates | Unassigned | Invalid | 0
382070 | #382059 | Story | Feature 382059: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #382061
382069 | #382059 | Story | Feature 382059: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #382061
382068 | #382059 | Story | Feature 382059: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
382067 | #382059 | Story | Feature 382059: IETM Update for Train/Communicate Repository | Unassigned | Invalid | 0 | #382061
382066 | #382059 | Story | Feature 382059: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #382061
382065 | #382059 | Story | Feature 382059: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #382062
382064 | #382059 | Story | Feature 382059: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #382061
382063 | #382059 | Story | Feature 382059: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #382067
382062 | #382059 | Story | Feature 382059: IA Posture Assessment | Unassigned | Invalid | 0 | #382061
382061 | #382059 | Story | Feature 382059: Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #382068
382060 | #382059 | Story | Feature 382059: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #382065
382059 | #381997 | Feature | Implement first set of prioritized System Document baseline updates | Unassigned | Rejected
382056 | #382040 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #382042
382055 | #382040 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
382054 | #382040 | Story | Feature 382040: UX IETM Development and Integration Updates | PI 14 | Invalid | 0
382053 | #382040 | Story | Feature 382040: IETM Development and Integration Updates | PI 14 | Invalid | 0
382052 | #382040 | Story | Feature 382040: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 14 | Invalid | 0 | #382042
382051 | #382040 | Story | Feature 382040: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 14 | Invalid | 0 | #382042
382049 | #382040 | Story | Feature 382040: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
382048 | #382040 | Story | Feature 382040: IETM Update for Implement Design Document Repository | PI 14 | Invalid | 0 | #382042
382047 | #382040 | Story | Feature 382040: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 14 | Invalid | 0 | #382042
382046 | #382040 | Story | Feature 382040: IA Patching and STIGs Part 1 of N | PI 14 | Invalid | 0 | #382043
382045 | #382040 | Story | Feature 382040: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 14 | Invalid | 0 | #382042
382044 | #382040 | Story | Feature 382040: Engineering IETM Development and Integration updates part 1 of N | PI 14 | Invalid | 0 | #382048
382043 | #382040 | Story | Feature 382040: IA Posture Assessment | PI 14 | Invalid | 0 | #382042
382042 | #382040 | Story | Feature 382040: Customer Demo Event - Feature 382040 | PI 14 | Invalid | 0 | #382049
382041 | #382040 | Story | Feature 382040: IA - Define Patch/ Stig Requirements | PI 14 | Invalid | 0 | #382046
382040 | #381996 | Feature | Implement Design Document Repository | PI 14 | Rejected
382036 | #382021 | Story | Create the Site Functional Test Case | PI 14 | Invalid | 0 | #382023
382035 | #382021 | Task | Hold Feature Review with SMEs | PI 14 | Invalid
382034 | #382021 | Story | Feature 382021: UX IETM Development and Integration Updates | PI 14 | Invalid | 0
382033 | #382021 | Story | Feature 382021: IETM Development and Integration Updates for Definition & Documentation of Repository Management | PI 14 | Invalid | 0
382032 | #382021 | Story | Feature 382021: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 14 | Invalid | 0 | #382023
382031 | #382021 | Story | Feature 382021: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 14 | Invalid | 0 | #382023
382030 | #382021 | Story | Feature 382021: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
382029 | #382021 | Story | Feature 382021: IETM Update for Define/Document Repository Management | PI 14 | Invalid | 0 | #382023
382028 | #382021 | Story | Feature 382021: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 14 | Invalid | 0 | #382023
382027 | #382021 | Story | Feature 382021: IA Patching and STIGs Part 1 of N | PI 14 | Invalid | 0 | #382024
382026 | #382021 | Story | Feature 382021: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 14 | Invalid | 0 | #382023
382025 | #382021 | Story | Feature 382021: Engineering IETM Development and Integration updates part 1 of N | PI 14 | Invalid | 0 | #382029
382024 | #382021 | Story | Feature 382021: IA Posture Assessment | PI 14 | Invalid | 0 | #382023
382023 | #382021 | Story | Feature 382021: Customer Demo Event - Feature 382021 | PI 14 | Invalid | 0 | #382030
382022 | #382021 | Story | Feature 382021: IA - Define Patch/ Stig Requirements | PI 14 | Invalid | 0 | #382027
382021 | #381996 | Feature | Define/Document Repository Management | PI 14 | Rejected
382012 | #382000 | Feature | Update Core system Design Documents | PI 14 | Rejected
382008 | #381997 | Feature | Define FrameMaker Document Conversion Process | PI 14 | Rejected
382002 | #381996 | Feature | Define Repository Structure | PI 14 | Rejected
381984 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (TOFF) | EA 14.4 | Invalid | 0
381963 |  | Problem | IETM Update: OD Recovery Procedures Should Say to Restart Computer If OA Manager is Blank | Unassigned | Assessing
381955 |  | Problem | ADS: No OAS alarms for burn duration being off | Unassigned | Assessing
381931 |  | Story | MUOS Tools Test | Unassigned | Invalid | 0
381895 |  | Story | Feature 290711: Deliver WH AWARE training | Unassigned | Invalid | 0
381758 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381757 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381756 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381755 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381754 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381753 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381752 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381751 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381750 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381749 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381748 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381747 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381746 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381745 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381744 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381743 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381742 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381741 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381740 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381736 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381735 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381734 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381715 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381713 |  | Story | Theresa is testing the RTC service Tool | Unassigned | Invalid | 0
381688 |  | Problem | Alarm Recovery procedure for PLN_9999 needs updating after recent design change. | Unassigned | Assessing
381685 |  | Problem | IETM update for Managing TSM Clients - Normal Operation Procedure. | Unassigned | Assessing
381674 | #381659 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #381661
381673 | #381659 | Task | Hold Feature Review with SMEs | Unassigned | New
381672 | #381659 | Story | <Feature 381659> UX IETM Development and Integration updates part 1 of N | Unassigned | New | 3
381671 | #381659 | Story | <Feature 381659> ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
381670 | #381659 | Story | <Feature 381659> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #381661
381669 | #381659 | Story | <Feature 381659> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #381661
381668 | #381659 | Story | <Feature 381659>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
381667 | #381659 | Story | <Feature 381659>:ILS IETM update (Template) | Unassigned | New | 3 | #381661
381666 | #381659 | Story | <Feature 381659> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #381661
381665 | #381659 | Story | <Feature 381659>: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #381662
381664 | #381659 | Story | <Feature 381659>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #381661
381663 | #381659 | Story | <Feature 381659> Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #381667
381662 | #381659 | Story | <Feature 381659> IA Posture Assessment | Unassigned | New | 8 | #381661
381661 | #381659 | Story | Feature Demo – Customer Demo Event - <Feature 381659> | Unassigned | New | 1 | #381668
381660 | #381659 | Story | <Feature 381659>: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #381665
381642 | #381627 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #381629
381641 | #381627 | Task | Hold Feature Review with SMEs | Unassigned | New
381640 | #381627 | Story | <Feature 381627> UX IETM Development and Integration updates part 1 of N | Unassigned | New | 3
381639 | #381627 | Story | <Feature 381627> ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
381638 | #381627 | Story | <Feature 381627> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #381629
381637 | #381627 | Story | <Feature 381627> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #381629
381636 | #381627 | Story | <Feature 381627>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
381635 | #381627 | Story | <Feature 381627>:ILS IETM update (Template) | Unassigned | New | 3 | #381629
381634 | #381627 | Story | <Feature 381627> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #381629
381633 | #381627 | Story | <Feature 381627>: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #381630
381632 | #381627 | Story | <Feature 381627>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #381629
381631 | #381627 | Story | <Feature 381627> Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #381635
381630 | #381627 | Story | <Feature 381627> IA Posture Assessment | Unassigned | New | 8 | #381629
381629 | #381627 | Story | Feature Demo – Customer Demo Event - <Feature 381627> | Unassigned | New | 1 | #381636
381628 | #381627 | Story | <Feature 381627>: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #381633
381617 | #1004171 | Story | Feature 1004171: Initiate CM PDO Processing for all CI's | EA 16.1 | New | 1
381613 | #381608 | Story | <Feature 381608>: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 14 | Invalid | 0 | #381610
381610 | #381608 | Story | Feature 381608: Feature Demo – Customer Demo Event | PI 14 | Invalid | 0 | #381617
381608 | #381600 | Feature | Implement Module Group Provisioning Changes (Traces only) | EA 14.1 | Done
381547 | #381524 | Problem | Provisioning Bridge database contention can bring down terminal provisioning (INC000004253880) | EA 15.3 | Closed |  | #1008736
381539 | #381524 | Story | Create the Site Functional Test Case | EA 15.3 | Done | 2 | #381526
381538 | #381524 | Story | Hold Feature Review with SMEs | EA 15.3 | Invalid | 0
381537 | #381524 | Story | Feature 381524: Prov Bridge Contention Fault Recovery Style Guide Compliance and Dry Runs | EA 15.2 | Done | 2 | #381536
381536 | #381524 | Story | Feature 381524: IETM Fault Recovery Development and Integration for Reduction of Provisioning Bridge Database Contention | EA 15.3 | Invalid | 0
381535 | #381524 | Story | <Feature 381524> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #381526
381534 | #381524 | Story | Feature 381524: Prepare Demo, validate PCRs and PWIs. | EA 15.3 | Done | 2 | #381526
381533 | #381524 | Story | Feature 381524: Initiate CM PDO Processing ProvBridge CI | EA 15.4 | Implementing | 1
381531 | #381524 | Story | Feature 381524: Create and Review STCD (Part 1) | EA 15.2 | Done | 2 | #381526
381530 | #381524 | Story | Feature 381524: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #381527
381529 | #381524 | Story | Feature 381524: Deployment Notes and Operator Impact Inputs Part 1 of N | EA 15.2 | Done | 1 | #381526
381528 | #381524 | Story | Feature 381524: Engineering IETM Fault Recovery Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #381532 #381526
381527 | #381524 | Story | Feature 381524 IA Posture Assessment and Cyber support | PI 15 | Invalid | 0 | #381526
381526 | #381524 | Story | Feature Demo – Customer Demo Event - <Feature 381524> | EA 15.4 | Implementing | 1 | #381533
381525 | #381524 | Story | Feature 381524: IA Posture Assessment and Cyber support | EA 15.3 | Done | 2 | #381530
381524 | #395610 | Feature | Reduce Provisioning Bridge Database Contention | EA 15.4 | Ready for Feature Demo
381247 | #377408 | Problem | Feature 377408: PKI Expiration Spreadsheet in IETM is out of date | EA 14.2 | Closed
381232 |  | Task | Story 393213: CM Release of 98-P55755M - Firewall - Network - SVD (EAD 17) | PI 15 | Invalid
381149 | #341999 | Story | Feature 341999: Finalize, Print, and Ship Materials- Connected AWARE Training for SC | PI 16 | New | 1
381083 | #381079 | Story | Re-apply STCD Problem 381036 Story | Unassigned | Invalid | 0
381082 | #381079 | Story | Re-apply Problem 381036 Story | Unassigned | Invalid | 0 | #381083
381081 | #381079 | Story | Rebase STCD Problem 381036 Story | Unassigned | Invalid | 0
381080 | #381079 | Story | Rebase Problem 381036 Story | Unassigned | Invalid | 0 | #381081
381079 | #363873 | Feature | MPC for Problem 381036 found in EAD 13 Deliveries | Unassigned | Rejected
381068 | #381053 | Story | Create the Site Functional Test Case | PI 17 | New | 2 | #381055
381067 | #381053 | Task | Hold Feature Review with SMEs | PI 17 | New
381066 | #381053 | Story | <Feature 381053> UX IETM Development and Integration updates part 1 of N | PI 17 | New | 3
381065 | #381053 | Story | Feature 381053: IETM Development and Integration Updates for Updating SPLUNK to Version TBD | PI 17 | New | 1
381064 | #381053 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 17 | Invalid | 0 | #381055
381063 | #381053 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 17 | Invalid | 0 | #381055
381062 | #381053 | Story | <Feature 381053>: Initiate CM PDO Processing for all CI's | PI 17 | New | 1
381061 | #381053 | Story | <Feature xxx>:ILS IETM update (Template) | PI 17 | Invalid | 0 | #381055
381060 | #381053 | Story | <Feature 381053> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 17 | New | 2 | #381055
381059 | #381053 | Story | <Feature 381053>: IA Patching and STIGs Part 1 of N | PI 17 | New | 5 | #381056
381058 | #381053 | Story | <Feature 381053>: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 17 | New | 2 | #381055
381057 | #381053 | Story | <Feature 381053> Engineering IETM Development and Integration updates part 1 of N | PI 17 | New | 3 | #381061
381056 | #381053 | Story | <Feature 381053> IA Posture Assessment | PI 17 | New | 8 | #381055
381055 | #381053 | Story | Feature Demo – Customer Demo Event - <Feature 381053> | PI 17 | New | 1 | #381062
381054 | #381053 | Story | <Feature 381053>: IA - Define Patch/ Stig Requirements | PI 17 | New | 2 | #381059
381053 | #381043 | Feature | Update Splunk to Version TBD | PI 17 | Draft
380936 | #380932 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
380935 | #380932 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #380936
380934 | #380932 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
380932 | #353840 | Feature | MPC for Problem 325778 found in Pre EAD 10 Deliveries | Unassigned | Rejected
380931 | #380916 | Story | Feature 380916: Create the Site Functional Test Case | Unassigned | Invalid | 0 | #380918
380927 | #380916 | Story | Feature 380916: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #380918
380922 | #380916 | Story | Feature 380916: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #380919
380920 | #380916 | Story | Feature 380916: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #380924
380919 | #380916 | Story | Feature 380916: IA Posture Assessment | Unassigned | Invalid | 0 | #380918
380867 | #343917 | Task | Story 343917: CM Release of 98-P59805M – NMS – NM – Planning – SC-GEO – SVD (EAD 15) | EA 14.1 | Done
380834 | #354174 | Story | Feature 354174: IETM Update for SPLUNK IETMs (Part 2) | PI 14 | Invalid | 0
380832 | #354174 | Story | Feature 354174 Splunk IETM: Part 2 - Engineering IETM Development and Integration Updates for Update IETMs, Task Analysis, etc | PI 14 | Invalid | 0
380823 | #380808 | Story | Create the Site Functional Test Case | PI 15 | Invalid | 0 | #380810
380822 | #380808 | Task | Hold Feature Review with SMEs | PI 15 | Invalid
380821 | #380808 | Story | Feature 380808: IETM Development and Integration Updates for Nutanix Deployment (Part 1 of 8) | EA 15.1 | Done | 3
380820 | #380808 | Story | Feature 380808: Engineering IETM Development and Integration for Nutanix(2) | PI 16 | New | 13 | #380821
380819 |  | Story | Feature 380808: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #380810
380818 | #380808 | Story | Feature 380808: IETM Test and Integration (2) | PI 16 | New | 13 | #380810
380817 | #380808 | Story | Feature 380808: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
380816 | #380808 | Story | Feature 380808: Update the JDTA task analysis | PI 15 | Invalid | 0 | #380810
380815 | #380808 | Story | Feature 380808: IETM Test and Integration (1) | PI 15 | Invalid | 0 | #380810
380814 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #380811
380813 | #380808 | Story | Feature 380808: Deployment Notes and Operator Impact Inputs- Early Look | EA 15.3 | Done | 5 | #380810
380812 | #380808 | Story | Feature 380808: Engineering IETM Development and Integration (1) | PI 15 | Invalid | 0 | #380816
380811 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #380810
380810 | #380808 | Story | Feature 380808: Hold Feature Demo | PI 16 | New | 1 | #380817
380809 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #380814
380808 | #383110 | Feature | OBS - Complete Nutanix Release, IA refresh, and IETMs for Nutanix DX360 Solution | PI 16 - In Progress | Implementing
380776 |  | Problem | Profile gets stuck in SYNC IN PROGRESS state (REGN - OTAFT) | Unassigned | Assessing
380738 |  | Story | Support customer during EAD 14.0 MFR generation/approval period | Unassigned | Invalid | 0
380705 |  | Story | Feature 380379: Create the Site Functional Test Case | Unassigned | Invalid | 0
380703 |  | Story | Feature 380379: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
380702 |  | Story | Feature 380379: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
380701 |  | Story | Feature 380379: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
380700 |  | Story | Feature 380379: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0
380695 |  | Story | Feature 380379: ILS IETM update (Template) | Unassigned | Invalid | 0
380693 |  | Story | Feature 380379: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0
380692 |  | Story | Feature 380379: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0
380690 |  | Story | Feature 380379: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
380682 |  | Story | Feature 380379: IA Posture Assessment | Unassigned | Invalid | 0
380677 |  | Story | Feature 380379: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0
380660 | #216351 | Feature | FM Whitelist updates for PI 14: Alarm Recovery Procedures | Unassigned | Rejected
380613 | #380598 | Story | Feature 380598: Create the Site Functional Test Case | Unassigned | New | 2 | #380600
380612 | #380598 | Task | Feature 380598: Hold Feature Review with SMEs | Unassigned | New
380611 | #380598 | Story | Feature 380598: UX IETM Development and Integration updates part 1 of N | Unassigned | New | 3
380610 | #380598 | Story | Feature 380598: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
380609 | #380598 | Story | Feature 380598: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #380600
380608 | #380598 | Story | Feature 380598: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #380600
380607 | #380598 | Story | Feature 380598: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
380606 | #380598 | Story | Feature 380598: ILS IETM update (Template) | Unassigned | New | 3 | #380600
380605 | #380598 | Story | Feature 380598: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #380600
380604 | #380598 | Story | Feature 380598: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #380601
380601 | #380598 | Story | Feature 380598: IA Posture Assessment | Unassigned | New | 8 | #380600
380583 | #380557 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #380570
380582 | #380557 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
380581 | #380557 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
380580 | #380557 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
380579 | #380557 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #380570
380578 | #380557 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #380570
380577 | #380557 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
380576 | #380557 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #380570
380575 | #380557 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #380570
380574 | #380557 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #380571
380573 | #380557 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #380570
380572 | #380557 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #380576
380571 | #380557 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #380570
380570 | #380557 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #380577
380569 | #380557 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #380574 #380567
380568 | #380557 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #380570
380567 | #380557 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #380560
380566 | #380557 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #380570
380565 | #380557 | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0 | #380570
380564 | #380557 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #380570
380563 | #380557 | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #380564
380562 | #380557 | Story | <Feature yyy> Create red lines Hardware drawings submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #380559
380561 | #380557 | Story | <Feature yyy> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #380559
380560 | #380557 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #380566
380559 | #380557 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #380570
380558 | #380557 | Story | <Feature yyy>: Logistics Considerations (non-IETM) (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #380570
380557 |  | Feature | <FRCB Feature xxx> | Unassigned | Rejected
380160 | #241246 | Story | <Feature xxx>: Execute STCD Feature Integration and testing including STCD updates identified | Unassigned | Invalid | 0 | #241249
380135 | #241246 | Story | <Feature xxx>: MFR 3 – Dev Team Resolves Final ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #241249 #241250
380103 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
379976 |  | Problem | RNC sends a rrcConnectionRelease when the radio send an RLC Reset message | Unassigned | Assessing
379965 | #371037 | Story | Feature 371037: Provide Development inputs to I-Level common document | Unassigned | Invalid | 0
379845 | #1015827 | Story | Feature 1015827: eRxIM changes for M503- IETM Updates Missing Alarm Recovery Procedures | PI 16 | New | 2 | #392064
379843 | #381702 | Feature | Explore integrating Splunk with SIEM | PI 15 | Rejected |  | #379825
379840 | #379825 | Story | Create the Site Functional Test Case | PI 15 | Invalid | 0 | #379827
379839 | #379825 | Task | Hold Feature Review with SMEs | PI 15 | Invalid
379838 | #379825 | Story | <Feature 379825> UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
379837 | #379825 | Story | Feature 379825: IETM Development and Integration Updates for Integration of SPLUNK with SIEM | PI 15 | Invalid | 0
379836 | #379825 | Story | <Feature 379825> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #379827
379835 | #379825 | Story | <Feature 379825> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #379827
379834 | #379825 | Story | <Feature 379825>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
379833 | #379825 | Story | Feature 379825:IETM update for Integration of SPLUNK with SIEM | PI 15 | Invalid | 0 | #379827
379832 | #379825 | Story | <Feature 379825> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #379827
379831 | #379825 | Story | <Feature 379825>: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #379828
379830 | #379825 | Story | <Feature 379825>: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #379827
379829 | #379825 | Story | <Feature 379825> Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #379833 #379837
379828 | #379825 | Story | <Feature 379825> IA Posture Assessment | PI 15 | Invalid | 0 | #379827
379827 | #379825 | Story | Feature Demo – Customer Demo Event - <Feature 379825> | PI 15 | Invalid | 0 | #379834
379826 | #379825 | Story | <Feature 379825>: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #379831
379825 | #381702 | Feature | Integrate SPLUNK with SIEM | PI 15 | Rejected
379776 | #379761 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #379763
379775 | #379761 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
379774 | #379761 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379773 | #379761 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379772 | #379761 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #379763
379771 | #379761 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #379763
379770 | #379761 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
379769 | #379761 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #379763
379768 | #379761 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #379763
379767 | #379761 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #379764
379766 | #379761 | Story | FM Whitelist updates for PI14 (1st release): Out-of-cycle/MPC Inputs | EA 14.4 | Done | 1 | #379763
379765 | #379761 | Story | FM Whitelist updates for PI14 (1st release): Engineering Whitelist updates (Implement, Test, Review) | EA 14.4 | Done | 5 | #379769
379764 | #379761 | Story | FM Whitelist updates for PI 14 (1st release): Identify Whitelist content (Systems) | EA 14.1 | Done | 2 | #379763
379763 | #379761 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #379770
379762 | #379761 | Story | FM Whitelist updates for PI14 (1st release): Review EAD 16 features and identify any alarms that need to be added to the whitelist | EA 14.2 | Done | 1 | #379767
379761 | #216351 | Feature | FM Whitelist updates for PI 14: Update whitelist and filter logic | EA 14.4 | Done
379512 | #379508 | Story | Re-apply STCD Problem 377009 Story | Unassigned | Invalid | 0
379511 | #379508 | Story | Re-apply Problem 377009 Story | Unassigned | Invalid | 0 | #379512
379510 | #379508 | Story | Rebase STCD Problem 377009 Story | Unassigned | Invalid | 0
379509 | #379508 | Story | Rebase Problem 377009 Story | Unassigned | Invalid | 0 | #379510
379508 | #356599 | Feature | MPC for Problem 377009 found in EAD 10 Deliveries | Unassigned | Rejected
379506 | #379491 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #379493
379505 | #379491 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
379504 | #379491 | Story | <Feature 379491> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379503 | #379491 | Story | <Feature 379491> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379502 | #379491 | Story | <Feature 379491> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #379493
379501 | #379491 | Story | <Feature 379491> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #379493
379500 | #379491 | Story | <Feature 379491>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
379499 | #379491 | Story | <Feature 379491>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #379493
379498 | #379491 | Story | <Feature 379491> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #379493
379497 | #379491 | Story | <Feature 379491>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #379494
379496 | #379491 | Story | <Feature 379491>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #379493
379495 | #379491 | Story | <Feature 379491> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #379499
379494 | #379491 | Story | <Feature 379491> IA Posture Assessment | Unassigned | Invalid | 0 | #379493
379493 | #379491 | Story | Feature Demo – Customer Demo Event - <Feature 379491> | Unassigned | Invalid | 0 | #379500
379492 | #379491 | Story | <Feature 379491>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #379497
379491 |  | Feature | <Feature 379491> | Unassigned | Rejected
379407 | #379392 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #379394
379406 | #379392 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
379405 | #379392 | Story | <Feature 379392> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379404 | #379392 | Story | <Feature 379392> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379403 | #379392 | Story | <Feature 379392> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #379394
379402 | #379392 | Story | <Feature 379392> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #379394
379401 | #379392 | Story | <Feature 379392>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
379400 | #379392 | Story | <Feature 379392>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #379394
379399 | #379392 | Story | <Feature 379392> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #379394
379398 | #379392 | Story | <Feature 379392>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #379395
379397 | #379392 | Story | <Feature 379392>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #379394
379396 | #379392 | Story | <Feature 379392> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #379400 #379404
379395 | #379392 | Story | <Feature 379392> IA Posture Assessment | Unassigned | Invalid | 0 | #379394
379394 | #379392 | Story | Feature 379392 – Customer Demo Event | Unassigned | Invalid | 0 | #379401
379393 | #379392 | Story | <Feature 379392>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #379398
379392 |  | Feature | <Feature xxx> | Unassigned | Rejected
379391 | #379387 | Story | Re-apply STCD Problem 377009 Story | Unassigned | Invalid | 0
379390 | #379387 | Story | Re-apply Problem 377009 Story | Unassigned | Invalid | 0 | #379391
379389 | #379387 | Story | Rebase STCD Problem 377009 Story | Unassigned | Invalid | 0
379388 | #379387 | Story | Rebase Problem 377009 Story | Unassigned | Invalid | 0 | #379389
379387 | #356599 | Feature | MPC for Problem 377009 found in EAD 10 Deliveries | Unassigned | Rejected
379380 | #379365 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #379367
379379 | #379365 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
379378 | #379365 | Story | <Feature 379365> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379377 | #379365 | Story | <Feature 379365> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
379376 | #379365 | Story | <Feature 379365> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #379367
379375 | #379365 | Story | <Feature 379365> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #379367
379374 | #379365 | Story | <Feature 379365>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
379373 | #379365 | Story | <Feature 379365>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #379367
379372 | #379365 | Story | <Feature 379365> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #379367
379371 | #379365 | Story | <Feature 379365>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #379368
379370 | #379365 | Story | <Feature 379365>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #379367
379369 | #379365 | Story | <Feature 379365> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #379373
379368 | #379365 | Story | <Feature 379365> IA Posture Assessment | Unassigned | Invalid | 0 | #379367
379367 | #379365 | Story | Feature Demo – Customer Demo Event - <Feature 379365> | Unassigned | Invalid | 0 | #379374
379366 | #379365 | Story | <Feature 379365>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #379371
379365 |  | Feature | <Feature 379365> | Unassigned | Rejected
379353 | #379349 | Story | Re-apply STCD Problem 377009 Story | Unassigned | Invalid | 0
379352 | #379349 | Story | Re-apply Problem 377009 Story | Unassigned | Invalid | 0 | #379353
379351 | #379349 | Story | Rebase STCD Problem 377009 Story | Unassigned | Invalid | 0
379350 | #379349 | Story | Rebase Problem 377009 Story | Unassigned | Invalid | 0 | #379351
379349 | #356599 | Feature | MPC for Problem 377009 found in EAD 10 Deliveries | Unassigned | Rejected
379231 |  | Problem | NTP Server SVD Error and Updates | Unassigned | Assessing
379221 | #262134 | Feature | Labs – TXO Ericsson – Test Ericsson parts from second part of 2030 completion order - Part A | EA 14.5 | Done
379157 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
379122 |  | Problem | IETM RNC SPM General Problem Alarm Recovery Procedure should replace SPB board if restarts don't work | Unassigned | Assessing
379082 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
379080 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
379052 | #379001 | Task | Re-apply Problem xxx Task for Deployment | Unassigned | New
379014 | #379001 | Story | Re-write and Test Problem xxx Story | Unassigned | New | 2
379007 |  | Story | Rebase and Test Problem xxx Story | Unassigned | Invalid | 0
378870 | #378866 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
378869 | #378866 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #378870
378868 | #378866 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
378866 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
378829 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
378726 |  | Story | Test Summary of workItem Automation Tool | Unassigned | Invalid | 0
378591 |  | Feature | Investigate Replacement of Dashboard Pie-Charts | Unassigned | Rejected
378590 |  | Story | AWARE & MHAL Going Connected: MIBs rules conversion - Part 2 | Unassigned | Invalid | 0
378588 | #217588 | Feature | Investigate moving DSN from T1 based status to channel based status | PI 14 | Rejected
378494 |  | Story | Feature 364218: Prepare Card Sorting Activity (Part 2) | Unassigned | Invalid | 0
378455 | #354537 | Story | Update Splunk servers to RHEL 7.x: Dev Test hardened OS image on VM (Splunk v6.5.3) | Unassigned | Invalid | 0
378406 | #343885 | Task | Story 343885: CM Release of 98-P54107T – GEO – AMS-GS SVD **MPC EAD12.19_August_UFO_Table_Update**** | EA 14.1 | Done
378289 |  | Problem | Jitter Causing Bad SA Reporting | Unassigned | Assessing
378267 | #378252 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #378254
378266 | #378252 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
378265 | #378252 | Story | <Feature 378252> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
378264 | #378252 | Story | <Feature 378252> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
378263 | #378252 | Story | <Feature 378252> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #378254
378262 | #378252 | Story | <Feature 378252> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #378254
378261 | #378252 | Story | <Feature 378252>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
378260 | #378252 | Story | <Feature 378252>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #378254
378259 | #378252 | Story | <Feature 378252> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #378254
378258 | #378252 | Story | <Feature 378252>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #378255
378257 | #378252 | Story | <Feature 378252>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #378254
378256 | #378252 | Story | <Feature 378252> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #378260
378255 | #378252 | Story | <Feature 378252> IA Posture Assessment | Unassigned | Invalid | 0 | #378254
378254 | #378252 | Story | Feature Demo – Customer Demo Event - <Feature 378252> | Unassigned | Invalid | 0 | #378261
378253 | #378252 | Story | <Feature 378252>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #378258
378252 | #225732 | Feature | Implement Providing a Reliable RTWP Measurement/Alarm Updates | Unassigned | Rejected
378251 | #378236 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #378238
378250 | #378236 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
378249 | #378236 | Story | <Feature 378236> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
378248 | #378236 | Story | <Feature 378236> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
378247 | #378236 | Story | <Feature 378236> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #378238
378246 | #378236 | Story | <Feature 378236> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #378238
378245 | #378236 | Story | <Feature 378236>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
378244 | #378236 | Story | <Feature 378236>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #378238
378243 | #378236 | Story | <Feature 378236> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #378238
378242 | #378236 | Story | <Feature 378236>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #378239
378241 | #378236 | Story | <Feature 378236>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #378238
378240 | #378236 | Story | <Feature 378236> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #378244
378239 | #378236 | Story | <Feature 378236> IA Posture Assessment | Unassigned | Invalid | 0 | #378238
378238 | #378236 | Story | Feature Demo – Customer Demo Event - <Feature 378236> | Unassigned | Invalid | 0 | #378245
378237 | #378236 | Story | <Feature 378236>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #378242
378236 | #378659 | Feature | Implement Missed ETI_5000 (bad CPICH) set/clear traps in Splunk Updates | Unassigned | Rejected
378130 | #332951 | Problem | IETM RNC Health Check procedure needs updates for missing checks | EA 15.4 | Approved
378015 | #378000 | Story | Feature 378000: Create the Site Functional Test Case | Unassigned | Invalid | 0 | #378002
378012 | #378000 | Story | Feature 378000: IETM Development and Integration updates | Unassigned | Invalid | 0
378009 | #378000 | Story | Feature 378000: Initiate CM PDO Processing for all CI's | EA 14.1 | Done | 1
378002 | #378000 | Story | Feature Demo – Customer Demo Event - Feature 378000 | EA 14.1 | Done | 1 | #378009
378000 | #347074 | Feature | TD 19-10: Finalize AWARE for SC and Update from WH Lessons Learned | EA 14.1 | Done
377718 | #243502 | Story | CM Release Work for EAD 15 Documents | EA 15.4 | Done | 1
377677 |  | Feature | Test Amy McKee (Remove when complete) | Unassigned | Rejected
377535 |  | Story | PCR Verification: Common Docs (PKI, HW/SW Mapping) and 3 SVDs (FM, Splunk App, Splunk Infra) | Unassigned | Invalid | 0
377452 | #377437 | Story | Feature 377437: Create the Site Functional Test Case | EA 15.1 | Done | 2 | #377439
377451 | #377437 | Task | Hold Feature Review with SMEs | EA 14.1 | Done
377450 | #377437 | Story | Feature 377437: ETT Laptop IETM Style Guide Review and Dry Runs | EA 14.4 | Invalid | 0
377449 | #377437 | Story | Feature 377437: IETM Development and Integration Updates for Gen 2 ETT Laptops | EA 15.2 | Done | 1
377448 | #377437 | Story | <Feature 377437> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #377439
377447 | #377437 | Story | <Feature 377437> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #377439
377446 | #377437 | Story | <Feature 377437>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
377445 | #377437 | Story | <Feature 377437>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #377439
377444 | #377437 | Story | <Feature 377437> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #377439
377443 | #377437 | Story | <Feature 377437>: IA Patching and STIGs Gen 2 ETT Laptop | Unassigned | Invalid | 0 | #377440
377442 | #377437 | Story | <Feature 377437>: Deployment Notes and Operator Impact Inputs | EA 15.2 | Done | 2 | #377439
377441 | #377437 | Story | <Feature 377437> Close out the ETT SVD Review | EA 15.3 | Done | 1 | #1020009
377440 | #377437 | Story | <Feature 377437> IA Posture Assessment | Unassigned | Invalid | 0 | #377439
377439 | #377437 | Story | Feature Demo – Customer Demo Event - <Feature 377437> | Unassigned | Invalid | 0 | #377446
377438 | #377437 | Story | <Feature 377437>: IA posture assessment for RF Alignment Tool on ETT Laptop | EA 15.1 | Done | 3 | #377443 #1004666
377437 | #251622 | Feature | Gen 2 ETT Laptop Obsolescence for Windows 10 and IA compliance | EA 15.4 | Implementing
377418 | #377408 | Task | Feature 377408: Upload Demo Documentation and Demo Status Workbook for Analysis Demo of the Coordinate and Complete Non-Feature IETM Content for EAD 16 (Analysis Demo) | EA 14.4 | Done
377415 | #377408 | Story | Feature Demo – Customer Demo Event - Feature 377408 | EA 14.4 | Done | 1
377413 | #377408 | Story | Feature 377408: IETM Admin Updates part 1 of 3 (EA 14.1) | EA 14.1 | Done | 3
377412 | #377408 | Story | Feature 377408: IETM Admin Updates part 2 of 3 (EA 14.2) | EA 14.2 | Done | 3
377411 | #377408 | Story | Feature 377408: IETM Admin Updates part 3 of 3 (EA 14.3) | EA 14.3 | Done | 3
377410 | #377408 | Story | Feature 377408: IETM Admin Updates part 4 of 4 (EA 16.4) | EA 14.4 | Invalid | 0
377409 | #377408 | Story | Feature 377408: IETM Admin Updates part 5 of 5 (EA 16.5) | EA 14.5 | Invalid | 0
377408 | #262146 | Feature | Coordinate and Complete Non-Feature IETM Content for EAD 16 (Recurring) | EA 14.4 | Done
377405 | #245573 | Feature | TOFF RT Logic PWI placeholder | PI 17 | Draft
377393 | #343917 | Task | Story 343917: CM Release of PL01-P55663M– ILS – ERS-AWARE Cabinet Assem (EAD 15) | EA 14.1 | Done
377205 |  | Problem | Services do not function correctly due to incorrect time after server reboot | Unassigned | Assessing
377138 |  | Problem | IETM: Backup HAIPE - Normal Operation Procedure into IETM | Unassigned | Assessing
377105 | #245573 | Feature | Support WF Maintenance and MIL-STD development | Unassigned | Rejected
377059 |  | Story | SA Ramp-Up - FM | Unassigned | Invalid | 0
377054 | #354537 | Story | Update Splunk servers to RHEL 7.x: Install hardened OS image on existing HW (Splunk v6.5.3) | Unassigned | Invalid | 0
377053 | #354537 | Story | Update Splunk servers to RHEL 7.x: Install hardened OS image on existing HW (Splunk v6.5.3) | Unassigned | Invalid | 0
377006 | #377002 | Story | Re-apply STCD Problem 377009 Story | Unassigned | Invalid | 0
377005 | #377002 | Story | Re-apply Problem 377009 Story | Unassigned | Invalid | 0 | #377006
377004 | #377002 | Story | Rebase STCD Problem 377009 Story | Unassigned | Invalid | 0
377003 | #377002 | Story | Rebase Problem 377009 Story | Unassigned | Invalid | 0 | #377004
377002 | #363872 | Feature | MPC for Problem 377009 found in EAD 11 Deliveries | Unassigned | Rejected
376741 |  | Story | Story for ACC ROM/Proposal | Unassigned | Invalid | 0
376669 | #343915 | Task | Story 343915: CM Release of UES for WF & RAN Patch (EAD 14 OOC) | Unassigned | Invalid
376653 | #342163 | Task | Feature 342163: Submit PDO for 99-P59435M – NMS – NM – Common – HW-SW Map | EA 15.4 | New
376651 | #342163 | Task | Feature 342163: Submit PDO for 98-P55506M - Network - HAIPEMgmt - SVD | EA 15.4 | New
376617 | #342163 | Task | Feature 342163: Submit PDO for 98-P55504M – Network – HAIPE – SVD | EA 15.4 | Invalid
376599 | #369527 | Story | SE cross training - misc 12.3 | Unassigned | Invalid | 0
376598 |  | Story | SE cross training - misc 12.2 | Unassigned | Invalid | 0
376533 |  | Task | Support of VM for Call Banks | Unassigned | New
376511 |  | Problem | SCS: OAS COLA Query Conversion Errors | Unassigned | Assessing
376487 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (UX) - 14.2 | EA 14.2 | Invalid | 0
376486 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (UX) - 14.3 | EA 14.3 | Invalid | 0
376480 | #342163 | Story | Feature 342163: Support UX IETM Updates | EA 15.1 | Done | 2
376472 | #318430 | Story | Feature 318430 ETT Laptop - Feature Demo – Customer Demo Event | EA 14.1 | Done | 3
376457 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SA) - 14.2 | EA 14.2 | Done | 1
376456 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SA) - 14.3 | EA 14.3 | Invalid | 0
376446 | #243410 | Feature | Update Call Bank Servers to Use Connected AWARE Architecture to support ATO | EA 15.4 | Implementing
376410 | #360123 | Story | Investigate Trap Loss Issues - SE | PI 14 | Invalid | 0
376408 | #360123 | Story | Feature 360123: Investigate Trap Loss Issues - ETI | PI 14 | Invalid | 0
376407 | #360123 | Story | Investigate Trap Loss Issues - SA | PI 14 | Invalid | 0
376406 | #371198 | Story | ULX Support - Phase 1/2: MAGIC Support - EA 12.3 | Unassigned | Invalid | 0
376404 | #371198 | Story | ULX Support - Phase 1/2: MAGIC Support - EA 12.2 | Unassigned | Invalid | 0
376398 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
376397 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
376396 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
376395 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
376394 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
376376 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376375 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376334 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | EA 14.4 | Done | 1
376333 | #382895 | Story | Feature 382895: ADI/EMI/PRISM Support - Test Planning Prep for WH Activity | EA 14.3 | Done | 1
376331 |  | Story | Feature 382895: Integrate & Test Final PRISM Build | Unassigned | Invalid | 0
376330 |  | Story | Feature 382895: Integrate & Test Checkpoint PRISM Build | Unassigned | Invalid | 0
376326 | #382895 | Story | Feature 382895: Final PRISM Build Integration | Unassigned | Invalid | 0
376325 | #382895 | Story | Feature 382895: Checkpoint PRISM Build Integration | PI 14 | Invalid | 0
376324 | #382895 | Story | Feature 382895: Initial PRISM Build Integration | Unassigned | Invalid | 0
376319 |  | Story | ADI/EMI/PRISM Integration: Baseline ETISP Loopback FPGA Build developement | Unassigned | Invalid | 0
376286 | #290638 | Story | Integrate NMS with AWARE: Updates to AAA (part 3 of 3) | Unassigned | Invalid | 0
376259 | #318430 | Story | Feature 318430 ETT: UX Updates for ETT Applications | Unassigned | Invalid | 0
376258 | #318430 | Story | Feature 318430 ETT: Update IETM for ETT Applications | Unassigned | Invalid | 0
376241 | #318430 | Story | Feature 318430 ETT: Aquire MATROX GRAPHICS DUALHEAD2GO DIGITAL EDITION | Unassigned | Invalid | 0
376236 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376234 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376231 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376229 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
376204 | #1002583 | Story | CDM Process Change: Start prototype of revised CDM Release Process | EA 15.4 | New | 5
376171 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) [Perform Initial Research] | PI 14 | Invalid | 0
376166 |  | Story | MHAL Webpage Support | Unassigned | Invalid | 0
376164 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) [Perform Initial Research] | PI 14 | Invalid | 0
376152 | #354537 | Story | Update Splunk servers to RHEL 7.x: Fix OS-only issues found on installed hardened OS image with existing HW (Splunk v6.5.3) | Unassigned | Invalid | 0
376148 | #257556 | Story | AWARE Fault Recovery Procedures: SE Support | Unassigned | Invalid | 0
376147 | #257556 | Story | AWARE Fault Recovery Procedures: SE Support | Unassigned | Invalid | 0
376146 |  | Story | PM Performance Improvements – IETM: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of 3 | Unassigned | Invalid | 0
376009 | #369521 | Story | EAD 13 SA On-site Support - EA 12.6 | Unassigned | Invalid | 0
376008 |  | Story | EAD 13 SA On-site Support - EA 12.5 | Unassigned | Invalid | 0
376006 | #369521 | Story | EAD 13 SA On-site Support - EA 12.3 | Unassigned | Invalid | 0
375951 |  | Task | Implement & Test SPLUNK HA for VLAB: IA Support/Ramp up - Part 4 | Unassigned | Invalid
375949 |  | Task | Implement & Test SPLUNK HA for VLAB: IA Support/Ramp up - Part 1 | Unassigned | Invalid
375872 | #371602 | Story | Feature 371602: Define possible framework/technical approaches | Unassigned | New | 5
375871 | #371602 | Story | Feature 371602: First order discussion of possible actions | Unassigned | New | 3
375850 |  | Story | 99-P52203E RevF Software to Hardware Mapping IP CORE 1 – unlink Title and Table, it breaks the SR generation tool. | Unassigned | New | 1
375842 |  | Story | 99-P59435M RevAB NM CSCI HSM missing instances on Workstations for GEM One Shortcut | Unassigned | Invalid | 0
375838 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SE) | EA 14.1 | Invalid | 0
375837 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SE) | EA 14.3 | Invalid | 0
375703 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (TOFF) | EA 14.2 | Invalid | 0
375702 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (TOFF) | EA 14.1 | Invalid | 0
375701 | #373090 | Story | Define Reliability Metrics identified by the customer | EA 14.2 | Done | 2
375594 | #354158 | Story | Feature 354158: Perform release activities for the RAN | Unassigned | Invalid | 0
375579 | #370104 | Story | TD 19-15: ULX Phase 3 Design: Placeholder for ETI effort | Unassigned | Invalid | 0
375566 | #1007900 | Problem | SIEM services blocked from starting by HIPS | EA 15.3 | Closed
375565 |  | Problem | MGS Adapter service will not start without manual intervention | Unassigned | Assessing
375553 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Support ACC migration analysis (12.7) | Unassigned | Invalid | 0
375552 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Support ACC migration analysis (12.6) | Unassigned | Invalid | 0
375551 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Support ACC migration analysis (12.5) | Unassigned | Invalid | 0
375549 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (12.1) | Unassigned | Invalid | 0
375531 | #375516 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #375518
375529 | #375516 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
375528 | #375516 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
375527 | #375516 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #375518
375526 | #375516 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #375518
375524 | #375516 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #375518
375520 | #375516 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #375524
375515 | #381043 | Feature | Define Splunk Version Update Path Forward | PI 16 | Approved
375460 | #375445 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #375447
375459 | #375445 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
375458 | #375445 | Story | <Feature 375445> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
375457 | #375445 | Story | <Feature 375445> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
375456 | #375445 | Story | <Feature 375445> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #375447
375455 | #375445 | Story | <Feature 375445> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #375447
375454 | #375445 | Story | <Feature 375445>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
375453 | #375445 | Story | <Feature 375445>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #375447
375452 | #375445 | Story | <Feature 375445> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #375447
375451 | #375445 | Story | <Feature 375445>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #375448
375450 | #375445 | Story | <Feature 375445>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #375447
375449 | #375445 | Story | <Feature 375445> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #375453
375448 | #375445 | Story | <Feature 375445> IA Posture Assessment | Unassigned | Invalid | 0 | #375447
375447 | #375445 | Story | Feature Demo – Customer Demo Event - <Feature 375445> | Unassigned | Invalid | 0 | #375454
375446 | #375445 | Story | <Feature 375445>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #375451
375445 |  | Feature | <Feature 375445> | Unassigned | Rejected
375419 | #1002345 | Problem | Signaling Link Unavailable alarm includes specifics in "Summary" such that O-Level could not find this specific alarm and perform recovery procedure. | PI 16 | Approved
375342 |  | Problem | IETM KMS Compromise Recovery Operating Procedures – Normal Operation Procedure update to prevent issue described in trouble ticket | Unassigned | Assessing
375324 |  | Story | Feature 382895: ADI Onsite Lab Integration support | Unassigned | Invalid | 0
375291 |  | Story | Implement & Test SPLUNK HA for VLAB: Capture and document redlines for network devices | Unassigned | Invalid | 0
375290 |  | Story | Implement & Test SPLUNK HA for VLAB: Integrate networking devices into VLAB | Unassigned | Invalid | 0
375207 | #1001062 | Story | Using Solaris 10, Investigate RDE build of RBS BOAM load module to determine if issue still exists | EA 15.3 | Done | 5
375203 | #297335 | Story | Using Solaris 10, Test Full RBS Build Project to determine if CL6x Compatibility Issues still exist | EA 14.3 | Invalid | 0
375053 | #354871 | Story | Feature 354871: MFR 3 - Dev Team supports Initial Cybersecurity Assessment | EA 16.1 | New | 1
375049 | #354871 | Story | Feature 354871: Execute STCD in VLAB (part 1 of 2) | EA 15.3 | Invalid | 0
375040 | #366838 | Story | Feature 366838: HW SME Troubleshooting for Units Returned from Site | Unassigned | Invalid | 0
374998 |  | Story | Integrate AWARE into SA Dashboards: Help Updates Review | Unassigned | Invalid | 0
374984 | #354537 | Story | Update Splunk servers to RHEL 7.x: Fix OS-only issues found on installed hardened OS image w/existing HW (Splunk v6.5.3) | Unassigned | Invalid | 0
374983 | #354537 | Story | Update Splunk servers to RHEL 7.x: Dev Test hardened OS image on existing HW (Splunk v6.5.3) | Unassigned | Invalid | 0
374976 |  | Story | Integrate NMS with AWARE: EPO and AV/HIDS Updates | Unassigned | Invalid | 0
374975 |  | Story | Integrate NMS with AWARE: PKI Updates | Unassigned | Invalid | 0
374974 |  | Story | Integrate NMS with AWARE: Updates to AAA | Unassigned | Invalid | 0
374973 |  | Story | Integrate NMS with AWARE: FM Topology Updates/Review/Verification | Unassigned | Invalid | 0
374972 |  | Story | Integrate NMS with AWARE: Update HW/SW Map | Unassigned | Invalid | 0
374971 |  | Story | Integrate NMS with AWARE: Define PPS for firewalls | Unassigned | Invalid | 0
374909 | #297335 | Story | Tools Team Support / LOE for RDE- Implement clearmake for Builds in the RDE | EA 14.1 | Done | 3
374768 | #1004171 | Problem | Group issues after RNC cells deactivate/reactivate | EA 15.4 | Approved
373948 | #373944 | Story | Re-apply STCD Problem 371037 Story | Unassigned | Invalid | 0
373947 | #373944 | Story | Re-apply Problem 371037 Story | Unassigned | Invalid | 0 | #373948
373944 | #363873 | Feature | MPC for Problem 373087 found in EAD 12 Deliveries | Unassigned | Rejected
373718 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373717 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373715 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373714 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373710 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373707 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373705 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373678 | #368860 | Story | Feature 368860: Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
373676 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
373675 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
373673 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
373448 | #367689 | Task | Feature 367689: Submit PDO for 98-P53523T - GIS - SVD | PI 16 | New
373447 | #343917 | Task | Story 343917: CM Release of 99-P57051M - NMS - NM Common - GSAM (EAD 15) [aka Account Maintenance Plan] | EA 14.1 | Done
373442 |  | Task | Story 343914: CM Release of 98-P55735M - GTS - SWITCH - SSA - HFCAPS - SVD (EAD 14) | Unassigned | Invalid
373435 |  | Problem | SIEM Security Daily Report on Secret ENclave no longer idenitifiies virus detections | Unassigned | Assessing
373410 |  | Problem | Windows 2012 Servers are not reporting all faults to FM | Unassigned | Assessing
373374 |  | Story | Meet with Development Team to Understand Usage and Develop a Common Vision for the Roadmap | Unassigned | Invalid | 0
373373 | #375936 | Story | Select 1 CI and investigate build in RTC | Unassigned | New | 5
373372 | #375936 | Story | Investigate SGSS Usage of RTC and ClearQuest/ ClearCase | Unassigned | New | 3
373366 |  | Problem | Restore ATM — Normal Operation Procedure references SVD | Unassigned | Assessing
373201 |  | Story | Fix Problem 292421 | Unassigned | Invalid | 0
373169 | #373154 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #373156
373168 | #373154 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
373167 | #373154 | Story | <Feature 373154> UX Research and Design Support | Unassigned | Invalid | 0
373166 | #373154 | Story | <Feature 373154> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
373165 | #373154 | Story | <Feature 373154> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #373156
373164 | #373154 | Story | <Feature 373154> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #373156
373163 | #373154 | Story | <Feature 373154>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
373162 | #373154 | Story | <Feature 373154>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #373156
373161 | #373154 | Story | <Feature 373154> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #373156
373160 | #373154 | Story | <Feature 373154>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #373157
373159 | #373154 | Story | <Feature 373154>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #373156
373158 | #373154 | Story | <Feature 373154> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #373162
373157 | #373154 | Story | Feature 373154: IA Posture Assessment | Unassigned | Invalid | 0 | #373156
373156 | #373154 | Story | Feature Demo – Customer Demo Event - <Feature 373154> | Unassigned | Invalid | 0 | #373163
373155 | #373154 | Story | <Feature 373154>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #373160
373098 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.4 | EA 15.4 | Implementing | 3
373097 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.3 | EA 15.3 | Done | 3
373096 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.2 | EA 15.2 | Done | 3
373095 | #372921 | Story | Support RMF IATT effort for call banks (Cyber) - 15.1 | EA 15.1 | Done | 3
373090 | #267568 | Feature | Determine execution plan for TOFF metrics collection and reporting | EA 14.4 | Done
373062 | #355216 | Story | Redlines from Site NW SV Relocation Antenna Pointing | Unassigned | Invalid | 0
373060 | #373045 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #373047
373059 | #373045 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
373058 | #373045 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
373057 | #373045 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
373056 | #373045 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #373047
373055 | #373045 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #373047
373054 | #373045 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
373053 | #373045 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #373047
373052 | #373045 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #373047
373051 | #373045 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #373048
373050 | #373045 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #373047
373049 | #373045 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #373053
373048 | #373045 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #373047
373047 | #373045 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #373054
373046 | #373045 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #373051
373045 |  | Feature | <Feature xxx> | Unassigned | Rejected
372997 | #369509 | Story | Refactor design based on test finding | Unassigned | Invalid | 0
372994 | #369509 | Story | Execute tests based on test plan | Unassigned | Invalid | 0
372951 | #369358 | Story | Start FRCB preparation (support ILS, identify the documentation) | Unassigned | Invalid | 0
372931 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SE) | EA 14.2 | Invalid | 0
372930 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (SA) - 14.4 | EA 14.4 | Done | 1
372929 | #373090 | Story | Placeholder to re-assess how to use Splunk to analyze data for TOFF (UX) [Perform Initial Research] - 14.4 | EA 14.4 | Invalid | 0
372921 | #216552 | Feature | Cyber: RMF Accreditation of Call Bank Radio System | PI 16 - In Progress | Implementing
372877 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
372875 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
372871 | #372845 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #372858
372870 | #372845 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
372869 | #372845 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
372868 | #372845 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
372867 | #372845 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #372858
372866 | #372845 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #372858
372865 | #372845 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
372864 | #372845 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #372858
372863 | #372845 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #372858
372861 | #372845 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #372858
372860 | #372845 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #372864
372858 | #372845 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #372865
372856 | #372845 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #372858
372855 | #372845 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #372848
372854 | #372845 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #372858
372853 | #372845 | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0 | #372858
372852 | #372845 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #372858
372851 | #372845 | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #372852
372850 | #372845 | Story | <Feature yyy> Create red lines Hardware drawings submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372847
372849 | #372845 | Story | <Feature yyy> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372847
372848 | #372845 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #372854
372847 | #372845 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #372858
372846 | #372845 | Story | <Feature yyy>: Logistics Considerations (non-IETM) (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372858
372845 |  | Feature | <FRCB Feature xxx> | Unassigned | Rejected
372844 | #372818 | Story | Feature 372818: Create the Site Functional Test Case | Unassigned | Invalid | 0 | #372831
372843 | #372818 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
372842 | #372818 | Story | Feature 372818: UX IETM Development and Integration Updates for FRCB | Unassigned | Invalid | 0
372841 | #372818 | Story | Feature 372818: IETM Development and Integration Update for FRCB | Unassigned | Invalid | 0
372840 | #372818 | Story | Feature 372818: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #372831
372839 | #372818 | Story | Feature 372818: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #372831
372838 | #372818 | Story | Feature 372818: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
372837 | #372818 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #372831
372836 | #372818 | Story | Feature 372818: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #372831
372835 | #372818 | Story | Feature 372818: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #372832
372834 | #372818 | Story | Feature 372818: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #372831
372833 | #372818 | Story | Feature 372818: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #372837
372832 | #372818 | Story | Feature 372818: IA Posture Assessment | Unassigned | Invalid | 0 | #372831
372831 | #372818 | Story | Feature Demo – Customer Demo Event - Feature 372818 | Unassigned | Invalid | 0 | #372838
372830 | #372818 | Story | Feature 372818: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #372835 #372828
372829 | #372818 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #372831
372828 | #372818 | Story | Feature 372818: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #372821
372827 | #372818 | Story | Feature 372818: IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #372831
372826 | #372818 | Story | Feature 372818: Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0 | #372831
372825 | #372818 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #372831
372824 | #372818 | Story | Feature 372818: System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #372825
372823 | #372818 | Story | <Feature yyy> Create red lines Hardware drawings submitted for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372820
372822 | #372818 | Story | <Feature yyy> Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372820
372821 | #372818 | Story | Feature 372818: IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #372827
372820 | #372818 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #372831
372819 | #372818 | Story | <Feature yyy>: Logistics Considerations (non-IETM) (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #372831
372818 |  | Feature | <FRCB Feature xxx> | Unassigned | Rejected
372810 | #367689 | Task | Feature 367689: Submit PDO for 98-P55607M – GTS – TIS – SVD | PI 15 | New
372743 |  | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.6) | Unassigned | Invalid | 0
372483 | #380808 | Task | Feature 380808: Submit PDO for 98-P55517M – OS – RHEL – ENT – SVD | PI 16 | New
372481 |  | Task | Story 343914: CM Release of 98-P55517M – OS – RHEL – ENT – SVD (EAD 14) | Unassigned | Invalid
372461 | #372457 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
372460 | #372457 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #372461
372457 | #353840 | Feature | MPC for Problem xxx found in Pre EAD 10 Deliveries | Unassigned | Rejected
372427 | #372423 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
372426 | #372423 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #372427
372425 | #372423 | Story | Rebase STCD Problem 299075 Story | Unassigned | Invalid | 0
372423 | #243414 | Feature | Backup Archive PWI Burn Down | Unassigned | Rejected
372420 | #372416 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
372419 | #372416 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #372420
372416 | #363872 | Feature | MPC for Problem 356889 found in EAD 11 Deliveries | Unassigned | Rejected
372404 | #363872 | Feature | MPC for Problem xxx found in EAD 11 Deliveries | Unassigned | Rejected
372389 |  | Problem | 98-P53544T HSS, SVD - add build files to the software manifest for release - required for scratch installation of the HSS. | Unassigned | Assessing
372388 |  | Problem | 98-P53543T CSCF, SVD - add build files to the software manifest for release - required for scratch installation of the CSCF. | Unassigned | Assessing
372371 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
372370 |  | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
372366 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
372363 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
372360 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
372357 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
372347 | #372343 | Story | Re-apply STCD Problem 371879 Story | Unassigned | Invalid | 0
372346 | #372343 | Story | Re-apply Problem 371879 Story | Unassigned | Invalid | 0 | #372347
372345 | #372343 | Story | Rebase STCD Problem 371879 Story | Unassigned | Invalid | 0
372344 | #372343 | Story | Rebase Problem 371879 Story | Unassigned | Invalid | 0 | #372345
372343 | #363873 | Feature | MPC for Problem 371879 found in EAD 12 Deliveries | Unassigned | Rejected
372326 | #372322 | Story | Re-apply STCD Problem 371879 Story | Unassigned | Invalid | 0
372325 | #372322 | Story | Re-apply Problem 371879 Story | Unassigned | Invalid | 0 | #372326
372324 | #372322 | Story | Rebase STCD Problem 371879 Story | Unassigned | Invalid | 0
372323 | #372322 | Story | Rebase Problem 371879 Story | Unassigned | Invalid | 0 | #372324
372322 | #363873 | Feature | MPC for Problem 371879 found in EAD 12 Deliveries | Unassigned | Rejected
372321 | #352946 | Story | Windows Server SHB: ACAS Scan and STIG | PI 16 | New | 3
372316 | #352946 | Story | Windows Server SHB: Planning & coordination | PI 16 | New | 5
372309 | #352946 | Story | Windows Server SHB: Identify minimal baseline capabilities | PI 16 | New | 1
372303 | #352946 | Story | Windows Server SHB: Identify minimal baseline capabilities | PI 16 | New | 1
372298 | #352946 | Story | Windows Server SHB: Identify minimal baseline capabilities | PI 16 | New | 1
372281 |  | Story | Feature 372270: 2FA Planning | Unassigned | Invalid | 0
372280 |  | Story | Feature 372270: 2FA Planning | Unassigned | Invalid | 0
372276 | #372272 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
372275 | #372272 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #372276
372274 | #372272 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
372273 | #372272 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #372274
372272 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
372177 | #372173 | Story | Re-apply STCD Problem 371879 Story | Unassigned | Invalid | 0
372176 | #372173 | Story | Re-apply Problem 371879 Story | Unassigned | Invalid | 0 | #372177
372175 | #372173 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
372174 | #372173 | Story | Rebase Problem 371879 Story | Unassigned | Invalid | 0 | #372175
372173 | #363873 | Feature | MPC for Problem 371879 found in EAD 12 Deliveries | Unassigned | Rejected
372101 |  | Story | SA SME Support: Help assessing Nutanix HW | Unassigned | Invalid | 0
371992 | #371988 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
371991 | #371988 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #371992
371988 | #353840 | Feature | MPC for Problem 335708 found in Pre-EAD 10 Deliveries | Unassigned | Rejected
371940 | #396437 | Story | RDE: Establish a Plan for the test build environment that does not impact the production environment | PI 14 | Invalid | 0
371934 | #375936 | Story | RDE Update build system to minimize baseline creation | Unassigned | New | 8
371885 | #371881 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
371884 | #371881 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #371885
371881 | #363873 | Feature | MPC for Problem 371879 found in EAD 12 Deliveries | Unassigned | Draft
371652 | #371602 | Story | Feature 371602: Evaluate options for displaying the eRxIM status | Unassigned | New | 5
371651 | #371602 | Story | Feature 371602: Investigate and quantify possible eRxIM impacts to users | Unassigned | New | 8
371650 | #371602 | Story | Feature 371602: Capture and document eRxIM algorithm artifacts | Unassigned | New | 3
371540 | #375516 | Story | Fix Problem 355049: ATO Maintenance: IA Remediation for Access Control and Password Complexity on Splunk Servers (Part 2) | Unassigned | Invalid | 0
371539 | #375516 | Story | Fix Problem 355049: ATO Maintenance: IA Remediation for Access Control and Password Complexity on Splunk Servers (Part 1) | Unassigned | Invalid | 0
371532 | #375516 | Story | Fix Problem 355066: ATO Maintenance: IA Remediation for Multifactor Authentication on Splunk Servers | Unassigned | Invalid | 0
371522 | #367689 | Story | Fix Problem 258308: SR 931715 - INC 000002212519 - FOUO Workstation Internet Explorer connection to Lantronix SLC16 console server Web page fails after certificate presentation | PI 16 | New | 2
371519 | #1013452 | Story | Fix Problem 348853: DD, HQ, HLR, & WHTIS Firewall (WH) are denying snmp (port 161) packets from fcap101-wh-nma to various node (port 161). | PI 16 | New | 2
371518 | #1013452 | Story | Fix Problem 358182: Redlines for Firewall Network SVD(98-P55755M) from EAD-10 Deployment | PI 16 | New | 1
371517 | #1011150 | Story | Fix Problem 333910: Firewall rule does not support packets from the mas-wh/nw port 13006/13005 to the OTAFT Servers port 5080 | EA 15.5 | New | 2
371515 | #1013452 | Story | Fix Problem 320596: Northwest (NW) GIS Firewall is denying IP protocol 50 ESP packets from WH NIPRNET HAIPE (whniprnethaipe1) to UE (APN12). | PI 16 | New | 2
371514 |  | Story | Fix PWIs | Unassigned | Invalid | 0
371493 | #371485 | Story | Feature 371485: Investigate RTWP Issues - WF-RAN Support | PI 15 | Invalid | 0
371492 | #371485 | Story | Investigate RTWP Issues - SE Support | PI 15 | Invalid | 0
371487 |  | Story | Create Deployment notes and operator impacts | Unassigned | Invalid | 0
371485 | #225732 | Feature | Investigate Providing a Reliable RTWP Measurement/Alarm | Unassigned | Rejected |  | #378252
371484 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
371482 |  | Story | SVD Updates | Unassigned | Invalid | 0
371479 | #342163 | Story | Fix Problem 364595: HW/SW Map: HAIPE Mgmt SVD must be added to workstations in NM HW/SW Mapping document | EA 15.1 | Done | 3
371473 |  | Story | Update TPM Version in support of ETISP eRxIM update - story 1 | Unassigned | Invalid | 0
371467 | #342163 | Story | Feature 342163: Fix Problem 352634: IETM: TACLANE 1G guide is linked for HAIPE Ds | EA 15.1 | Done | 1
371236 | #382895 | Story | Feature 382895: Administrative Lab Preparation (Prop passes, etc.) | EA 14.4 | Invalid | 0
371234 | #382895 | Story | Feature 382895: Final PRISM Build - Full Test Case | Unassigned | Invalid | 0
371223 |  | Story | ADI/EMI/PRISM Integration: EMI/PRISM tagup Support | Unassigned | Invalid | 0
371212 | #371198 | Story | ULX Support - Phase 1/2: Support for B2U Hawaii RAF design for ONR RIF - EA 12.1 | Unassigned | Invalid | 0
371210 | #371198 | Story | ULX Support - Phase 1/2: MAGIC Support - EA 12.1 | Unassigned | Invalid | 0
371168 | #371080 | Story | UX Support to define process for baselining user-created Splunk dashboards: Define User Requirements | PI 15 | Invalid | 0
371153 | #371080 | Story | Add ARSTRAT Dashboard Validation and Signoff to Deployment Process | PI 15 | Invalid | 0
371152 | #371080 | Story | Add ARSTRAT Lab Access and Support to Increment Planning Process | PI 15 | Invalid | 0
371141 | #251537 | Story | Update IETM - Earth Terminal Facility (ETF)-Power Down (combined with Story 371142) | Unassigned | Invalid | 0 | #371445
371118 |  | Problem | Restart Ping Probes- Normal Operation Procedure (EAD 12 Training Findings) | Unassigned | Assessing
371111 |  | Problem | Stop MUOS Application Server — Normal Operation Procedure (EAD 12 Training Findings) | Unassigned | Assessing
371110 |  | Problem | Start MUOS Application Server — Normal Operation Procedure (EAD 12 Training Findings) | Unassigned | Assessing
371105 |  | Problem | Periodically Clear SQL Error Logs-Normal Operation Procedure (EAD 12 Training Findings) | Unassigned | Assessing
371087 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
371084 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
371083 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
371082 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
371081 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: SME Support ACC migration analysis | Unassigned | Invalid | 0
371080 | #371610 | Feature | Integrate ARSTRAT Dashboards into Planning/Test/Validation Processes | PI 15 | Rejected
371075 |  | Task | Story 393213: CM Release of 98-P59291M – SCS – OA – SVD (EAD 17) | Unassigned | Invalid
371051 |  | Task | Hold Feature Review with SMEs | Unassigned | Invalid
370990 |  | Feature | <Feature xxx> | Unassigned | Rejected
370921 |  | Feature | Provide ADNS HAIPE Routability Similar to IP Teleport Splunk Dashboard | Unassigned | Rejected
370819 |  | Problem | Splunk Intersite Link Status Timestamps sometimes show the date 6/1/17 | Unassigned | Assessing
370658 |  | Problem | Splunk Global System Status: Sometimes difficult to notice service affecting problems on pie charts | Unassigned | Assessing
370639 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
370633 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
370615 | #368860 | Story | Feature 368860: Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) [Perform Initial Research] | PI 14 | Invalid | 0
370614 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
370613 |  | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
370278 | #370263 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #370265
370277 | #370263 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
370276 | #370263 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
370275 | #370263 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
370274 | #370263 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #370265
370273 | #370263 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #370265
370272 | #370263 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
370271 | #370263 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #370265
370270 | #370263 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #370265
370269 | #370263 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #370266
370268 | #370263 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #370265
370267 | #370263 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #370271
370266 | #370263 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #370265
370265 | #370263 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #370272
370264 | #370263 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #370269
370263 |  | Feature | <Feature xxx> | Unassigned | Rejected
370246 | #367689 | Story | Feature 367689: Generate MUOS Technical Bulletin | PI 16 | New | 1
370178 |  | Story | PI 12 Alarm Recovery Procedures: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #370169
370175 | #370167 | Story | PI 12 Alarm Recovery Procedures: ILS IETM update (Template) | Unassigned | Invalid | 0 | #370169
370173 | #370167 | Story | PI 12 Alarm Recovery Procedures: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #370170
370170 | #370167 | Story | PI 12 Alarm Recovery Procedures: IA Posture Assessment | Unassigned | Invalid | 0 | #370169
370168 | #370167 | Story | PI 12 Alarm Recovery Procedures: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #370173
370109 | #370104 | Story | TD 19-15: ULX Phase 3 Design: INVALID | Unassigned | Invalid | 0
370106 | #370104 | Story | TD 19-15: ULX Phase 3 Design: INVALID | Unassigned | Invalid | 0
370030 | #369538 | Task | Feature 369538 - Tracking Alignment Site # 2 - SC: Logistics Support of Tracking Activity (EA 12.4) | Unassigned | Invalid
370029 | #369538 | Task | Feature 369538 - Tracking Alignment Site # 2 - SC: Logistics Support of Tracking Activity (EA 12.3) | Unassigned | Invalid
369983 | #1007900 | Task | Re-apply STCD Problem MPC EAD_12.8 VSEL On-Demand Scan Move to Weekly Story | PI 16 | Invalid
369982 | #1007900 | Task | Re-apply Problem 369985 Story for (MPC EAD 12.8) - VSEL On-Demand Scan Move to Weekly | PI 16 | Invalid |  | #369983
369981 | #1007900 | Task | Rebase STCD Problem MPC EAD_12.8 VSEL On-Demand Scan Move to Weekly Story | PI 16 | Invalid
369980 | #1007900 | Task | Rebase Problem 369985 MPC EAD_12.8 VSEL On-Demand Scan Move to Weekly Story | PI 16 | New |  | #369981
369979 |  | Feature | MPC for Problem 369985 MPC EAD_12.8 VSEL found in EAD 12 Deliveries | Unassigned | Rejected
369893 | #369879 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
369892 | #369879 | Story | <Feature 369879> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
369891 | #369879 | Story | <Feature 369879> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
369890 | #369879 | Story | <Feature 369879> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #369881
369889 | #369879 | Story | <Feature 369879> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #369881
369888 | #369879 | Story | <Feature 369879>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
369887 | #369879 | Story | <Feature 369879>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #369881
369886 | #369879 | Story | <Feature 369879> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #369881
369885 | #369879 | Story | <Feature 369879>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #369882
369884 | #369879 | Story | <Feature 369879>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #369881
369883 | #369879 | Story | <Feature 369879> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #369887
369882 | #369879 | Story | <Feature 369879> IA Posture Assessment | Unassigned | Invalid | 0 | #369881
369881 | #369879 | Story | Feature Demo – Customer Demo Event - <Feature 369879> | Unassigned | Invalid | 0 | #369888
369880 | #369879 | Story | <Feature 369879>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #369885
369879 |  | Feature | <Feature 369879> | Unassigned | Rejected
369758 | #369754 | Story | Feature 369754: IA - update the IA section in the design documentation | PI 17 | New | 2
369757 | #369754 | Story | Feature 369754: Design File Transfer | PI 17 | New | 8
369756 | #369754 | Story | Feature 369754: Design File Transfer | PI 17 | New | 8
369733 |  | Task | Cyber Security Team Support - Kent - part 1 | Unassigned | New
369663 |  | Story | Feature 257556: Agile Team Test (Install, PCR Verification) Part 2 of 2 | Unassigned | Invalid | 0
369576 |  | Feature | Firepower IDS replacement for Security | Unassigned | Rejected
369546 | #368169 | Story | Feature 368169 Agile Team Test and complete Kickstart installation procedure (Tester) | Unassigned | New | 3
369545 | #369538 | Task | Feature 369538 - Tracking Alignment Site # 2 - SC: Logistics Support of Tracking Activity (EA 12.2) | Unassigned | Invalid
369542 | #368169 | Story | Feature 368169 Agile Team Initial research and development of Kickstart server install | Unassigned | New | 5
369532 | #358755 | Story | ROM for TT&C | Unassigned | Invalid | 0
369525 | #369521 | Story | EAD 13 SA On-site Support - EA 12.2 | Unassigned | Invalid | 0
369483 | #367689 | Story | Feature 367689: Update PKI to remove Console Servers | PI 16 | New | 3
369482 | #367689 | Story | Feature 367689: Update GIS/TIS SVDs to remove Web GUI | PI 16 | New | 5
369188 | #365261 | Story | Allow PPA User Accounts to be Deleted (Design): Initial analysis (Systems) | EA 16.2 | New | 1
369184 |  | Story | Analyze, Design, and Document data movement with RAN - 11.6 | Unassigned | Invalid | 0
369178 | #365261 | Story | Allow PPA User Accounts to be Deleted (Design): Initial analysis (SME) | EA 16.1 | New | 5 | #369188
369111 | #263127 | Story | Define Changes for Development | PI 14 | Invalid | 0
369103 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369102 | #368860 | Story | Feature 368860: Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369101 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369100 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369098 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369097 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369096 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | EA 14.1 | Invalid | 0
369095 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369094 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369093 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369092 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369091 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369090 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369089 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369088 | #368860 | Story | Feature: 368860 High-Level System Archi | PI 14 | Invalid | 0
369087 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369086 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369085 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | PI 14 | Invalid | 0
369084 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369083 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369082 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning Phase 1 (SME Support) | PI 14 | Invalid | 0
369081 | #368860 | Story | Feature: 368860 Canadian Foreign Military Sales (FMS) Planning (SME Support) | EA 14.1 | Invalid | 0
369012 | #344196 | Story | MUOS Geolocation Support/Maintenance: Remove all legacy GEO from NEDB | Unassigned | Invalid | 0
368860 | #368857 | Feature | Canadian Foreign Military Sales (FMS) Planning Phase 1 | EA 14.5 | Done
368850 |  | Problem | Add access to VLab GEO servers from workstations ws213 and ws205 | Unassigned | Closed
368831 | #365261 | Story | Allow PPA User Accounts to be Deleted (Design): SME support for Systems Design | EA 16.3 | New | 5
368828 | #368824 | Story | Re-apply STCD Problem 334428 Story | Unassigned | Invalid | 0
368827 | #368824 | Story | Re-apply Problem 334428 Story | Unassigned | Invalid | 0 | #368828
368826 | #368824 | Story | Rebase STCD Problem 334428 Story | Unassigned | Invalid | 0
368825 | #368824 | Story | Rebase Problem 334428 Story | Unassigned | Invalid | 0 | #368826
368823 | #365261 | Story | Allow PPA User Accounts to be Deleted (Design): Systems Design | EA 16.3 | New | 5
368773 |  | Task | Assessing FM server Cyber PWIs - EA 11.4 | Unassigned | Invalid
368488 | #356094 | Story | SE Support | PI 15 | Invalid | 0
368419 |  | Task | Assess Problem 355240 | Unassigned | Invalid
368327 | #368323 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
368326 | #368323 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #368327
368323 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
368322 | #368318 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
368321 | #368318 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #368322
368318 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
368316 | #368312 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
368315 | #368312 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #368316
368312 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
368305 | #358873 | Story | Feature 358873: Demo RBS/RNC- Analysis (or Inspection) of Minor Format Updates for Style Guide Compliance | Unassigned | Invalid | 0
368299 |  | Task | Assessing Splunk Infra Cyber PWIs - Ken | Unassigned | Invalid
368283 | #368268 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #368270
368282 | #368268 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
368281 | #368268 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
368280 | #368268 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
368279 | #368268 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #368270
368278 | #368268 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #368270
368277 | #368268 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
368276 | #368268 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #368270
368275 | #368268 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #368270
368274 | #368268 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #368271
368273 | #368268 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #368270
368272 | #368268 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #368276
368271 | #368268 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #368270
368270 | #368268 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #368277
368269 | #368268 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #368274
368268 |  | Feature | <Feature xxx> | Unassigned | Rejected
368257 |  | Problem | MPC Test PWI for Template work | Unassigned | Triage
368245 |  | Problem | Splunk: Extraneous cell IDs reported in fmevents index | Unassigned | Assessing
368194 | #368169 | Story | Feature 368169 CM and archive – Hardware asset, SVD and kickstart procedure | Unassigned | New | 3
368193 | #368169 | Story | Feature 368169 Complete ESAC/Contractual/purchase license approvals for software usage with MUOS program: | Unassigned | New | 3
368192 | #368169 | Story | Feature 368169 Identify ILS laptop hardware/software configuration needed for kickstart server then purchase or obtain | Unassigned | New | 3
368190 | #368169 | Story | Feature 368169 Agile Team Test and complete installation procedure on TXO CSCF in lab (Tester) | Unassigned | New | 3
368189 | #369536 | Story | Feature 368169 UX IETM Development and Integration updates - Create or modify old procedure to kickstart HSS/CSCF equipment with the new ILS laptop kickstart server. | Unassigned | New | 3
368188 | #369536 | Story | Feature 368169 ILS IETM Development and Integration updates - Create or modify old procedure to kickstart HSS/CSCF equipment with the new ILS laptop kickstart server. | Unassigned | New | 2
368187 | #369536 | Story | Feature 368170 Engineering IETM Development and Integration updates - Create or modify old procedure to kickstart HSS/CSCF equipment with the new ILS laptop kickstart server. | Unassigned | New | 3
368184 | #369536 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #368171
368183 | #368169 | Task | Hold Feature Review with SMEs | Unassigned | New
368182 | #369536 | Story | Feature 368169 UX IETM Development and Integration updates - Create procedure to install software on ILS laptop purchased for this activity | Unassigned | New | 3
368181 | #369536 | Story | Feature 368169 ILS IETM Development and Integration updates - Create procedure to install software on ILS laptop purchased for this activity. | Unassigned | New | 5
368180 | #368169 | Story | Feature 368169 Agile Team Test and complete Kickstart installation procedure (UX) | Unassigned | New | 2 | #368171
368179 | #369536 | Story | Feature 368169 Agile Team Test and complete installation procedure on TXO CSCF in lab (ILS) | Unassigned | New | 3 | #368171
368178 | #368169 | Story | Feature 368169: Initiate CM PDO Processing for all CI's | Unassigned | New | 2
368177 | #369536 | Story | Feature 368169:ILS IETM update (Template) | Unassigned | New | 3 | #368171
368176 | #368169 | Story | Feature 368169 Agile Team Test and complete Kickstart server installation procedure (SME/Developer) | Unassigned | New | 2 | #368171
368175 | #368169 | Story | Feature 368169: IA Patching and STIGs | Unassigned | New | 5 | #368172
368174 | #369536 | Story | Feature 368169: Deployment Notes and Operator Impact Inputs | Unassigned | New | 3 | #368171
368173 | #369536 | Story | Feature 368170 Engineering IETM Development and Integration updates -Create procedure to install software on ILS laptop purchased for this activity. | Unassigned | New | 3 | #368177
368172 | #368169 | Story | Feature 368170 IA Posture Assessment and/or Address IA concerns | Unassigned | New | 8 | #368171
368171 | #369536 | Story | Feature Demo – Customer Demo Event - Feature 368170 | Unassigned | New | 1 | #368178
368170 | #368169 | Story | Feature 368169: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #368175
368137 |  | Problem | OSSRC - Need ability to clear old alarms stuck in ossrc | Unassigned | Assessing
367948 | #219598 | Feature | Investigate Changing Inter-site Status so That "No News=Bad News" | Unassigned | Rejected
367917 | #367902 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #367904
367916 | #367902 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
367915 | #367902 | Story | <Feature 367902> UX Research and Design Support | Unassigned | Invalid | 0
367914 | #367902 | Story | <Feature 367902> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
367913 | #367902 | Story | <Feature 367902> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #367904
367912 | #367902 | Story | <Feature 367902> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #367904
367911 | #367902 | Story | <Feature 367902>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
367910 | #367902 | Story | <Feature 367902>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #367904
367909 | #367902 | Story | <Feature 367902> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #367904
367908 | #367902 | Story | <Feature 367902>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #367905
367907 | #367902 | Story | <Feature 367902>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #367904
367906 | #367902 | Story | <Feature 367902> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #367910
367905 | #367902 | Story | Feature 367902: IA Posture Assessment | Unassigned | Invalid | 0 | #367904
367904 | #367902 | Story | Feature Demo – Customer Demo Event - <Feature 367902> | Unassigned | Invalid | 0 | #367911
367903 | #367902 | Story | <Feature 367902>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #367908
367901 | #367886 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #367888
367900 | #367886 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
367899 | #367886 | Story | <Feature 367886> UX Research and Design Support | Unassigned | Invalid | 0
367898 | #367886 | Story | <Feature 367886> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
367897 | #367886 | Story | <Feature 367886> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #367888
367896 | #367886 | Story | <Feature 367886> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #367888
367895 | #367886 | Story | <Feature 367886>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
367894 | #367886 | Story | <Feature 367886>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #367888
367893 | #367886 | Story | <Feature 367886> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #367888
367892 | #367886 | Story | <Feature 367886>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #367889
367891 | #367886 | Story | <Feature 367886>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #367888
367890 | #367886 | Story | <Feature 367886> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #367894
367889 | #367886 | Story | Feature 367886: IA Posture Assessment | Unassigned | Invalid | 0 | #367888
367888 | #367886 | Story | Feature Demo – Customer Demo Event - <Feature 367886> | Unassigned | Invalid | 0 | #367895
367887 | #367886 | Story | <Feature 367886>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #367892
367858 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (Cyber Input) | Unassigned | Invalid | 0
367857 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (12.3) | Unassigned | Invalid | 0
367856 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Perform ACC mitigation analysis (12.2) | Unassigned | Invalid | 0
367854 |  | Story | Support ACC migration analysis | Unassigned | Invalid | 0
367853 | #367851 | Story | Analysis to migrate to Advanced Cryptographic Capability: Support ACC migration analysis (12.4) | Unassigned | Invalid | 0
367827 | #360123 | Story | Investigate Trap Loss Issues - SE | PI 14 | Invalid | 0
367826 | #360123 | Story | Investigate Trap Loss Issues - ETI | PI 14 | Invalid | 0
367825 | #360123 | Story | Investigate Trap Loss Issues - SA | PI 14 | Invalid | 0
367808 | #367804 | Story | Re-apply STCD Problem 368257 Story | Unassigned | Invalid | 0
367807 | #367804 | Story | Re-apply Problem 368257 Story | Unassigned | Invalid | 0 | #367808
367806 | #367804 | Story | Rebase STCD Problem 368257 Story | Unassigned | Invalid | 0
367805 | #367804 | Story | Rebase Problem 368257 Story | Unassigned | Invalid | 0 | #367806
367804 | #363873 | Feature | MPC for Problem 368257 found in EAD 12 Deliveries | Unassigned | Rejected
367794 | #367790 | Story | Re-apply STCD Problem 347605 Story | Unassigned | Invalid | 0
367793 | #367790 | Story | Re-apply Problem 347605 Story | Unassigned | Invalid | 0 | #367794
367792 | #367790 | Story | Rebase STCD Problem 347605 Story | Unassigned | Invalid | 0
367791 | #367790 | Story | Rebase Problem 347605 Story | Unassigned | Invalid | 0 | #367792
367790 | #363873 | Feature | MPC for Problem 347605 found in EAD 12 Deliveries | Unassigned | Draft
367785 | #384136 | Problem | Feature 384136: HBSS: IETM procedure needed to check for expired DAT files on Linux hosts | EA 14.5 | Closed
367720 |  | Problem | Create procedure to clean up stuck KMS Group Events for IETM | Unassigned | Assessing
367704 | #367689 | Story | Feature 367689: Create the Site Functional Test Case | PI 16 | New | 2 | #367691
367703 | #367689 | Task | Feature 367689: Hold Feature Review with SMEs | PI 16 | New
367702 | #367689 | Story | Feature 367689: IETM Style Guide Review and Dry Runs - Remove Need for Web GUI with Console Servers | PI 16 | New | 3
367699 |  | Story | Feature 367689: Convert Web GUI installation to CLI | Unassigned | Invalid | 0 | #367691
367698 | #367689 | Task | Feature 367689: Initiate CM PDO Processing for all CI's | PI 16 | New
367697 | #367689 | Story | Feature 367689: IETM Update for Remove Need for Web GUI with Console Servers | PI 16 | New | 3 | #367691
367696 | #367689 | Story | Feature 367689: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 16 | New | 2 | #367691
367695 | #367689 | Story | Feature 367689: IA Patching and STIGs Part 1 of N | PI 16 | New | 5 | #367692
367694 | #367689 | Story | Feature 367689: Deployment Notes and Operator Impact Inputs | PI 16 | New | 1 | #367691
367693 | #367689 | Story | Feature 367689: Engineering IETM Development and Integration updates part 1 of N | PI 16 | New | 5 | #367697 #367702
367692 | #367689 | Story | Feature 367689 - Remove Need for Web GUI with Console Servers: IA Posture Assessment | PI 16 | New | 8 | #367691
367691 | #367689 | Story | Feature Demo – Customer Demo Event - Feature 367689 - Remove Need for Web GUI with Console Servers | PI 16 | New | 1 | #367698
367690 | #367689 | Story | Feature 367689: IA - Define Patch/ STIG Requirements | PI 16 | New | 2 | #367695
367689 | #243395 | Feature | Remove Need for Web GUI with Console Servers | PI 16 - In Progress | Implementing
367623 | #373090 | Story | Monthly Analysis and Reporting | EA 14.3 | Invalid | 0
367622 | #373090 | Story | Monthly Analysis and Reporting | EA 14.2 | Done | 1
367466 |  | Problem | Feedback on Splunk IP Teleport Connection Status help page - part 2 | Unassigned | Assessing
367440 |  | Problem | IETM legacy issues for Restore DNS— Normal Operation Procedure from review 964214 | Unassigned | Assessing
367438 |  | Problem | IETM legacy issues for Restore ATM — Normal Operation Procedure from review 964214 | Unassigned | Assessing
367315 |  | Problem | MGS Update Virus Definitions Procedure is not O-Level Appropriate | Unassigned | Assessing
367306 |  | Story | Optimize Saved Searches Part 2 | Unassigned | Invalid | 0
367042 |  | Story | CVPA Remediation - SNMP and LB: Verify AMP (EA 11.3) | Unassigned | Invalid | 0
367010 |  | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.5) | Unassigned | Invalid | 0
367009 | #366838 | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.4) | Unassigned | Invalid | 0
367008 |  | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.3) | Unassigned | Invalid | 0
367007 | #366838 | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.2) | Unassigned | Invalid | 0
367006 | #366838 | Story | Feature 366838: Evaluation of HW FRB Support (EA 12.1) | Unassigned | Invalid | 0
366947 | #366943 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
366946 | #366943 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #366947
366945 | #366943 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
366944 | #366943 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #366945
366943 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Rejected
366887 | #1016383 | Problem | DSN GW Loss of Sync alarms for signaling ports are not on the whitelist | PI 16 | Approved
366866 |  | Problem | whtisextids & nwtisextids overlap the interface between the TIS CE routers in the functional block diagram | Unassigned | Assessing
366852 | #366848 | Story | Re-apply STCD Problem 342366 Story | Unassigned | Invalid | 0
366851 | #366848 | Story | Re-apply Problem 342366 Story | Unassigned | Invalid | 0 | #366852
366834 | #366830 | Task | Re-apply STCD Problem 347605 Story | Unassigned | Invalid
366833 | #366830 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #366834
366832 | #342163 | Task | Rebase STCD - Problem 347605 | Unassigned | Invalid
366831 | #342163 | Story | Rebase Problem 347605 Story (EA 15.1) | EA 15.1 | Done | 2 | #366832
366830 | #363872 | Feature | MPC for Problem 347605 found in EAD 11 Deliveries | Unassigned | Rejected
366782 | #366778 | Story | Re-apply STCD Problem 366270 Story | Unassigned | Invalid | 0
366781 | #366778 | Story | Re-apply Problem 366270 Story | Unassigned | Invalid | 0 | #366782
366780 | #366778 | Story | Rebase STCD Problem 366270 Story | Unassigned | Invalid | 0
366779 | #366778 | Story | Rebase Problem 366270 Story | Unassigned | Invalid | 0 | #366780
366771 | #366767 | Story | Re-apply STCD Problem 364509 Story | Unassigned | Invalid | 0
366770 | #366767 | Story | Re-apply Problem 364509 Story | Unassigned | Invalid | 0 | #366771
366769 | #366767 | Story | Rebase STCD Problem 364509 Story | Unassigned | Invalid | 0
366768 | #366767 | Story | Rebase Problem 364509 Story | Unassigned | Invalid | 0 | #366769
366632 |  | Problem | Speed up the Splunk reporting of problems when the DSN GW is inaccessible | Unassigned | Assessing
366630 |  | Problem | TIS CE router "bgp peer connection idle" alarm does not auto clear when BGP peer recovers | Unassigned | Assessing
366628 |  | Problem | EAD-12 Deployment: Drawing redlines for NW Geolocation shielded cables | Unassigned | Assessing
366374 | #366348 | Story | Lab - Polatis Switch Replacement - Test SNMP Interface | Unassigned | Invalid | 0
366334 | #385854 | Task | Purchase Dependency: MS Windows Workstation Licenses (SWIT) | PI 14 | Done
366327 | #385854 | Task | Purchase Dependency: MS Visual Studio Pro 2017 Licenses | PI 14 | Done
366316 | #385854 | Task | Purchase Dependency: MS Visio Std Licenses | PI 14 | Done
366283 | #356094 | Story | Implement SA Dashboard Rule Changes in Support of False Cell Down During ET Switchover | PI 15 | Invalid | 0
366282 | #356094 | Story | Implement NetCool Rule Changes in Support of False Cell Down During ET Switchover | PI 15 | Invalid | 0
366280 | #250467 | Story | Determine Cause of RCGApps.com Using Outdated CRLs | Unassigned | Invalid | 0
366272 | #385854 | Task | Purchase Dependency: MS Office Std Licenses | PI 14 | Done
366269 | #385854 | Task | Purchase Dependency: Windows Server 2012 Licenses | PI 14 | Done
366171 |  | Problem | Update IETM for Recovery from expired CRLs section per issue found during PKI deployment | Unassigned | Assessing
366163 | #245573 | Feature | OTA Radios experience high levels of LOCAL ABNORMAL RELEASE errors per trouble tickets | Unassigned | Draft
365627 |  | Problem | INC000004006080 (WH- WH-Splunk GUI locked-up and became unresponsive). | Unassigned | Assessing
365510 |  | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
365509 |  | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #365510
365508 |  | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
365507 |  | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #365508
365503 | #365499 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
365502 | #365499 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #365503
365501 | #365499 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
365500 | #365499 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #365501
365374 |  | Story | RF Alignment NW (Relocation): Prep ACU configuration changes (part 2) - Jonathan | Unassigned | Invalid | 0
365304 | #365293 | Story | DB mgmt of terminal profiles: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #365295
365303 | #365293 | Story | DB mgmt of terminal profiles: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #365295
365301 | #365293 | Story | DB mgmt of terminal profiles: ILS IETM update (Template) | Unassigned | Invalid | 0 | #365295
365299 | #365293 | Story | DB mgmt of terminal profiles: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #365296
365296 | #365293 | Story | DB mgmt of terminal profiles: IA Posture Assessment | Unassigned | Invalid | 0 | #365295
365294 | #365293 | Story | DB mgmt of terminal profiles: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #365299
365292 | #365277 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #365279
365285 | #365277 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #365279
365280 | #365277 | Story | IETM for Apportionment Management and Estimation: IA Posture Assessment | Unassigned | Invalid | 0 | #365279
365276 | #365261 | Story | Create the Site Functional Test Case | PI 15 | Invalid | 0 | #365263
365275 | #365261 | Task | Hold Feature Review with SMEs | PI 15 | Invalid
365274 | #365261 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
365273 | #365261 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
365272 | #365261 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #365263
365271 | #365261 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #365263
365270 | #365261 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
365269 | #365261 | Story | <Feature xxx>:ILS IETM update (Template) | PI 15 | Invalid | 0 | #365263
365268 | #365261 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #365263
365267 | #365261 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #365264
365266 | #365261 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #365263
365265 | #365261 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #365269
365264 | #365261 | Story | <Feature xxx> IA Posture Assessment | PI 15 | Invalid | 0 | #365263
365263 | #365261 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | PI 15 | Invalid | 0 | #365270
365262 | #365261 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #365267
365261 | #1020650 | Feature | Allow PPA User Accounts to be Deleted (Design) | PI 16 - Candidate | Approved
365260 | #365245 | Story | Create the Site Functional Test Case | PI 15 | Invalid | 0 | #365247
365259 | #365245 | Task | Hold Feature Review with SMEs | PI 15 | Invalid
365258 | #365245 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
365257 | #365245 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
365256 | #365245 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #365247
365255 | #365245 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #365247
365254 | #365245 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
365253 | #365245 | Story | <Feature xxx>:ILS IETM update (Template) | PI 15 | Invalid | 0 | #365247
365252 | #365245 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #365247
365251 | #365245 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #365248
365250 | #365245 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #365247
365249 | #365245 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #365253
365248 | #365245 | Story | <Feature xxx> IA Posture Assessment | PI 15 | Invalid | 0 | #365247
365247 | #365245 | Story | Feature Demo – Customer Demo Event - Misc PPA updates (Enabler) | PI 15 | Invalid | 0 | #365254
365246 | #365245 | Story | Misc PPA updates (Enabler): IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #365251
365212 | #365208 | Story | Rebase Problem 338982 Story | Unassigned | Invalid | 0
365210 | #365208 | Story | Rebase STCD Problem 338982 Story | Unassigned | Invalid | 0
365190 | #365133 | Story | Solaris P2V ranadm1 and ranadm2- Retire physical Solaris Machines | Unassigned | Implementing | 1
365189 | #365133 | Story | Feature 365133: Solaris P2V ranadm1 and ranadm2- Validate Virtualized Server and Functionality- RAN Team Support | Unassigned | New | 1
365188 | #365170 | Story | Rebase Problem 329794 and Problem 329795 Story | Unassigned | Invalid | 0
365186 | #365170 | Story | Rebase STCD Problem 329794 and Problem 329795 Story | Unassigned | Invalid | 0
365135 | #365133 | Story | Solaris P2V ranadm1 and ranadm2- Validate Virtualized Server and Functionality- Tools Support | Unassigned | New | 1
365049 | #365133 | Story | Solaris P2V ranadm1 and ranadm2- Update Clearcase consistent with underlying ldom version | Unassigned | New | 2
365034 | #365133 | Story | Solaris P2V ranadm1 and ranadm2- Standup New Image | Unassigned | Implementing | 1
364853 |  | Problem | Issues with P2P 9.6k+64k II MultiRAB calls (G729 then 32k AM data call) at MUSIC lab | Unassigned | Assessing
364632 | #245572 | Feature | Rebase MPC r.1.3.21 to address SCS OA file server issues, update SVD, including all changes from R 1.4 deployment | PI 17 | Analyzing
364595 | #342163 | Problem | HW/SW Map: HAIPE Mgmt SVD must be added to workstations in NM HW/SW Mapping document | EA 15.1 | Closed
364371 | #364367 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
364370 | #364367 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #364371
364369 | #342163 | Story | Rebase STCD - Problem 357946 | Unassigned | Invalid | 0
364368 | #342163 | Story | HAIPE Mgmt: Rebase Problem 357946 and Problem 360439 (EA 15.2) | EA 15.2 | Done | 2 | #364369
364367 | #363872 | Feature | MPC for Problem xxx found in EAD 11 Deliveries | Unassigned | Rejected
364272 | #392530 | Problem | 98-P55616M RevF Version 20181214 IA Updates SVD verification is not good enough for verifying mas server | EA 14.2 | Closed
364225 |  | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
364224 |  | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #364225
364221 | #363872 | Feature | MPC for Problem 359932 found in EAD 11 Deliveries | Unassigned | Done
364217 | #343914 | Task | Story 343914: CM Release of 99-P53449E - ILS - IETM (EAD 14) | EA 14.1 | Done
364211 | #364204 | Story | Feature 364204: Support IA Posture Assessment customer review | Unassigned | Invalid | 0
364210 | #364204 | Story | Feature 364204: Produce IA Posture Assessment | Unassigned | Invalid | 0
364165 |  | Task | Story 353837: CM Release of 98-P57055M – MS – SCSsim4GTS-ETI – SVD (EAD 16 OOC) | EA 15.2 | Invalid
364164 |  | Task | Story 353837: CM Release of 98-P53367T -MS- NMSsim4GT - SVD (EAD 16 OOC) | EA 15.2 | Invalid
364116 |  | Task | Story 353837: CM Release of 98-P57054M - MS -RNCsim4GTS-ETI - SVD (EAD 17) | EA 15.2 | Invalid
364111 | #343920 | Task | Story 343917: CM Release of 98-P53342T - MS _Simulation Framework - SVD (EAD 15) | PI 14 | Invalid
363895 |  | Problem | ETISP Digi Passport pings from FOUO workstation provide inconsistent access to primary and redundant network interfaces | Unassigned | Assessing
363886 |  | Problem | DNSEM needs to be removed from “Non-Redundant Equipment - Functional Description” IETM procedure | Unassigned | Assessing
363883 | #363879 | Story | Re-apply STCD Problem xxx Story | Unassigned | New | 2
363882 | #363879 | Story | Re-apply Problem xxx Story | Unassigned | New | 2 | #363883
363881 | #363879 | Story | Rebase STCD Problem xxx Story | Unassigned | New | 2
363880 | #363879 | Story | Rebase Problem xxx Story | Unassigned | New | 2 | #363881
363879 | #363873 | Feature | MPC for Problem xxx found in EAD 12 Deliveries | Unassigned | Draft
363878 | #363874 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
363877 | #363874 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #363878
363876 | #363874 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
363875 | #363874 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #363876
363874 | #363872 | Feature | MPC for Problem xxx found in EAD 11 Deliveries | Unassigned | Draft
363871 | #363867 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
363870 | #363867 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #363871
363869 | #363867 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
363868 | #363867 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #363869
363867 | #356599 | Feature | MPC for Problem xxx found in EAD 10 Deliveries | Unassigned | Draft
363799 | #363784 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #363786
363798 | #363784 | Task | Hold Feature Review with SMEs | Unassigned | New
363797 | #363784 | Story | <Provide OTAP Server status information in Splunk index> UX IETM Development and Integration updates part 1 of N | Unassigned | New | 3
363796 | #363784 | Story | <Provide OTAP Server status information in Splunk index> ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
363795 | #363784 | Story | <Provide OTAP Server status information in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #363786
363794 | #363784 | Story | <Provide OTAP Server status information in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #363786
363793 | #363784 | Story | <Provide OTAP Server status information in Splunk index>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
363792 | #363784 | Story | <Provide OTAP Server status information in Splunk index>:ILS IETM update (Template) | Unassigned | New | 3 | #363786
363791 | #363784 | Story | <Provide OTAP Server status information in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #363786
363790 | #363784 | Story | <Provide OTAP Server status information in Splunk index>: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #363787
363789 | #363784 | Story | <Provide OTAP Server status information in Splunk index>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #363786
363788 | #363784 | Story | <Provide OTAP Server status information in Splunk index> Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #363792
363787 | #363784 | Story | Feature 363784 OTAP Splunk: IA Posture Assessment | Unassigned | New | 8 | #363786
363786 | #363784 | Story | Feature Demo – Customer Demo Event - <Provide OTAP Server status information in Splunk index> | Unassigned | New | 1 | #363793
363785 | #363784 | Story | Provide OTAP Server status information in Splunk index: Provide OTAP Server status information in Splunk index>: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #363790
363686 | #241246 | Story | <Feature xxx>: Provide Development inputs to common documents | Unassigned | Invalid | 0 | #241249
363573 | #1001691 | Feature | Develop strategy for improving WCDMA, NMS, and GEO troubleshooting methodology/procedures | PI 17 | Approved
363565 | #363550 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #363552
363564 | #363550 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
363562 | #363550 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
363561 | #363550 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #363552
363560 | #363550 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #363552
363556 | #363550 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #363553
363551 | #363550 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #363556
363550 |  | Feature | <Feature xxx> | Unassigned | Rejected
363394 | #363379 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #363381
363393 | #363379 | Task | Hold Feature Review with SMEs | Unassigned | New
363392 | #363379 | Story | <Include additional frequency profile data in Splunk index> UX IETM Development and Integration updates part 1 of N | Unassigned | New | 3
363391 | #363379 | Story | <Include additional frequency profile data in Splunk index> ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
363390 | #363379 | Story | <Include additional frequency profile data in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #363381
363389 | #363379 | Story | <Include additional frequency profile data in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #363381
363388 | #363379 | Story | <Include additional frequency profile data in Splunk index>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
363387 | #363379 | Story | <Include additional frequency profile data in Splunk index>:ILS IETM update (Template) | Unassigned | New | 3 | #363381
363386 | #363379 | Story | <Include additional frequency profile data in Splunk index> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #363381
363385 | #363379 | Story | <Include additional frequency profile data in Splunk index>: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #363382
363384 | #363379 | Story | <Include additional frequency profile data in Splunk index>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #363381
363383 | #363379 | Story | <Include additional frequency profile data in Splunk index> Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #363387
363382 | #363379 | Story | Feature 363379 freq Splunk index: IA Posture Assessment | Unassigned | New | 8 | #363381
363381 | #363379 | Story | Feature Demo – Customer Demo Event - <Include additional frequency profile data in Splunk index> | Unassigned | New | 1 | #363388
363380 | #363379 | Story | <Include additional frequency profile data in Splunk index>: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #363385
363347 | #243502 | Story | CM Release Work for EAD 14 Documents | EA 15.4 | Done | 1
363308 | #363293 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #363295
363307 | #363293 | Task | Hold Feature Review with SMEs | Unassigned | New
363306 | #363293 | Story | Feature 363293 UX Research and Design Support | Unassigned | New | 3
363305 | #363293 | Story | Feature 363293 ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
363304 | #363293 | Story | Feature 363293 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #363295
363303 | #363293 | Story | Feature 363293 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #363295
363302 | #363293 | Story | Feature 363293: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
363301 | #363293 | Story | Feature 363293:ILS IETM update (Template) | Unassigned | New | 3 | #363295
363300 | #363293 | Story | Feature 363293 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #363295
363299 | #363293 | Story | Feature 363293: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #363296
363298 | #363293 | Story | Feature 363293: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #363295
363297 | #363293 | Story | Feature 363293 Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #363301
363296 | #363293 | Story | Feature 363298: IA Posture Assessment | Unassigned | New | 8 | #363295
363295 | #363293 | Story | Feature Demo – Customer Demo Event - Feature 363293 | Unassigned | New | 1 | #363302
363294 | #363293 | Story | Feature 363293: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #363299
362958 | #1013136 | Problem | Techeval issue: Waveform fatal error during congestion test. | EA 16.1 | Close Pending
362885 |  | Problem | Remove p2pprov account from system | Unassigned | Assessing
362882 |  | Problem | Splunk sysadmin accounts not set up consistently across the 3 servers | Unassigned | Assessing
362873 |  | Problem | IETM Backup SGSN - Normal Operation Procedure update | Unassigned | Assessing
362724 | #345871 | Story | Lab - Maintain Labs: SA Lab Support (EA 11.1) | Unassigned | Invalid | 0
362703 |  | Story | CoC Node Changes in Apportionments and SARs: Review/Rework | Unassigned | Invalid | 0
362682 |  | Story | GEO SME support for Troubleshooting Low Hanging Fruit | Unassigned | Invalid | 0
362681 |  | Story | Splunk Software Update: Update DB Connect (VM) and Regression Tests | Unassigned | Invalid | 0
362674 |  | Story | GEO SME support for Troubleshooting Low Hanging Fruit | Unassigned | Invalid | 0
362651 | #352892 | Story | ULX Integration into ETISP: ULX Support (Gale 11.4) | Unassigned | Invalid | 0
362650 |  | Task | ULX Integration into ETISP: ULX Support (Gale 11.3) | Unassigned | Invalid
362648 | #352892 | Story | ULX Integration into ETISP: ULX Support (Jones 11.5) | Unassigned | Invalid | 0
362645 |  | Story | ULX Integration into ETISP: ULX Support (Jones 11.1) | Unassigned | Invalid | 0
362599 | #352893 | Story | Support of ADI/EMI/PRISM Integration: SME Support - (Tom 11.4) | Unassigned | Invalid | 0
362596 |  | Story | Placeholder for PI 12 | Unassigned | Invalid | 0
362584 |  | Story | Placeholder for PI 12 | Unassigned | Invalid | 0
362582 |  | Story | Placeholder for PI 12 | Unassigned | Invalid | 0
362557 |  | Story | Integrate AWARE into SA Dashboards: Placeholder | Unassigned | Invalid | 0
362532 |  | Story | Placeholder for PI 11 | Unassigned | Invalid | 0
362460 | #352946 | Story | Windows Server SHB: Review DISA Windows SHB Implementation Guidance | PI 16 | New | 5
362352 |  | Story | PM Performance Improvements – PM Server: Implement Unacknowledged messages in transit from FOUO to Secret. (Ramp-UP) | Unassigned | Invalid | 0
362344 |  | Story | Relocation - Splunk impacts and support: Send screenshots for Approval (Mike Syring) | Unassigned | Invalid | 0
362342 |  | Story | Juniper Routers have expired vendor certificates: Final Scans and Assessment | Unassigned | Invalid | 0
362341 |  | Story | Juniper Routers have expired vendor certificates: Final Posture Assessment Update | Unassigned | Invalid | 0
362339 |  | Story | Juniper Routers have expired vendor certificates: Load in VLab and execute STCD | Unassigned | Invalid | 0
362334 |  | Story | Integrate AWARE into SA Dashboards: (UX Designer) - Dashboard Development | Unassigned | Invalid | 0
362332 |  | Story | Integrate AWARE into SA Dashboards: Placeholder | Unassigned | Invalid | 0
362318 | #352946 | Story | Windows Server SHB: Input from HBSS SMEs | PI 16 | New | 1
362317 |  | Story | Feature 341794: Mapping a new spacecraft to its Service Region: OSS-RC SME support | Unassigned | Invalid | 0
362311 | #352946 | Story | Windows Server SHB: Integrate and verify HBSS client load | PI 16 | New | 1
362306 | #352946 | Story | Windows Server SHB: Close ports/protocols and verify closed | PI 16 | New | 3
362305 | #352946 | Story | Windows Server SHB: Remove unnecessary services and software | PI 16 | New | 5
362303 | #352946 | Story | Windows Server SHB: Identify minimal baseline capabilities | PI 16 | New | 3
362297 | #352946 | Story | Windows Server SHB: Hardware identified/validated | PI 16 | New | 2
362276 | #257550 | Story | Integrate AWARE into SA Dashboards: SME Support (11.2) | Unassigned | Invalid | 0
362249 |  | Story | Feature 350115: Evaluation of HW FRB Support | Unassigned | Invalid | 0
361135 | #354224 | Story | Quarterly support to PMW-146 for site IA assessment and data analysis - story A | Unassigned | Invalid | 0
361052 | #349974 | Story | SA Technical Support - EA 11.2 | Unassigned | Invalid | 0
361043 |  | Story | SA Trouble Ticket Support - EA 11.6 | Unassigned | Invalid | 0
361035 | #349985 | Story | MAGIC Trouble Ticket Support - EA 11.2 | Unassigned | Invalid | 0
361016 | #360121 | Story | GEO Troubleshooting Docs CoCo Review: UX IETM Creation | Unassigned | Invalid | 0
360938 |  | Story | Get SME Buy-In on v1 Wireframse SA Help/Troubleshooting: Site Development | Unassigned | Invalid | 0
360895 | #360121 | Story | Create the Site Functional Test Case (Splunk/GEO Troubleshooting Low Hanging Fruit) | Unassigned | Invalid | 0 | #360882
360889 | #360121 | Story | Initiate CM PDO Processing for all CI's (Splunk/GEO Troubleshooting Low Hanging Fruit): Engineering Docs | Unassigned | Invalid | 0
360887 | #360121 | Story | Agile Team Test- GEO Troubleshooting Low Hanging Fruit (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #360882
360886 | #360121 | Story | Splunk/GEO Troubleshooting Low Hanging Fruit: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #360883
360883 | #360121 | Story | Splunk/GEO Troubleshooting Low Hanging Fruit: IA Posture Assessment | Unassigned | Invalid | 0 | #360882
360881 | #360121 | Story | Splunk/GEO Troubleshooting Low Hanging Fruit: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #360886
360880 |  | Feature | <Feature xxx> | Unassigned | Rejected
360804 |  | Story | RF Alignment NW (Relocation): SME support for on-site work (week 1) - Nadolski | Unassigned | Invalid | 0
360802 |  | Story | RF Alignment NW (Relocation): SME support for on-site work (week 1) - Jones | Unassigned | Invalid | 0
360782 |  | Problem | ACAS Scanning Reachability for HSS | Unassigned | Assessing
360742 |  | Story | Fix Problem 327556: Add alarm recovery procedure for PM__9006 - IETM Creation | Unassigned | Invalid | 0
360739 |  | Story | Fix Problem 310530:Update alarm recovery procedure for PM 8001 - IETM Creation | Unassigned | Invalid | 0
360734 | #360073 | Story | Add JMS_1001 and JMS_1004 to Whitelist (Problem 329722) | Unassigned | Invalid | 0
360637 | #360622 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #360624
360636 | #360622 | Task | Hold Feature Review with SMEs | Unassigned | New
360635 | #360622 | Story | Feature 360622 UX Research and Design Support | Unassigned | New | 3
360634 | #360622 | Story | Feature 360622 ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
360633 | #360622 | Story | Feature 360622 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #360624
360632 | #360622 | Story | Feature 360622 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #360624
360631 | #360622 | Story | Feature 360622: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
360630 | #360622 | Story | Feature 360622: IETM Update for Update other File Transferring Equipment to use new Tectia Solution | Unassigned | New | 3 | #360624
360629 | #360622 | Story | Feature 360622 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #360624
360628 | #360622 | Story | Feature 360622: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #360625
360627 | #360622 | Story | Feature 360622: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #360624
360626 | #360622 | Story | Feature 360622 Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #360630
360625 | #360622 | Story | Feature 360622: IA Posture Assessment | Unassigned | New | 8 | #360624
360624 | #360622 | Story | Feature Demo – Customer Demo Event - Feature 360622 | Unassigned | New | 1 | #360631
360623 | #360622 | Story | Feature 360622: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #360628
360610 |  | Task | PM Performance Improvements – PM Server: Build OSS-RC Interface CI | Unassigned | Invalid
360546 |  | Problem | ATO Maintenance: T400XR - Backup/Audit | Unassigned | Assessing
360529 | #377405 | Problem | ATO Maintenance: T400XR - False Positives | PI 17 | Approved
360498 | #262985 | Story | Distribute AWARE Alarms/Events to NMS: MHAL Updates for Fault Notifier (Part 1) | Unassigned | Invalid | 0
360493 |  | Story | AWARE & MHAL Going Connected: I-Level webpage improvements | Unassigned | Invalid | 0
360446 |  | Problem | HAIPE Installation/Power Up Procedure Missing Steps to Delete and Rediscover Device in GEM One | Unassigned | Assessing
360442 |  | Problem | Update TACLANE Configuration files to Add Circuit ID to the Device Name in Parenthesis | Unassigned | Assessing
360433 | #360418 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #360420
360432 | #360418 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
360431 | #360418 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
360430 | #360418 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
360429 | #360418 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #360420
360428 | #360418 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #360420
360427 | #359876 | Story | OBS - Baseline Image of RHEL 7.X: Add RHEL 7.x image to Clear Case | Unassigned | Invalid | 0
360426 | #360418 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #360420
360424 | #360418 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #360421
360423 | #360418 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #360420
360422 | #360418 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #360426
360420 | #360418 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #360427
360418 |  | Feature | <Feature xxx> | Unassigned | Rejected
360414 |  | Task | OBS - Baseline Image of RHEL 7.X: ESAC for stig config scripts | Unassigned | Invalid
360406 | #360092 | Story | PM Reliability: Update CIs for Tectia Solution - SIEM (SFTP Copier) | Unassigned | Invalid | 0
360390 | #360092 | Story | PM Reliability: Update CIs for Tectia Solution - SIEM (SFTP Copier) | Unassigned | Invalid | 0
360386 | #360092 | Story | PM Reliability: Regression Test Other Equipment that does File Transfers | Unassigned | Invalid | 0
360294 | #1001912 | Problem | MUOSAT-SP: MGEN tab broken starting with SoftPhone 3.0 | EA 15.1 | Closed
360293 | #376446 | Problem | MUOSAT-SP: Notify automation when 'Waveform Launch Failure' occurs, and similar errors | EA 15.3 | Closed
360292 | #376446 | Problem | MUOSAT-SP: Pass TX denied reason code to MHAL | EA 15.3 | Closed
360286 | #376446 | Problem | MUOSAT-SP: Bootstrap provisioning doesn't work in SoftPhone starting with version 3.0 | EA 15.3 | Closed
360283 | #1001912 | Problem | MUOSAT-SP: Dialed digits should not be checked in PtN calls. | EA 15.1 | Closed
360281 | #376446 | Problem | MUOSAT-SP: Group join retry code prevents softphone shutdown | EA 15.3 | Closed
360275 | #1001912 | Problem | MUOSAT-SP: Display Rx Signal Strength | EA 15.1 | Closed
360271 | #1001912 | Problem | MUOSAT-SP: Document Build Environment Setup | EA 15.1 | Closed
360268 | #1001912 | Problem | MUOSAT-SP: Don't allow user to press group join button more than once | EA 15.1 | Closed
360155 | #360140 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #360142
360152 | #360140 | Story | Feature 360140 ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
360151 | #360140 | Story | Feature 360140 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #360142
360150 | #360140 | Story | Feature 360140 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #360142
360147 | #360140 | Story | Feature 360140 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #360142
360146 | #360140 | Story | Feature 360140: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #360143
360144 | #360140 | Story | Feature 360140 Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #360148
360143 | #360140 | Story | Feature 360140: IA Posture Assessment | Unassigned | Invalid | 0 | #360142
360141 | #360140 | Story | Feature 360140: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #360146
360123 | #378659 | Feature | Investigate Missed ETI_5000 (bad CPICH) set/clear traps in Splunk | Unassigned | Rejected |  | #378236
360107 | #360092 | Story | PM Performance Improvements – PM Clients: Create the Site Functional Test Case | Unassigned | Invalid | 0 | #360094
360106 | #360092 | Task | PM Performance Improvements – PM Clients: Hold Feature Review with SMEs | Unassigned | Invalid
360105 | #360092 | Story | PM Performance Improvements  PM Clients: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
360104 | #360092 | Story | PM Performance Improvements – PM Clients: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
360103 | #360092 | Story | PM Performance Improvements – PM Clients: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #360094
360102 | #360092 | Story | PM Performance Improvements – PM Clients: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #360094
360101 | #360092 | Story | PM Performance Improvements – PM Clients: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
360100 | #360092 | Story | PM Performance Improvements – PM Clients: ILS IETM update (Template) | Unassigned | Invalid | 0 | #360094
360099 | #360092 | Story | PM Performance Improvements – PM Clients: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #360094
360098 | #360092 | Story | PM Performance Improvements – PM Clients: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #360095
360097 | #360092 | Story | PM Performance Improvements – PM Clients: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #360094
360096 | #360092 | Story | PM Performance Improvements – PM Clients: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #360100
360095 | #360092 | Story | PM Performance Improvements – PM Clients: IA Posture Assessment | Unassigned | Invalid | 0 | #360094
360094 | #360092 | Story | Feature Demo – Customer Demo Event - Feature 360092: PM Performance Improvements – PM Clients | Unassigned | Invalid | 0 | #360101
360093 | #360092 | Story | PM Performance Improvements – PM Clients: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #360098
360081 | #360073 | Story | PM Performance Improvements – IETM:ILS IETM update (Template) | Unassigned | Invalid | 0 | #360075
360076 |  | Story | Feature 360073: IA Posture Assessment | Unassigned | Invalid | 0 | #360075
360056 | #338100 | Feature | Review and prioritize any open GEO availability and robustness issues | Unassigned | Rejected
360046 |  | Problem | ACAS Scanning Reachability for CSCF | Unassigned | Assessing
359983 | #245573 | Feature | SCS Work Placeholder | PI 17 | Draft
359804 |  | Problem | Update Netcool so that 'available' alarm clears 'unavailable' alarm for HPHLR Time Synchronization | Unassigned | Assessing
359582 | #359567 | Story | Create the Site Functional Test Case | PI 14 | Invalid | 0 | #359569
359581 | #359567 | Task | Hold Feature Review with SMEs | PI 14 | Invalid
359580 | #359567 | Story | Feature 359567 UX Research and Design Support | PI 14 | Invalid | 0
359579 | #359567 | Story | Feature 359567 ILS IETM Development and Integration updates part 1 of N | PI 14 | Invalid | 0
359578 | #359567 | Story | Feature 359567 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 14 | Invalid | 0 | #359569
359577 | #359567 | Story | Feature 359567 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 14 | Invalid | 0 | #359569
359576 | #359567 | Story | Feature 359567: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
359575 | #359567 | Story | Feature 359567: IETM Update for Add Disc Nearing Capacity Alarms to the Whitelist | PI 14 | Invalid | 0 | #359569
359574 | #359567 | Story | Feature 359567 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 14 | Invalid | 0 | #359569
359573 | #359567 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | PI 14 | Invalid | 0 | #359570
359572 | #359567 | Story | Feature 359567: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 14 | Invalid | 0 | #359569
359571 | #359567 | Story | Feature 359567 Engineering IETM Development and Integration updates part 1 of N | PI 14 | Invalid | 0 | #359575
359570 | #359567 | Story | <Feature xxx> IA Posture Assessment | PI 14 | Invalid | 0 | #359569
359569 | #359567 | Story | Feature Demo – Customer Demo Event - Feature 359567 | PI 14 | Invalid | 0 | #359576
359568 | #359567 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | PI 14 | Invalid | 0 | #359573
359567 | #245566 | Feature | Add disk nearing capacity alarms to the whitelist | Unassigned | Rejected
359536 |  | Problem | TFDU Alarming Unreliable | Unassigned | Assessing
359342 |  | Problem | Alarm Recovery PLN_9985: Unable to Analyze a Carrier Config | Unassigned | Assessing
359338 | #381524 | Problem | Alarm Recovery GP__9022: Clarify which section to perform of Referenced Procedure | EA 15.3 | Closed
359118 | #390441 | Story | Develop and Deploy Updated Branching and Merging Process | PI 15 | Invalid | 0
359107 |  | Task | Support of ADI/EMI/PRISM Integration: SME Support - (Tom 11.3) | Unassigned | Invalid
359095 | #325227 | Problem | ATO Maintenance: FM Servers - Password Complexity | Unassigned | Assessing
358997 |  | Story | HBSS Support for Adversarial Assessment Cyber Testing Week 2 | Unassigned | Invalid | 0
358956 | #352892 | Story | ULX Integration into ETISP: ULX Support (Rich 11.6) | Unassigned | Invalid | 0
358936 | #330187 | Story | SV Relocation - Geolocation impacts: Update HBSS kernel module for GEO | Unassigned | Invalid | 0
358881 | #216364 | Feature | Updates for ET Alarm Recovery Procedures [O-Level - Needs Updates] | PI 17 - Candidate | Analyzing
358876 | #355216 | Task | RF Alignment NW (Relocation): Tracking Knowledge Transfer - 11.2 | Unassigned | Invalid
358866 |  | Problem | Extreme switch replacement error | Unassigned | Assessing
358839 |  | Feature | Feature 358839: CVPA Remediation - TOFF (PI 11 Re-Baseline) | Unassigned | Rejected
358775 |  | Problem | Redline to OTAP instructions in the PKI Deployment Plan | Unassigned | Assessing
358753 | #358738 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #358740
358752 | #358738 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
358751 | #358738 | Story | Feature 358738 UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
358750 | #358738 | Story | Feature 358738 ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
358749 | #358738 | Story | Feature 358738 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #358740
358748 | #358738 | Story | Feature 358738 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #358740
358747 | #358738 | Story | Feature 358738: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
358745 | #358738 | Story | Feature 358738 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #358740
358744 | #358738 | Story | Feature 358738: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #358741
358743 | #358738 | Story | Feature 358738: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #358740
358742 | #358738 | Story | Feature 358738 Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #358746
358741 | #358738 | Story | Feature 358738: IA Posture Assessment | Unassigned | Invalid | 0 | #358740
358740 | #358738 | Story | Feature Demo – Customer Demo Event - Feature 358738 | Unassigned | Invalid | 0 | #358747
358739 | #358738 | Story | Feature 358738: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #358744
358738 | #243395 | Feature | Address PM Performance Improvements for SA - Part 2 | Unassigned | Rejected
358717 |  | Story | ROI Analysis | Unassigned | Invalid | 0
358712 | #1001062 | Story | Tools Team Support - Troubleshoot UE and Cell Timeout using full automated build system (RDE) | EA 15.5 | Invalid | 0
358692 | #358755 | Story | ROM for TT&C - Obsolescence | Unassigned | Invalid | 0
358691 | #358755 | Story | ROM for TT&C - Systems Engineering | Unassigned | Invalid | 0
358671 |  | Story | Create STCD Including Site Functional Tests | Unassigned | Invalid | 0
358670 | #358656 | Task | Feature 358656: Feature Review with SMEs | EA 15.1 | Done
358669 |  | Story | Feature 358656: ET Alarm Recovery Procedures IETM Style Guide Review and Dry Run (Part 1) | Unassigned | Invalid | 0
358668 |  | Story | Feature 358656: IETM Development and Integration Updates for Address Missing and "Not Appropriate for O-Level Operator" ET Alarm Recovery Procedures | Unassigned | Invalid | 0
358667 |  | Story | Feature 358656 Create and Test New ET Alarm Recovery Procedures Part 2 of 2 | Unassigned | Invalid | 0 | #358658
358666 |  | Story | Feature 358656 Create and Test New ET Alarm Recovery Procedures Part 1 of 2 | Unassigned | Invalid | 0 | #358658
358665 |  | Story | Feature 358656: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
358664 | #358656 | Story | Feature 358656: IETM Update for Addressing the Missing and "Not Appropriate for O-level Operator" ET Alarm Recovery Procedures | EA 15.4 | Done | 2 | #358658
358663 | #358656 | Story | Feature 358656 Test New and Existing Procedures | EA 15.4 | Implementing | 5 | #358658
358662 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #358659
358661 | #358656 | Story | Feature 358656: Deployment Notes and Operator Impact Inputs | EA 16.1 | New | 1 | #358658
358660 | #358656 | Story | Feature 358656 Engineering ET IETM Development and Integration updates (Part 6 - No Procedures Exist) | EA 16.1 | New | 5 | #358664
358659 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #358658
358658 | #358656 | Story | Feature 358656: Feature Demo – Prep and Customer Demo Event | EA 16.1 | New | 3 | #358665
358657 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #358662
358656 | #216364 | Feature | TO-4: Address Missing and "Not Appropriate for O-level Operator" ET Alarm Recovery Procedures | PI 16 - In Progress | Implementing
358572 | #325227 | Problem | ATO Maintenance: FM Servers - General Configuration Settings to resolve Cyber RMF Findings - part 1 | Unassigned | Assessing
358528 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #358515
358527 |  | Task | Hold Feature Review with SMEs | Unassigned | Invalid
358526 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
358525 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
358524 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #358515
358523 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #358515
358522 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
358472 | #352892 | Task | ULX Integration into ETISP: Help define options to provide a viable U2B interface for ULX in Hawaii | Unassigned | Invalid
358429 | #325227 | Problem | ATO Maintenance: FM Servers - Fix run control scripts world execution privileges | Unassigned | Assessing
358349 |  | Story | Feature Demo - Customer Demo Event - Feature 358113: CVPA Remediation - SNMP and LB | Unassigned | Invalid | 0
358322 | #325227 | Problem | ATO Maintenance: FM Servers - Remove .rhosts, etc. OBE | Unassigned | Assessing
358182 | #1013452 | Problem | Redlines for Firewall Network SVD(98-P55755M) from EAD-10 Deployment | PI 16 | Approved
358180 | #342163 | Task | Rebase MPC 11.5 (Problem 355000) | EA 15.3 | Done
358154 |  | Problem | UEs on APN11 and APN12 can not initiate isakmp connections with NIPRNET HAIPE due to firewall blocking traffic | Unassigned | Assessing
358128 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #358115
358127 |  | Task | Hold Feature Review with SMEs | Unassigned | Invalid
358126 | #358113 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
358124 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #358115
358123 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #358115
358121 | #358113 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #358115
358119 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #358116
358116 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #358115
358115 |  | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #358122
358114 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #358119
358111 |  | Task | Hold Feature Review with SMEs | Unassigned | Invalid
358108 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #358099
358107 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #358099
358103 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #358100
358100 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #358099
358098 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #358103
358034 | #354847 | Story | Create features for AJM execution | Unassigned | New | 5
358032 | #354847 | Story | Timeline for RTLOGIC AJM Delivery | Unassigned | New | 5
358014 | #354847 | Story | Work with sub-contract management to get RTLOGIC under contract | Unassigned | New | 3
357946 | #342163 | Problem | GEM One FALSE critical faults associated with topology widget | EA 15.1 | Closed
356950 | #356946 | Story | Re-apply STCD Problem 329746 Story | Unassigned | Invalid | 0
356949 | #356946 | Story | Re-apply Problem 329746 Story | Unassigned | Invalid | 0 | #356950
356948 | #356946 | Story | Rebase STCD Problem 329746 Story | Unassigned | Invalid | 0
356946 | #353840 | Feature | MPC for Problem 329746 (SA) found in Pre EAD 10 Deliveries | Unassigned | Rejected
356945 | #342163 | Story | Feature 342163: Update TACLANE STCD (including IETM procedures) - EA 15.3 | EA 15.3 | Done | 2
356858 |  | Story | Splunk Data migration plan and instructions: Determine feasibility of soak testing | Unassigned | Invalid | 0
356851 |  | Problem | ScGeoStatusCollector service begame 'hung' while waiting a result from remote SOAP invocation of TPM workflow. | Unassigned | Assessing
356632 | #356628 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
356631 | #356628 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #356632
356630 | #356628 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
356629 | #356628 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #356630
356628 | #353840 | Feature | MPC for Problem xxx (Cyber Issue- Derek Johnson working) found in Pre EAD 10 Deliveries | Unassigned | Rejected
356604 | #356600 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
356603 | #356600 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #356604
356602 | #356600 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
356601 | #356600 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #356602
356600 | #356599 | Feature | MPC for Problem xxx (Cyber Issue- Derek Johnson Working) found in EAD 10 Deliveries | Unassigned | Rejected
356520 | #351017 | Story | Feature 351017 HBSS Feature SVD reviews and redlines Sprint 4 | Unassigned | New | 3
356519 | #351017 | Story | Feature 351017 HBSS Feature SVD Updates Sprint 3 | Unassigned | New | 3
356518 | #351017 | Story | Feature 351017 HBSS Feature SVD Updates Sprint 2 | Unassigned | New | 3
356512 | #351017 | Story | Feature 351017: IA Posture Assessment | Unassigned | New | 2
356509 | #351017 | Story | Feature Demo Prep - Feature 351017: | Unassigned | New | 2
356416 | #343253 | Story | Feature 343253: Cabinet Drawing Updates for the Misc RAID Array Enhancements | Unassigned | New | 2
356407 | #343253 | Story | Feature 343253: Drawing Updates for the Misc RAID Array Enhancements | Unassigned | New | 2
356242 |  | Problem | AmsStatusAdapter code should be modified to react consistently to malformed SFRE data | Unassigned | Assessing
356235 |  | Problem | ATO Maintenance: STIG alignment for Windows 2012 inf servers; i) Acct Mgmt. | Unassigned | Assessing
356200 |  | Problem | ATO Maintenance: Windows 2012 inf servers a) Password Complexity | Unassigned | Assessing
356146 | #356131 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #356133
356145 | #356131 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
356144 | #356131 | Story | Feature 356131 UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
356143 | #356131 | Story | Feature 356131 ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
356142 | #356131 | Story | Feature 356131 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #356133
356141 | #356131 | Story | Feature 356131 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #356133
356140 | #356131 | Story | Feature 356131: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
356138 | #356131 | Story | Feature 356131 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #356133
356137 | #356131 | Story | Feature 356131: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #356134
356136 | #356131 | Story | Feature 356131: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #356133
356135 | #356131 | Story | Feature 356131 Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #356139
356134 | #356131 | Story | Feature 356131: IA Posture Assessment | Unassigned | Invalid | 0 | #356133
356133 | #356131 | Story | Feature Demo – Customer Demo Event - Feature 356131 | Unassigned | Invalid | 0 | #356140
356132 | #356131 | Story | Feature 356131: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #356137
356131 | #245573 | Feature | Resolve Use of 3 ETISPs during Spare Housekeeping | Unassigned | Rejected
356124 |  | Story | Feature 328477 Agile Team Test: Update Feature STCD for Problem 329620 - EA 10.5 | Unassigned | Invalid | 0
356118 |  | Story | Feature 355026: PWI for Change SNMP version on LBs | Unassigned | Invalid | 0
356117 |  | Story | Feature 355026: PWI for Win10 workstations | Unassigned | Invalid | 0
356116 |  | Story | Feature 355026: PWI for AMS-GS database server | Unassigned | Invalid | 0
356115 |  | Story | Feature 355026: PWI for Change passwords on gis and open NFS | Unassigned | Invalid | 0
356114 |  | Story | Feature 355026: MPC for Change passwords on obk11, ocm11 and otp11 | Unassigned | Invalid | 0
356113 |  | Story | Feature 355026: PWI for changing passwords on ups10x-yy-fms | Unassigned | Invalid | 0
356109 | #356094 | Story | Feature 356094: Create the Site Functional Test Case | PI 15 | Invalid | 0 | #356096
356108 | #356094 | Task | Feature 356094: Hold Feature Review with SMEs | PI 15 | Invalid
356107 | #356094 | Story | Feature 356094 False Report of Cell Failures during ET switchover- UX Support for SA Help | PI 15 | Invalid | 0
356106 | #356094 | Story | Feature 356094 ILS IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
356105 | #356094 | Story | Feature 356094 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | PI 15 | Invalid | 0 | #356096
356104 | #356094 | Story | Feature 356094 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | PI 15 | Invalid | 0 | #356096
356103 | #356094 | Story | Feature 356094: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
356102 | #356094 | Story | Feature 356094: IETM Update for Resolve False Report of Cell Failures by SA Dashboards during ET switchover | PI 15 | Invalid | 0 | #356096
356101 | #356094 | Story | Feature 356094 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | PI 15 | Invalid | 0 | #356096
356100 | #356094 | Story | Feature 356094: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #356097
356099 | #356094 | Story | Feature 356094: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #356096
356098 | #356094 | Story | Feature 356094 Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #356102
356097 | #356094 | Story | Feature 356094: IA Posture Assessment | PI 15 | Invalid | 0 | #356096
356096 | #356094 | Story | Feature Demo – Customer Demo Event - Feature 356094 | PI 15 | Invalid | 0 | #356103
356095 | #356094 | Story | Feature 356094: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #356100
356094 | #225732 | Feature | ETI - Resolve False Report of Cell Failures by SA Dashboards during ET switchover | Unassigned | Rejected
356042 |  | Problem | Splunk server /var/spool/mail/root files are filling up | Unassigned | Assessing
356030 |  | Story | PI 11 MAGIC MOT&E TT support | Unassigned | Invalid | 0
356029 |  | Story | PI 11 SA MOT&E TT support | Unassigned | Invalid | 0
355962 | #355947 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #355949
355961 | #355947 | Task | Hold Feature Review with SMEs | Unassigned | New
355960 | #355947 | Story | Feature 355947 UX Research and Design Support | Unassigned | New | 3
355959 | #355947 | Story | Feature 355947 ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
355958 | #355947 | Story | Feature 355947 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #355949
355957 | #355947 | Story | Feature 355947 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #355949
355956 | #355947 | Story | Feature 355947: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
355955 | #355947 | Story | Feature 355947:ILS IETM update (Template) | Unassigned | New | 3 | #355949
355954 | #355947 | Story | Feature 355947 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #355949
355953 | #355947 | Story | Feature 355947: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #355950
355952 | #355947 | Story | Feature 355947: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #355949
355951 | #355947 | Story | Feature 355947 Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #355955
355950 | #355947 | Story | Feature 355947: IA Posture Assessment | Unassigned | New | 8 | #355949
355949 | #355947 | Story | Feature Demo – Customer Demo Event - Feature 355947 | Unassigned | New | 1 | #355956
355948 | #355947 | Story | Feature 355947: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #355953
355947 | #243410 | Feature | Feature 355947: Upgrade GEM One to Latest Version | PI 17 | Draft
355910 | #355895 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #355897
355909 | #355895 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
355907 | #355895 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355906 | #355895 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #355897
355905 | #355895 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #355897
355904 | #257556 | Story | Feature 257556: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355903 | #257556 | Task | Feature 257556: IETM Update for Providing AWARE Fault Recovery Procedures | Unassigned | Invalid |  | #355897
355902 |  | Story | Feature 257556 - Recovery Procedures: Demo 3 - Agile Team Test (Install, PCR Verification) | Unassigned | Invalid | 0
355901 | #355895 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #355898
355898 | #355895 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #355897
355896 | #355895 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #355901
355895 |  | Feature | <Feature xxx> | Unassigned | Rejected
355808 | #342000 | Story | Feature 342000: Connected AWARE IETMs - Update task analysis | Unassigned | Invalid | 0
355791 |  | Story | Juniper Routers have expired vendor certificates: IA Create Posture Assessment (Part 2) | Unassigned | Invalid | 0
355783 |  | Story | Juniper Routers have expired vendor certificates: Apply patches and STIGs | Unassigned | Invalid | 0
355735 | #355661 | Story | Feature 355661: Create and Test Site Validation Plan | Unassigned | Invalid | 0
355734 | #355661 | Story | Feature 355661: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
355731 |  | Story | Splunk Software Update: UX IETM Review | Unassigned | Invalid | 0
355729 | #355718 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #355720
355728 | #355718 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #355720
355726 | #355718 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #355720
355722 |  | Story | Splunk Software Update: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355721 |  | Story | Splunk Software Update: IA Posture Assessment (David) | Unassigned | Invalid | 0
355718 |  | Feature | <Feature xxx> | Unassigned | Rejected
355709 | #355661 | Story | Feature 355661: Update ETISP Build Tools to Support Linux | Unassigned | Invalid | 0
355708 | #355661 | Story | Feature 355661: Update SVD for ETISP (UX) | Unassigned | Invalid | 0
355707 | #355661 | Story | Feature 355661: Update SVD for ETISP | Unassigned | Invalid | 0
355705 | #355661 | Story | Feature 355661: Create Posture Assessment for Feature | Unassigned | Invalid | 0
355704 | #355661 | Story | Feature 355661: STIG and Scan ETISP Feature | Unassigned | Invalid | 0
355703 | #355661 | Story | Feature 355661: Create Posture Assessment Template | Unassigned | Invalid | 0
355702 | #355661 | Story | Feature 355661: PDO Release Feature | Unassigned | Invalid | 0
355701 | #355661 | Story | Feature 355661: Update IETM for ETISP (ILS) | Unassigned | Invalid | 0
355700 | #355661 | Story | Feature 355661: Update IETM for ETISP (UX) | Unassigned | Invalid | 0
355698 | #355661 | Story | Feature 355661: Update IETM for ETISP | Unassigned | Invalid | 0
355697 | #355661 | Story | Feature 355661: Prep and Hold Feature Demo | Unassigned | Invalid | 0
355696 | #355661 | Story | Feature 355661: Load in VLab and Execute STCD | Unassigned | Invalid | 0
355694 | #355661 | Story | Feature 354159: Perform Software Integration in VLab | Unassigned | Invalid | 0
355669 | #355661 | Story | Feature 355661: Implement design and perform development testing (4) | Unassigned | Invalid | 0
355668 | #355661 | Story | Feature 355661: Implement design and perform development testing (3) | Unassigned | Invalid | 0
355667 | #355661 | Story | Feature 355661: Implement design and perform development testing (2) | Unassigned | Invalid | 0
355665 | #355661 | Story | Feature 355661: Implement design and perform development testing (1) | Unassigned | Invalid | 0
355663 | #355661 | Story | Feature 355661: SME Support for support of ETISP OS Upgrade | Unassigned | Invalid | 0
355662 | #355661 | Story | Feature 355661: SME Support for support of ETISP OS Upgrade | Unassigned | Invalid | 0
355629 |  | Story | Feature 355026: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) (Change SNMP version on LBs) | Unassigned | Invalid | 0
355628 | #351017 | Story | Feature 351017 Win2012R2 STIGs Update | Unassigned | New | 8
355623 |  | Story | Feature 355026: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) (AMS-GS database server) | Unassigned | Invalid | 0
355620 |  | Task | Story 343914: CM Release of 98-P55483M – OS – WindowsServer2012 – SVD (EAD 14) | Unassigned | New
355601 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Proxy LB Server Correct Certificate Authority Findings Remedy - implement fix | Unassigned | Invalid | 0
355531 | #355230 | Story | Feature Demo – Customer Demo Event - ETT Redlines for Feature 355230 | Unassigned | Invalid | 0
355530 | #355230 | Story | Feature 355230: RF Alignment: Post Travel Data Analysis & Archiving - Nadolski | Unassigned | Invalid | 0
355529 | #355230 | Story | Feature 355230: RF Alignment: Post Travel Data Analysis & Archiving - Jones | Unassigned | Invalid | 0
355528 | #355230 | Story | Feature 355230: Engineering Procedure Development and Integration updates | Unassigned | Invalid | 0
355527 | #355230 | Story | Feature 355230: ETT Updates - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
355526 | #355230 | Story | Feature 355230: ETT Updates - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355525 | #355230 | Story | Feature 355230: ETT Updates - Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
355523 | #355230 | Story | Feature 355230: ETT Redlines - Review Close Out and Build Request | Unassigned | Invalid | 0
355522 | #355230 | Story | Feature 355230: ETT Redlines - Initiate CoCo Review and address comments | Unassigned | Invalid | 0
355521 | #355230 | Story | Feature 355230: ETT Redlines - Update ETT SVD | Unassigned | Invalid | 0
355520 | #355230 | Story | Feature 355230: RF Alignment: SME support for on-site work (week 2) - Nadolski | Unassigned | Invalid | 0
355519 | #355230 | Story | Feature 355230: RF Alignment: SME support for on-site work (week 2) - Jones | Unassigned | Invalid | 0
355518 | #355230 | Story | Feature 355230: RF Alignment: SME support for on-site work (week 1) - Nadolski | Unassigned | Invalid | 0
355517 | #355230 | Story | Feature 355230: RF Alignment: SME support for on-site work (week 1) - Jones | Unassigned | Invalid | 0
355516 | #355230 | Story | Feature 355230: RF Alignment: Logistics actions to support site activity (Rich) | Unassigned | Invalid | 0
355515 | #355230 | Story | Feature 355230: RF Alignment: Logistics actions to support site activity (Glen J) | Unassigned | Invalid | 0
355514 | #355230 | Story | Feature 355230: RF Alignment: Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355513 | #355230 | Story | Feature 355230: RF Alignment: Prep tasks to facilitate site Trip - Jones | Unassigned | Invalid | 0
355512 | #355230 | Story | Feature 355230: RF Alignment: Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355511 | #355230 | Story | Feature 355230: RF Alignment: Prep tasks to facilitate site Trip - Jones | Unassigned | Invalid | 0
355509 | #360140 | Story | Feature Demo  Customer Demo Event - ETT Redlines for Feature 355229 | Unassigned | Invalid | 0
355508 |  | Story | Feature 355229: RF Alignment: Post Travel Data Analysis & Archiving - Nadolski | Unassigned | Invalid | 0
355507 | #355229 | Story | Feature 355229: Tracking Alignment: Post Travel Data Analysis & Archiving - Engineer 1 | EA 14.5 | Done | 3
355506 | #360140 | Story | Feature 355229: Engineering Procedure Development and Integration updates | Unassigned | Invalid | 0
355504 | #360140 | Story | Feature 355229: ETT Updates - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355503 | #360140 | Story | Feature 355229: ETT Updates - Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
355498 |  | Story | Feature 355229: RF Alignment: SME support for on-site work (week 2) - Nadolski | Unassigned | Invalid | 0
355497 | #355229 | Story | Feature 355229: Tracking Alignment: SME support for on-site work - Engineer 1 (Sprint 3) | EA 14.4 | Done | 8
355496 |  | Story | Feature 355229: RF Alignment: SME support for on-site work (week 1) - Nadolski | Unassigned | Invalid | 0
355495 | #355229 | Story | Feature 355229: Tracking Alignment: SME support for on-site work - Engineer 1 (Sprint 2) | EA 14.3 | Done | 8
355494 |  | Story | Feature 355229: RF Alignment: Logistics actions to support site activity (Rich) | Unassigned | Invalid | 0
355492 |  | Story | Feature 355229: RF Alignment: Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355491 |  | Story | Feature 355229: RF Alignment: Prep tasks to facilitate site Trip - Jones | Unassigned | Invalid | 0
355490 |  | Story | Feature 355229: RF Alignment: Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355487 |  | Story | Feature Demo – Customer Demo Event - ETT Redlines for Feature 355228: RF Alignment Site # 3 (Relocation) | Unassigned | Invalid | 0
355486 | #355228 | Story | RF Alignment Site # 3 (Relocation): Post Travel Data Analysis & Archiving - Engineer 2 | Unassigned | Invalid | 0
355485 | #355228 | Story | Feature 355228: Post Travel Data Analysis & Archiving - Engineer 1 | EA 14.5 | Done | 1
355484 | #342786 | Story | Feature 342786: Engineering Procedure Development and Integration updates | PI 15 | Invalid | 0
355483 | #342786 | Story | Feature 342786: ETT Updates - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | PI 15 | Invalid | 0
355482 | #342786 | Story | Feature 342786: ETT Updates - Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
355481 | #342786 | Story | Feature 342786: ETT Updates - Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0
355480 | #342786 | Story | Feature 342786: IETM Updates for ETT Redlines | PI 15 | Invalid | 0
355479 | #342786 | Story | Feature 342786: ETT Redlines - Review Close Out and Build Request | PI 15 | Invalid | 0
355478 | #342786 | Story | Feature 342786: ETT Redlines - Initiate CoCo Review and address comments | PI 15 | Invalid | 0
355477 | #342786 | Story | Feature 342786: ETT Redlines - Update ETT SVD | PI 15 | Invalid | 0
355475 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 2 - Week 1 | EA 14.2 | Done | 5
355474 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 3 - Week 1 | EA 14.3 | Done | 5
355473 | #355228 | Story | RF Alignment Site # 3 (Relocation): SME support for on-site work - Engineer 2 (Sprint 3) | Unassigned | Invalid | 0
355470 | #355228 | Story | RF Alignment Site # 3 (Relocation): SME support for on-site work - Engineer 2 (Sprint 5) | Unassigned | Invalid | 0
355469 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 5 - Week 1 | EA 14.5 | Done | 3
355468 | #355228 | Story | RF Alignment Site # 3 (Relocation): SME support for on-site work - Engineer 2 (Sprint 4) | Unassigned | Invalid | 0
355467 | #355228 | Story | Feature 355228: SME support for on-site work - Sprint 4 - Week 1 | EA 14.4 | Done | 5
355465 | #355227 | Story | Feature Demo  Customer Demo Event - ETT Redlines for Feature 355227 | Unassigned | Invalid | 0
355462 | #355227 | Story | Feature 355227: Engineering Procedure Development and Integration updates | Unassigned | Invalid | 0
355461 | #355227 | Story | Feature 355227: ETT Updates - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
355460 | #355227 | Story | Feature 355227: ETT Updates - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355459 | #355227 | Story | Feature 355227: ETT Updates - Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
355458 | #355227 | Story | Feature 355227: IETM Updates for ETT Redlines | Unassigned | Invalid | 0
355457 | #355227 | Story | Feature 355227: ETT Redlines - Review Close Out and Build Request | Unassigned | Invalid | 0
355456 | #355227 | Story | Feature 355227: ETT Redlines - Initiate CoCo Review and address comments | Unassigned | Invalid | 0
355455 | #355227 | Story | Feature 355227: ETT Redlines - Update ETT SVD | Unassigned | Invalid | 0
355448 |  | Story | RF Alignment Site - SC:Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355446 |  | Story | RF Alignment Site - SC:Prep tasks to facilitate site Trip - Nadolski | Unassigned | Invalid | 0
355444 | #355227 | Story | Feature 355227 - RF Alignment Site - SC: Coordinate Visitor Requests for SC | Unassigned | Invalid | 0
355372 | #355075 | Story | Create the Site Functional Test Case | PI 15 | Invalid | 0 | #355359
355371 | #355075 | Task | Hold Feature Review with SMEs | PI 15 | Invalid
355370 | #355075 | Story | Feature 355075: Firewall PWIs IETMs Review for Style Guide Compliance and Dry Runs | PI 15 | Invalid | 0
355369 |  | Story | Feature 355075: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355368 | #1021037 | Problem | Interior routers are routing packets to the incorrect interfaces | PI 16 | Ready for IRM Approval
355367 | #355075 | Story | Feature 355075: Agile Team Test (STCD Dev & Test) | PI 15 | Invalid | 0 | #355359
355366 | #355075 | Story | Feature 355075: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
355365 | #355075 | Story | Feature 355075: IETM Update for Firewall PWI Burn Down | PI 15 | Invalid | 0 | #355359
355364 | #355075 | Story | Feature 355075: Agile Team Test (Install & PCR Verification) | PI 15 | Invalid | 0 | #355359
355363 | #355075 | Story | Feature 355075: IA Patching and STIGs Part 1 of N | PI 15 | Invalid | 0 | #355360
355362 | #355075 | Story | Feature 355075: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #355359
355361 | #355075 | Story | Feature 355075 Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #355365
355360 | #355075 | Story | Feature 355075 IA Posture Assessment | PI 15 | Invalid | 0 | #355359
355359 | #355075 | Story | Feature Demo – Customer Demo Event - Feature 355075 | PI 15 | Invalid | 0 | #355366
355358 | #355075 | Story | Feature 355075: IA - Define Patch/ Stig Requirements | PI 15 | Invalid | 0 | #355363
355357 |  | Feature | <Feature xxx> | Unassigned | Rejected
355347 | #383110 | Problem | Splunk reported radios operating in NW cells could access WH static IP addresses when WH RAF was disconnected | Unassigned | Approved
355290 |  | Story | Invalid | Unassigned | Invalid | 0
355289 |  | Story | Feature 355216: RF Alignment: Post Travel Data Analysis & Archiving - Nadolski | Unassigned | Invalid | 0
355287 | #355216 | Story | RF Alignment NW (Relocation): Engineering Procedure Development and Integration updates | Unassigned | Invalid | 0
355286 | #355216 | Story | RF Alignment NW (Relocation): ETT Updates - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
355285 | #355216 | Story | RF Alignment NW (Relocation): ETT Updates - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355284 |  | Story | Invalid | Unassigned | Invalid | 0
355283 | #355216 | Story | Feature 355216: IETM Updates for ETT Redlines | Unassigned | Invalid | 0
355282 |  | Story | Invalid | Unassigned | Invalid | 0
355281 |  | Story | Feature 355216: ETT Redlines - Initiate CoCo Review and address comments | Unassigned | Invalid | 0
355280 |  | Story | Invalid | Unassigned | Invalid | 0
355275 |  | Story | Feature 355216: RF Alignment: Logistics actions to support site activity (Rich) | Unassigned | Invalid | 0
355274 |  | Story | Feature 355216: RF Alignment: Logistics actions to support site activity (Glen J) | Unassigned | Invalid | 0
355269 | #355216 | Story | Feature 355216: RF Alignment NW (Relocation) - Logistics actions to support activity | Unassigned | Invalid | 0
355241 | #1001263 | Problem | Browser refresh will cause two simultaneous bulk key load operations (INC000003920384) | Unassigned | Approved
355229 | #330151 | Feature | Tracking Alignment Site # 4 (Relo) - AU | EA 14.5 | Done
355228 | #330151 | Feature | RF and Tracking Alignment Site # 3 (Relo) - WH | EA 14.5 | Done
355203 | #354537 | Story | Update Splunk servers to RHEL 7.x: Update Splunk & RHEL 7 | Unassigned | Invalid | 0
355145 | #354537 | Story | Update Splunk servers to RHEL 7.x: Create the Site Functional Test Case | Unassigned | Invalid | 0
355144 |  | Task | Update Splunk servers to RHEL 7.x: Hold Feature Review with SMEs (SA Internal Review) | Unassigned | Invalid
355143 | #354537 | Story | Update Splunk servers to RHEL 7.x: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355141 | #355130 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #355132
355140 | #355130 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #355132
355139 | #354537 | Story | Update Splunk servers to RHEL 7.x: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
355138 | #355130 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #355132
355135 | #354537 | Story | Update Splunk servers to RHEL 7.x: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #355132
355134 | #354537 | Story | Update Splunk servers to RHEL 7.x: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355131 |  | Story | Update Splunk servers to RHEL 7.x: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0
355130 |  | Feature | <Feature xxx> | Unassigned | Rejected
355111 |  | Task | Story 1011568: CM Release of 69-P57163M – GTS – NME 9 (EAD 18) | PI 16 | Invalid
355110 |  | Task | Story 1011568: CM Release of 69-P57162M – GTS – NME 8 (EAD 18) | PI 16 | Invalid
355108 |  | Problem | ATO Maintenance: IA Remediation for F5 BigIP DMZ Proxy/Load Balancers prxylb201 and prxylb202 | Unassigned | Assessing
355103 |  | Task | Story 1011568: CM Release of PL01-P53578E001 – NME 8 Cabinet Assembly - NMA, Parts List (EAD 18) | PI 16 | Invalid
355102 | #380808 | Task | Feature 380808: Submit PDO for PL01-P53569E – NME 9 Cabinet Assembly - NMA, Parts List | PI 16 | New
355075 | #243395 | Feature | Firewall PWI Burn down | PI 15 | Rejected
355069 |  | Task | Story 1011568: CM Release of 01-P53578E001 – GTS – NME 8 Cabinet Assembly (EAD 18) | PI 16 | Invalid
355055 |  | Task | Story 1011568: CM Release of 01-P53569E001 – GTS – NME 9 Cabinet Assembly (EAD 18) | PI 16 | Invalid
355049 | #354680 | Problem | ATO Maintenance: IA Remediation for Access Control and Password Complexity on Splunk Servers | EA 14.3 | Closed
355039 |  | Story | Feature 355026: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
355032 |  | Story | Feature 355026: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #355029
355028 |  | Story | Feature Demo – Customer Demo Event - Feature 355026 | Unassigned | Invalid | 0 | #355035
355027 |  | Story | Feature 355026: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #355032
355022 |  | Problem | ATO Maintenance: IA Remediation for Audit Generation and Distribution on Splunk Servers | PI 16 | Approved
355005 |  | Feature | CVPA Remediation | Unassigned | Rejected
354999 |  | Problem | ATM: fabric configuration security ipfiltering command is missing the gis-xx server ip address for backups | Unassigned | Assessing
354942 | #354871 | Story | Feature 354871: MFR 3 - Dev Team Resolves ACAS Scan and STIG Findings Part 1 of 2 | EA 16.1 | New | 3
354939 | #354871 | Story | Feature 354871: IETM support of NAVSOC and OA Workstation upgrade | EA 14.1 | Done | 1
354910 | #354680 | Story | Feature 354680 (Site): Formal updates of PKI part 2 | EA 14.3 | Done | 2
354909 | #354680 | Story | Feature 354680 (Site): Splunk HA final lab testing: Indexer & search head critical failure recovery | EA 14.3 | Done | 2
354906 | #354871 | Story | Feature 354871: Initiate CM PDO Processing for all CI's | EA 16.5 | New | 1
354905 | #354871 | Story | Feature 354871: Prep and Hold Feature Demo | EA 15.4 | Invalid | 0
354899 | #354871 | Story | Feature 354871: Create Deployment Notes and Operator Impact Inputs | EA 16.1 | New | 1
354886 |  | Story | Test of NAVSOC and OA Workstation upgrade | Unassigned | Invalid | 0
354885 | #354871 | Story | Feature 354871: Load baseline and execute STCD in VLab | EA 16.3 | New | 3
354884 | #354871 | Story | Feature 354871: Load baseline and execute STCD in VLab | EA 16.3 | New | 3
354874 |  | Story | Cyber support for NAVSOC and OA Workstation upgrade | Unassigned | Invalid | 0
354871 | #241501 | Feature | OBS - NAVSOC: OA workstation upgrade | PI 16 - In Progress | Implementing
354864 | #245573 | Feature | Evaluate improvements to uplink flux management to better protect the Satellite LNA | Unassigned | Draft
354863 |  | Story | Support for Windows execution plan development | Unassigned | Invalid | 0
354856 |  | Story | Support for MTC execution plan development | Unassigned | Invalid | 0
354843 |  | Story | Support for ETI execution plan development | Unassigned | Invalid | 0
354830 | #354680 | Story | Feature 354680 (Site): Developer testing of all Splunk HA install scripts | EA 14.1 | Done | 5
354795 | #245567 | Feature | Implement OSS-RC changes to turn on PM-pegs | Unassigned | Rejected
354781 | #354755 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #354768
354780 | #354755 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
354779 | #354755 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354778 | #354755 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354777 | #354755 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #354768
354776 | #354755 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #354768
354775 | #354755 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
354774 | #354755 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #354768
354773 | #354755 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #354768
354772 | #354755 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #354769
354771 | #354755 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #354768
354770 | #354755 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #354774
354769 | #354755 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #354768
354768 | #354755 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #354775
354767 | #354755 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #354765 #354772
354766 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | PI 14 | Invalid | 0 | #354768
354765 | #354755 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #354758
354764 | #354755 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #354768
354763 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: Test Report | EA 14.5 | Done | 3 | #354768
354762 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: Complete System Operational Verification Test, SOVT | EA 14.4 | Invalid | 0 | #354768
354761 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: System Operational Verification Test, SOVT, Test Inputs for Feature | EA 14.2 | Done | 3 | #354762
354760 | #352931 | Story | Feature 352931: Prepare Docs for SPLUNK HA FRCB - Create Redlines on Hardware Drawings Submitted for IDP (Template for HW/FRCB Deployable Feature) | PI 14 | Invalid | 0 | #354757
354759 | #352931 | Story | Feature 352931: Prepare Docs for SPLUNK HA FRCB - Define Power Consumption Changes for IDP (Template for HW/FRCB Deployable Feature) | PI 14 | Invalid | 0 | #354757
354758 | #354755 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #354764
354757 | #352931 | Story | Feature 352931: Prepare Docs for SPLUNK HA FRCB - Completion of Installation Design Plan IDP (Redlines for Hardware Drawings Submitted), needed 110 days prior to FRCB; | PI 14 | Invalid | 0 | #354768
354755 |  | Feature | <FRCB Feature xxx> | Unassigned | Rejected
354746 |  | Story | PM Performance Improvements – PM Server: Test changes based on Site Results | Unassigned | Invalid | 0
354742 | #354734 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #354736
354733 | #354680 | Story | Feature 354680 (Site): Formal Update of AMP | EA 14.1 | Done | 1
354722 | #351909 | Feature | TD19-10: Prepare Splunk Optimization MFR Use Case 3 Package | PI 14 - Candidate | Rejected
354718 | #354703 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #354705
354716 | #354703 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354715 | #354703 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354714 | #354703 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #354705
354712 | #354703 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
354711 | #354703 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #354705
354709 | #354703 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #354706
354708 | #354703 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #354705
354707 | #354703 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #354711
354706 | #354703 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #354705
354704 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #354709
354703 |  | Feature | <Feature xxx> | Unassigned | Rejected
354699 | #263244 | Story | Investigate RNC Board Failures | Unassigned | Invalid | 0
354698 | #263244 | Story | Investigate RNC Board Failures | Unassigned | Invalid | 0
354695 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #354682
354693 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354692 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354691 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #354682
354690 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #354682
354689 | #354680 | Story | Feature 354680 (Site): Splunk HA review | EA 14.4 | Done | 2
354688 |  | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #354682
354687 | #354680 | Story | Feature 354680 (Site): Execute STCD (1st Run of Feature Tests) | EA 14.3 | Done | 2 | #354682
354686 | #354680 | Story | Feature 354680 (Site): IA Patching and STIGs (Update RHEL Image) | EA 14.1 | Done | 5 | #354683
354685 | #354680 | Story | Feature 354680 (Site): Deployment Notes and Operator Impact Inputs Part 1 of N | EA 14.4 | Done | 2 | #354682
354684 |  | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #354688
354683 | #354680 | Story | Feature 354680 (Site): IA Posture Assessment - part 1 | EA 14.2 | Done | 2 | #354682
354682 | #354680 | Story | Feature 354680 (Site): Feature Demo – Customer Demo Event - Splunk (Site) | EA 14.5 | Done | 2
354681 | #354680 | Story | Feature 354680 (Site): IA - Initial Scan on Splunk HA loaner equipment | EA 14.1 | Done | 3 | #354686
354680 | #351909 | Feature | TD19-10: Implement SPLUNK HA for Site | EA 14.5 | Done
354675 |  | Story | Splunk Data migration plan and instructions: Identification of validation tests | Unassigned | Invalid | 0
354666 | #352931 | Story | Prepare Docs for SPLUNK HA FRCB: SE support in defining acceptance tests of the clustered architecture at site | EA 14.4 | Done | 2
354646 | #241501 | Feature | OBS: PRC-155 Replacement Trade Study | EA 14.5 | Done
354643 | #354627 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #354630
354642 | #354627 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
354641 | #354627 | Story | Feature 354627 UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354640 | #354627 | Story | Feature 354627 ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354639 | #354627 | Story | Feature 354627 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #354630
354638 | #354627 | Story | Feature 354627 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #354630
354637 | #354627 | Story | Feature 354627: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
354636 | #354627 | Story | Feature 354627:ILS IETM update (Template) | Unassigned | Invalid | 0 | #354630
354635 | #354627 | Story | Feature 354627 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #354630
354634 | #354627 | Story | Feature 354627: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #354631
354633 | #354627 | Story | Feature 354627: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #354630
354632 | #354627 | Story | Feature 354627 Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #354636
354631 | #354627 | Story | Feature 354627: IA Posture Assessment | Unassigned | Invalid | 0 | #354630
354630 | #354627 | Story | Feature Demo – Customer Demo Event - Feature 354627 | Unassigned | Invalid | 0 | #354637
354629 | #354627 | Story | Feature 354627: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #354634
354627 |  | Feature | Feature 354627: | Unassigned | Rejected
354579 | #392743 | Problem | ATO Maintenance: Fix Several General Configuration Settings on Solaris 10 Servers m11 and m12 | EA 14.4 | Closed
354558 | #354680 | Story | Feature 354680 (Site): HBSS support for RHEL 7.x on the Splunk HA architecture | EA 14.2 | Done | 2
354516 | #351017 | Story | Feature 351017: HIPS Options policy must include high-risk applications | Unassigned | New | 3
354515 | #351017 | Story | Feature 351017: HIPS Options policy must include high-risk applications | Unassigned | New | 2
354488 | #330886 | Story | IA STIGs and Patched | Unassigned | Invalid | 0
354463 |  | Story | Integrate AWARE into SA Dashboards: Placeholder | Unassigned | Invalid | 0
354457 |  | Problem | ATO Maintenance: GIS Servers - Audit | Unassigned | Assessing
354434 |  | Problem | ATO Maintenance: GIS Servers - Access control & account management | Unassigned | Assessing
354426 |  | Story | Create/Execute STCD (part 2) | Unassigned | Invalid | 0
354412 | #354372 | Story | Lab - TXO Ericsson -Re-test 8 GPB51s from Initial 2018 bulk buy warranty replacement boards | EA 14.5 | Invalid | 0
354395 | #354372 | Story | Lab - TXO Ericsson -Re-test 2 PWB Assembly SCB3s from Initial 2018 bulk buy warranty replacement boards | EA 14.5 | Invalid | 0
354384 |  | Story | Relocation: ACU configuration changes (part 2) | Unassigned | Invalid | 0
354372 | #262134 | Feature | Lab - TXO Ericsson - Re-test Ericsson parts from TXO from Initial 2018 bulk buy warranty replacement boards | EA 14.5 | Done
354329 | #354325 | Story | Re-apply STCD Problem 341469 Story | Unassigned | Invalid | 0
354328 | #354325 | Story | Re-apply Problem 341469 Story | Unassigned | Invalid | 0 | #354329
354327 | #364632 | Story | Feature 364632: Rebase STCD Problem 341469 Story | PI 17 | New | 2
354326 | #364632 | Story | Feature 364632: Rebase Problem 341469 Story | PI 17 | New | 2 | #354327
354321 |  | Problem | ATO Maintenance: GIS Servers - Update login banners | Unassigned | Assessing
354254 | #257550 | Story | Integrate AWARE into SA Dashboards: Create the Site Functional Test Case | Unassigned | Invalid | 0
354252 |  | Story | Feature 257550: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354251 |  | Story | Feature 257550: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
354247 |  | Story | Feature 257550: ILS IETM update (Template) | Unassigned | Invalid | 0 | #354241
354245 |  | Story | Feature 257550: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #354242
354243 |  | Story | Feature 257550: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #354247
354240 |  | Story | Feature 257550: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #354245
354239 |  | Feature | <Feature xxx> | Unassigned | Rejected
354229 | #355661 | Story | Feature 355661: Create STCD and review with Stakeholders | Unassigned | Invalid | 0
354193 | #354174 | Story | Feature 354174 Splunk IETM: Update Task Analysis for SPLUNK | EA 14.1 | Done | 2
354190 | #351017 | Story | Feature 351017 HBSS Feature SVD Updates Sprint 1 | Unassigned | New | 3
354189 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #354176
354185 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #354176
354184 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #354176
354182 | #354174 | Story | Feature 354174: IETM Update for SPLUNK Update | EA 14.3 | Done | 8 | #354176
354181 | #354174 | Story | Feature 354174 Splunk IETM: Define STCD | EA 14.3 | Done | 2 | #354176
354180 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #354177
354179 | #354174 | Story | Feature 354174 Splunk IETM: Deployment Notes and Operator Impact Inputs for Update IETMs, Task Analysis, etc | EA 14.4 | Done | 1 | #354176
354177 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #354176
354176 | #354174 | Story | Feature Demo – Customer Demo Event - Feature 354174: Update IETMs, Task Analysis, etc | EA 14.4 | Done | 1 | #354183
354175 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #354180
354174 | #351909 | Feature | TD19-10: SPLUNK HA Update IETMs, Task Analysis, etc | EA 14.4 | Done
354170 |  | Story | Update IETM for ETISP configuration utility workaround | Unassigned | Invalid | 0
353837 | #243502 | Story | CM Release Work for EAD 16 OOC | EA 15.4 | New | 1
353654 | #342163 | Problem | IETM: Backup HAIPE- Normal Operation Procedure Refers to a Section in GEM One User Manual that Does Not Exist | EA 15.3 | Closed
353451 | #353364 | Story | Re-apply STCD Problem xxx Story | Unassigned | Invalid | 0
353449 | #353364 | Story | Re-apply Problem xxx Story | Unassigned | Invalid | 0 | #353451
353431 | #353364 | Story | Rebase STCD Problem xxx Story | Unassigned | Invalid | 0
353417 | #353364 | Story | Rebase Problem xxx Story | Unassigned | Invalid | 0 | #353431
353403 |  | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #353390
353402 |  | Task | Hold Feature Review with SMEs | Unassigned | New
353401 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
353400 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
353399 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #353390
353398 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #353390
353397 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
353396 |  | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #353390
353395 |  | Story | Splunk App - Test and Demo Updated Beam Map (M503) | Unassigned | Invalid | 0 | #353390
353394 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #353391
353393 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #353390
353392 |  | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #353396
353391 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #353390
353389 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #353394
353388 |  | Feature | <Feature xxx> | Unassigned | Rejected
353380 | #353345 | Story | Feature 353345: Create Training Plan for Refresher Training in WH | EA 14.1 | Done | 1
353364 | #353840 | Feature | MPC for Problem xxx found in Pre EAD 10 Deliveries | Unassigned | Implementing
353350 | #353345 | Story | Feature 353345: Refresher Training WH - Complete Customer Response Matrix (CRM) | EA 14.2 | Done | 1
353349 | #353345 | Story | Feature 353345: Conduct Refresher Training in WH (Trainer 1) | EA 14.1 | Done | 3
353348 | #353345 | Story | Feature 353345: Travel to Site to Conduct Refresher Training at WH (Trainer 1) | EA 14.1 | Done | 2
353347 | #353345 | Story | Feature 353345: Finalize, Print, and Ship Materials- Maintainer Refresher Training WH | EA 14.1 | Done | 1
353345 | #262146 | Feature | Deliver Maintainer Refresher Training in WH | EA 14.2 | Done
353262 | #353256 | Story | Feature 353256: Maintainer Refresher Training AU - Complete Customer Response Matrix (CRM) | EA 16.4 | New | 1
353261 | #353256 | Story | Feature 353256: Conduct Maintainer Refresher Training in AU (Trainer 1) (Days 1-3) | EA 16.2 | New | 3
353259 | #353256 | Story | Feature 353256: Travel to AU Site to Conduct Maintainer Refresher Training in AU (Trainer 1) | EA 16.2 | New | 2
353258 | #353256 | Task | Feature 353256: Verify the Shipping of Materials Maintainer Refresher Training AU | EA 14.3 | Done
353257 | #353256 | Task | Feature 353256: Create Training Plan for Refresher Training in AU | EA 14.1 | Done
353256 | #262146 | Feature | Deliver Maintainer Refresher Training in AU | PI 16 | Implementing
353255 | #353134 | Story | Feature 353134: Familiarize Trainer with Maintainer Refresher Training in SC | EA 14.2 | Done | 3
353254 | #353134 | Story | Feature 353134: Maintainer Refresher Training SC - Complete Customer Response Matrix (CRM) | PI 16 | New | 1
353253 | #353134 | Story | Feature 353134: Conduct Maintainer Refresher Training in SC Days 1-3 (Trainer 1) | EA 16.5 | New | 3
353252 |  | Story | SA PWI Backlog Burndown EA 11.5 (Alex W.) | Unassigned | Invalid | 0
353251 |  | Story | SA PWI Backlog Burndown EA 11.5 (Ken R.) | Unassigned | Invalid | 0
353250 |  | Story | SA PWI Backlog Burndown EA 11.5 (Ricardo M.) | Unassigned | Invalid | 0
353249 |  | Story | SA PWI Backlog Burndown EA 11.5 (Mike M.) | Unassigned | Invalid | 0
353248 |  | Story | SA PWI Backlog Burndown EA 11.5 (Khai B.) | Unassigned | Invalid | 0
353247 |  | Story | SA PWI Backlog Burndown EA 11.5 (Craig J.) | Unassigned | Invalid | 0
353246 |  | Story | SA PWI Backlog Burndown EA 11.5 (Katie I.) | Unassigned | Invalid | 0
353245 |  | Story | SA PWI Backlog Burndown EA 11.5 (Dustin D.) | Unassigned | Invalid | 0
353244 |  | Story | SA PWI Backlog Burndown EA 11.5 (Colin B.) | Unassigned | Invalid | 0
353243 |  | Story | SA PWI Backlog Burndown EA 11.5 (Joel A.) | Unassigned | Invalid | 0
353242 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Josh W.) | Unassigned | Invalid | 0
353241 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Michael V.) | Unassigned | Invalid | 0
353240 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Aidan S.) | Unassigned | Invalid | 0
353239 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Rich N.) | Unassigned | Invalid | 0
353238 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Patrick M.) | Unassigned | Invalid | 0
353237 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Glen L.) | Unassigned | Invalid | 0
353236 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Mike K.) | Unassigned | Invalid | 0
353235 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Keith K.) | Unassigned | Invalid | 0
353234 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Jonathan J.) | Unassigned | Invalid | 0
353233 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Carl D.) | Unassigned | Invalid | 0
353232 |  | Story | MAGIC PWI Backlog Burndown EA 11.5 (Anil B) | Unassigned | Invalid | 0
353231 |  | Story | SA PWI Backlog Burndown EA 11.4 (Alex W.) | Unassigned | Invalid | 0
353230 |  | Story | SA PWI Backlog Burndown EA 11.4 (Ken R.) | Unassigned | Invalid | 0
353229 |  | Story | SA PWI Backlog Burndown EA 11.4 (Ricardo M.) | Unassigned | Invalid | 0
353228 |  | Story | SA PWI Backlog Burndown EA 11.4 (Mike M.) | Unassigned | Invalid | 0
353227 |  | Story | SA PWI Backlog Burndown EA 11.4 (Khai B.) | Unassigned | Invalid | 0
353226 |  | Story | SA PWI Backlog Burndown EA 11.4 (Craig J.) | Unassigned | Invalid | 0
353225 |  | Story | SA PWI Backlog Burndown EA 11.4 (Katie I.) | Unassigned | Invalid | 0
353224 |  | Story | SA PWI Backlog Burndown EA 11.4 (Dustin D.) | Unassigned | Invalid | 0
353223 |  | Story | SA PWI Backlog Burndown EA 11.4 (Colin B.) | Unassigned | Invalid | 0
353222 |  | Story | SA PWI Backlog Burndown EA 11.4 (Joel A.) | Unassigned | Invalid | 0
353221 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Josh W.) | Unassigned | Invalid | 0
353220 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Michael V.) | Unassigned | Invalid | 0
353219 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Aidan S.) | Unassigned | Invalid | 0
353218 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Rich N.) | Unassigned | Invalid | 0
353217 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Patrick M.) | Unassigned | Invalid | 0
353216 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Glen L.) | Unassigned | Invalid | 0
353215 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Mike K.) | Unassigned | Invalid | 0
353214 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Keith K.) | Unassigned | Invalid | 0
353213 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Jonathan J.) | Unassigned | Invalid | 0
353212 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Carl D.) | Unassigned | Invalid | 0
353211 |  | Story | MAGIC PWI Backlog Burndown EA 11.4 (Anil B) | Unassigned | Invalid | 0
353210 |  | Story | SA PWI Backlog Burndown EA 11.3 (Alex W.) | Unassigned | Invalid | 0
353209 |  | Story | SA PWI Backlog Burndown EA 11.3 (Ken R.) | Unassigned | Invalid | 0
353208 |  | Story | SA PWI Backlog Burndown EA 11.3 (Ricardo M.) | Unassigned | Invalid | 0
353207 |  | Story | SA PWI Backlog Burndown EA 11.3 (Mike M.) | Unassigned | Invalid | 0
353206 |  | Story | SA PWI Backlog Burndown EA 11.3 (Khai B.) | Unassigned | Invalid | 0
353205 |  | Story | SA PWI Backlog Burndown EA 11.3 (Craig J.) | Unassigned | Invalid | 0
353204 |  | Story | SA PWI Backlog Burndown EA 11.3 (Katie I.) | Unassigned | Invalid | 0
353203 |  | Story | SA PWI Backlog Burndown EA 11.3 (Dustin D.) | Unassigned | Invalid | 0
353202 |  | Story | SA PWI Backlog Burndown EA 11.3 (Colin B.) | Unassigned | Invalid | 0
353201 |  | Story | SA PWI Backlog Burndown EA 11.3 (Joel A.) | Unassigned | Invalid | 0
353200 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Josh W.) | Unassigned | Invalid | 0
353199 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Michael V.) | Unassigned | Invalid | 0
353198 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Aidan S.) | Unassigned | Invalid | 0
353197 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Rich N.) | Unassigned | Invalid | 0
353196 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Patrick M.) | Unassigned | Invalid | 0
353195 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Glen L.) | Unassigned | Invalid | 0
353194 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Mike K.) | Unassigned | Invalid | 0
353193 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Keith K.) | Unassigned | Invalid | 0
353192 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Jonathan J.) | Unassigned | Invalid | 0
353191 |  | Story | MAGIC PWI Backlog Burndown EA 11.3 (Carl D.) | Unassigned | Invalid | 0
353190 |  | Story | MAGIC PWI Backlog Burndown EA 11.1 (Glen J.) | Unassigned | Invalid | 0
353189 |  | Story | SA PWI Backlog Burndown EA 11.2 (Alex W.) | Unassigned | Invalid | 0
353188 |  | Story | SA PWI Backlog Burndown EA 11.2 (Ken R.) | Unassigned | Invalid | 0
353187 |  | Story | SA PWI Backlog Burndown EA 11.2 (Ricardo M.) | Unassigned | Invalid | 0
353186 |  | Story | SA PWI Backlog Burndown EA 11.2 (Mike M.) | Unassigned | Invalid | 0
353185 | #353134 | Story | Feature 353134: Travel to SC to Conduct Maintainer Refresher Training in SC (Trainer 1) | EA 16.5 | New | 2
353184 |  | Story | SA PWI Backlog Burndown EA 11.2 (Khai B.) | Unassigned | Invalid | 0
353183 |  | Story | SA PWI Backlog Burndown EA 11.2 (Craig J.) | Unassigned | Invalid | 0
353182 |  | Story | SA PWI Backlog Burndown EA 11.2 (Katie I.) | Unassigned | Invalid | 0
353181 |  | Story | SA PWI Backlog Burndown EA 11.2 (Dustin D.) | Unassigned | Invalid | 0
353180 |  | Story | SA PWI Backlog Burndown EA 11.2 (Colin B.) | Unassigned | Invalid | 0
353179 |  | Story | MAGIC PWI Triage/Assessment Support - EA 11.6 | Unassigned | Invalid | 0
353178 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Josh W.) | Unassigned | Invalid | 0
353177 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Michael V.) | Unassigned | Invalid | 0
353176 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Aidan S.) | Unassigned | Invalid | 0
353175 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Rich N.) | Unassigned | Invalid | 0
353174 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Patrick M.) | Unassigned | Invalid | 0
353173 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Glen L.) | Unassigned | Invalid | 0
353172 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Mike K.) | Unassigned | Invalid | 0
353171 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Keith K.) | Unassigned | Invalid | 0
353170 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Jonathan J.) | Unassigned | Invalid | 0
353169 |  | Story | MAGIC PWI Backlog Burndown EA 11.2 (Carl D.) | Unassigned | Invalid | 0
353168 |  | Story | SA PWI Triage/Assessment Support - EA 11.6 | Unassigned | Invalid | 0
353154 |  | Story | MAGIC PWI Backlog Burndown EA 11.1 (Rich N.) | Unassigned | Invalid | 0
353153 |  | Story | MAGIC PWI Backlog Burndown EA 11.1 (Tom G.) | Unassigned | Invalid | 0
353136 | #353134 | Story | Feature 353134: Finalize, Print, and Ship Materials- Maintainer Refresher Training SC | EA 14.2 | Done | 1
353134 | #262146 | Feature | Deliver Maintainer Refresher Training in SC | PI 16 - In Progress | Implementing
353030 |  | Problem | FM reporting wrong fault for TFDU | Unassigned | Assessing
352973 | #352960 | Story | Feature 352960: RBS Group 1&2 Calibration Procedure: UX IETM Review | Unassigned | Invalid | 0 | #352968
352972 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
352971 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
352949 | #216552 | Feature | Cyber Feature PI-11 | Unassigned | Rejected
352948 | #216552 | Feature | Cyber Feature PI-11 | Unassigned | Rejected
352947 | #216552 | Feature | Cyber Feature PI-11 | Unassigned | Rejected
352946 | #1022224 | Feature | WinOBS: Windows Server 2019 SHB Testing & Implementation Planning | PI 16 | Approved |  | #1015810
352945 | #350955 | Feature | HBSS FOUO Planning | Unassigned | Rejected
352944 |  | Feature | Virtualization Testing & Implementation Planning | Unassigned | Rejected
352931 | #351909 | Feature | TD19-10: Prepare Docs for SPLUNK HA FRCB in support of EAD 17 | EA 14.5 | Done
352919 | #352910 | Task | Feature 352910: Initiate CM PDO Processing for all CI's for TD19-10: Update SPLUNK Drawings | PI 14 | Invalid
352915 | #352910 | Story | Feature 352910: Deployment Notes and Operator Impact Inputs for TD19-10: Update SPLUNK Drawings | PI 14 | Invalid | 0 | #352912
352912 | #352910 | Story | Feature Demo – Customer Demo Event - Feature 352910 (TD19-10: Update SPLUNK Drawings) | PI 14 | Invalid | 0 | #352919
352877 | #325227 | Story | Feature 325227: FM Servers - General Configuration Settings to resolve Cyber RMF Findings - part 2 | Unassigned | New | 13
352846 | #352831 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #352833
352845 | #352831 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
352844 | #352831 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
352843 | #352831 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
352842 | #352831 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #352833
352841 | #352831 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #352833
352840 | #352831 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
352839 | #352831 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #352833
352838 | #352831 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #352833
352837 | #352831 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #352834
352836 | #352831 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #352833
352835 | #352831 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #352839
352834 | #352831 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #352833
352833 | #352831 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #352840
352832 | #352831 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #352837
352831 |  | Feature | <Feature xxx> | Unassigned | Rejected
352824 | #322974 | Story | Feature 322974: UX Inputs for Completion of Addition of IMSIs to RNC CDRs | Unassigned | Invalid | 0
352804 |  | Story | FM Whitelist updates for PI12(1st release): Review EAD 14 features and identify any alarms that need to be added to the whitelist | Unassigned | Invalid | 0
352636 | #342163 | Problem | IETM: GEM One content in Security Management needs to be updated and verified in the lab | EA 15.3 | Closed
352634 | #342163 | Problem | IETM: TACLANE 1G guide is linked for HAIPE Ds | EA 15.1 | Closed
352633 | #342163 | Problem | IETM: GEM One steps do not belong in NMF Power Up procedure | EA 15.3 | Closed
352632 | #342163 | Problem | IETM: Current HAIPE G Clock Maintenance steps require local update; should use GEM One | EA 15.3 | Closed
352631 | #342163 | Problem | IETM: Audit Logs section of HAIPE Management GEM One-Normal Operations is not procedural | EA 15.3 | Closed
352630 | #342163 | Problem | IETM: Instructions for checking for HAIPE Faults and FFVS expiration are missing from HAIPE Management procedure | EA 15.3 | Closed
352544 | #351017 | Story | Feature 351017 Policy Auditor File Integrity (FIM) Module Lab Prototyping | Unassigned | New | 8
352529 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
352414 | #279283 | Story | Lab - TXO Test Procedure - SGSN - IBS7V3 Board (High) | EA 14.2 | Done | 3
352413 | #279283 | Story | Lab - TXO Test Procedure - SGSN - IBASV3 Board (High) | EA 14.1 | Done | 3
352412 | #279283 | Story | Lab - TXO Test Procedure - SGSN - GPBV3 Board (High) | EA 14.1 | Done | 3
352411 | #279283 | Story | Lab - TXO Test Procedure - GGSN - 4 Port Ethernet Board (High) | EA 14.4 | Done | 3
352410 | #279283 | Story | Lab - TXO Test Procedure - CSCF/HSS - PM Board (High) | EA 14.3 | Done | 3
352409 | #279283 | Story | Lab - TXO Test Procedure - CSCF/HSS - PMD Board (High) | EA 14.3 | Done | 3
352408 | #279283 | Story | Lab - TXO Test Procedure - ATM- 4 Port OC-3 Board (High) | EA 14.3 | Done | 3
352407 | #279283 | Story | Lab - TXO Test Procedure - RBS - SCB3 Board (High) | EA 14.2 | Done | 3
352406 | #279283 | Story | Lab - TXO Test Procedure - RBS - GPB51 Board (High) | EA 14.1 | Done | 3
352403 | #279283 | Story | Lab - TXO Test Procedure - RNC - ET-M4 Board (High) | EA 14.2 | Done | 3
352367 | #351050 | Story | Feature 351050 Conduct Trade Study - Common, Compliant Low/High Sides Architecture - Dev2 | Unassigned | New | 8
352364 | #351050 | Story | Feature 351050 Conduct Trade Study - Common, Compliant Low/High Sides Architecture - Dev1 | Unassigned | New | 8
352362 | #351050 | Story | Feature 351050 Implement Prototype: ePO and Manage Hosts - Common, Compliant Low/High Sides Architecture - Dev2 | Unassigned | New | 8
352361 | #351050 | Story | Feature 351050 Implement Prototype: ePO and Manage Hosts - Common, Compliant Low/High Sides Architecture - Dev1 | Unassigned | New | 8
352347 | #279283 | Story | Lab - TXO Test Procedure - RBS - AIU Board (High) | EA 14.1 | Done | 3
352337 | #351050 | Story | Feature 351050 Conduct Trade Study - Common, Compliant Low/High Sides Architecture - IA | Unassigned | New | 8
352336 | #351050 | Story | Feature 351050 Implement Prototype: ePO and Manage Hosts - Common, Compliant Low/High Sides Architecture - IA | Unassigned | New | 8
352334 | #351050 | Story | Feature 351050 Setup and Configure Lab for Prototype | Unassigned | New | 13
352333 | #351050 | Story | Feature 351050 Start Development Docs (including SVD) | Unassigned | New | 13
352326 | #351050 | Story | Feature 351050 Acquire Common HBSS HW and SW | Unassigned | New | 13
352314 | #351050 | Story | Feature 351050 Technical Support for HBSS Requirements | Unassigned | New | 2
352204 | #352189 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #352191
352203 | #352189 | Task | Hold Feature Review with SMEs | Unassigned | New
352202 | #352189 | Story | Feature 352189 UX Research and Design Support | Unassigned | New | 3
352201 | #352189 | Story | Feature 352189: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
352200 | #352189 | Story | Feature 352189: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #352191
352199 | #352189 | Story | Feature 352189: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #352191
352198 | #352189 | Story | Feature 352189: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
352197 | #352189 | Story | Feature 352189:ILS IETM update (Template) | Unassigned | New | 3 | #352191
352196 | #352189 | Story | Feature 352189: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #352191
352195 | #352189 | Story | Feature 352189: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #352192
352194 | #352189 | Story | Feature 352189: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #352191
352193 | #352189 | Story | Feature 352189: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #352197
352192 | #352189 | Story | Feature 352189: IA Posture Assessment | Unassigned | New | 8 | #352191
352191 | #352189 | Story | Feature Demo – Customer Demo Event - Feature 352189 | Unassigned | New | 1 | #352198
352190 | #352189 | Story | Feature 352189: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #352195
352045 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy: Manage Hosts - HBSS Low Side - SF | Unassigned | New | 13
352044 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy: Manage Hosts - HBSS Low Side - RAF | Unassigned | New | 13
352043 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy: Manage Hosts - HBSS Low Side - NMF | Unassigned | New | 13
352027 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy New ePO (5.9.x) - HBSS Low Side - Dev2 | Unassigned | New | 13
352024 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy New ePO (5.9.x) - HBSS Low Side - Dev1 | Unassigned | New | 13
352017 | #351997 | Story | Feature 351997 Develop, Implement, and Deploy New ePO (5.9.x) - HBSS Low Side - IA | Unassigned | New | 13
352012 | #351997 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #351999
352011 | #351997 | Task | Hold Feature Review with SMEs | Unassigned | New
352010 | #351997 | Story | Feature 351997 UX Research and Design Support | Unassigned | New | 3
352009 | #351997 | Story | Feature 351997: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
352008 | #351997 | Story | Feature 351997: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351999
352007 | #351997 | Story | Feature 351997: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351999
352006 | #351997 | Story | Feature 351997: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
352005 | #351997 | Story | Feature 351997:ILS IETM update (Template) | Unassigned | New | 3 | #351999
352004 | #351997 | Story | Feature 351997: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351999
352003 | #351997 | Story | Feature 351997: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #352000
352002 | #351997 | Story | Feature 351997: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351999
352001 | #351997 | Story | Feature 351997: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #352005
352000 | #351997 | Story | Feature 351997: IA Posture Assessment | Unassigned | New | 8 | #351999
351999 | #351997 | Story | Feature Demo – Customer Demo Event - Feature 351997 | Unassigned | New | 1 | #352006
351998 | #351997 | Story | Feature 351997: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #352003
351992 | #351977 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #351979
351991 | #351977 | Task | Hold Feature Review with SMEs | Unassigned | New
351990 | #351977 | Story | Feature 351977 UX Research and Design Support | Unassigned | New | 3
351989 | #351977 | Story | Feature 351977: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351988 | #351977 | Story | Feature 351977: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351979
351987 | #351977 | Story | Feature 351977: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351979
351986 | #351977 | Story | Feature 351977: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351985 | #351977 | Story | Feature 351977:ILS IETM update (Template) | Unassigned | New | 3 | #351979
351984 | #351977 | Story | Feature 351977: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351979
351983 | #351977 | Story | Feature 351977: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351980
351982 | #351977 | Story | Feature 351977: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351979
351981 | #351977 | Story | Feature 351977: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351985
351980 | #351977 | Story | Feature 351977: IA Posture Assessment | Unassigned | New | 8 | #351979
351979 | #351977 | Story | Feature Demo – Customer Demo Event - Feature 351977 | Unassigned | New | 1 | #351986
351978 | #351977 | Story | Feature 351977: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351983
351974 | #351959 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #351961
351973 | #351959 | Task | Hold Feature Review with SMEs | Unassigned | New
351972 | #351959 | Story | Feature 351959 UX Research and Design Support | Unassigned | New | 3
351971 | #351959 | Story | Feature 351959: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351970 | #351959 | Story | Feature 351959: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351961
351969 | #351959 | Story | Feature 351959: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351961
351968 | #351959 | Story | Feature 351959: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351967 | #351959 | Story | Feature 351959:ILS IETM update (Template) | Unassigned | New | 3 | #351961
351966 | #351959 | Story | Feature 351959: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351961
351965 | #351959 | Story | Feature 351959: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351962
351964 | #351959 | Story | Feature 351959: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351961
351963 | #351959 | Story | Feature 351959: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351967
351962 | #351959 | Story | Feature 351959: IA Posture Assessment | Unassigned | New | 8 | #351961
351961 | #351959 | Story | Feature Demo – Customer Demo Event - Feature 351959 | Unassigned | New | 1 | #351968
351960 | #351959 | Story | Feature 351959: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351965
351957 | #351942 | Story | Create the Site Functional Test Case | Unassigned | New | 2 | #351944
351956 | #351942 | Task | Hold Feature Review with SMEs | Unassigned | New
351955 | #351942 | Story | Feature 351942 UX Research and Design Support | Unassigned | New | 3
351954 | #351942 | Story | Feature 351942: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351953 | #351942 | Story | Feature 351942: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351944
351952 | #351942 | Story | Feature 351942: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351944
351951 | #351942 | Story | Feature 351942: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351950 | #351942 | Story | Feature 351942:ILS IETM update (Template) | Unassigned | New | 3 | #351944
351949 | #351942 | Story | Feature 351942: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351944
351948 | #351942 | Story | Feature 351942: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351945
351947 | #351942 | Story | Feature 351942: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351944
351946 | #351942 | Story | Feature 351942: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351950
351945 | #351942 | Story | Feature 351942: IA Posture Assessment | Unassigned | New | 8 | #351944
351944 | #351942 | Story | Feature Demo – Customer Demo Event - Feature 351942 | Unassigned | New | 1 | #351951
351943 | #351942 | Story | Feature 351942: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351948
351884 | #320587 | Story | Feature 320587: Manage on-site patching: Sprint 10.4 - Gerald | Unassigned | Invalid | 0
351841 |  | Task | CQ PCR Scrub for MUOSAT Database and import into RTC | Unassigned | Invalid
351819 | #351105 | Story | Feature 351105 Conduct Trade Study - Managed Hosts - MAC Module - Dev2 | Unassigned | New | 5
351817 | #351105 | Story | Feature 351105 Conduct Trade Study - Managed Hosts - MAC Module - Dev1 | Unassigned | New | 5
351816 | #351105 | Story | Feature 351105 Implement Prototype: Managed Hosts - MAC Module - Dev2 | Unassigned | New | 8
351815 | #351105 | Story | Feature 351105 Implement Prototype: Managed Hosts - MAC Module - Dev1 | Unassigned | New | 8
351814 | #351105 | Story | Feature 351105 Acquire HBSS product: Managed Hosts - MAC Module - Dev2 | Unassigned | New | 3
351813 | #351105 | Story | Feature 351105 Acquire HBSS product: Managed Hosts - MAC Module - Dev1 | Unassigned | New | 3
351811 | #351068 | Story | Feature 351086 Analyze and Determine STIG Fixes : ePO - SQL DB - Dev1 | Unassigned | New | 8
351646 | #1013136 | Problem | MILSTD: Packet data delay ramping up in 'steps' far below expectations when using DTI | EA 16.1 | Close Pending
351640 |  | Problem | WH- Incorrect Timestamps on GeoProc Logs | Unassigned | Assessing
351580 | #351068 | Story | Feature 351086 Analyze and Determine STIG Fixes : ePO - SQL DB - IA | Unassigned | New | 8
351579 | #351068 | Story | Feature 351086 Assess DB STIGs : ePO - SQL DB | Unassigned | New | 5
351572 | #380808 | Problem | Splunk Cell Status Dashboard Errors- Findings from EAD 10 Training Delivery | PI 16 | Approved
351556 | #351105 | Story | Feature 351105 Conduct Trade Study - Managed Hosts - MAC Module - IA | Unassigned | New | 5
351555 | #351105 | Story | Feature 351105 Implement Prototype: Managed Hosts - MAC Module - IA | Unassigned | New | 8
351554 | #351105 | Story | Feature 351105 Acquire HBSS product: Managed Hosts - MAC Module - IA | Unassigned | New | 3
351552 | #351086 | Story | Feature 351086 Conduct Trade Study - ePO - ArcSight Connector Module - IA | Unassigned | New | 5
351549 | #351086 | Story | Feature 351086 Implement Prototype: ePO - ArcSight Connector Module - Dev1 | Unassigned | New | 8
351546 | #351086 | Story | Feature 351086 Acquire HBSS product: ePO - ArcSight Connector Module | Unassigned | New | 1
351544 | #351086 | Story | Feature 351086: Define Customer Requirements: ePO - ArcSight Connector Module | Unassigned | New | 2
351533 |  | Story | SV Relocation - Geolocation impacts: UFO Table Update MPCs - Approvals | Unassigned | Invalid | 0
351532 |  | Story | SV Relocation - Geolocation impacts: UFO Table Update MPCs | Unassigned | Invalid | 0
351531 |  | Story | SV Relocation - Geolocation impacts: Update SVD for UFO Table Updates | Unassigned | Invalid | 0
351530 |  | Story | SV Relocation - Geolocation impacts: Process UFO Table RPMs | Unassigned | Invalid | 0
351526 |  | Story | SV Relocation - Geolocation impacts: AMS-GS Account Maintenance Plan - Update PCR & Start Code Review | Unassigned | Invalid | 0
351524 |  | Story | SV Relocation - Geolocation impacts: Code Collaborator Review for IETM updates | Unassigned | Invalid | 0
351522 |  | Story | SV Relocation - Geolocation impacts: Engineering IETM updates | Unassigned | Invalid | 0
351521 |  | Story | Invalid | Unassigned | Invalid | 0
351520 |  | Story | Invalid | Unassigned | Invalid | 0
351514 |  | Story | SV Relocation - Geolocation impacts: Support Integration | Unassigned | Invalid | 0
351496 | #327110 | Story | Alarm/PM Data Flow Performance - SE Support | Unassigned | Invalid | 0
351495 | #327110 | Story | Alarm/PM Data Flow Performance - SE Support | Unassigned | Invalid | 0
351492 | #327108 | Story | Alarm Flow - SA Support | Unassigned | Invalid | 0
351491 | #327108 | Story | Alarm Flow - SE Support | Unassigned | Invalid | 0
351490 | #327108 | Story | Alarm Flow - SE Support | Unassigned | Invalid | 0
351486 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
351485 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
351484 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
351466 | #349614 | Story | Feature 349614: SME provide redlines to the IETM procedures | Unassigned | Invalid | 0
351442 |  | Story | Feature 351434: IETM Update to Allow Changing CoC Nodes in Apportionments and SARs | Unassigned | Invalid | 0
351440 |  | Story | CoC Node Changes in Apportionments and SARs: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0
351435 |  | Story | CoC Node Changes in Apportionments and SARs: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0
351404 |  | Task | Chris Curtis OOP reminder: | Unassigned | New
351402 |  | Task | Will OOP reminder: Classes Started (M,W: 10:30-12:30) | Unassigned | Invalid
351124 | #351109 | Story | Feature 351109: Create the Site Functional Test Case | Unassigned | New | 2 | #351111
351123 | #351109 | Task | Hold Feature Review with SMEs | Unassigned | New
351122 | #351109 | Story | Feature 351109: UX Research and Design Support | Unassigned | New | 3
351121 | #351109 | Story | Feature 351109: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351120 | #351109 | Story | Feature 351109: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351111
351119 | #351109 | Story | Feature 351109: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351111
351118 | #351109 | Story | Feature 351109:: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351117 | #351109 | Story | Feature 351109::ILS IETM update (Template) | Unassigned | New | 3 | #351111
351116 | #351109 | Story | Feature 351109: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351111
351115 | #351109 | Story | Feature 351109:: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351112
351114 | #351109 | Story | Feature 351109:: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351111
351113 | #351109 | Story | Feature 351109: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351117
351112 | #351109 | Story | Feature 351109: IA Posture Assessment | Unassigned | New | 8 | #351111
351111 | #351109 | Story | Feature Demo – Customer Demo Event - Feature 351109: | Unassigned | New | 1 | #351118
351110 | #351109 | Story | Feature 351109:: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351115
351107 | #350955 | Feature | HBSS: Analysis and Design: Identified/Applicable Managed Hosts - MAC Module. | Unassigned | Rejected
351102 | #351087 | Story | Feature 351089: Create the Site Functional Test Case | Unassigned | New | 2 | #351089
351101 | #351087 | Task | Hold Feature Review with SMEs | Unassigned | New
351100 | #351087 | Story | Feature 351087: UX Research and Design Support | Unassigned | New | 3
351099 | #351087 | Story | Feature 351087: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351098 | #351087 | Story | Feature 351087: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351089
351097 | #351087 | Story | Feature 351087: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351089
351096 | #351087 | Story | Feature 351087:: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351095 | #351087 | Story | Feature 351087::ILS IETM update (Template) | Unassigned | New | 3 | #351089
351094 | #351087 | Story | Feature 351087: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351089
351093 | #351087 | Story | Feature 351087:: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351090
351092 | #351087 | Story | Feature 351087:: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351089
351091 | #351087 | Story | Feature 351087: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351095
351090 | #351087 | Story | Feature 351087: IA Posture Assessment | Unassigned | New | 8 | #351089
351089 | #351087 | Story | Feature Demo – Customer Demo Event - Feature 351087: | Unassigned | New | 1 | #351096
351088 | #351087 | Story | Feature 351087:: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351093
351085 | #351070 | Story | Feature 351070: Create the Site Functional Test Case | Unassigned | New | 2 | #351072
351084 | #351070 | Task | Hold Feature Review with SMEs | Unassigned | New
351083 | #351070 | Story | Feature 351070: UX Research and Design Support | Unassigned | New | 3
351082 | #351070 | Story | Feature 351070: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
351081 | #351070 | Story | Feature 351070: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #351072
351080 | #351070 | Story | Feature 351070: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #351072
351079 | #351070 | Story | Feature 351070:: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351078 | #351070 | Story | Feature 351070::ILS IETM update (Template) | Unassigned | New | 3 | #351072
351077 | #351070 | Story | Feature 351070: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #351072
351076 | #351070 | Story | Feature 351070:: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #351073
351075 | #351070 | Story | Feature 351070:: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #351072
351074 | #351070 | Story | Feature 351070: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #351078
351073 | #351070 | Story | Feature 351070: IA Posture Assessment | Unassigned | New | 8 | #351072
351072 | #351070 | Story | Feature Demo – Customer Demo Event - Feature 351070: | Unassigned | New | 1 | #351079
351071 | #351070 | Story | Feature 351070:: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351076
351069 | #350955 | Feature | HBSS: Design and identify fixes: STIG compliance ePO - SQL DB | Unassigned | Rejected
351067 |  | Story | Update MPC 10.12 for Informational Update | Unassigned | Invalid | 0
351066 | #351051 | Story | Feature 351051: Create the Site Functional Test Case | Unassigned | Invalid | 0 | #351053
351065 | #351051 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
351064 | #351051 | Story | Feature 351051: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
351063 | #351051 | Story | Feature 351051: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
351062 | #351051 | Story | Feature 351051: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #351053
351061 | #351051 | Story | Feature 351051: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #351053
351060 | #351051 | Story | Feature 351051:: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
351059 | #351051 | Story | Feature 351051::ILS IETM update (Template) | Unassigned | Invalid | 0 | #351053
351058 | #351051 | Story | Feature 351051: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #351053
351057 | #351051 | Story | Feature 351051:: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #351054
351056 | #351051 | Story | Feature 351051:: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #351053
351055 | #351051 | Story | Feature 351051: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #351059
351054 | #351051 | Story | Feature 351051: IA Posture Assessment | Unassigned | Invalid | 0 | #351053
351053 | #351051 | Story | Feature Demo – Customer Demo Event - Feature 351051: | Unassigned | Invalid | 0 | #351060
351052 | #351051 | Story | Feature 351051:: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #351057
351051 | #350955 | Feature | HBSS: Develop, Implement, and Deploy: HIPS Options policy must include high-risk applications. | Unassigned | Rejected
351033 |  | Feature | HBSS: Develop, Implement, and Deploy: ePO - HIPS Solaris update and Options policy must include high-risk applications | Unassigned | Rejected
351032 | #351017 | Story | Feature 351017: Create the Site Functional Test Case | Unassigned | New | 2 | #351019
351031 | #351017 | Task | Feature 351017: Hold Feature Review with SMEs | Unassigned | New
351030 | #351017 | Story | Feature 351017: UX IETM Development and Integration updates HBSS administrator to review weekly FIM events | Unassigned | New | 3
351029 | #351017 | Story | Feature 351017: ILS IETM Development and Integration updates | Unassigned | New | 1
351028 | #351017 | Story | Feature 351017: Agile Team Test PCR Verification, STCD Dev & Continued Testing | Unassigned | New | 5 | #351019
351027 | #351017 | Story | Feature 351017: Agile Team Test: Begin Testing, Complete Installs, Redline SVD, Continued STCD Dev | Unassigned | New | 5 | #351019
351026 | #351017 | Story | Feature 351017:: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
351025 | #351017 | Story | Feature 351017: IETM Update for ePO - Policy Auditor File Integrity (FIM) Module, Win2012R2 STIGs Update, HIPS Option Policy Findings | Unassigned | New | 3 | #351019
351024 | #351017 | Story | Feature 351017: Agile Team Test Install, STCD Dev & begin Testing of EPO updates | Unassigned | New | 5 | #351019
351023 | #351017 | Story | Feature 351017:: IA Patching and STIGs of 2012 Servers for EPO | Unassigned | New | 5 | #351020
351022 | #351017 | Story | Feature 351017:: Deployment Notes and Operator Impact Inputs for FIM for HBSS Administrator | Unassigned | New | 2 | #351019
351021 | #351017 | Story | Feature 351017: Engineering IETM Development and Integration updates HBSS administrator checking FIM for events. | Unassigned | New | 5 | #351025
351020 | #351017 | Story | Feature 351017: Initial IA Posture Assessment | Unassigned | New | 5 | #351019
351019 | #351017 | Story | Feature Demo – Customer Demo Event - Feature 351017: | Unassigned | New | 1 | #351026
351018 | #351017 | Story | Feature 351017:: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #351023
351011 | #324842 | Problem | ATO Maintenance: Communication Session Cyber Finding for RAF and SF LB CI | Unassigned | Assessing
351010 | #324842 | Problem | ATO Maintenance: PPSM for RAF and SF LB CI | Unassigned | Assessing
350877 | #341794 | Story | Create the Site Functional Test Case | Unassigned | Invalid | 0 | #350863
350876 | #341794 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
350873 | #341794 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #350863
350871 | #341794 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #350863
350870 |  | Story | Mapping a New Spacecraft to its Service Region: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
350869 | #341794 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #350863
350867 | #341794 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #350864
350864 | #341794 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #350863
350862 | #341794 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #350867
350861 |  | Feature | <Feature xxx> | Unassigned | Rejected
350784 |  | Feature | Define PPA database maintenance plan | Unassigned | Rejected
350717 | #349614 | Task | Feature 349614: Kick off of IETM for Correct Verbiage Regarding Configuration Components Coming from M-Demo 06 Out-brief | Unassigned | Done
350647 | #350632 | Story | Allow Region Sets to be Deleted with SARs: Create the Site Functional Test Plan | Unassigned | Invalid | 0 | #350634
350226 | #245437 | Feature | Address Splunk dashboard updates identified in PWIs to assist operators | Unassigned | Rejected
349856 | #345972 | Task | TXO Integration Support - Integrate CSCF & IR | Unassigned | Done
349765 |  | Problem | Large CRL Files result in Tectia authentication issues for PM data collection | Unassigned | Assessing
349589 |  | Story | Integrate AWARE with 8L: Test IB_050305008L_AWARE | Unassigned | Invalid | 0
349191 |  | Story | SA PWI EAD10.8 MPC Documentation | Unassigned | Invalid | 0
348936 | #348921 | Story | Create the Site Validation Test Case | Unassigned | Invalid | 0 | #348923
348935 | #348921 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
348927 | #348921 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #348924
348924 | #348921 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #348923
348922 | #348921 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #348927
348921 |  | Feature | <Feature xxx> | Unassigned | Rejected
348853 | #1013452 | Problem | DD, HQ, HLR, & WHTIS Firewall (WH) are denying snmp (port 161) packets from fcap101-wh-nma to various node (port 161). | PI 16 | Approved
348848 |  | Problem | Issues with "Load Balancer: BigIPService Down Recovery -> Normal Operation Procedure" recovery procedure in the IETM | Unassigned | Assessing
348075 | #338135 | Story | SA SME Support - EAD 11 On-site testing (Colin) | Unassigned | Invalid | 0
348061 | #340845 | Task | Terri Babineaux LOE for RDE / RAN Environment for EA 10.1 | Unassigned | Done
347964 |  | Problem | Document how to specify preset requests so that HAIPE config white paper rules are followed for MFT provisioning | Unassigned | Assessing
347930 |  | Story | SA PWI EAD11.y MPC Documentation | Unassigned | Invalid | 0
347833 |  | Task | CM Release of Zeta SVD (EAD 13) | Unassigned | Invalid
347788 |  | Story | SA PWI EAD11.x MPC Documentation | Unassigned | Invalid | 0
347583 | #341407 | Task | Story 341407: CM Release of 99-P52182E – GTS – HSM – ERS (February IA Patching) | Unassigned | Invalid
347345 |  | Story | Update Custom Alarms IETM for correct severity of AMQ_0001 | Unassigned | Invalid | 0
347203 | #390386 | Story | Feature 347199: Develop/ Update Plan for TPS database upgrade | PI 14 | Invalid | 0 | #347208
347180 | #388076 | Problem | GOVT: OTA urlc_ul crash | EA 14.3 | Closed
347176 | #1013136 | Problem | MILSTD: Group powerLevel in GSLA not calculated correctly upon group rejoin after OTAFT | EA 16.1 | Close Pending
347065 | #347051 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
347064 | #347051 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
347063 | #347051 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
347062 | #347051 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #347053
347061 | #347051 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #347053
347060 | #347051 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
347059 | #347051 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #347053
347058 | #347051 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #347053
347057 | #347051 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #347054
347056 | #347051 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #347053
347055 | #347051 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #347059
347054 | #347051 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #347053
347053 | #347051 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #347060
347052 | #347051 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #347057
347051 | #347072 | Feature | Improve MHAL Director Execution Limitations | Unassigned | Rejected
347050 | #347036 | Task | AWARE Cycle-Time Reductions at WH: Hold Feature Review with SMEs | Unassigned | Invalid
347049 |  | Story | Feature 347036: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
347048 |  | Story | Feature 347036: IETM Development and Integration Updates for TD19-10: Procure AWARE Equipment & Update Drawings for SC | Unassigned | Invalid | 0
347047 |  | Story | Feature 347036: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #347038
347046 |  | Story | Feature 347036: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #347038
347045 |  | Story | Feature 347036: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
347044 |  | Story | Feature 347036: IETM Update for TD19-10: Procure AWARE Equipment & Update Drawings for SC | Unassigned | Invalid | 0 | #347038
347043 |  | Story | Feature 347036: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #347038
347042 |  | Story | Feature 347036: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #347039
347040 |  | Story | Feature 347036: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #347044
347038 |  | Story | Feature Demo – Customer Demo Event - Feature 347036 | Unassigned | Invalid | 0 | #347045
347037 |  | Story | Feature 347036: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #347042
347005 |  | Task | Hold Feature Review with SMEs | Unassigned | Invalid
347003 |  | Story | Feature 346991: IETM Development and Integration Updates for Implementation of AWARE Cycle-Time Reductions at WH | Unassigned | Invalid | 0
347002 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #346993
346999 |  | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #346993
346998 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #346993
346995 |  | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #346999
346992 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #346997
346990 | #346976 | Task | Connected AWARE IA Posture Improvement: Hold Feature Review with SMEs | Unassigned | Invalid
346989 |  | Story | Feature 346984: UX IETM Development and Integration updates part 1 of N for IA Posture Improvement of Connected AWARE | Unassigned | Invalid | 0
346987 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #346978
346986 |  | Story | Connected AWARE IA Posture Improvement: Demo 1 - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0
346985 | #346976 | Story | Connected AWARE IA Posture Improvement: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
346983 |  | Story | Connected AWARE IA Posture Improvement: Demo 1- Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0
346980 |  | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #346984
346972 | #346958 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
346971 | #346958 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
346970 | #346958 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
346969 | #346958 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #346960
346968 | #346958 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #346960
346967 | #346958 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
346966 | #346958 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #346960
346965 | #346958 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #346960
346964 | #346958 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #346961
346963 | #346958 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #346960
346962 | #346958 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #346966
346961 | #346958 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #346960
346960 | #346958 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #346967
346959 | #346958 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #346964
346958 | #304593 | Feature | Implement AWARE Connectivity | Unassigned | Rejected
346932 |  | Problem | Splunk displays UNKNOWN feederlink status & no feederlink configuration during FEP outage | Unassigned | Assessing
346821 |  | Problem | GSS & WCDMA service dashboards experienced Splunk errors | Unassigned | Assessing
346743 |  | Story | Feature 337646: Analyze Incorporate fixes into the design of the Congestion Management dashboards. (PWI 221090) | Unassigned | Invalid | 0
346616 | #318212 | Story | Feature 318212: Build DC Cables | Unassigned | Invalid | 0
346596 | #217406 | Feature | Analyze Future Splunk License Needs | PI 16 | Rejected
346580 | #328496 | Story | SME Support | Unassigned | Invalid | 0
346579 | #328496 | Story | SME Support | Unassigned | Invalid | 0
346532 |  | Problem | MUOS Geolocation: Update Zeta AMS-GS UI Server document Section titled "PKI Updates" to include copying only public key material for app201 and app202 servers onto the UI server | Unassigned | Assessing
346524 |  | Problem | MUOS Geolocation: Update PKI document to copy only the bare minimum files needed for UI and DB server | Unassigned | Assessing
346512 | #328348 | Story | MPC for MUOS Geo UFO Table Update | Unassigned | Invalid | 0
346510 | #328348 | Story | MPC for MUOS Geo UFO Table Update | Unassigned | Invalid | 0
346507 | #328348 | Story | Training for Site Validation Plan/Procedures with Deployment Team and Stakeholders | Unassigned | Invalid | 0
346468 |  | Story | Feature 337646: Resolve PM Data Delivery issues (PWI 343430) - EA 10.3 | Unassigned | Invalid | 0
346431 | #313526 | Story | Define AWARE Linux/Java architecture | Unassigned | Invalid | 0
346356 | #346342 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
346354 | #346342 | Story | Feature 346342: UX IETM Development and Integration updates MAS Stop | Unassigned | Invalid | 0
346353 | #346342 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #346344
346352 | #346342 | Story | Feature 346342: Agile Team Test and Customer Inspection - MAS Stop | Unassigned | Invalid | 0 | #346344
346351 | #346342 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
346348 | #346342 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #346345
346346 | #346342 | Story | <Feature 346342: Engineering IETM Development and Integration updates part 1 of 2 - MAS Start | Unassigned | Invalid | 0 | #346350
346345 | #346342 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #346344
346343 | #346342 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #346348
346329 |  | Story | PI 10 Support of ADI/EMI/PRISM Integration: SME Support(10.6) | Unassigned | Invalid | 0
346323 | #338117 | Story | PI 10 Support of ADI/EMI/PRISM Integration: SME Support (10.4) | Unassigned | Invalid | 0
346320 | #338117 | Story | PI 10 Support of ADI/EMI/PRISM Integration: SME Support (10.3) | Unassigned | Invalid | 0
346286 |  | Story | Obsolescence: (Windows) Trade Study - OTAP / KMS (3) | Unassigned | Invalid | 0
346285 |  | Story | Obsolescence: (Windows) Trade Study - OTAP / KMS (1) | Unassigned | Invalid | 0
346260 |  | Story | Obsolescence: (Windows) Trade Study - OTAP / KMS (2) | Unassigned | Invalid | 0
346258 |  | Story | Obsolescence: (Windows) Trade Study - OTAP / KMS (1) | Unassigned | Invalid | 0
346098 |  | Story | Feature 337646: Improve the stability of Tectia on mas-nw/wh (PWI 327185) | Unassigned | Invalid | 0
346097 |  | Story | Feature 337646: Improve the stability of Tectia on mas-nw/wh (PWI 327185) | Unassigned | Invalid | 0
346095 | #337646 | Story | Feature 337646: Implement fix - stability of Tectia on mas-nw/wh (Problem 327185) | Unassigned | Invalid | 0
346092 |  | Story | Feature 337646: Custom alarm IETM support for PM to send faults (PWI 327911) | Unassigned | Invalid | 0
346087 |  | Story | Feature 337646: Update Ping Probe Alarm Recovery Procedures (Implement) | Unassigned | Invalid | 0
346086 | #345040 | Story | Incorporate fixes into the design of the Congestion Management dashboards. (Problem 221090) | Unassigned | Invalid | 0
346084 | #345040 | Story | Feature 345040: Update STCD for PWI, Install, Test, and Verify PCR (Problem 329720) | Unassigned | Invalid | 0
346083 | #345040 | Story | Feature 345040: FCAP FaultMgmt SVD (Problem 329720) - IETM Update | Unassigned | Invalid | 0
346082 | #345040 | Story | Feature 345040: Complete Review - FCAP FaultMgmt SVD (Problem 329720) | Unassigned | Invalid | 0
346081 | #345040 | Story | Feature 345040: Implement Update FCAP FaultMgmt SVD (Problem 329720) | Unassigned | Invalid | 0
346079 |  | Story | Feature 337646: Update ActiveMQ SVD (PWI 329614) - EA 10.6 | Unassigned | Invalid | 0
346078 | #329614 | Story | Feature 337646: Update ActiveMQ SVD (PWI 329614) - EA 10.5 | Unassigned | Invalid | 0
346076 |  | Story | Feature 337646: Update ActiveMQ SVD (PWI 329614) - EA 10.3 | Unassigned | Invalid | 0
346075 |  | Story | Feature 337646: Update ActiveMQ SVD (PWI 329614) - EA 10.2 | Unassigned | Invalid | 0
346074 |  | Story | Feature 337646: Update ActiveMQ SVD (PWI 329614) - EA 10.1 | Unassigned | Invalid | 0
345997 | #338148 | Story | MAGIC Trouble Ticket Support (EA 10.3) | Unassigned | Invalid | 0
345990 | #338153 | Story | MAGIC HW FRB Support (EA 10.3) | Unassigned | Invalid | 0
345965 | #338135 | Story | MAGIC SME Support (EA 10.3) | Unassigned | Invalid | 0
345964 |  | Story | MAGIC SME Support (EA 10.2) - Duplicate of 338128 | Unassigned | Invalid | 0
345830 | #340486 | Story | ODE Post Upgrade Optimization of Clear Trigger Cleanup | PI 17 | New | 8
345825 | #315562 | Story | WCDMA Service Status: Phase 2 - DSN & IP Teleport: Initial IA Scan | Unassigned | Invalid | 0
345818 |  | Story | Lab - TXO - Upgrade RNC to Class C | Unassigned | Invalid | 0
345808 | #1013136 | Problem | MAINT: WF got stuck during expedited for mobility | EA 16.1 | Implementing
345802 | #388076 | Problem | HMS: Restart Measurement after RAU while joined to a Group | EA 14.3 | Closed
345796 | #1001912 | Problem | MAINT: Group Talker loses data | EA 15.1 | Closed
345795 | #1013136 | Problem | MAINT: Group Tx denied continuosly, WF did not go OOS | EA 16.1 | Implementing
345779 | #1001912 | Problem | GOVT: WF task crash when active KS deleted | EA 15.1 | Closed
345748 | #1013136 | Problem | GOVT: WF Implementation Missing for Design to Resolve Group Key Discrepancy between Profile and CS/S | EA 16.1 | Close Pending
345718 | #388076 | Problem | MAINT: WF got stuck when tx override in EMCON mode | EA 14.3 | Closed
345715 | #388076 | Problem | HMS: Periodic Ranging not executed when T318 timer expires during RAU | EA 14.3 | Closed
345710 |  | Story | RR2: Uncovered state timer changes | Unassigned | Invalid | 0
345707 | #1013136 | Problem | HMS: Normal RRC Connection Release on a RAU retry is triggering OOS | EA 16.1 | Implementing
345694 | #1015911 | Problem | RR2: UE fails to trigger mobility when the group id is removed from the groupEnabled messages. | PI 16 | Approved
345687 | #1013136 | Problem | RR2: Invalid Cell ID/ sbcIndex displayed during EMCON in boot up. | EA 16.1 | Close Pending
345678 | #1001912 | Problem | RR2: OTAFTed GK Key returned success by AsNas when AIM failed the decryption | EA 14.4 | Closed
345641 | #1013136 | Problem | MAINT: Not Restoring C0 Header Compression Contexts Entering Monitor Mode or Unjoining Group | EA 16.1 | Close Pending
345638 |  | Story | N2N: Group AM Retransmission Optimization for Lower RABs | Unassigned | Invalid | 0
345633 | #1013136 | Problem | GOVT: The new commonGK key index is blanked out when updating the Current commonGk with the Next commonGk key data | EA 16.1 | Close Pending
345603 | #340486 | Story | ODE- Create/ Update Post Upgrade Optimization Plan | PI 17 | New | 1
345398 | #255707 | Feature | Support PMW-146 Initial Provisioning Time Tiger Team | PI 14 | Rejected
345352 | #338135 | Story | SME Cross Training | Unassigned | Invalid | 0
345232 | #346596 | Story | Determine amount of additional Splunk Licenses | PI 16 | Invalid | 0
345211 | #288136 | Story | Feature 288136: Investigate issue and determine solution | Unassigned | Invalid | 0
345209 | #288136 | Story | Feature 288136: Investigate issue and determine solution | Unassigned | New | 5
345056 | #1013136 | Problem | GOVT: WF does not range in group listener | EA 16.1 | Implementing
345055 |  | Problem | OTAP needs to generate a critical alarm when the OTAP Application service is stopped. | Unassigned | Assessing
345040 | #245437 | Feature | Reserve time for PWIs after WCDMA and provisioning SA deployment | Unassigned | Rejected
344747 |  | Story | SME support - Situational Awareness (FM, PM) for TD 19-10 Service Management - 10.2 | Unassigned | Invalid | 0
344348 | #344334 | Task | NAVSOC-RAF Redundancy Deficiency: Hold Feature Review with SMEs - Feature 344334 | Unassigned | Invalid
344347 | #344334 | Story | NAVSOC-RAF Redundancy Deficiency: NAVSOC-RAF Redundancy IR1 router failure: UX IETM Review | Unassigned | Invalid | 0
344346 | #344334 | Story | Feature 344334: IETM Development and Integration Updates to Fix Problem 303052 - NAVSOC-RAF Redundancy Deficiency (SR 933835/INC000002314514: AJM Connections) | Unassigned | Invalid | 0
344345 |  | Story | Feature 344334: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #344336
344338 | #344334 | Story | NAVSOC-RAF Redundancy Deficiency: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #344342
344314 | #333889 | Task | Assess Problem 341471 | Unassigned | Invalid
344304 | #344290 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
344303 | #344290 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
344302 | #344290 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
344301 | #344290 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #344292
344300 | #344290 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #344292
344299 |  | Story | ETT Redlines: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
344296 | #344290 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #344293
344295 |  | Story | ETT Redlines: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #344292
344293 | #344290 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #344292
344292 |  | Story | Feature Demo – Customer Demo Event - ETT Redlines | Unassigned | Invalid | 0 | #344299
344291 | #344290 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #344296
344290 |  | Feature | <Feature xxx> | Unassigned | Rejected
344275 |  | Story | Integrate AWARE with 8L: Burn In Test - Radio Support Part 2 | Unassigned | Invalid | 0
344258 |  | Story | Feature 257550: Initial Task Analysis for TD19-10: Analysis of AWARE Operator Interface Changes to Support O-level | Unassigned | Invalid | 0
344228 |  | Story | 10.5 SME Support (SA SME Support) | Unassigned | Invalid | 0
344221 |  | Story | Feature 344215: RF Alignment AU - Post Travel Data Analysis & Archiving - Jones | Unassigned | Invalid | 0
344212 | #344196 | Story | MUOS Geolocation Support/Maintenance: HW/SW Mapping | Unassigned | Invalid | 0
344211 |  | Story | Remove Legacy Alt Geo: Initiate CM PDO Processing for CIs | Unassigned | Invalid | 0
344202 | #344196 | Story | MUOS Geolocation Support/Maintenance: IA Patching and STIGs for removing GEO from SW | Unassigned | Invalid | 0 | #344199
344197 | #344196 | Story | MUOS Geolocation Support/Maintenance: IA - Define Patch/ Stig Requirements for removing legacy from SW | Unassigned | Invalid | 0 | #344202
344194 |  | Story | Procure additional Splunk Licenses | Unassigned | Invalid | 0
344182 | #290957 | Story | Support RCG Logging Design - SE | PI 15 | Invalid | 0
344181 | #290957 | Story | Support RCG Logging Design - SE | PI 15 | Invalid | 0
344180 | #290957 | Story | Support RCG Logging Design - WF-RAN | PI 15 | Invalid | 0
344173 | #344164 | Story | RDE BackUp CONTINGENCY - Configure the existing RAN Veritas Backup system to support UCS hosted servers | Unassigned | Invalid | 0
344164 | #243505 | Feature | RDE Backup CONTINGENCY Plan | Unassigned | Rejected
344081 |  | Problem | SPLUNK incorrectly display congestion on a cell that had been cleared of congestion | Unassigned | Assessing
343920 | #243502 | Story | CM Release Work for EAD 16 | EA 15.4 | New | 1
343918 | #243502 | Story | CM Release Work for EAD 15 OOC | EA 15.4 | New | 1
343917 | #243502 | Story | CM Release Work for EAD 15 | EA 15.4 | New | 1
343914 | #243502 | Story | CM Release Work for EAD 14 | EA 15.1 | Done | 1
343885 | #243502 | Story | CM Release Work for EAD 13 OOC | EA 15.4 | New | 1
343804 | #356094 | Story | Feature 356094: Implement Suppression of False Cell Down During ET Switchover | PI 15 | Invalid | 0
343784 | #343771 | Story | Feature 343771: UX IETM Development and Integration updates | Unassigned | Invalid | 0
343778 |  | Story | Feature 343771: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0
343740 | #343729 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #343731
343739 | #343729 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #343731
343447 | #338135 | Story | SME PPA Cross Training | Unassigned | Invalid | 0
343446 | #338135 | Story | SME PPA Cross Training | Unassigned | Invalid | 0
343287 | #343273 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
343284 | #343273 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #343275
343283 | #343273 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #343275
343282 | #343273 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
343279 | #343273 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #343276
343278 | #343273 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #343275
343276 | #343273 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #343275
343274 | #343273 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #343279
343273 | #216649 | Feature | Rejected: Update IETMs to Monitor for Module Level Provisioned Groups | Unassigned | Rejected
343263 |  | Story | SME support MHAL Web Server - Alex | Unassigned | Invalid | 0
343262 |  | Story | SME support MHAL Web Server - Craig | Unassigned | Invalid | 0
343163 | #241246 | Story | <Feature xxx>: Review the Site Functional Test Plan within STCD and get customer stakeholder approval | Unassigned | Invalid | 0 | #241249
343140 |  | Story | CPICH SME Support | Unassigned | Invalid | 0
343138 | #329082 | Story | CPICH SME Support | Unassigned | Invalid | 0
343065 | #343061 | Feature | Analysis of CDR to determine root cause and implications (CSCFR, MAS, SGSN and DSN GW) | Unassigned | Rejected
342873 | #293338 | Story | Developer testing and acceptance of Virtualized Developer Workstations | EA 14.3 | Done | 5
342862 | #293338 | Story | Research Licenses and approach for SWIT Builds in the SDE | EA 14.2 | Done | 3 | #1000852
342829 |  | Story | Support Zeta Weekly Tag Ups - 10.6 | Unassigned | Invalid | 0
342814 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #342805
342813 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #342805
342811 | #342803 | Story | Feature 342803: Geo Support and Maintenance Delivery - IETM Update | Unassigned | Invalid | 0 | #342805
342809 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #342806 #371759
342804 |  | Story | Geo: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #342809
342802 | #293338 | Story | SWIT Virtualization - Create VMs for Developer Workstations from Templates | EA 14.3 | Done | 8 | #342850 #342851 #334844 #334849 #342873
342800 | #342786 | Task | Feature 342786: Hold Feature Review with SMEs | PI 15 | Invalid
342799 | #342786 | Story | Feature 342786: UX IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0
342798 | #342786 | Story | Feature 342786: IETM Development and Integration Updates for Incorporation of Redlines for Antennae ET Tracking Procedure for KaBand Robustness SUT switching (I-level) | PI 15 | Invalid | 0
342797 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #342788
342796 | #342786 | Story | Feature 342786: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) - Part 2 | PI 15 | Invalid | 0 | #342788
342795 | #342786 | Story | Feature 342786: Release I-Level doc/ Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
342794 | #342786 | Story | Feature 342786: IETM Update for Incorporation of Redlines for Antennae ET Tracking Procedure for KaBand Robustness SUT Switching | PI 15 | Invalid | 0 | #342788
342793 | #342786 | Story | Feature 342786: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) - Part 1 | PI 15 | Invalid | 0 | #342788
342792 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #342789
342791 | #342786 | Story | Feature 342786: Deployment Notes and Operator Impact Inputs Part 1 of N | PI 15 | Invalid | 0 | #342788
342790 | #342786 | Story | Feature 342786: Engineering IETM Development and Integration updates part 1 of N | PI 15 | Invalid | 0 | #342794
342789 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #342788
342788 | #342786 | Story | Feature Demo – Customer Demo Event - 342786 - Incorporate Redlines for Antennae ET Tracking Procedure for KaBand Robustness SUT switching | PI 15 | Invalid | 0 | #342795
342787 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #342792
342786 | #245572 | Feature | Incorporate Redlines for Antennae ET Tracking Procedure for KaBand Robustness SUT switching | PI 15 - In Progress | Rejected
342632 |  | Story | Feature 339182: Create List of Functions the Replacement FOUO Printer Requires | Unassigned | Invalid | 0
342560 | #293338 | Story | SDE - Document SWIT Dev Env Network, Hardware, Servers, Storage, Virtualization | EA 14.5 | Done | 5
342439 | #329146 | Story | PKI site support for certificate updates - part 13 | Unassigned | Invalid | 0
342438 | #329146 | Story | PKI site support for certificate updates - part 12 | Unassigned | Invalid | 0
342437 | #329146 | Story | PKI site support for certificate updates - part 11 | Unassigned | Invalid | 0
342395 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
342337 |  | Story | SME Support for ULX- 9.5 | Unassigned | Invalid | 0
342177 | #342163 | Task | Feature 342163: Hold Feature Review with SMEs | EA 15.1 | Done
342175 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
342174 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #342165
342173 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #342165
342172 | #342163 | Story | Feature 342163: Initiate CM PDO Processing for all CI's | EA 15.4 | New | 1
342171 | #342163 | Story | Feature 342163: IETM Update for Incorporating Site Redlines for TACLANE Obsolescence | EA 15.2 | Done | 3 | #342165
342170 | #342163 | Story | Feature 342163: Agile Team develop and review | Unassigned | Invalid | 0 | #342165
342169 |  | Story | IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #342166
342168 | #342163 | Story | Feature 342163: Deployment Notes and Operator Impact [Engineering Docs] | EA 15.1 | Done | 1 | #342165
342166 | #342163 | Story | Feature 342163: IA Posture Assessment | EA 15.1 | Done | 1 | #342165
342165 | #342163 | Story | Feature Demo – Customer Demo Event - 342163 Site Redlines for TACLANE Obsolecence | EA 15.4 | New | 1 | #342172
342164 |  | Story | IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #342169
342163 | #245808 | Feature | Site Redlines for TACLANE Obsolescence (Identified during EAD 11 deployment) | EA 15.4 | Ready for Feature Demo
342162 |  | Task | GD Scottsdale AWARE Italy Support (Invalidated) | Unassigned | Invalid
342160 | #1013259 | Story | Feature 1013259: Sicily On-site AWARE RF alignment | PI 17 | New | 8
342159 |  | Story | Perform AWARE RF alignment | Unassigned | Invalid | 0
342054 | #347074 | Feature | Complete development of Sicily Connected AWARE | PI 16 - In Progress | Implementing |  | #1013259
342036 |  | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0
342035 |  | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
342034 |  | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #342021
342033 |  | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #342032
342032 |  | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0
342031 |  | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
342030 |  | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
342029 |  | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0
342028 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
342027 |  | Story | <Feature yyy>: IA Posture Assessment - Define Patch and STIG Requirements | Unassigned | Invalid | 0 | #342034
342026 | #342018 | Story | Feature 342018: Test Report, needed 30 days prior to FRCB. | EA 14.1 | Done | 1
342024 | #342018 | Story | Docs for Connected AWARE Sicily FRCB: System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0
342021 |  | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #342029
342018 | #347074 | Feature | TD19-10: Prepare Docs for Connected AWARE Sicily FRCB (to support deployment post MOT&E) | EA 14.1 | Done
342016 |  | Story | SA Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
342013 | #342000 | Story | Connected AWARE IETMs: JDTA Task Analysis | Unassigned | Invalid | 0
342012 |  | Story | ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
342011 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #342002
342009 | #342000 | Story | Connected AWARE IETMs: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
342006 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #342003
342003 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #342002
342001 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #342006
341999 | #347074 | Feature | Deliver Connected AWARE Training for Sicily EAD 18 Deployment | PI 16 | Approved
341940 | #341939 | Story | Feature 341939: Analysis & Creation of Procedure to Reset the Battery Settings after Replacement (PLC Module) | Unassigned | Invalid | 0
341932 |  | Problem | NMS SVD Changes Needed for Repair and Replace - AV/HIDS | Unassigned | Assessing
341800 |  | Story | Generate and submit Test Report for FRCB | Unassigned | Invalid | 0
341469 | #364632 | Problem | SCS OA File Server: SVD: Redline Update SVD to include all changes from R 1.4 deployment | PI 17 | Assessing
341396 | #341382 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
341395 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
341394 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
341393 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #341384
341392 |  | Story | UX IETM Support | Unassigned | Invalid | 0 | #341384
341391 | #341382 | Task | Feature 341382: Initiate CM PDO Processing for all CI's | Unassigned | Invalid
341388 |  | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #341385
341385 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #341384
341383 |  | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #341388
341357 | #341343 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
341356 | #341343 | Story | Feature 341343 UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
341355 | #341343 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
341354 | #341343 | Story | Feature 341343 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #341345
341353 | #341343 | Story | Feature 341343 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #341345
341351 | #341343 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #341345
341349 | #341343 | Story | Feature 341343 IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #341346
341347 | #341343 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #341351
341344 | #341343 | Story | Feature 341343: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #341349
341337 | #297966 | Story | Feature 297966: Create Site Validation Plan | Unassigned | Invalid | 0
340924 | #338135 | Story | Support WH site installs 10.2 | Unassigned | Invalid | 0
340556 | #365133 | Task | IT Dependency: RDE Solaris P2V of RAN Solaris Servers (17 items) | Unassigned | In Development
340486 | #1022632 | Feature | ODE Network Post-Upgrade Optimization | PI 17 - Candidate | Approved
340457 |  | Story | LOE TT Support - EA 10.3 | Unassigned | Invalid | 0
340456 |  | Story | LOE TT Support - EA 10.2 | Unassigned | Invalid | 0
340455 |  | Story | LOE TT Support - EA 10.1 | Unassigned | Invalid | 0
340423 |  | Story | ETISP Trouble Ticket Support (2) - EA 10.6 | Unassigned | Invalid | 0
340422 |  | Story | ETISP Trouble Ticket Support (2) - EA 10.4 | Unassigned | Invalid | 0
340421 |  | Story | ETISP Trouble Ticket Support (2) - EA 10.2 | Unassigned | Invalid | 0
339786 |  | Feature | <Feature xxx> | Unassigned | Rejected
339768 |  | Feature | <Feature xxx> | Unassigned | Rejected
339760 | #339746 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
339759 | #339746 | Story | UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339758 | #339746 | Story | ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339757 | #339746 | Story | Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #339748
339756 | #339746 | Story | Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #339748
339754 | #339746 | Story | ILS IETM update (Template) | Unassigned | Invalid | 0 | #339748
339752 | #339746 | Story | IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #339749
339750 | #339746 | Story | Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #339754
339749 | #339746 | Story | IA Posture Assessment | Unassigned | Invalid | 0 | #339748
339747 | #339746 | Story | IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #339752
339745 | #339731 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
339744 | #339731 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339743 | #339731 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339742 | #339731 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #339733
339741 | #339731 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #339733
339740 | #339731 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
339739 | #339731 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #339733
339738 | #339731 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #339733
339737 | #339731 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #339734
339736 | #339731 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #339733
339735 | #339731 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #339739
339734 | #339731 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #339733
339733 | #339731 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #339740
339732 | #339731 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #339737
339731 |  | Feature | <Feature xxx> | Unassigned | Rejected
339442 |  | Story | SVD Update: MAS installation - PWI 287761 (EA 9.5) | Unassigned | Invalid | 0
339428 |  | Story | Test TXO boards identified for EA 9.4 | Unassigned | Invalid | 0
339321 | #1004171 | Problem | Module May Repeatedly Reject Provisioning of a Group | EA 15.4 | Verifying
339222 | #333889 | Task | Assess Problem 223592 | Unassigned | Invalid
339195 |  | Story | Feature 339182: UX Integration Updates & Training Needs for the Replacement and Upgrade the FOUO Printer in the NMF | Unassigned | Invalid | 0
339194 |  | Story | Feature 339182: Update IETM | Unassigned | Invalid | 0
339193 |  | Story | Feature 339182: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 for Replace and Upgrade the FOUO printer in the NMF | Unassigned | Invalid | 0
339190 |  | Story | Feature 339182: Update IETM | Unassigned | Invalid | 0 | #339184
339188 |  | Story | Feature 339182: IA Patching and STIGs for Replace and Upgrade the FOUO printer in the NMF | Unassigned | Invalid | 0 | #339185
339144 | #338744 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
339143 |  | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339142 | #339130 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339141 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #339132
339138 | #339130 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #339132
339135 | #339130 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #339132
339134 | #339130 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #339138
339132 | #339130 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #339139
339130 |  | Feature | <Feature xxx> | Unassigned | Rejected
339098 | #329146 | Story | Remote SME support for AMS-GS servers | Unassigned | Invalid | 0
339071 |  | Story | ETISP - Test updated ETISP L3 test procedures | Unassigned | Invalid | 0
339064 | #339050 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
339063 | #339050 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339062 | #339050 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
339061 | #339050 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #339052
339060 | #339050 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #339052
339059 | #339050 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
339058 | #339050 | Story | <Feature xxx>:ILS IETM update (Template) | Unassigned | Invalid | 0 | #339052
339057 | #339050 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #339052
339056 | #339050 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #339053
339055 | #339050 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #339052
339054 | #339050 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #339058
339053 | #339050 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #339052
339052 | #339050 | Story | Feature Demo – Customer Demo Event - <Feature xxx> | Unassigned | Invalid | 0 | #339059
339051 | #339050 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #339056
339050 | #225732 | Feature | Convert OSS-RC Alarm Forwarding Procedure to O-Level | Unassigned | Rejected
338900 |  | Story | LOE - TT Support - EA 10.1 | Unassigned | Invalid | 0
338897 |  | Story | LOE TT Support - EA 10.4 | Unassigned | Invalid | 0
338894 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.4 | Unassigned | Invalid | 0
338893 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.3 | Unassigned | Invalid | 0
338892 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.2 | Unassigned | Invalid | 0
338891 |  | Story | Daily Ground Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.1 | Unassigned | Invalid | 0
338890 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.6 | Unassigned | Invalid | 0
338889 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.5 | Unassigned | Invalid | 0
338888 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.4 | Unassigned | Invalid | 0
338887 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.3 | Unassigned | Invalid | 0
338886 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.2 | Unassigned | Invalid | 0
338885 |  | Story | Daily Call Bank Health Check Issues Analysis and Reporting (Incident, PWI or Trouble Ticket) - EA 10.1 | Unassigned | Invalid | 0
338868 |  | Story | Weekly TOFF Data Consolidation - EA 10.3 | Unassigned | Invalid | 0
338867 |  | Story | Weekly TOFF Data Consolidation - EA 10.2 | Unassigned | Invalid | 0
338866 |  | Story | Weekly TOFF Data Consolidation - EA 10.1 | Unassigned | Invalid | 0
338865 |  | Story | Recommend Metrics Collection for Revised Metric Plan - EA 10.6 | Unassigned | Invalid | 0
338864 |  | Story | Recommend Metrics Collection for Revised Metric Plan - EA 10.5 | Unassigned | Invalid | 0
338863 |  | Story | Recommend Metrics Collection for Revised Metric Plan - EA 10.3 | Unassigned | Invalid | 0
338850 |  | Story | Daily Ground Health Check and Incident Capture for TOFF Metrics - EA 10.3 | Unassigned | Invalid | 0
338849 |  | Story | Daily Ground Health Check and Incident Capture for TOFF Metrics - EA 10.2 | Unassigned | Invalid | 0
338848 |  | Story | Daily Ground Health Check and Incident Capture for TOFF Metrics - EA 10.1 | Unassigned | Invalid | 0
338841 |  | Story | Daily Ground Health Check and Incident Capture for TOFF Metrics - EA 10.4 | Unassigned | Invalid | 0
338840 |  | Story | EA 10.5 Capture Daily Ground Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
338839 |  | Story | EA 10.2 Capture Daily Ground Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
338838 |  | Story | Weekly TOFF Data Consolidation - EA 10.4 | Unassigned | Invalid | 0
338436 |  | Story | Swap out radios in Taunton | Unassigned | Invalid | 0
338327 |  | Story | Coordinate Site Validation Plan/Procedures with Deployment Team and Stakeholders | Unassigned | Invalid | 0
338325 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Feature Demo Prep | Unassigned | Invalid | 0
338324 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Coordinate Site Validation Plan/Procedures with Deployment Team and Stakeholders | Unassigned | Invalid | 0
338317 | #338135 | Story | EAD 11 TACLANE Deployment - WH | Unassigned | Invalid | 0
338309 | #338303 | Story | Configuration management Architecture baseline and Tools evaluation (SA Component) | Unassigned | Invalid | 0
338307 | #338303 | Story | Configuration management Architecture baseline and Tools evaluation (SE Component) | Unassigned | Invalid | 0
338139 |  | Story | MAGIC SME Support | Unassigned | Invalid | 0
338108 |  | Story | Coordinate Site Validation Plan/Procedures with Deployment Team and Stakeholders | Unassigned | Invalid | 0
337710 | #328348 | Story | Site Validation Plan/Procedures with Deployment Team and Stakeholders | Unassigned | Invalid | 0
337660 | #337646 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
337659 |  | Story | Feature 337646: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
337658 |  | Story | Feature 337646: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
337652 | #337646 | Story | Feature 337646: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #337649
337650 |  | Story | Feature 337646: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #337654
337647 | #337646 | Story | Feature 337646: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #337652
337645 |  | Feature | Reserve time for bug fixes from MOT&E specific to SA | Unassigned | Rejected
337573 | #294836 | Story | KG175A Replacement: Router SVD review and build | Unassigned | Invalid | 0
337428 | #1013452 | Problem | Update firewalls to allow SSH from a Tectia client on a Windows 10 workstation | PI 16 | Approved |  | #339392
337050 | #327942 | Story | MAGIC Trouble Ticket Support (EA 9.2) | Unassigned | Invalid | 0
336988 | #245570 | Problem | RNC - RNH sends cellAvailableInd to GNH when op_state is disabled | Unassigned | Assessing
336799 | #393391 | Problem | CSCF and HSS files on root partition fill up | PI 16 | Approved
336784 |  | Problem | Update Splunk dashboard help to explain that some WCDMA failure patterns may imply AWARE failures & not system failures | Unassigned | Assessing
336717 | #336703 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
336716 | #336703 | Story | UX Support Availability and Capability Maps: Dashboard Review | Unassigned | Invalid | 0
336715 | #336703 | Story | Feature 336703: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
336714 | #336703 | Story | Feature 336703: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #336705
336713 | #336703 | Story | Feature 336703: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #336705
336712 | #336703 | Story | Feature 336703: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
336711 | #336703 | Story | Feature 336703: ILS IETM update (Template) | Unassigned | Invalid | 0 | #336705
336710 | #336703 | Story | Feature 336703: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #336705
336709 | #336703 | Story | Feature 336703: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #336706
336708 | #336703 | Story | Feature 336703: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #336705
336707 | #336703 | Story | Feature 336703: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #336711
336706 | #336703 | Story | Feature 336703: IA Posture Assessment | Unassigned | Invalid | 0 | #336705
336705 | #336703 | Story | Feature Demo – Customer Demo Event - Feature 336703 | Unassigned | Invalid | 0 | #336712
336704 | #336703 | Story | Feature 336703: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #336709
336703 | #267568 | Feature | Splunk Ground Availability and Capability Maps for Warfighter | Unassigned | Rejected
336576 |  | Task | Story 326024: CM Release of MUOS_IG_GS_Network_Router_SVD_98-P55509M (EAD 11) | Unassigned | Invalid
336239 | #1004171 | Problem | GNH router forwarding table corruption | EA 15.4 | Verifying
336200 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - OS Configuration | Unassigned | New | 5
336199 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - OS Configuration | Unassigned | New | 1
336197 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Access Control | Unassigned | New | 1
336194 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - SQL | Unassigned | New | 1
336190 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Audit and Syslog | Unassigned | New | 1
336189 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Remove Unneeded Services | Unassigned | New | 1
336186 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - SSL Configuration | Unassigned | New | 1
336184 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Web Server Configuration | Unassigned | New | 5
336177 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - File and Host Intrusion Protection | Unassigned | New | 5
336176 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - File and Host Intrusion Protection | Unassigned | New | 1
336171 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Fault Management Application Replacement | Unassigned | New | 1
336170 | #336156 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
336169 | #336156 | Story | test of RTC Template: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #336158
336168 | #336156 | Story | test of RTC Template: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #336158
336167 | #336156 | Story | test of RTC Template: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
336166 | #336156 | Story | test of RTC Template: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
336165 | #336156 | Story | test of RTC Template: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
336164 | #336156 | Story | test of RTC Template: ILS IETM update | Unassigned | Invalid | 0 | #336158
336163 | #336156 | Story | test of RTC Template: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #336158
336162 | #336156 | Story | test of RTC Template: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #336159
336161 | #336156 | Story | test of RTC Template: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #336158
336160 | #336156 | Story | test of RTC Template: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #336164
336159 | #336156 | Story | test of RTC Template: IA Posture Assessment | Unassigned | Invalid | 0 | #336158
336158 | #336156 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #336167
336157 | #336156 | Story | test of RTC Template: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #336162
336156 |  | Feature | test of RTC template | Unassigned | Rejected
336155 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Fault Management Application Replacement | Unassigned | New | 5
336148 | #336108 | Story | Feature 336108: Windows 2003 NMF FCAPS Servers in FOUO and Secret Enclaves - Routing Protocols | Unassigned | New | 1
336140 | #336127 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #336129
336139 | #336127 | Story | Feature 336127: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 for Adding Java to Windows 10 for Laptops and Workstations | Unassigned | Invalid | 0 | #336129
336137 | #336127 | Story | Feature 336127: UX IETM Development and Integration updates for Adding Java to Windows 10 Laptops and Workstations | Unassigned | Invalid | 0
336135 | #336127 | Story | Feature 336127: IETM update for Adding Java to Windows 10 Laptops and Workstations | Unassigned | Invalid | 0 | #336129
336131 | #336127 | Story | Feature 336127: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #336135
336122 | #336108 | Task | Feature 336108: Hold Feature Review with SMEs | Unassigned | New
336121 | #336108 | Story | Feature 336108: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #336110
336120 | #336108 | Story | Feature 336108: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #336110
336119 | #336108 | Story | Feature 336108: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
336118 | #336108 | Story | Feature 336108: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
336117 | #336108 | Story | Feature 336108: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
336116 | #336108 | Story | Feature 336108: ILS IETM update | Unassigned | New | 3 | #336110
336115 | #336108 | Story | Feature 336108: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #336110
336114 | #336108 | Story | Feature 336108: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #336111
336113 | #336108 | Story | Feature 336108: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #336110
336112 | #336108 | Story | Feature 336108: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #336116
336111 | #336108 | Story | Feature 336108: IA Posture Assessment | Unassigned | New | 8 | #336110
336110 | #336108 | Story | Feature 336108: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #336119
336109 | #336108 | Story | Feature 336108: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #336114
336074 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update Login Banners | Unassigned | New | 1
336073 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update SNMP v3 (for default name, get bulk, etc.) | Unassigned | New | 1
336072 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update Internet Transport and Routing Configurations | Unassigned | New | 1
336071 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update Syslog and Audits (audit log rotations, audit password protection) | Unassigned | New | 1
336070 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update OS Configuration (root account management, access control program, dynamic kernel functions) | Unassigned | New | 1
336066 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - File Integrity and Host Protection (HBSS, system package management) | Unassigned | New | 1
336063 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Access Control (password complexity, password expiry, crypto, UID, GID, etc.) | Unassigned | New | 1
336062 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Apply NTP Updates . | Unassigned | New | 1
336061 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update the Web Server Configuration (HTTP Trace/Track, Apache Server, etc.). | Unassigned | New | 1
336057 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Configure Run Control Script (limit execution rights) | Unassigned | New | 1
336053 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Remove unneeded services (rlogin, rsh, telnet, etc.) | Unassigned | New | 1
336052 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Update OS Configuration attributes | Unassigned | New | 1
336049 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Directory and File Access Controls | Unassigned | New | 1
336048 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Remove Host Files (.rhosts, .shosts, .host.equiv, .forward, etc.) | Unassigned | New | 1
336043 | #335969 | Story | Feature 335969: Solaris 9 DNS servers - Boot from Boot Device | Unassigned | New | 1
335986 |  | Problem | fcap101-wh-nma issue - whiassfw1 firewall reports that fcap101-wh-nma communication with etnbe-au/nw/sc/wh over port 8081 is not allowed. | Unassigned | Assessing
335983 | #335969 | Task | Feature 335969: Hold Feature Review with SMEs | Unassigned | New
335982 | #335969 | Story | Feature 335969: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #335971
335981 | #335969 | Story | Feature 335969: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #335971
335980 | #335969 | Story | Feature 335969: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
335979 | #335969 | Story | Feature 335969: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
335978 | #335969 | Story | Feature 335969: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
335977 | #335969 | Story | Feature 335969: ILS IETM update | Unassigned | New | 3 | #335971
335976 | #335969 | Story | Feature 335969: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #335971
335975 | #335969 | Story | Feature 335969: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #335972
335974 | #335969 | Story | Feature 335969: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #335971
335973 | #335969 | Story | Feature 335969: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #335977
335972 | #335969 | Story | Feature 335969: IA Posture Assessment | Unassigned | New | 8 | #335971
335971 | #335969 | Story | Feature 335969: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #335980
335970 | #335969 | Story | Feature 335969: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #335975
335966 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Login Banners | Unassigned | New | 1
335965 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Internet Transport and Routing configurations | Unassigned | New | 1
335964 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Syslog and Audits (audit log rotations, audit password protection | Unassigned | New | 1
335963 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - File Integrity and Host Protection (HBSS, system package management) | Unassigned | New | 1
335961 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Access Control (password complexity, password expiry, crypto, UID, GID, etc.) | Unassigned | New | 1
335960 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - OS Configuration (non-executable stacks, system access control, directory paths, etc.) | Unassigned | New | 1
335959 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Directory Access Controls (public directories, /etc directories, ftp access, etc.) | Unassigned | New | 1
335958 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - NTP Updates | Unassigned | New | 1
335957 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - SSL Cert fixes. | Unassigned | New | 1
335955 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Update Webserver Configuration | Unassigned | New | 1
335954 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Remove Track/Trace for HTTP | Unassigned | New | 1
335952 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Fix Citrix published applications, etc. | Unassigned | New | 1
335949 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - LDAP server update (fix NULL searches) | Unassigned | New | 1
335946 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Configure Run Control Script | Unassigned | New | 1
335944 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Remove host files | Unassigned | New | 1
335942 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Boot only from boot device configuration | Unassigned | New | 1
335941 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - eDirectory eHost configuration changes | Unassigned | New | 1
335934 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - SNMP v3 Updates | Unassigned | New | 1
335932 | #335885 | Story | Feature 335885: Solaris 9 servers in NMF FOUO - Remove unneeded services. | Unassigned | New | 1
335899 | #335885 | Task | Feature 335885: Hold Feature Review with SMEs | Unassigned | New
335898 | #335885 | Story | Feature 335885: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #335887
335897 | #335885 | Story | Feature 335885: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #335887
335896 | #335885 | Story | Feature 335885: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
335895 | #335885 | Story | Feature 335885: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
335894 | #335885 | Story | Feature 335885: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
335893 | #335885 | Story | Feature 335885: ILS IETM update | Unassigned | New | 3 | #335887
335892 | #335885 | Story | Feature 335885: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #335887
335891 | #335885 | Story | Feature 335885: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #335888
335890 | #335885 | Story | Feature 335885: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #335887
335889 | #335885 | Story | Feature 335885: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #335893
335888 | #335885 | Story | Feature 335885: IA Posture Assessment | Unassigned | New | 8 | #335887
335887 | #335885 | Story | Feature 335885: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #335896
335886 | #335885 | Story | Feature 335885: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #335891
335705 |  | Task | Test | Unassigned | Invalid
335549 | #333889 | Task | Assess Problem 329643 | Unassigned | Invalid
335067 | #346561 | Story | Part 2 - Triage lab/site data | Unassigned | Invalid | 0
335066 | #346561 | Story | Part 1 - Triage lab/site data | Unassigned | Invalid | 0
335009 |  | Story | DSN & IP Teleport - Splunk review/rework (Ken) | Unassigned | Invalid | 0
334997 |  | Story | DSN & IP Teleport - PM collector config updates | Unassigned | Invalid | 0
334996 |  | Story | DSN & IP Teleport - Update GSS, P2P, and P2N help screens | Unassigned | Invalid | 0
334995 |  | Story | DSN & IP Teleport - Test retrieval for all OIDs (via SNMP GET / MIBBLE) | Unassigned | Invalid | 0
334938 |  | Story | Support CSE OTA IATT Package development - 9.1 | Unassigned | Invalid | 0
334851 |  | Story | DSN & IP Teleport - Create site verification test plan | Unassigned | Invalid | 0
334748 | #297334 | Story | Prototype Migrated P-Number Account in Domain-Consolidated Environment | Unassigned | Invalid | 0
334747 |  | Task | Pre-Planning for Tools Laptops - Continue NetMac investigation | Unassigned | Invalid
334746 |  | Task | Pre-Planning for Tools Laptops - Continue NetMac investigation | Unassigned | Invalid
334678 |  | Story | Initiate CM PDO Processing for MAS SVD (PWI 287761) | Unassigned | Invalid | 0
334669 |  | Story | SVD Update: MAS installation - PWI 287761 (EA 9.2) | Unassigned | Invalid | 0
334561 | #300843 | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334560 | #300843 | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334559 |  | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334558 |  | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334556 | #300843 | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334555 | #300843 | Story | Perform compromised terminal an KMS testing | Unassigned | Invalid | 0
334532 |  | Story | Integrate AWARE with 8L: ILS IETM updates | Unassigned | Invalid | 0
334511 |  | Problem | Update FM Troubleshooting procedure in IETM so that if one cannot login, can restart Netcool process as part of troubleshooting steps. | Unassigned | Assessing
334431 |  | Story | Feature 305186: Evaluate AJM Chassis PN# 01-P53220E001, SN# 105 and SN# EM201: Repare and Validate/Verify | Unassigned | Invalid | 0
334430 |  | Story | Feature 305186: Evaluate AJM Chassis PN# 01-P53220E001, SN# 105 and SN# EM201: Fault Isolation and Evaluation | Unassigned | Invalid | 0
334423 | #294836 | Story | KG175A Replacement: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB - part 2 | Unassigned | Invalid | 0
334412 | #331829 | Story | Work with PMW-146 and site personnel to socialize draft Access Control Policy (Part 2) | Unassigned | Invalid | 0
334396 | #297335 | Story | RDE: BuildForge - Perform test of BuildForge RBS Full Build in RDE | EA 15.5 | Implementing | 5 | #344115
334228 |  | Story | Support AWARE On-Site Testing - Global Test Groups: MHAL SME Support - 9.5 | Unassigned | Invalid | 0
334227 |  | Story | Support AWARE On-Site Testing - Global Test Groups: AWARE SME Support - 9.5 | Unassigned | Invalid | 0
334226 | #290673 | Story | Support AWARE On-Site Testing - Global Test Groups: AWARE SME Support - 9.4 | Unassigned | Invalid | 0
333910 | #1021499 | Problem | Firewall rule does not support packets from the mas-wh/nw port 13006/13005 to the OTAFT Servers port 5080 | PI 16 | Approved
333801 |  | Story | SME Support for ULX - 9.5 | Unassigned | Invalid | 0
333800 |  | Story | SME Support for ULX - 9.4 | Unassigned | Invalid | 0
333799 |  | Story | SME Support for ULX - 9.3 | Unassigned | Invalid | 0
333798 |  | Story | SME Support for ULX - 9.2 | Unassigned | Invalid | 0
333797 | #328476 | Story | SME Support for ULX- 9.6 | Unassigned | Invalid | 0
333794 | #328476 | Story | SME Support for ULX- 9.5 | Unassigned | Invalid | 0
333788 |  | Story | Invalid | Unassigned | Invalid | 0
333779 | #328476 | Story | ETISP SME Support for ULX - 9.4 | Unassigned | Invalid | 0
333773 | #328476 | Story | ETISP SME Support for ULX - 9.3 | Unassigned | Invalid | 0
333730 | #284582 | Story | GD Support of Zeta - EAD 9/10: Initiate CM PDO Processing for IETM | Unassigned | Invalid | 0
333685 |  | Story | AMS-GS UFO Table Update: Update SVD for UFO Table | Unassigned | Invalid | 0
333415 |  | Story | Intake during PI 09 | Unassigned | Invalid | 0
333414 |  | Story | Intake during PI 09 | Unassigned | Invalid | 0
333413 |  | Story | Intake during PI 09 | Unassigned | Invalid | 0
332951 | #216364 | Feature | Add/update IETM alarm recovery procedures for RBS alarms (5 of 6) | EA 15.4 | Implementing
332900 |  | Story | Breif the penetration test community on GDS protections: Provide SME support for Training Brief & Q&A | Unassigned | Invalid | 0
332860 |  | Story | Feature 318212: Install & Test Server in Hayden Lab | Unassigned | Invalid | 0
332859 |  | Story | Feature 318212: Install & Test Server in Roosevelt Lab | Unassigned | Invalid | 0
332828 | #307985 | Story | Integrate AWARE with 8L: Gain ownership of HMS Region & VOBs | Unassigned | Invalid | 0
332792 | #315562 | Story | WCDMA Service Status: Phase 2 - DSN & IP Teleport: IA Final Scan | Unassigned | Invalid | 0
332761 | #294836 | Story | KG175A Replacement: HW/SW Map updates for IASS1&2 | Unassigned | Invalid | 0
332688 | #294836 | Story | KG175A Replacement: Drawings Support (NME10, NME11, NME12) | Unassigned | Invalid | 0
332373 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.3, story d) | Unassigned | Invalid | 0
332372 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.3, story c) | Unassigned | Invalid | 0
332371 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.3, story b) | Unassigned | Invalid | 0
332370 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.3, story a) | Unassigned | Invalid | 0
332369 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.2, story d) | Unassigned | Invalid | 0
332368 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.2, story c) | Unassigned | Invalid | 0
332367 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.2, story b) | Unassigned | Invalid | 0
332366 | #298325 | Story | GD support for Government Cybersecurity System Inspection (CSI) (Sprint 9.2, story a) | Unassigned | Invalid | 0
332350 | #298325 | Story | GD support for site IA assessment and data analysis - pursuit of May 2019 ATO renewal (Sprint 9.4, story a) | Unassigned | Invalid | 0
332303 | #332289 | Task | Hold Feature Review with SMEs | Unassigned | New
332302 | #332289 | Story | Feature 332289: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #332291
332301 | #332289 | Story | Feature 332289: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #332291
332300 | #332289 | Story | Feature 332289: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
332299 | #332289 | Story | Feature 332289: UX Research and Design Support | Unassigned | New | 3
332298 | #332289 | Story | Feature 332289: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
332296 | #332289 | Story | Feature 332289: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #332291
332295 | #332289 | Story | Feature 332289: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #332292
332294 | #332289 | Story | Feature 332289: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #332291
332293 | #332289 | Story | Feature 332289: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #332297
332292 | #332289 | Story | Feature 332289: IA Posture Assessment | Unassigned | New | 8 | #332291
332291 | #332289 | Story | Feature Demo – Customer Demo Event - Feature 332289 | Unassigned | New | 1 | #332300
332290 | #332289 | Story | Feature 332289: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #332295
332281 | #393265 | Problem | GGSN Alarm Recovery Procedures -Feedback from NCTAMS EAD 9 Training (9-10 Oct 2018) | EA 15.4 | Approved
332215 |  | Task | PWI to Feature Test | Unassigned | Invalid
332213 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
332211 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
332210 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
332002 | #1008506 | Problem | IETM Procedure update from DTA-4 Finding: Action to Restore Service for PRVB0030 alarm. | EA 15.2 | Closed
331989 | #396669 | Problem | Update IETM Recovery Procedure for RCG_0062 per trouble ticket information | EA 15.4 | Verifying
331423 | #232016 | Story | Identify Changes for Monitoring OSS-RC Alarm Forwarding - WF-RAN Development | PI 15 | Invalid | 0
331422 | #232016 | Story | Identify Changes for Monitoring OSS-RC Alarm Forwarding - SE | PI 15 | Invalid | 0
331415 | #331371 | Story | Feature 331371: Create STCD and Review with Stakeholders | Unassigned | New | 1
331413 | #331371 | Story | Feature 331371: Feature Demo - Customer Demo Event | Unassigned | New | 1
331412 | #331371 | Story | Feature 331371: Deployment Notes and Operator Impact Inputs | Unassigned | New | 1
331411 | #331371 | Story | Feature 331371: ILS IETM Updates for Create RANI O-Level IETM to monitor and recover network connection | Unassigned | New | 2
331407 | #331371 | Story | Feature 331371: Test IETM Updates | Unassigned | New | 3
331406 | #331371 | Story | Feature 331371: Engineering IETM Updates | Unassigned | New | 5
331186 | #325102 | Task | Investigate Graphical Vtree error in RDE CC | Unassigned | New
331185 | #325102 | Task | Resolve RDE Scheduled Job Errors for CC | Unassigned | Done
331183 | #327943 | Story | CSE SME Support 9.5 | Unassigned | Invalid | 0
330888 |  | Story | Relocation: ETISP configuration changes | Unassigned | Invalid | 0
330522 | #1001062 | Story | Address long build times to compile RNC load modules in RDE | EA 15.2 | Done | 1
330485 | #294836 | Story | KG175A Replacement: Continue the updates to the Drawings - Part 2 | Unassigned | Invalid | 0 | #330487
330409 | #330206 | Story | Splunk App KMZ - Customer Demo | Unassigned | Invalid | 0
330408 | #330206 | Story | Splunk App KMZ - Install, Execute STCD, and Verify | Unassigned | Invalid | 0
330407 | #330206 | Story | Splunk App KMZ - IA Final Scan | Unassigned | Invalid | 0
330406 | #330206 | Story | Splunk App KMZ - IA Posture Assessment | Unassigned | Invalid | 0
330405 | #330206 | Story | Splunk App KMZ - Review, Rework, and Build | Unassigned | Invalid | 0
330404 | #330206 | Story | Splunk App KMZ - Create new file and Test | Unassigned | Invalid | 0
330198 |  | Feature | Relocation: ET and ETISP activities - monitor and tune eRxIM | Unassigned | Rejected
330102 | #325102 | Task | Transfer CBC templates to the RAN | Unassigned | Done
329938 | #329924 | Task | Hold Feature Review with SMEs: Improve ping probe health status alarms | Unassigned | Invalid
329937 | #329924 | Story | Improve ping probe health status alarms Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #329926
329936 | #329924 | Story | Improve ping probe health status alarms Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #329926
329935 | #329924 | Story | Improve ping probe health status alarms: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
329933 | #329924 | Story | Improve ping probe health status alarms ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
329932 | #329924 | Story | Feature 329924: IETM Update for Improving the Ping Probe Health Status Alarms | Unassigned | Invalid | 0 | #329926
329931 | #329924 | Story | Improve ping probe health status alarms Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #329926
329930 | #329924 | Story | Improve ping probe health status alarms: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #329927
329929 | #329924 | Story | Improve ping probe health status alarms: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #329926
329928 | #329924 | Story | Improve ping probe health status alarms Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #329932
329926 | #329924 | Story | Feature Demo – Customer Demo Event: Improve ping probe health status alarms | Unassigned | Invalid | 0 | #329935
329925 | #329924 | Story | Improve ping probe health status alarms: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #329930
329825 |  | Problem | Update AMS-GS SVD to include reference to IETM procedure for MAC Learning | Unassigned | Assessing
329815 | #359983 | Problem | INC000001369487: Recover from a failed AutoOD with observed ground station error procedure issues | PI 17 | Assessing
329808 | #359983 | Problem | INC000001385346: HQ - Current OD recovery procedure for multiday failure takes more than a single working shift | PI 17 | Assessing
329807 | #359983 | Problem | INC000001359939: HQ - MUOS OAS - Interrupted telemetry when OD task chains are scheduled near momentum dumps. | PI 17 | Assessing
329784 |  | Problem | IETM: Scrub Fault Management Elements Table for Aggregations in FM Troubleshooting Module | Unassigned | Assessing
329776 | #359983 | Problem | SPAS00000172955: HQ - OAS MUS ephemeris stopping at first maneuver in time span | PI 17 | Assessing
329774 | #1018285 | Problem | Feature 1018285: IETM: Update CRL instructions to clarify how to copy files | PI 16 | Ready for IRM Approval
329772 | #1010421 | Problem | SPAS00000171676: ISEA Requires SME support to resolve TFBR 0173-16 | EA 15.3 | Closed
329741 |  | Problem | IETM: Add JMS Monitor Alarms (SPAS00000167103) | Unassigned | Assessing
329723 |  | Problem | IETM: Add troubleshooting section for McAfee NIDS (SPAS00000165306) | Unassigned | Assessing
329718 |  | Problem | IETM: Document translation of Radiant Mercury channel names to MGS Adapter message queues (SPAS00000163423) | Unassigned | Assessing
329717 |  | Problem | IETM: TCA Reinstall Steps Missing from TPM Troubleshooting Section (SPAS00000155923 & SPAS00000164096) | Unassigned | Assessing
329711 | #367689 | Problem | TIS Lantronix is pointing to the wrong siem collector | PI 16 | Approved
329703 |  | Problem | IETM: Document what to do with the Windows Service Pack Installer Update service | Unassigned | Assessing
329696 |  | Problem | SPAS00000149252: NW, MAS-NW, METASTAT, DISK DRIVE REQUIRES MAINTENANCE | Unassigned | Assessing
329686 | #1004171 | Problem | SPAS00000147363: B3 RNC : Stuck RadioLink on group fixed-net causes UE poor voice issue on Group Service Leg (GSL) | EA 15.4 | Verifying
329683 | #392058 | Problem | Feature 392058: IETM ETISP Alarm procedure for ETI_2620 add checks for ET issues prior to restart | EA 15.1 | Closed
329681 |  | Problem | IETM: Need repair and replace procedures for db201 and db202 (SPAS00000150492) | Unassigned | Assessing
329669 |  | Problem | IETM: Provide troubleshooting instructions for GeoProc path status (SPAS00000142273) | Unassigned | Assessing
329642 | #1015565 | Problem | IETM: Add procedures to support binary backup of RNC image and restoration from it | PI 16 | Approved
329633 |  | Problem | IETM: Repair and replace of servers should discuss using hard drives from failed system (SPAS00000144079) | Unassigned | Assessing
329631 |  | Problem | IETM: DL145 NMO Operator installation procedure | Unassigned | Assessing
329611 |  | Problem | CAI Addm 20: OTA-FT updates for UE Sync Robustness | Unassigned | Assessing
329592 |  | Task | TCC: NMS B3: Change group min and max power default settings | Unassigned | Invalid
329591 |  | Task | NMS: McAfee Inturshield and the FM tool need to setup for SNMP TRAPS | Unassigned | Invalid
329590 |  | Task | TTS Platform SVD is missing instructions to set the MTU size | Unassigned | Invalid
329589 |  | Task | TTS Platform SVD is missing clear instructions on how to perform a clean install (for a spare) | Unassigned | Invalid
329523 |  | Task | Test - Enhancement | Unassigned | Invalid
329478 |  | Task | Test - Enhancement | Unassigned | Invalid
329476 |  | Task | Test-Mateo | Unassigned | Invalid
329467 |  | Task | Mateo Test | Unassigned | Invalid
329459 |  | Task | PWI Reserve: Re-Assess Problem 321757 | Unassigned | Invalid
329420 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to NTP & SNMP | Unassigned | New | 5
329417 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to Link control/ssh | Unassigned | New | 5
329413 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to Session Control | Unassigned | New | 5
329412 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to audit data control | Unassigned | New | 5
329410 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to Application & Configuration Management | Unassigned | New | 5
329406 | #329380 | Story | Feature 329380: FEP - Remediate IA Findings related to Access Control | Unassigned | New | 5
329394 | #329380 | Task | Feature 329380: Hold Feature Review with SMEs | Unassigned | New
329393 | #329380 | Story | Feature 329380: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #329382
329392 | #329380 | Story | Feature 329380: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #329382
329391 | #329380 | Story | Feature 329380: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
329390 | #329380 | Story | Feature 329380: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
329389 | #329380 | Story | Feature 329380: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
329388 | #329380 | Story | Feature 329380: ILS IETM update | Unassigned | New | 3 | #329382
329387 | #329380 | Story | Feature 329380: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #329382
329386 | #329380 | Story | Feature 329380: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #329383
329385 | #329380 | Story | Feature 329380: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #329382
329384 | #329380 | Story | Feature 329380: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #329388
329383 | #329380 | Story | Feature 329380: IA Posture Assessment | Unassigned | New | 8 | #329382
329382 | #329380 | Story | Feature 329380: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #329391
329381 | #329380 | Story | Feature 329380: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #329386
329337 |  | Task | 2018 Ethics Refresher Training – due 10/22 (Gerald V.) | Unassigned | Invalid
329336 |  | Task | 2018 Ethics Refresher Training – due 10/22 (Michael V.) - DUPLICATE | Unassigned | Invalid
329332 |  | Task | 2018 Ethics Refresher Training – due 10/22 (Chris M.) - DUPLICATE | Unassigned | Invalid
329096 | #329082 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
329092 | #329082 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
329091 | #329082 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
329090 | #329082 | Story | <Feature xxx>:ILS IETM update | Unassigned | Invalid | 0 | #329084
329088 | #329082 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #329085
329086 | #329082 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #329090
329080 |  | Task | Maryam OOP reminder: 10/24/2019 | Unassigned | New
329037 | #328212 | Story | Define underlying PWIs and effort for "Feature 329380: Remediate IA Findings (identified 2Q 2018) for Front End Processor (FEP) device" (non-Cyber SME portion) | Unassigned | Invalid | 0
328944 |  | Task | Remove Event ID 6029 - MAS Registrar Out Sync alarm from Whitelist and from IETM Custom Alarms recovery procedures | Unassigned | New
328779 |  | Task | duplicate | Unassigned | Invalid
328651 | #328637 | Task | Training Lead Attend Training | Unassigned | Invalid
328644 | #328637 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #328639
328643 | #328637 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #328640
328641 | #328637 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #328645
328640 | #328637 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #328639
328639 | #328637 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #328648
328638 | #328637 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #328643
328603 | #328590 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #328592
328599 | #328590 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
328598 | #328590 | Story | <Feature xxx>:ILS IETM update | Unassigned | Invalid | 0 | #328592
328596 | #328590 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #328593
328595 | #328590 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #328592
328594 | #328590 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #328598
328593 | #328590 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #328592
328592 | #328590 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #328601
328591 | #328590 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #328596
328589 | #395871 | Story | Refresh PPA U2B External Interference System Parameters - initial support | EA 14.1 | Done | 1
328499 | #328496 | Story | ETISP SME Support | Unassigned | Invalid | 0
328495 |  | Story | SME Support for ULX - 9.1 | Unassigned | Invalid | 0
328490 |  | Story | Feature 328477: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #328479
328488 | #328477 | Story | Feature 328477: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
328483 | #328477 | Story | Feature 328477: IA Patching and STIGs | Unassigned | Invalid | 0 | #328480
328478 | #328477 | Story | Feature 328477: IA - Define Patch/ Stig Requirements (developer input) | Unassigned | Invalid | 0 | #328483
328470 | #216654 | Story | Teleport ICD Update | Unassigned | Invalid | 0
328461 | #216654 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
328460 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #328449
328459 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #328449
328458 | #216654 | Story | <Feature 216654>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
328457 |  | Story | <Feature 216654> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
328456 |  | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
328454 | #216654 | Story | <Feature 216654> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #328449
328453 | #216654 | Story | <Feature 216654>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #328450
328452 | #216654 | Story | TIS Firewalls Update | Unassigned | Invalid | 0 | #328449
328451 |  | Story | <Feature 216654> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #328455
328450 | #216654 | Story | <Feature 216654> IA Posture Assessment | Unassigned | Invalid | 0 | #328449
328449 | #216654 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #328458
328448 | #216654 | Story | <Feature 216654>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #328453
328447 |  | Feature | <Feature xxx> | Unassigned | Rejected
328428 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
328285 |  | Task | Hemant | Unassigned | Invalid
328156 | #325102 | Task | Install RoseRT on UNIX | Unassigned | Invalid
328154 | #327108 | Story | Alarm Flow - WF-RAN Support | Unassigned | Invalid | 0
328152 | #327110 | Story | Alarm/PM Data Flow Performance - WF-RAN Support | Unassigned | Invalid | 0
328151 | #327110 | Story | Alarm/PM Data Flow Performance - SA Support | Unassigned | Invalid | 0
328142 | #328128 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
328141 | #328128 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #328130
328140 | #328128 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #328130
328139 | #328128 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
328138 | #328128 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
328137 | #328128 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
328136 | #328128 | Story | <Feature xxx>:ILS IETM update | Unassigned | Invalid | 0 | #328130
328135 | #328128 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #328130
328134 | #328128 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #328131
328133 | #328128 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #328130
328132 | #328128 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #328136
328131 | #328128 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #328130
328130 | #328128 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #328139
328129 | #328128 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #328134
328128 |  | Feature | <Feature xxx> | Unassigned | Rejected
328105 | #327942 | Story | MAGIC PWI Support (EA 9.4) | Unassigned | Invalid | 0
328100 | #327946 | Story | Feature 327946 MAGIC HW FRB Support (EA 9.4) | Unassigned | Invalid | 0
328099 | #327946 | Story | Feature 327946 MAGIC HW FRB Support (EA 9.3) | Unassigned | Invalid | 0
328098 | #327946 | Story | Feature 327946 MAGIC HW FRB Support (EA 9.2) | Unassigned | Invalid | 0
328096 | #327946 | Story | Feature 327946:MAGIC HW FRB Support (EA 9.1) | Unassigned | Invalid | 0
328094 | #327943 | Story | MAGIC SME Support (EA 9.5) | Unassigned | Invalid | 0
328093 | #327943 | Story | MAGIC SME Support (EA 9.4) | Unassigned | Invalid | 0
328092 | #327943 | Story | MAGIC SME Support (EA 9.3) | Unassigned | Invalid | 0
327930 | #325102 | Task | Test Server 3 Servers after Solaris 11 Patching | Unassigned | Done
327929 | #325102 | Task | Go Over John Hartin's old Servers | Unassigned | New
327837 | #327823 | Task | Hold Feature Review with SMEs | Unassigned | New
327836 | #327823 | Story | Feature 327823: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #327825
327835 | #327823 | Story | <Feature 327823> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #327825
327834 | #327823 | Story | <Feature 327823>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
327833 | #327823 | Story | <Feature 327823> UX Research and Design Support | Unassigned | New | 3
327832 | #327823 | Story | Feature 327823: IETM Development and Integration updates part 1 of N | Unassigned | New | 1
327831 | #327823 | Story | Feature 327823: IETM update for Deletion of Group Key Set from a Terminal Profile | Unassigned | New | 3 | #327825
327830 | #327823 | Story | <Feature 327823> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #327825
327829 | #327823 | Story | <Feature 327823>: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #327826
327828 | #327823 | Story | <Feature 327823>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #327825
327827 | #327823 | Story | Feature 327823: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #327831
327826 | #327823 | Story | Feature 327823: IA Posture Assessment | Unassigned | New | 8 | #327825
327825 | #327823 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #327834
327824 | #327823 | Story | <Feature 327823>: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #327829
327818 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
327762 | #327759 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #327761
327760 | #327759 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #327765
327758 | #327744 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
327757 | #327744 | Story | Feature 327744: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #327746
327756 | #327744 | Story | Feature 327744: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #327746
327755 | #327744 | Story | <Feature 327744>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
327754 | #327744 | Story | <Feature 327744> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
327753 | #327744 | Story | <Feature 327744> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
327752 | #327744 | Story | <Feature 327744>:ILS IETM update | Unassigned | Invalid | 0 | #327746
327751 | #327744 | Story | <Feature 327744> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #327746
327750 | #327744 | Story | <Feature 327744>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #327747
327749 | #327744 | Story | <Feature 327744>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #327746
327748 | #327744 | Story | <Feature 327744> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #327752
327747 | #327744 | Story | <Feature 327744> IA Posture Assessment | Unassigned | Invalid | 0 | #327746
327746 | #327744 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #327755
327745 | #327744 | Story | <Feature 327744>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #327750
327744 |  | Feature | <Feature 327744> | Unassigned | Rejected
327436 |  | Story | EA 9.4 Firewall Health Check and capture metrics | Unassigned | Invalid | 0
327435 | #293867 | Story | EA 9.3 Firewall Health Check and capture metrics | Unassigned | Invalid | 0
327434 |  | Story | EA 9.2 Firewall Health Check and capture metrics | Unassigned | Invalid | 0
327080 | #245563 | Feature | AMS-GS - Investigate Solutions to Improve GD's lab to Better Match Zeta's lab. | Unassigned | Analyzing
326987 |  | Task | QCI - Q3 (Gerald V.) | Unassigned | Invalid
326965 |  | Problem | Create Splunk Help for Knowledge Object Sharing- ARSTRAT Feedback from EAD 8 Training Event | Unassigned | Assessing
326697 | #325102 | Task | Transfer Disk Array data to NAS - Part I | Unassigned | Done
326648 | #325102 | Task | Attend an ICM Release Demo | Unassigned | New
326645 | #325102 | Task | Investigate the server process that handles CQ requests | Unassigned | Done
326643 | #325102 | Task | Deal with unresolved checkouts in ClearCase | Unassigned | Done
326641 | #325102 | Task | CleanUp Lost+Found items in ClearCase | Unassigned | Done
326449 |  | Task | Test - 1 | Unassigned | Invalid
326342 |  | Story | Feature 326329: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
326341 |  | Story | Feature 326329: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0
326340 |  | Story | Feature 326329: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
326339 | #326329 | Story | Feature 326329: MAS Start/Stop and CSCF Troubleshoot UX IETM Review | Unassigned | Invalid | 0
326338 |  | Story | Feature 326329: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
326335 |  | Story | Feature 326329: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0
326333 |  | Story | Feature 326329: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
326332 |  | Story | Feature 326329: IA Posture Assessment - CSCF | Unassigned | Invalid | 0
326331 |  | Story | Feature Demo – Customer Demo Event - Feature 326329 | Unassigned | Invalid | 0
326330 |  | Story | Feature 326329: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0
326302 | #325102 | Task | Build - Test a Manual build of the RNC Em load module in RDE | Unassigned | Done
326298 | #325102 | Task | Build - Test a Manual build of the RNC GPS load module in RDE | Unassigned | Done
326296 | #325102 | Task | Build - Test a Manual build of the RNC CenDh load module in RDE | Unassigned | Done
326295 | #325102 | Task | Build - Test a Manual build of the RNC CenAgps load module in RDE | Unassigned | Done
326294 | #325102 | Task | Build - Test a Manual build of the RNC Bdh load module in RDE | Unassigned | Done
326290 | #325102 | Task | Build - Test a Manual build of the RNC Rnsap load module in RDE | Unassigned | Done
326289 | #325102 | Task | Build - Test a Manual build of the RNC Dh load module in RDE | Unassigned | Done
326248 |  | Task | SME Reserve: EAD 9 Depot Support | Unassigned | Invalid
326176 | #320679 | Story | Define OTA-FT service status - Systems 1 | Unassigned | New | 3
326172 | #320679 | Story | UX Research Support: OTA-FT Service Status | Unassigned | New | 2
326169 | #320679 | Story | UX Design: OTA-FT Service Status | Unassigned | New | 3
326165 | #320679 | Story | Define OTA-FT service status - Systems 2 | Unassigned | New | 2
326163 | #320679 | Story | Define OTA-FT service status - Systems 3 | Unassigned | New | 1
326036 | #325102 | Task | Document Strategy for VOB Schema Upgrade and Synchronization | Unassigned | Done
326035 | #325102 | Task | Build - Test a Manual build of the RNC Ranap load module in RDE | Unassigned | Done
325796 | #322837 | Task | Story 322837: CM Release of MUOS_IG_GS_NMS_NM_PL_01-P53573E (EAD 9) | Unassigned | Done
325772 | #325746 | Story | Feature 325746: inf Server Audit Generation and Distribution | Unassigned | New | 13
325771 | #325746 | Story | Feature 325746: inf Server Account Management | Unassigned | New | 8
325770 | #325746 | Story | Feature 325746: inf Server General Configuration Updates | Unassigned | New | 2
325769 | #325746 | Story | Feature 325746: inf Server SQL Server Audits | Unassigned | New | 8
325768 | #325746 | Story | Feature 325746: inf Server SQL Server Database Access | Unassigned | New | 5
325767 | #325746 | Story | Feature 325746: inf Server SSL Certificates | Unassigned | New | 8
325766 | #325746 | Story | Feature 325746: inf Server Remove Unnecessary Services, etc. | Unassigned | New | 2
325765 | #325746 | Story | Feature 325746: inf Server Named Pipes Configuration | Unassigned | New | 3
325764 | #325746 | Story | Feature 325746: inf Server Role Based Access Control | Unassigned | New | 5
325763 | #325746 | Story | Feature 325746: inf Server Password Complexity Fixes | Unassigned | New | 3
325760 | #325746 | Task | Feature 325746: Hold Feature Review with SMEs | Unassigned | New
325759 | #325746 | Story | Feature 325746: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #325748
325758 | #325746 | Story | Feature 325746: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #325748
325757 | #325746 | Story | Feature 325746: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325756 | #325746 | Story | Feature 325746: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325755 | #325746 | Story | Feature 325746: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325754 | #325746 | Story | Feature 325746: IETM update for Remediation of IA Findings for Windows 2012 based inf101-wh-nma server device (2Q 2018) | Unassigned | New | 3 | #325748
325753 | #325746 | Story | Feature 325746: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #325748
325752 | #325746 | Story | Feature 325746: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #325749
325751 | #325746 | Story | Feature 325746: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #325748
325750 | #325746 | Story | Feature 325746: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325754
325749 | #325746 | Story | Feature 325746: IA Posture Assessment | Unassigned | New | 8 | #325748
325748 | #325746 | Story | Feature 325746: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325757
325747 | #325746 | Story | Feature 325746: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #325752
325617 |  | Story | Support PMW IA for AWARE addition into Ground ATO (EA 8.2 - Gerald) | Unassigned | Invalid | 0
325551 | #245898 | Feature | Rejected: Obsolescence: (Windows) Trade Study - Custom Code | Unassigned | Rejected
325532 | #326270 | Task | Story 322837: CM Release of PL01-P53586E: PL, NME 4 Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325531 | #322837 | Task | Story 322837: CM Release of PL01-P53576E: PL, NME 6 Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325529 | #326270 | Task | Story 322837: CM Release of PL01-P53568E: PL, NME 3 Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325528 | #326270 | Task | Story 322837: CM Release of PL01-P53567E: PL, NME 2 Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325527 | #322837 | Task | Story 322837: CM Release of PL01-P53566E PL, NME 1 Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325526 | #326270 | Task | Story 322837: CM Release of PL01-P51736E001/002/003/004 PL, RFA Cabinet Assy, Parts List for EAR 8.5 (EAD 9) | Unassigned | Done
325505 | #322837 | Task | Story 322837: CM Release of 30-P53010E Cable Assembly, Ethernet, RJ45-RJ45, On-Site for EAR 8.5 (EAD 9) | Unassigned | Done
325398 | #325102 | Task | Make a Knowledge Management Plan | Unassigned | New
325397 | #325102 | Task | Investigate Create View execution on Windows platform in RDE | Unassigned | Done
325276 | #325102 | Task | Create an update model for Ranccadm tools path | Unassigned | Done
325271 | #325227 | Story | Feature 325227: FM Servers - SNMP configuration fix | Unassigned | New | 13
325267 | #325227 | Story | Feature 325227: FM Servers - SSL Certificates | Unassigned | New | 8
325266 | #325227 | Story | Feature 325227: FM Servers - Password Complexity | Unassigned | New | 13
325264 | #325227 | Story | Feature 325227: FM Servers - Access control (Role based, FIPS 140-2 algorithms) | Unassigned | New | 13
325260 | #325227 | Story | Feature 325227: FM Servers - Audit generation and distribution | Unassigned | New | 8
325259 | #325227 | Story | Feature 325227: FM Servers - Remove or disable unneeded services/apps | Unassigned | New | 13
325258 | #325227 | Story | Feature 325227: FM Servers - Login banner is incorrect | Unassigned | New | 1
325257 | #325227 | Story | Feature 325227: FM Servers - General Configuration Settings to resolve Cyber RMF Findings - part 1 | Unassigned | New | 8
325255 | #325227 | Story | Feature 325227: FM Servers - Fix Boot Device | Unassigned | New | 8
325253 | #325227 | Story | Feature 325227: FM Servers - Fix run control scripts world execution privileges | Unassigned | New | 13
325251 | #325227 | Story | Feature 325227: FM Servers - Remove .rhosts, etc. | Unassigned | New | 8
325250 | #325227 | Story | Feature 325227: FM Servers - Remove insecure telnet | Unassigned | New | 3
325249 | #325126 | Story | Feature 325126: inf Server Audit Generation and Distribution | Unassigned | New | 13
325248 | #325227 | Story | Feature 325227: FM Servers - Remove insecure .rsh shell | Unassigned | New | 3
325247 | #325126 | Story | Feature 325126: Develop Replacement for Backup/Archive Client on inf Servers | Unassigned | New | 13
325246 | #325126 | Story | Feature 325126: Research Suitable Replacement for Current Backup/Archive Client | Unassigned | New | 5
325241 | #325227 | Task | Hold Feature Review with SMEs | Unassigned | New
325240 | #325227 | Story | Feature 325227: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #325229
325239 | #325227 | Story | Feature 325227: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #325229
325238 | #325227 | Story | Feature 325227: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325237 | #325227 | Story | Feature 325227: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325236 | #325227 | Story | Feature 325227: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325235 | #325227 | Story | Feature 325227: IETM update for Remediation of IA Findings for NMS-FM Solaris 9 servers (2Q 2018) | Unassigned | New | 3 | #325229
325234 | #325227 | Story | Feature 325227: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #325229
325233 | #325227 | Story | Feature 325227: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #325230
325232 | #325227 | Story | Feature 325227: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #325229
325231 | #325227 | Story | Feature 325227: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325235
325230 | #325227 | Story | Feature 325227: IA Posture Assessment | Unassigned | New | 8 | #325229
325229 | #325227 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325238
325228 | #325227 | Story | Feature 325227: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #325233
325226 | #325212 | Task | Feature 325212: Hold Feature Review with SMEs | Unassigned | Invalid
325225 | #325212 | Story | Feature 325212: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #325214
325224 | #325212 | Story | Feature 325212: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #325214
325223 | #325212 | Story | Feature 325212: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
325222 | #325212 | Story | Feature 325212: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325221 | #325212 | Story | Feature 325212: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325220 | #325212 | Story | Feature 325212: ILS IETM update | Unassigned | Invalid | 0 | #325214
325219 | #325212 | Story | Feature 325212: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #325214
325218 | #325212 | Story | Feature 325212: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #325215
325217 | #325212 | Story | Feature 325212: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #325214
325216 | #325212 | Story | Feature 325212: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #325220
325215 | #325212 | Story | Feature 325212: IA Posture Assessment | Unassigned | Invalid | 0 | #325214
325214 | #325212 | Story | Feature 325212: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #325223
325213 | #325212 | Story | Feature 325212: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #325218
325211 | #325126 | Story | Feature 325126: inf Server Account Management | Unassigned | New | 8
325210 | #325126 | Story | Feature 325126: inf Server General Configuration Updates | Unassigned | New | 2
325178 | #325142 | Story | Feature 325142: GIS and MAS Servers - Remove unused software / disable unused ports | Unassigned | New | 5
325176 | #325142 | Story | Feature 325142: GIS and MAS Servers - Remove embedded authentication data | Unassigned | New | 8
325174 | #325126 | Story | Feature 325126: inf Server SQL Server Audits | Unassigned | New | 8
325173 | #325126 | Story | Feature 325126: inf Server SQL Server Database Access | Unassigned | New | 5
325171 | #325142 | Story | Feature 325142: GIS and MAS Servers - General Configuration Settings | Unassigned | New | 8
325170 | #325126 | Story | Feature 325126: inf Server SSL Certificates | Unassigned | New | 8
325167 | #325126 | Story | Feature 325126: inf Server Remove Unnecessary Services, etc. | Unassigned | New | 2
325166 | #325142 | Story | Feature 325142: GIS and MAS Servers - Audit Generation and Distribution | Unassigned | New | 8
325165 | #325126 | Story | Feature 325126: inf Server Named Pipes Configuration | Unassigned | New | 3
325164 | #325126 | Story | Feature 325126: inf Server Role Based Access Control | Unassigned | New | 5
325161 | #325126 | Story | Feature 325126: inf Server Password Complexity Fixes | Unassigned | New | 3
325157 | #325102 | Task | Coordinate Rack moves for the NAS Shelf Extension | Unassigned | Done
325156 | #325142 | Task | Hold Feature Review with SMEs | Unassigned | New
325155 | #325142 | Story | Feature 325142: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #325144
325154 | #325142 | Story | Feature 325142: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #325144
325153 | #325142 | Story | Feature 325142: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325152 | #325142 | Story | Feature 325142: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325151 | #325142 | Story | Feature 325142: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325150 | #325142 | Story | Feature 325142: IETM update for Remediation of IA Findings for GIS/MAS Solaris 9 servers (2Q 2018) | Unassigned | New | 3 | #325144
325149 | #325142 | Story | Feature 325142: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #325144
325148 | #325142 | Story | Feature 325142: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #325145
325147 | #325142 | Story | Feature 325142: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #325144
325146 | #325142 | Story | Feature 325142: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325150
325145 | #325142 | Story | Feature 325142: IA Posture Assessment | Unassigned | New | 8 | #325144
325144 | #325142 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325153
325143 | #325142 | Story | Feature 325142: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #325148
325140 | #325126 | Task | Feature 325126: Hold Feature Review with SMEs | Unassigned | New
325139 | #325126 | Story | Feature 325126: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #325128
325138 | #325126 | Story | Feature 325126: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #325128
325137 | #325126 | Story | Feature 325126: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325136 | #325126 | Story | Feature 325126: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325135 | #325126 | Story | Feature 325126: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325134 | #325126 | Story | Feature 325126: IETM update for Remediation of IA Findings for Windows 2003 based inf servers (2Q 2018) | Unassigned | New | 3 | #325128
325133 | #325126 | Story | Feature 325126: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #325128
325132 | #325126 | Story | Feature 325126: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #325129
325131 | #325126 | Story | Feature 325126: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #325128
325130 | #325126 | Story | Feature 325126: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325134
325129 | #325126 | Story | Feature 325126: IA Posture Assessment | Unassigned | New | 8 | #325128
325128 | #325126 | Story | Feature 325126: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325137
325127 | #325126 | Story | Feature 325126: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #325132
325124 | #325142 | Story | Feature 325142: GIS and MAS Servers - Access Control and Account Management Improvements | Unassigned | New | 13
325122 | #324993 | Story | Feature 324993: mm11/mm12 Server General Configuration Settings | Unassigned | New | 3
325121 | #325142 | Story | Feature 325142: GIS and MAS Servers - Update login banners | Unassigned | New | 3
325120 |  | Feature | Feature 325120: GIS/MAS 2Q 2018 Cyber RMF Remedies | Unassigned | Rejected
325119 | #324993 | Story | Feature 324993: mm11/mm12 Server Run Control Scripts | Unassigned | New | 13
325118 | #324993 | Story | Feature 324993: mm11/mm12 Server Removal of insecure programs | Unassigned | New | 13
325117 | #324993 | Story | Feature 324993: mm11/mm12 Server Boot Configuration | Unassigned | New | 2
325114 | #324993 | Story | Feature 324993: mm11/mm12 Server rsh daemon removal | Unassigned | New | 2
325113 | #324993 | Story | Feature 324993: mm11/mm12 Server Audit Generation and Distribution Remedies | Unassigned | New | 13
325110 | #324993 | Story | Feature 324993: mm11/mm12 Server Access Control Updates | Unassigned | New | 13
325109 | #324993 | Story | Feature 324993: mm11/mm12 Server File Removals | Unassigned | New | 1
325107 | #324993 | Story | Feature 324993: mm11/mm12 Server SNMP Configuration Fixes | Unassigned | New | 2
325103 | #325080 | Story | Feature 325080: TTC Gateway - Configuration Updates to fix findings | Unassigned | New | 5
325100 | #325080 | Story | Feature 325080: TTC Gateway - Audit Generation and Distribution | Unassigned | New | 8
325098 | #325080 | Story | Feature 325080: TTC Gateway - Access Control and Account Management Improvements | Unassigned | New | 8
325094 | #325080 | Task | Hold Feature Review with SMEs | Unassigned | New
325093 | #325080 | Story | Feature 325080: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #325082
325092 | #325080 | Story | Feature 325080: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #325082
325091 | #325080 | Story | Feature 325080: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325090 | #325080 | Story | Feature 325080: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325089 | #325080 | Story | Feature 325080: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325088 | #325080 | Story | Feature 325080: ILS IETM update | Unassigned | New | 3 | #325082
325087 | #325080 | Story | Feature 325080: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #325082
325086 | #325080 | Story | Feature 325080: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #325083
325085 | #325080 | Story | Feature 325080: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #325082
325084 | #325080 | Story | Feature 325080: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325088
325083 | #325080 | Story | Feature 325080: IA Posture Assessment | Unassigned | New | 8 | #325082
325082 | #325080 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325091
325081 | #325080 | Story | Feature 325080: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #325086
325077 | #325063 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
325076 | #325063 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #325065
325075 | #325063 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #325065
325074 | #325063 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
325073 | #325063 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325072 | #325063 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325071 | #325063 | Story | <Feature xxx>:ILS IETM update | Unassigned | Invalid | 0 | #325065
325070 | #325063 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #325065
325069 | #325063 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #325066
325068 | #325063 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #325065
325067 | #325063 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #325071
325066 | #325063 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #325065
325065 | #325063 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #325074
325064 | #325063 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #325069
325063 |  | Feature | <Feature xxx> | Unassigned | Rejected
325053 | #324932 | Story | Feature 324932: Splunk update configurations for Firefox browser | Unassigned | New | 3
325052 | #324932 | Story | Feature 324932: Splunk SSL Certs to be fixed or replaced. | Unassigned | Invalid | 0
325051 | #324932 | Story | Feature 324932: Splunk session timeouts | Unassigned | New | 5
325050 | #324932 | Story | Feature 324932: Splunk prevent concurrent logins | Unassigned | Invalid | 0
325048 | #324932 | Story | Feature 324932: Splunk Update login banners | Unassigned | Invalid | 0
325045 | #324932 | Story | Feature 324932: Splunk Add Multifactor Authentication | Unassigned | New | 1
325044 | #324932 | Story | Feature 324932: Splunk Low Disk Space Warning | Unassigned | New | 1
325039 | #324993 | Story | Feature 324993: mm11/mm12 Server Banners Not Compliant | Unassigned | New | 1
325030 | #324932 | Story | Feature 324932: Splunk Update Access Control and Password Complexity Configuration | Unassigned | New | 1
325027 | #324932 | Story | Feature 324932: Splunk Audit Generation and Distribution | Unassigned | New | 8
325007 | #324993 | Task | Hold Feature Review with SMEs | Unassigned | New
325006 | #324993 | Story | Feature 324993: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #324995
325005 | #324993 | Story | Feature 324993: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #324995
325004 | #324993 | Story | Feature 324993: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
325003 | #324993 | Story | Feature 324993 UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
325002 | #324993 | Story | Feature 324993: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
325001 | #324993 | Story | Feature 324993:ILS IETM update | Unassigned | New | 3 | #324995
325000 | #324993 | Story | Feature 324993: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #324995
324999 | #324993 | Story | Feature 324993: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #324996
324998 | #324993 | Story | Feature 324993: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #324995
324997 | #324993 | Story | Feature 324993: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #325001
324996 | #324993 | Story | Feature 324993: IA Posture Assessment | Unassigned | New | 8 | #324995
324995 | #324993 | Story | Feature 324993: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #325004
324994 | #324993 | Story | Feature 324993: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #324999
324946 | #324932 | Task | Hold Feature Review with SMEs | Unassigned | New
324945 | #324932 | Story | Feature 324932: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #324934
324944 | #324932 | Story | Feature 324932: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #324934
324943 | #324932 | Story | Feature 324932: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
324942 | #324932 | Story | Feature 324932: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324941 | #324932 | Story | Feature 324932: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
324940 | #324932 | Story | Feature 324932: ILS IETM update | Unassigned | New | 3 | #324934
324939 | #324932 | Story | Feature 324932: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #324934
324938 | #324932 | Story | Feature 324932: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #324935
324937 | #324932 | Story | Feature 324932: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #324934
324936 | #324932 | Story | Feature 324932: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #324940
324935 | #324932 | Story | Feature 324932: IA Posture Assessment | Unassigned | New | 8 | #324934
324934 | #324932 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #324943
324933 | #324932 | Story | Feature 324932: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #324938
324907 | #324842 | Story | Feature 324842: Load Balancers - Configure Session Timeouts in SSH | Unassigned | New | 2
324904 | #324842 | Story | Feature 324842: Load Balancers - remove and update untrusted SSL certificates | Unassigned | New | 2
324902 | #324842 | Story | Feature 324842: Configure Load Balancers for PPS correction | Unassigned | New | 3
324868 | #324842 | Story | Feature 324842: Upgrade Load Balancers to SNMPv3 and fix default community name configuration. | Unassigned | New | 2
324866 | #324842 | Story | Feature 324842: Load Balancers - Audit file generation and distribution for Load Balancers | Unassigned | New | 5
324864 | #324842 | Story | Feature 324842: Load Balancers - Access Control improvements and Account Management. | Unassigned | New | 8
324861 |  | Problem | IETM Update for Ticket INC000003462045: WH - Unable to fully remove user accounts from MUOS system | Unassigned | Assessing
324857 | #245575 | Story | Baseline MPC EAD8.13 TIS Firewall Config Updates | Unassigned | Invalid | 0
324856 | #324842 | Task | Hold Feature Review with SMEs | Unassigned | New
324855 | #324842 | Story | Feature 324842: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | New | 5 | #324844
324854 | #324842 | Story | Feature 324842: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | New | 5 | #324844
324853 | #324842 | Story | Feature 324842: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
324852 | #324842 | Story | Feature 324842: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324851 | #324842 | Story | Feature 324842: ILS IETM Development and Integration updates part 1 of N | Unassigned | New | 1
324850 | #324842 | Story | Feature 324842: ILS IETM update | Unassigned | New | 3 | #324844
324849 | #324842 | Story | Feature 324842: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | New | 2 | #324844
324848 | #324842 | Story | Feature 324842: IA Patching and STIGs Part 1 of N | Unassigned | New | 5 | #324845
324847 | #324842 | Story | Feature 324842: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | New | 2 | #324844
324846 | #324842 | Story | Feature 324842: Engineering IETM Development and Integration updates part 1 of N | Unassigned | New | 3 | #324850
324845 | #324842 | Story | Feature 324842: IA Posture Assessment | Unassigned | New | 8 | #324844
324844 | #324842 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #324853
324843 | #324842 | Story | Feature 324842: IA - Define Patch/ Stig Requirements | Unassigned | New | 2 | #324848
324798 | #324667 | Story | Feature 324667: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
324797 | #324667 | Story | Feature 324667: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0
324794 | #324667 | Story | Feature 324667: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324789 | #324667 | Story | Feature 324667: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0
324787 | #324667 | Story | Feature 324667: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324765 | #320172 | Task | Add daily updates to 320172 | Unassigned | Done
324688 |  | Task | Feature 324674: Hold Feature Review with SMEs | Unassigned | New
324687 |  | Story | Feature 324674: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0
324686 |  | Story | Feature 324674: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0
324684 |  | Story | Feature 324674: UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324683 |  | Story | Feature 324674: ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324680 |  | Story | Feature 324674: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0
324679 |  | Story | Feature 324674: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0
324678 |  | Story | Feature 324674: Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324677 | #324674 | Story | Feature 324674: IA Posture Assessment | Unassigned | Invalid | 0
324676 |  | Story | Feature 324674: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
324675 |  | Story | Feature 324674: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0
324661 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Proxy LB Server Correct Certificate Authority Findings Remedy - determine feasibility | Unassigned | Invalid | 0
324655 | #324591 | Story | Feature 324591: Proxy LB Server Account Management Findings Remedy | Unassigned | Invalid | 0
324604 |  | Story | Feature 324591: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #324593
324603 |  | Story | Feature 324591: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #324593
324602 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
324598 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #324593
324597 | #324591 | Story | Feature 324591: IA Patching and STIGs for PI 11 IA freshness | Unassigned | Invalid | 0 | #324594
324596 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #324593
324595 | #324591 | Story | Feature 324591: Remediate IA Findings for F5 BigIP DMZ - Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #324599
324593 | #324591 | Story | Feature Demo – Customer Demo Event - Feature 324591: Remediate IA Findings for F5 BigIP DMZ | Unassigned | Invalid | 0 | #324602
324433 | #307330 | Task | Story 307330: CM Release of MUOS_IG_GS_GTS_RN_ETI_ETT_SVD_98-P55479M for EAR 8.5 (EAD 10) | Unassigned | Invalid
324430 | #324416 | Task | Hold Feature Review with SMEs | Unassigned | Invalid
324429 | #324416 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 3 of N | Unassigned | Invalid | 0 | #324418
324428 | #324416 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 of N | Unassigned | Invalid | 0 | #324418
324427 | #324416 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
324426 | #324416 | Story | <Feature xxx> UX IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324425 | #324416 | Story | <Feature xxx> ILS IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0
324424 | #324416 | Story | <Feature xxx>:ILS IETM update | Unassigned | Invalid | 0 | #324418
324423 | #324416 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 of N | Unassigned | Invalid | 0 | #324418
324422 | #324416 | Story | <Feature xxx>: IA Patching and STIGs Part 1 of N | Unassigned | Invalid | 0 | #324419
324421 | #324416 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs Part 1 of N | Unassigned | Invalid | 0 | #324418
324420 | #324416 | Story | <Feature xxx> Engineering IETM Development and Integration updates part 1 of N | Unassigned | Invalid | 0 | #324424
324419 | #324416 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #324418
324418 | #324416 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #324427
324417 | #324416 | Story | <Feature xxx>: IA - Define Patch/ Stig Requirements | Unassigned | Invalid | 0 | #324422
324416 |  | Feature | <Feature xxx> | Unassigned | Rejected
324401 | #307330 | Task | Story 307330: CM Release of MUOS_IG_GS_GEO_SVD_98-P54107T for EAR 8.5 (EAD 10) | Unassigned | Invalid
324056 | #307330 | Task | Story 307330: CM Release of MUOS_IG_GS_Network_ExtremeSwitch_SVD_98-P59856M003 for EAR 8.5 (EAD 10) | Unassigned | Invalid
323902 | #307330 | Task | Story 307330: CM Release of xx-xxxxxxx NAVSOC Parts List (EAD 10) | Unassigned | Invalid
323900 | #307330 | Task | Story 307330: CM Release of 99-P53198T NEDB for EAR 8.3 (EAD 10) | Unassigned | Invalid
323895 | #307330 | Task | Story 307330: CM Release of 98-P54191T FaultMgmt for EAR 8.5 (EAD 10) | Unassigned | Invalid
323893 | #307330 | Task | Story 307330: CM Release of 98-P59858M NM_Splunk_Application for EAR 8.5 (EAD 10) | Unassigned | Invalid
323892 |  | Task | Story 307330: CM Release of 99-P57051M MUOS_Ground_System_Account_Maintenance_Plan for EAR 8.3 (EAD 10) | Unassigned | Invalid
323890 | #307330 | Task | Story 307330: CM Release of PL01-P59548V001 ILS_Laptop_GEN2 Parts List (EAD 10) | Unassigned | Invalid
323889 | #307330 | Task | Story 307330: CM Release of 99-P54142T ILS_Laptop_GEN2 HW/SW Mapping (EAD 10) | Unassigned | Invalid
323888 | #307330 | Task | Story 307330: CM Release of 98-P54141T ILS_Laptop_GEN2 (EAD 10) | Unassigned | Invalid
323871 |  | Task | Test | Unassigned | Invalid
322985 | #322974 | Story | Complete addition of IMSIs to RNC CDRs: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #322980
322984 | #322974 | Story | Feature Demo – System Test, STCD development and Demo Prep: Complete addition of IMSIs to RNC CDRs | Unassigned | Invalid | 0 | #322976
322983 | #322974 | Story | Complete addition of IMSIs to RNC CDRs: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
322982 | #322974 | Story | Feature 322974: IETM Updates for Completion of Addition of IMSIs to RNC CDRs | Unassigned | Invalid | 0 | #322976
322981 | #322974 | Story | Complete addition of IMSIs to RNC CDRs Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #322976 #322984
322980 | #322974 | Story | Complete addition of IMSIs to RNC CDRs: IA Patching and STIGs | Unassigned | Invalid | 0 | #322977
322979 | #322974 | Story | Complete addition of IMSIs to RNC CDRs: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #322976
322978 | #322974 | Story | Complete addition of IMSIs to RNC CDRs Engineering IETM updates | Unassigned | Invalid | 0 | #322982
322977 | #322974 | Story | Complete addition of IMSIs to RNC CDRs IA Posture Assessment | Unassigned | Invalid | 0 | #322976
322976 | #322974 | Story | Feature Demo – Customer Demo Event: Complete addition of IMSIs to RNC CDRs | Unassigned | Invalid | 0 | #322983
322975 | #322974 | Story | Complete addition of IMSIs to RNC CDRs: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #322980 #322985
322906 |  | Story | Taunton OTA Test System: Additional Support (placeholder) | Unassigned | Invalid | 0
322835 | #241246 | Task | <Feature xxx> Hold Feature Review with SMEs | Unassigned | Invalid
322782 | #311386 | Story | Feature 311386: Incorporate M505 FSW 5.0.0 Ka Band Robustness into next full SCS Release | Unassigned | New | 3
322781 | #311386 | Story | Feature 311386: Incorporate M504 FSW 5.0.0 Ka Band Robustness into next full SCS Release | Unassigned | New | 3
322780 | #311386 | Story | Feature 311386: Incorporate M501 FSW 5.1.0 into next full SCS Release | Unassigned | New | 3
322670 | #317868 | Story | Travel and resolve RCG Site issues | Unassigned | Invalid | 0
322569 | #302092 | Story | Update functional architecture diagram for selected option for Boundary Protection capability investigation (Step 2.5) (story b) - Ready for 8.4 | Unassigned | Invalid | 0
322551 |  | Story | Update functional architecture diagram for selected option for Boundary Protection capability investigation (Step 2.5) (story b) | Unassigned | Invalid | 0
322423 |  | Story | Feature 239677: Test New Build KaDemod RF Drawer | Unassigned | Invalid | 0
322332 |  | Story | AWARE/MHAL Upgrades for Group/PTN Testing: Agile Team Test | Unassigned | Invalid | 0
322171 |  | Story | Need SME to evaluate Digi Passport Console Server | Unassigned | Invalid | 0
321984 |  | Story | GD Support of Zeta - EAD 9/10: AVHIDS SVD - Verify PCR | Unassigned | Invalid | 0
321983 |  | Story | GD Support of Zeta - EAD 9/10: AVHIDS SVD - Update PCR & Start Code Review | Unassigned | Invalid | 0
321982 |  | Story | GD Support of Zeta - EAD 9/10: AVHIDS SVD - Code Review Closure & Build Request | Unassigned | Invalid | 0
321980 |  | Story | GD Support of Zeta - EAD 9/10: HBSS SVD - Verify PCR | Unassigned | Invalid | 0
321979 |  | Story | GD Support of Zeta - EAD 9/10: HBSS SVD - Code Review Closure & Build Request | Unassigned | Invalid | 0
321959 |  | Story | AWARE/MHAL Upgrades for Group/PTN Testing: ERS Poarts List - Verify PCR | Unassigned | Invalid | 0
321958 |  | Story | AWARE/MHAL Upgrades for Group/PTN Testing: ERS Parts List - Code Review Closure & Build Request | Unassigned | Invalid | 0
321957 |  | Story | AWARE/MHAL Upgrades for Group/PTN Testing: ERS Parts List - Update PCR & Start Code Review | Unassigned | Invalid | 0
321950 |  | Story | AWARE/MHAL Upgrades for Group/PTN Testing: AVHIDS SVD for AWARE McAffee - Code Review Closure & Build Request | Unassigned | Invalid | 0
321841 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #321836
321840 |  | Story | Feature Demo – System Test, STCD Execution and Demo Prep | Unassigned | Invalid | 0
321838 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #321832
321836 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #321833
321833 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #321832
321831 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #321841 #321836
321778 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
321769 | #321773 | Feature | Investigate MUOS 503 constellation changes and any UHF/legacy payload impacts to AMS-GS | Unassigned | Analyzing
321745 | #395855 | Problem | Feature 395855: Drawing Updates based on Redlines for 01-P51661E – GTS – PCU Cabinet - RAF, SCD | EA 14.2 | Closed
321724 | #1008506 | Problem | INC000003462045: Security Management IETM procedure updates | EA 15.4 | Approved
321652 | #298324 | Story | Close on final decision for Ground System IA accreditation boundaries | Unassigned | Invalid | 0
321647 | #298324 | Story | Resolve action items from IA boundary partitioning meeting with leadership | Unassigned | Invalid | 0
321643 | #298324 | Story | Present IA accreditation boundary partitioning trades to program leadership (PMW-146, LM, GD) | Unassigned | Invalid | 0
321642 | #298324 | Story | Define pros and cons of each IA accreditation boundary partitioning option | Unassigned | Invalid | 0
321636 |  | Story | Story 4 under Feature 295962 | Unassigned | Invalid | 0
321635 |  | Story | Story 3 under Feature 295962 | Unassigned | Invalid | 0
321634 |  | Story | Story 2 under Feature 295962 | Unassigned | Invalid | 0
321633 |  | Story | Story 1 under Feature 295962 | Unassigned | Invalid | 0
321563 |  | Story | TD19-10 ULX Integration into ETISP: SE SME Early Support of the UHF over MUOS | Unassigned | Invalid | 0
321410 | #296198 | Story | Document impacts to current Device Access Control architecture for each option | Unassigned | New | 1
321409 | #296198 | Story | Identify different Device Access Control options to address gaps | Unassigned | New | 2
321408 | #296198 | Story | Present current MUOS Device Access Control Security Functional architecture and gaps to IA and System stakeholders | Unassigned | New | 1
321407 | #296198 | Story | Update Device Access Control Capability Investigation document with selected options to pursue in Part 2 | Unassigned | New | 2
321406 | #296198 | Story | Present Device Access Control options to address gaps to IA and System stakeholders | Unassigned | New | 1
321405 | #296198 | Story | Perform gap analysis of current MUOS Device Access Control security functional architecture | Unassigned | New | 5
321404 | #296198 | Story | Document current Device Access Control functional architecture - part 2 | Unassigned | New | 3
321403 | #296198 | Story | Document current Device Access Control functional architecture - part 1 | Unassigned | New | 2
321402 | #296198 | Story | Document Device Access Control security control mappings | Unassigned | New | 1
321401 | #296198 | Story | Document Device Access Control capability findings/controls/measures | Unassigned | New | 2
321349 |  | Problem | 993529/INC000003443396: WH- Incorrect Timestamps on Tivoli Provisioning Manager (TPM) Workflow Logs | Unassigned | Assessing
321315 | #316311 | Story | RTC feature intake | Unassigned | New | 1
321314 | #316311 | Story | Present completed Capability Investigation to IA and System stakeholders and update per comments | Unassigned | New | 2
321313 | #316311 | Story | ROM estimate associated complexity/cost/effort | Unassigned | New | 1
321312 | #316311 | Story | Document security posture and recommended priority | Unassigned | New | 1
321311 | #316311 | Story | Update functional architecture description for selected option | Unassigned | New | 5
321310 | #316311 | Story | Present trade results to IA and System stakeholders | Unassigned | New | 1
321304 | #316311 | Story | Document trade | Unassigned | New | 3
321296 | #245898 | Feature | Investigate Impact of Geo Migrating from RedHat 6.8 to RedHat 7 | Unassigned | Analyzing
321294 | #316311 | Story | Document implementation options | Unassigned | New | 3
321291 | #316311 | Story | Investigate different options | Unassigned | New | 3
321255 | #298324 | Story | Work with PMW-146 IA personnel on defining options for partitioning Ground System IA accreditation boundary into multiple smaller pieces than current Ground System | Unassigned | Invalid | 0
321161 | #294836 | Story | Feature 294836: KG175A Replacement: HW/SW Map updates for 99-P54410V TRAFSEC2 | Unassigned | Invalid | 0 | #318634
321144 |  | Task | test | Unassigned | New
321034 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 CI Update HBSS SVD | Unassigned | New | 5
320778 |  | Story | Win10 LAPTOP Tools and Workstation Update: SME Support for Windows 10 (PI 08) - 8.4 | Unassigned | Invalid | 0
320777 |  | Story | Win10 LAPTOP Tools and Workstation Update: SME Support for Windows 10 (PI 08) - 8.3 | Unassigned | Invalid | 0
320712 | #316299 | Story | ROM estimate for selected option for Software Integrity/Application Protection capability investigation (Step 2.7) | Unassigned | Invalid | 0
320671 |  | Story | Present architecture and gap analysis for Software Integrity/Application Protection capability investigation - Part 1 | Unassigned | Invalid | 0
320645 |  | Story | Perform gap analysis for Software Integrity/Application Protection capability investigation - part 1 | Unassigned | Invalid | 0
320644 |  | Task | Win10 LAPTOP Tools Update: Complete NETMAC Purchase | Unassigned | Invalid
320625 |  | Story | Win10 LAPTOP Tools and Workstation Update: SME Support for Windows 10 (PI 08) - 8.2 | Unassigned | Invalid | 0
320596 | #1013452 | Problem | Northwest (NW) GIS Firewall is denying IP protocol 50 ESP packets from WH NIPRNET HAIPE (whniprnethaipe1) to UE (APN12). | PI 16 | Approved
320237 | #1001062 | Story | RDE BuildForge - Update Email properties in BuildForge scripts and Management Console | EA 15.2 | Done | 1
320072 | #245575 | Problem | Northwest (NW) TIS Firewall is denying IKE packets from UE P2N (APN12) destine to NW NIPRNET HAIPE | Unassigned | Closed
319918 | #287302 | Story | Feature 287302: Northwest preventive maintenance planning: Part 4 | Unassigned | Invalid | 0
319917 | #287302 | Story | Feature 287302: Northwest preventive maintenance planning: Part 3 | Unassigned | Invalid | 0
319911 | #287304 | Story | Feature 287304: Geraldton preventive maintenance planning: Part 4 | Unassigned | Invalid | 0
319910 | #287304 | Story | Feature 287304: Geraldton preventive maintenance planning: Part 3 | Unassigned | Invalid | 0
319909 | #287304 | Story | Feature 287304: Geraldton preventive maintenance planning: Part 2 | Unassigned | Invalid | 0
319892 |  | Story | Auto - Call - Training for configuring (existing) VMWare virtual machines for automation software development | Unassigned | Invalid | 0
319890 |  | Story | Auto - Call - Roll out MultiHAL V1.4 to the Call Banks | Unassigned | Invalid | 0
319882 | #319864 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #319874
319881 | #319864 | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
319880 | #319864 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #319867
319879 | #319864 | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #319878
319878 | #319864 | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #319874
319877 | #319864 | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #319874
319876 | #319864 | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #319874
319875 | #319864 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #319874
319874 | #319864 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #319872 #319881
319873 | #319864 | Story | <Feature yyy>: IA Posture Assessment - Define Patch and STIG Requirements | Unassigned | Invalid | 0 | #319880
319872 | #319864 | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
319871 | #319864 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #319874
319870 | #319864 | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #319871
319869 | #319864 | Story | <Feature yyy> ILS Create red lines Hardware drawings submitted for IDP | Unassigned | Invalid | 0 | #319866
319868 | #319864 | Story | <Feature yyy> ILS Define Power Consumption Changes for IDP | Unassigned | Invalid | 0 | #319866
319867 | #319864 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #319875
319866 | #319864 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #319874
319865 | #319864 | Story | <Feature yyy>: ILS Considerations (non-IETM) | Unassigned | Invalid | 0 | #319874
319864 |  | Feature | <Feature yyy> HW/FRCB Deployable Feature | Unassigned | Rejected
319817 | #319806 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #319812
319816 | #319806 | Story | Feature 319806: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #319808
319815 | #319806 | Story | Feature 319806: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
319812 | #319806 | Story | Feature 319806: IA Patching and STIGs | Unassigned | Invalid | 0 | #319809
319809 | #319806 | Story | Feature 319806: IA Posture Assessment | Unassigned | Invalid | 0 | #319808
319807 | #319806 | Story | Feature 319807: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #319817 #319812
319759 | #383110 | Problem | Resource Usage Dashboard table title (Last Reported Value...) fails to refresh/update | Unassigned | Approved
319731 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI 98-P55537M Log Tool | Unassigned | New | 5
319730 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI 98-P55537M Log Tool | Unassigned | New | 5
319729 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI Securify | Unassigned | New | 3
319726 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI Thales Remove Workstation No longer used. | Unassigned | New | 3
319725 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI TPM | Unassigned | New | 5
319654 |  | Story | TFDU Maintenance: Engineering IETM updates (Part 2) | Unassigned | Invalid | 0
319589 |  | Story | Feature 319587: Design IETM and procedure changes | Unassigned | Invalid | 0
319586 |  | Story | TD19-10 ULX Integration into ETISP: ETISP SME Support | Unassigned | Invalid | 0
319583 |  | Story | TD19-10 ULX Integration into ETISP: A&A SME Support | Unassigned | Invalid | 0
319551 | #294458 | Story | Feature 294458: Perform EAD 9 Training (ARSTRAT) | Unassigned | Invalid | 0 | #319553
319395 | #319381 | Story | Feature 319381: Implementation Placeholder | Unassigned | Invalid | 0
319392 | #319381 | Story | Feature 319381: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #319387
319391 | #319381 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #319383
319390 | #319381 | Story | Feature 319381: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
319389 | #319381 | Story | Feature 319381:ILS IETM updates | Unassigned | Invalid | 0 | #319383
319388 | #319381 | Story | Feature 319381 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #319391 #319383
319387 | #319381 | Story | Feature 319381: IA Patching and STIGs | Unassigned | Invalid | 0 | #319384
319386 | #319381 | Story | Feature 319381: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #319383
319385 | #319381 | Story | Feature 319381 Engineering IETM updates | Unassigned | Invalid | 0 | #319389
319384 | #319381 | Story | Feature 319381 IA Posture Assessment | Unassigned | Invalid | 0 | #319383
319383 | #319381 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #319390
319382 | #319381 | Story | Feature 319381: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #319387 #319392
319381 | #217635 | Feature | Improve Splunk Help for Indexed Provisioning Data | Unassigned | Rejected
319371 |  | Story | WCDMA Service Status Phase 2 - TOFF support (lab testing strategy) | Unassigned | Invalid | 0
319367 |  | Story | WCDMA Service Status Phase 2 - TOFF support (lab testing strategy) | Unassigned | Invalid | 0
319351 | #383110 | Problem | Splunk Help Does not Provide Sufficient Documentation for Indexed Provisioning Data | Unassigned | Approved
319127 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 CI Update Windows 10 SVD | Unassigned | New | 5
319126 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 IA Freshness Win 10 & XP | Unassigned | New | 8
319122 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update NEDB, NMCSCI | Unassigned | New | 5
319121 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update Drawings, Parts Lists, Floor Plan, Drawing Tree. | Unassigned | New | 5
319120 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update LAN Switch CI to enable ports for new WS | Unassigned | New | 5
319113 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI Account Maint Plan | Unassigned | New | 3
319112 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI PKI Doc | Unassigned | New | 3
319111 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI HW/SW Mapping | Unassigned | New | 3
319109 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI HSS | Unassigned | New | 3
319108 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI Backup Archive | Unassigned | New | 3
319107 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI VX Builder | Unassigned | New | 3
319106 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI GS_KeyMgmt | Unassigned | New | 3
319103 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI NETMac GUI | Unassigned | New | 3
319102 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update CI McAfee Firewall | Unassigned | New | 13
319101 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update OSS-RC | Unassigned | New | 13
319100 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update Tectia | Unassigned | New | 3
319098 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update Common LIb | Unassigned | New | 3
319097 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Update Printer CI for WS | Unassigned | New | 3
319085 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 IA Posture Assessment - review of developer input | Unassigned | New | 1 | #319080
319084 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #319076
319083 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Initiate CM PDO Processing for all CI's | Unassigned | New | 1
319082 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 ILS IETM updates | Unassigned | New | 3 | #319076
319081 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #319084 #319076
319080 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 IA Patching and STIGs | Unassigned | New | 8 | #319077
319079 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #319076
319078 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Engineering IETM updates | Unassigned | New | 3 | #319082
319077 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 IA Posture Assessment | Unassigned | New | 8 | #319076
319076 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 Feature Demo – Customer Demo Event | Unassigned | New | 1 | #319083
319075 | #319074 | Story | Feature 319074: Workstation Expansion Phase 3 IA Posture Assessment - development input | Unassigned | New | 2 | #319080 #319085
318827 | #1021037 | Problem | HP HLR time sync faults occurring within tolerance but risk timing being out-of-sync if exceeded | PI 16 | Ready for IRM Approval
318822 | #318811 | Story | <Feature 318811>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #318817
318821 | #318811 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #318813
318820 | #318811 | Story | <Feature 318811>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
318819 | #318811 | Story | Feature 318811: IETM updates for Implementation of display of "throughput" in DSN/MVG and IP Teleport SA | Unassigned | Invalid | 0 | #318813
318818 | #318811 | Story | <Feature 318811> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #318813 #318821
318817 | #318811 | Story | <Feature 318811>: IA Patching and STIGs | Unassigned | Invalid | 0 | #318814
318816 | #318811 | Story | <Feature 318811>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #318813
318815 | #318811 | Story | <Feature 318811> Engineering IETM updates | Unassigned | Invalid | 0 | #318819
318814 | #318811 | Story | Feature 318811: IA Posture Assessment | Unassigned | Invalid | 0 | #318813
318813 | #318811 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #318820
318812 | #318811 | Story | <Feature 318811>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #318817 #318822
318793 |  | Story | Feature 318212: Scan (Radio Call Bank Server) | Unassigned | Invalid | 0
318791 |  | Story | Feature 318212: Scan (Roosevelt Radio Call Bank MOXAs) | Unassigned | Invalid | 0
318788 |  | Story | Feature 318212: IA Patching and STIG (Hayden Radio Call Banks MOXA) | Unassigned | Invalid | 0
318787 |  | Story | Feature 318212: IA Patching and STIG (Roosevelt Radio Call Banks MOXA) | Unassigned | Invalid | 0
318785 |  | Story | Feature 318212: IA Patching and STIG (Roosevelt Radio Call Bank Servers) | Unassigned | Invalid | 0
318742 | #241246 | Story | <Feature xxx> UX Research and Design Support | Unassigned | Invalid | 0
318741 | #241246 | Story | <Feature xxx>: ILS Incorporation of IETM updates and integration support | Unassigned | Invalid | 0
318653 | #316161 | Story | <IETM Feature XXX> Initiate CM PDO Release of all artifacts | Unassigned | New | 1
318648 | #316161 | Story | <IETM Feature xxx>:ILS IETM Final Updates (S7) | Unassigned | New | 1 | #316163
318647 | #316161 | Story | <IETM Feature xxx> Final STCD Execution for IETM updates (S6) | Unassigned | New | 3 | #318648 #316163
318577 | #251537 | Story | Win10 LAPTOP Tools Update: Windows 10 Workstation CI IA Freshness. | Unassigned | Invalid | 0
318536 | #316161 | Story | <IETM Feature xxx> Formal Review of IETM Procedures (S5) | Unassigned | New | 2 | #318647
318525 | #316161 | Story | <IETM Feature xxx>: ILS Training Development based upon Operator Impacts (S3) | Unassigned | New | 2 | #316163
318511 | #316161 | Story | <IETM Feature xxx> ILS support for Agile Team Test (Integrate, Test) (S3) | Unassigned | New | 0
318509 | #316161 | Story | <IETM Feature xxx> UX support for Agile Team Test (Integrate, Test) (S3) | Unassigned | New | 0
318508 | #316161 | Story | <IETM Feature xxx> Test support for Agile Team Test (Integrate, Test) (S3) | Unassigned | New | 0
318476 | #316161 | Story | <IETM Feature xxx> STCD Development for IETM (S2) | Unassigned | New | 0
318462 | #1011279 | Story | Feature 1011279: ETT: Depot Build and Deliver ETT Laptops | EA 14.3 | Done | 2
318444 | #316161 | Story | <IETM Feature xxx> Perform Analysis and Design (S1) | Unassigned | New | 3 | #316165 #318476 #316166
318441 |  | Story | ETT Laptop: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #318436
318439 | #318430 | Story | Feature 318430 ETT: Initiate CM PDO Processing for all CI's | EA 14.1 | Done | 2
318432 | #318430 | Story | Feature 318430 ETT: Feature Demo – Customer Demo Event - ETT Laptop | EA 14.1 | Done | 3 | #318439 #390060
318431 |  | Story | ETT Laptop: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #318436 #318441
318430 | #251622 | Feature | Windows 10 Laptop for ETT | EA 14.2 | Done
318421 |  | Story | AJM/MTC Laptop: Cross-training for creating windows images | Unassigned | Invalid | 0
318420 | #1011279 | Story | Feature 1011279: AJM/MTC Laptop: Depot build and be ready for AJM/MTC laptops delivery | EA 14.3 | Done | 3 | #318418
318418 | #1011279 | Task | Feature 1011279 AJM/MTC & ETT Laptop: Confirm Laptops are Fully Prepared for Shipment to Site | EA 14.3 | Done
318389 | #318380 | Story | Feature 318380 AJM: Initiate CM PDO Processing for all CI's | EA 14.1 | Done | 1
318380 | #251622 | Feature | Windows 10 Laptop for AJM/MTC | EA 14.1 | Done
318306 | #251622 | Feature | Windows 10 LAPTOP ETI Laptop | Unassigned | Rejected
318303 | #251622 | Feature | Windows 10 LAPTOP AJM\MTC | Unassigned | Rejected
318295 | #318289 | Task | Review the logs from Mervin twice a week (EA 8.5) | Unassigned | Invalid
318294 | #318289 | Task | Review the logs from Mervin twice a week (EA 8.4) | Unassigned | Invalid
318293 |  | Task | Review the logs from Mervin twice a week (EA 8.3) | Unassigned | Invalid
318292 |  | Task | Review the logs from Mervin twice a week (EA 8.2) | Unassigned | Invalid
318290 | #318289 | Task | Review the logs from Mervin twice a week (EA 8.1) | Unassigned | Invalid
318289 |  | Story | A&A ScrumMaster Housekeeping - PI 08 | Unassigned | Invalid | 0
318288 |  | Task | Review the logs from Mervin twice a week (EA 7.6) | Unassigned | Invalid
318287 |  | Task | Review the logs from Mervin twice a week (EA 7.5) | Unassigned | Invalid
318213 |  | Story | Feature 318212: IA Patching and STIG (Taunton Radio Call Bank Servers) | Unassigned | Invalid | 0
318210 |  | Story | Feature 278274: Feature Demo Prep - ETT updates | Unassigned | Invalid | 0 | #318208
318121 | #315734 | Story | Feature 315734: Develop Engineering IETM procedures for the graceful power down/up process to support replacement of Routing Boards (NME 1 Cabinet 01-P53566E001 (01-P57217M002)) | Unassigned | Invalid | 0
317958 | #251537 | Story | Win10 LAPTOP Tools and Workstation Update: NetMac new Windows 10 version needs tested to Dehydrator | Unassigned | Invalid | 0
317955 | #251537 | Story | Win10 LAPTOP Tools Update: FEPs will need to upgraded to a new Version 98-P55613M | Unassigned | Invalid | 0 | #317954 #317957 #317958
317943 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: Verify PCR for ETT update alignment procedures to include updates to the AWARE sections | Unassigned | Invalid | 0
317921 |  | Story | Support PMW Scrub of existing A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Invalid | 0
317919 |  | Story | Support PMW Scrub of existing A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Invalid | 0
317918 |  | Story | Support PMW Scrub of existing A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Invalid | 0
317917 |  | Task | CM Release of MUOS_IG_GS_Network_LB_SVD_98-P55464M003 for EAR 7.6 (EAD 9) | Unassigned | Invalid
317916 |  | Task | CM Release of MUOS_IG_GS_GTS_SWITCH_SSA_LB_SVD_98-P55734M003 for EAR 7.6 (EAD 9) | Unassigned | Invalid
317884 |  | Task | Rejected: Obsolescence: (Windows) Trade Study - AAA/DNS | Unassigned | Invalid
317859 | #317840 | Story | <Feature 317840> Test Equipment IATT Finalization - Final Scans | Unassigned | Invalid | 0
317857 |  | Problem | 98-P54139T MUOS Interactive Technical Manual (IETM) needs to be updated to point to 99-P53449E Interactive Electronic Technical Manual | Unassigned | Assessing
317851 | #317840 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #317846
317850 | #317840 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #317842
317849 | #317840 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
317848 | #317840 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #317842
317847 | #317840 | Story | <Feature 317840> Test Equipment IATT Finalization - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #317842 #317850
317846 | #317840 | Story | <Feature 317840> Test Equipment IATT Finalization - IA Patching and STIGs (MOXA) | Unassigned | Invalid | 0 | #317843
317845 | #317840 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #317842
317844 | #317840 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #317848
317843 | #317840 | Story | <Feature 317840> Test Equipment IATT Finalization - Final IA Posture Assessment | Unassigned | Invalid | 0 | #317842
317842 | #317840 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #317849
317841 | #317840 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #317846 #317851
317840 | #245560 | Feature | Feature 317840: Test Equipment IATT Finalization | Unassigned | Rejected
317838 |  | Problem | INC000003250586 (DNSDHCP PRIMARY & SECONDARY IN WH AND NW - Ipworks bouncing) | Unassigned | Assessing
317820 | #241246 | Story | <Feature xxx>:MFR 3 – Dev Team Resolves ACAS Scan and STIG Findings | Unassigned | Invalid | 0 | #380135
317816 | #241246 | Story | <Feature xxx>: Create STCD and review with stakeholders | Unassigned | Invalid | 0 | #241249 #248455 #343163 #380160
317750 |  | Story | Analysis and Design fix for RNC Issue with RTWP measurements and Alarms | Unassigned | Invalid | 0
317683 |  | Story | Feature 318212: Scan (Taunton Radio Call Bank MOXAs) | Unassigned | Invalid | 0
317329 | #316161 | Story | <IETM Feature xxx>: SME Support of IETM Review Part 1 | Unassigned | New | 2
317322 |  | Story | <IETM Feature xxx>: UX Support of Engineering IETM Updates Part 1 | Unassigned | Invalid | 0
317321 |  | Task | 19-10 Proposal Training | Unassigned | Invalid
317320 |  | Task | 19-10 Proposal Training | Unassigned | Invalid
317319 |  | Task | 19-10 Proposal Training | Unassigned | Invalid
317317 |  | Task | 19-10 Proposal Training | Unassigned | Invalid
317316 |  | Task | 19-10 Proposal Training | Unassigned | Invalid
317230 |  | Story | June UFO Table Update MPCs (Part 2) | Unassigned | Invalid | 0
317159 | #317151 | Story | <Feature 317151> Prepare for Test Equipment IATT Extension - ILS IETM updates | Unassigned | Invalid | 0 | #317153
317157 |  | Story | Feature 318212: IA Patching and STIG (Taunton Radio Call Banks MOXA) | Unassigned | Invalid | 0 | #317154
317150 |  | Feature | Prepare for Test Equipment IATT Extension (Mitigate Vulnerabilities) | Unassigned | Rejected
316973 |  | Story | Test Story | Unassigned | Invalid | 0
316866 |  | Problem | INC000003381432: A particular tape on the high side has an Access field of “Unavailable" | Unassigned | Assessing
316438 |  | Story | Investigate Issue and Determine Solution | Unassigned | Invalid | 0
316429 | #316423 | Story | Feature 316423: IA Patching and STIGs | Unassigned | Invalid | 0 | #316426
316422 | #316411 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #316417
316421 | #316411 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #316413
316420 | #316411 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
316419 | #316411 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #316413
316418 | #316411 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #316413 #316421
316417 | #316411 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #316414
316416 | #316411 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #316413
316415 | #316411 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #316419
316414 | #316411 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #316413
316413 | #316411 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #316420
316412 | #316411 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #316417 #316422
316411 |  | Feature | <Feature xxx> | Unassigned | Rejected
316365 |  | Story | UX - Review and Input of RNC alarms (5 of 5) | Unassigned | Invalid | 0
316354 | #316343 | Story | Feature 316343: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #316349
316353 | #316343 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #316345
316352 | #316343 | Story | Feature 316343: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
316351 | #316343 | Story | Feature 316343: IETM updates for AWARE/MHAL Test Execution Upgrades | Unassigned | Invalid | 0 | #316345
316350 | #316343 | Story | Feature 316343: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #316353 #316345
316349 | #316343 | Story | Feature 316343: IA Patching and STIGs | Unassigned | Invalid | 0 | #316346
316348 | #316343 | Story | Feature 316343: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #316345
316347 | #316343 | Story | Feature 316343: Engineering IETM updates | Unassigned | Invalid | 0 | #316351
316346 | #316343 | Story | Feature 316343: IA Posture Assessment | Unassigned | Invalid | 0 | #316345
316345 | #316343 | Story | Feature Demo – Customer Demo Event - Feature 316343 | Unassigned | Invalid | 0 | #316352
316344 | #316343 | Story | Feature 316343: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #316354 #316349
316343 | #347072 | Feature | AWARE/MHAL Test Execution Upgrades Necessary to Better Support Unexpected Results | Unassigned | Rejected
316333 | #305457 | Task | CM Release of MUOS_IG_GS_NMS_NM_Security_SIEM_SW_98-P59428M5 for EAR 7.6 (EAD 9) | Unassigned | Invalid
316300 |  | Story | UX - Review and Input of RBS alarms (5 of 5) | Unassigned | Invalid | 0
316286 |  | Story | UX - Review and Input of RBS alarms (5 of 5) | Unassigned | Invalid | 0
316277 | #296125 | Story | Scrub MUOSAT CRs and transition to RTC work items where applicable | Unassigned | Invalid | 0
316262 | #316251 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #316257
316261 | #316251 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #316253
316260 | #316251 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
316259 | #316251 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #316253
316258 | #316251 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #316261 #316253
316257 | #316251 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #316254
316256 | #316251 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #316253
316255 | #316251 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #316259
316254 | #316251 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #316253
316253 | #316251 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #316260
316252 | #316251 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #316257 #316262
316251 |  | Feature | <Feature xxx> | Unassigned | Rejected
316198 | #316178 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #316188
316197 | #316178 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #316188
316196 | #316178 | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
316195 | #316178 | Story | <Feature yyy>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #316194
316194 | #316178 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #316181
316193 | #316178 | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #316192
316192 | #316178 | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #316188
316191 | #316178 | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #316198 #316188
316190 | #316178 | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #316188
316189 | #316178 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #316188
316188 | #316178 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #316196 #316186
316187 | #316178 | Story | <Feature yyy>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #316195
316186 | #316178 | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
316185 | #316178 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #316188
316184 | #316178 | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #316185
316183 | #316178 | Story | <Feature yyy> ILS Create red lines Hardware drawings submitted for IDP | Unassigned | Invalid | 0 | #316180
316182 | #316178 | Story | <Feature yyy> ILS Define Power Consumption Changes for IDP | Unassigned | Invalid | 0 | #316180
316181 | #316178 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #316189
316180 | #316178 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #316188
316179 | #316178 | Story | <Feature yyy>: ILS Considerations (non-IETM) | Unassigned | Invalid | 0 | #316188
316178 |  | Feature | <Feature yyy> HW/FRCB Deployable Feature | Unassigned | Rejected
316172 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #316167
316171 |  | Story | <IETM Feature xxx>: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
316170 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
316169 | #316161 | Story | <IETM Feature xxx>:ILS IETM Initial updates (S4) | Unassigned | New | 3 | #318536
316168 | #316161 | Story | <IETM Feature xxx> Developer support for Agile Team Test (Integrate, Test) (S3) | Unassigned | New | 0 | #316169
316167 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #316164
316166 | #316161 | Story | <IETM Feature xxx>: Deployment Notes and Operator Impact Inputs (S2) | Unassigned | New | 2 | #316163 #318525
316165 | #316161 | Story | <IETM Feature xxx> Initial Engineering IETM updates (S2) | Unassigned | New | 0 | #316168
316164 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0
316163 | #316161 | Story | <IETM Feature xxx>: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #318653
316162 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #316172 #316167
316161 |  | Feature | IETM Feature <xxx> | Unassigned | Draft
315850 |  | Story | AWARE/MHAL Test Execution Upgrades: Updated Sequencing | Unassigned | Invalid | 0
315808 | #315230 | Story | Update Intersite dashboard | Unassigned | Invalid | 0
315807 | #315230 | Story | Redesign Intersite dashboard logic | Unassigned | Invalid | 0
315717 |  | Story | Limit who can close a story to PO's and Scrum Masters | Unassigned | Done | 1
315716 |  | Story | Need to update Feature Template so that SIT and IA stories are part of the Agile Development Teams | Unassigned | Done | 0
315607 | #1007900 | Problem | [Urgent] SR 984301 / INC000003355751: MUOS -McAfee preventing ETISP to go into running | EA 15.1 | Closed
315600 | #315230 | Story | Create OOC/MPC package for new dashboards | Unassigned | Invalid | 0
315599 | #315230 | Story | Splunk App review rework | Unassigned | Invalid | 0
315598 | #315230 | Story | Review Splunk App updates | Unassigned | Invalid | 0
315597 | #315230 | Story | Update help pages | Unassigned | Invalid | 0
315596 | #315230 | Story | Update GSS dashboard | Unassigned | Invalid | 0
315595 | #315230 | Story | Create Ping Probe Status dashboard | Unassigned | Invalid | 0
315594 | #315230 | Story | Review UX Design | Unassigned | Invalid | 0
315573 | #315562 | Story | WCDMA Service Status: Phase 2 - DSN & IP Teleport: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0
315570 | #315562 | Story | Feature 315562: WCDMA Service Status: Phase 2 - DSN & IP Teleport: IETM updates | Unassigned | Invalid | 0 | #315564
315566 |  | Story | WCDMA Service Status: Phase 2 - DSN & IP Teleport Engineering IETM updates | Unassigned | Invalid | 0
315563 | #315562 | Story | WCDMA Service Status: Phase 2 - DSN & IP Teleport: IA Posture Assessment - development input | Unassigned | Invalid | 0
315506 |  | Story | FRB 2018-18 C6 HPA Sustainability - IETM update to collect logs from failed HPAs | Unassigned | Invalid | 0
315393 | #315230 | Story | Dashboard design for Ping Probe Situational Awareness | Unassigned | Invalid | 0
315388 | #315379 | Story | Commvault functionality | Unassigned | Invalid | 0
315387 | #315379 | Story | StorageCraft functionality | Unassigned | Invalid | 0
315386 | #315379 | Story | StorageCraft Database recovery | Unassigned | Invalid | 0
315385 | #315379 | Story | Commvault Database recovery | Unassigned | Invalid | 0
315384 | #315379 | Story | Test StorageCraft backup and restore Windows and RHEL | Unassigned | Invalid | 0
315383 | #315379 | Story | Test Commvault to backup and restore Windows and RHEL | Unassigned | Invalid | 0
315381 | #315379 | Story | install evaluation copy StorageCraft in SWIT LAB and test | Unassigned | Invalid | 0
315380 | #315379 | Story | install evaluation copy Commvault in SWIT LAB and test | Unassigned | Invalid | 0
315379 | #247162 | Feature | Obsolescence: Evaluation of Backup and Archive Software | Unassigned | Rejected
315273 |  | Story | Feature 290856: SME support for AWARE Phase 1 Training. | Unassigned | Invalid | 0
315270 |  | Story | Feature 290777: AMS-GS Training: Engineering SME support (WH) | Unassigned | Invalid | 0
315239 | #315230 | Story | Ping Probe Situational Awareness: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
315238 | #315230 | Story | Ping Probe Situational Awareness:ILS IETM updates | Unassigned | Invalid | 0 | #315232
315237 | #315230 | Story | Ping Probe Situational Awareness Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #315232 #315240
315236 | #315230 | Story | Ping Probe Situational Awareness: IA Patching and STIGs | Unassigned | Invalid | 0 | #315233
315235 | #315230 | Story | Ping Probe Situational Awareness: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #315232
315234 | #315230 | Story | Ping Probe Situational Awareness Engineering IETM updates | Unassigned | Invalid | 0 | #315238
315233 | #315230 | Story | Ping Probe Situational Awareness IA Posture Assessment | Unassigned | Invalid | 0 | #315232
315232 | #315230 | Story | Ping Probe Situational Awareness - Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #315239
315096 |  | Story | GD Support of Zeta - EAD-9/10: Update Account Maintanence plan | Unassigned | Invalid | 0
315070 | #310667 | Story | Obsolescence: Trade Study - AWARE | Unassigned | Invalid | 0
315069 | #310667 | Story | Obsolescence: Trade Study - AWARE | Unassigned | Invalid | 0
315068 | #310667 | Story | Obsolescence: Trade Study - AWARE | Unassigned | Invalid | 0
315026 | #310667 | Story | Obsolescence - Windows; cybersecurity value/impact analysis, security requirements and architecture definition | Unassigned | Invalid | 0
314866 |  | Story | 19-10 Proposal Support: AWARE (Section 2.6.1.3) - AWARE BOE Review | Unassigned | Invalid | 0
314706 |  | Story | Feature 247009:KG175A Replacement - GEM Application Workstation Investigation | Unassigned | Invalid | 0
314668 |  | Story | 19-10 Proposal Support - 2.9 MUOS WCDMA service optimization | Unassigned | Invalid | 0
314450 |  | Story | Provide AWARE O-Level IETMs: Transition PCR for AWARE Component Health Check Procedure to ILS | Unassigned | Invalid | 0
314449 |  | Story | Provide AWARE O-Level IETMs: Transition PCR for AWARE Test Execution Health Check Procedure to ILS | Unassigned | Invalid | 0
314444 |  | Story | ARSTRAT Proposed Changes to RF Alignment - Outline Option to Reduce SIte Downtime | Unassigned | Invalid | 0
314323 | #275633 | Story | Prepare AMS-GS IETMs: IA Posture Assessment | Unassigned | Invalid | 0
314137 |  | Story | AWARE/MHAL Test Execution Upgrades Necessary to Support Group/PTN Testing | Unassigned | Invalid | 0
314105 |  | Story | Standalone AWARE - Test Groups and Test Call Scenarios: Provide Procedures to Support Global Test Groups | Unassigned | Invalid | 0
313739 | #310297 | Story | Unclass GDS: Refine backlog/intake for subsequent increments - A&A | Unassigned | New | 5
313738 | #310297 | Story | TD 19-18 Unclass GDS: Refine backlog/intake for subsequent increments - Systems | Unassigned | New | 5
313734 | #310297 | Story | TD 19-18 Unclass GDS: System Architecture Brief - Systems | Unassigned | New | 13
313670 | #354174 | Problem | INC000003301067: WH- SOL_001_filesys_<filesystem> in "List_of_Custom_Alarms.pdf" incorrect command in IETM procedure. | EA 14.4 | Closed
313550 |  | Story | AWARE IA Posture Improvement Continuation: UX support285527 | Unassigned | Invalid | 0
313548 |  | Story | MHAL SME support | Unassigned | Invalid | 0
313339 | #293940 | Story | Troubleshoot OSSRC IETM Redline Updates293940 | Unassigned | Invalid | 0
313116 | #245566 | Task | RNC CchFrameSynch alarms - ADD | Unassigned | Done
313114 | #245566 | Task | ETISP CPICH power alarms - ADD | Unassigned | Done
312832 | #312821 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #312827
312831 | #312821 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #312823
312830 | #312821 | Story | Finalize Ka-band robustness SUT switching: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
312829 | #312821 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #312823
312828 | #312821 | Story | Finalize Ka-band robustness SUT switching: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #312823 #312831
312827 | #312821 | Story | Finalize Ka-band robustness SUT switching: IA Patching and STIGs | Unassigned | Invalid | 0 | #312824
312826 | #312821 | Story | Finalize Ka-band robustness SUT switching: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #312823
312825 | #312821 | Story | Finalize Ka-band robustness SUT switching: Engineering IETM updates | Unassigned | Invalid | 0 | #312829
312824 | #312821 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #312823
312823 | #312821 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #312830
312822 | #312821 | Story | Finalize Ka-band robustness SUT switching: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #312832 #312827
312821 | #245572 | Feature | Finalize Ka-band robustness SUT switching (Create an IETM ET configuration procedure) | Unassigned | Rejected
312134 | #310297 | Story | Unclass GDS: System Architecture Brief - Waveform | Unassigned | New | 8
312133 | #310297 | Story | Unclass GDS: System Architecture Brief - A&A | Unassigned | New | 13
312096 | #268111 | Task | AWARE System Troubleshooting | Unassigned | Invalid
311942 |  | Task | Aaron Smith O O P 7/14 - 7/18 | Unassigned | Invalid
311750 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: SVD Update of Appendix M Support (Part 2) | Unassigned | Invalid | 0
311620 |  | Problem | ICM release MUOSD00314916 98-P55500M RevF GDS MS WINDOWS 2003 BASELINE SVD has an issue when it is selected in the Site Release Record | Unassigned | Triage
311467 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: Verify PCR for Account Maintenance Plan | Unassigned | Invalid | 0
311406 | #311386 | Story | Feature 311386: Perform File Updates | Unassigned | New | 5
311403 | #311386 | Story | Feature 311386: Remove old Geolocation Applications | Unassigned | New | 5
311401 | #311386 | Story | Feature 311386: IETM Troubleshooting and Data Collection IETM Procedures for bad ranging data | Unassigned | New | 8
311400 | #311386 | Story | Feature 311386: Store Ranging Data and alarm bad ranging Data | Unassigned | New | 8
311398 | #311386 | Story | Feature 311386: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #311393
311397 | #311386 | Story | Feature 311386: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #311389
311396 | #311386 | Story | Feature 311386: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
311395 | #311386 | Story | Feature 311386: ILS IETM updates | Unassigned | New | 3 | #311389
311394 | #311386 | Story | Feature 311386: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #311397 #311389
311393 | #311386 | Story | Feature 311386: IA Patching and STIGs | Unassigned | New | 8 | #311390
311392 | #311386 | Story | Feature 311386: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #311389
311391 | #311386 | Story | Feature 311386: Engineering IETM updates | Unassigned | New | 3 | #311395
311390 | #311386 | Story | Feature 311386: IA Posture Assessment | Unassigned | New | 8 | #311389
311389 | #311386 | Story | Feature 311386: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #311396
311388 | #311386 | Story | Feature 311386: IA Posture Assessment - development input | Unassigned | New | 2 | #311393 #311398
311349 | #311347 | Story | Investigate NetCool Changes for Additional Data | Unassigned | Invalid | 0
310806 | #309972 | Story | Unclass GDS: ILS Drawings #3 | Unassigned | New | 13
310804 | #309972 | Story | Unclass GDS: ILS Drawings #2 | Unassigned | New | 13
310803 | #309972 | Story | Unclass GDS: ILS Drawings | Unassigned | New | 13
310667 | #241501 | Feature | TD 19-10: Trade Study - AWARE | Unassigned | Rejected
310664 | #309972 | Story | Unclass GDS: Training #2 (Placeholder) | Unassigned | New | 13
310662 | #309972 | Story | Unclass GDS: Training (Placeholder) | Unassigned | New | 13
310619 | #310609 | Story | Unclass GDS - NMS: Feature Demo ? System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #310611
310614 | #310609 | Story | Unclass GDS - NMS: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #310611
310611 | #310609 | Story | Unclass GDS - NMS: Feature Demo ? Customer Demo Event | Unassigned | Invalid | 0 | #310618
310588 | #310578 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #310580
310583 | #310578 | Story | Unclass GDS - Firewall/Switches/Routers: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #310580
310580 | #310578 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #310587
310542 | #310532 | Story | Unclass GDS Workstation: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #310534
310537 | #310532 | Story | Unclass GDS Workstation: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #310534
310534 | #310532 | Story | Unclass GDS Workstation: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #310541
310454 | #310443 | Story | Unclass GDS TACLANE: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #310449
310453 | #310443 | Story | Unclass GDS TACLANE: Feature Demo ? System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #310445
310449 | #310443 | Story | Unclass GDS TACLANE: IA Patching and STIGs | Unassigned | Invalid | 0 | #310446
310448 | #310443 | Story | Unclass GDS TACLANE: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #310445
310446 | #310443 | Story | Unclass GDS TACLANE: IA Posture Assessment | Unassigned | Invalid | 0 | #310445
310445 | #310443 | Story | Unclass GDS TACLANE: Feature Demo ? Customer Demo Event | Unassigned | Invalid | 0 | #310452
310444 | #310443 | Story | Unclass GDS TACLANE: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #310449 #310454
310309 | #310299 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #310301
310304 | #310299 | Story | Unclass GDS Load Balancer: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #310301
310301 | #310299 | Story | Unclass GDS Load Balancer: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #310308
310179 |  | Task | Reject: Obsolescence: Trade Study - Fault Management | Unassigned | Invalid
309992 | #309972 | Story | Unclass GDS: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #309988
309991 | #309972 | Story | Unclass GDS Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 13 | #309982
309990 | #309972 | Story | Unclass GDS: Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | New | 5 | #309982
309989 | #309972 | Story | Unclass GDS: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
309988 | #309972 | Story | Unclass GDS: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | New | 8 | #309975
309987 | #309972 | Story | Unclass GDS: Engineering IETM updates | Unassigned | Invalid | 0 | #309986
309986 | #309972 | Story | Unclass GDS:ILS IETM updates | Unassigned | New | 13 | #309982
309985 | #309972 | Story | Unclass GDS: Agile Team Test (Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #309982 #309991
309984 | #309972 | Story | Unclass GDS: Deployment Notes and Operator Impact Inputs | Unassigned | New | 3 | #309982
309983 | #309972 | Story | Unclass GDS: IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | New | 8 | #309982
309982 | #309972 | Story | Unclass GDS: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #309989 #309980
309981 | #309972 | Story | Unclass GDS: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #309992
309980 | #309972 | Story | Unclass GDS: Test Report, needed 30 days prior to FRCB. | Unassigned | New | 3
309979 | #309972 | Story | Unclass GDS: Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | New | 5 | #309982
309978 | #309972 | Story | Unclass GDS: System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | New | 5 | #309979
309977 | #309972 | Story | Unclass GDS: ILS Create red lines Hardware drawings submitted for IDP | Unassigned | New | 5 | #309974
309976 | #309972 | Story | Unclass GDS: ILS Define Power Consumption Changes for IDP | Unassigned | New | 5 | #309974
309975 | #309972 | Story | Unclass GDS: IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #309983
309974 | #309972 | Story | Unclass GDS: Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | New | 5 | #309982
309973 | #309972 | Story | Unclass GDS: ILS Considerations (non-IETM) | Unassigned | New | 5 | #309982
309919 |  | Story | ARSTRAT Proposed Changes to RF Alignment: Internal working group review (goals, analysis and changes trade space, feasibility and advantages) | Unassigned | Invalid | 0
309918 |  | Story | ARSTRAT Proposed Changes to RF Alignment: Internal working group review (goals, analysis and changes trade space, feasibility and advantages) | Unassigned | Invalid | 0
309722 | #309690 | Story | Feature 309690: Code Collaborator Review - Execute MUS Generated Set Geolocation Scan Table | Unassigned | Invalid | 0
309721 | #309690 | Story | Feature 309690: Code Collaborator Review - Generate Set Geolocation Scan Table | Unassigned | Invalid | 0
309720 | #309690 | Story | Feature 309690: Code Collaborator Review - Channelizer Configuration Application - Normal Procedure and Generate Channelizer Perform File - Normal Procedure | Unassigned | Invalid | 0
309714 | #309690 | Story | Feature 309690: Generate Set Geolocation Scan Table - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
309700 | #309690 | Story | Feature 309690: Feature Demo – System Test, STCD development and Demo Prep - Generate Set Geo Location Scan Table | Unassigned | Invalid | 0 | #309692
309698 | #309690 | Story | Feature 309690: ILS IETM updates | Unassigned | Invalid | 0 | #309692
309697 | #309690 | Story | Feature 309690: Execute MUS Generated Set Geolocation Scan Table - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #309700 #309692
309695 | #309690 | Story | Feature 309690: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #309692
309692 | #309690 | Story | Feature 309690: Feature Demo – Customer Demo Event - OOH Rev N IETM Changes | Unassigned | Invalid | 0 | #309699
309689 | #307985 | Story | Integrate AWARE with 8L: Burn In Test - Radio Support | Unassigned | Invalid | 0
309459 |  | Task | Mark OOP reminder: | Unassigned | Done
309180 | #309169 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #309175
309179 | #309169 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #309171
309178 | #309169 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
309177 | #309169 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #309171
309176 | #309169 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #309171 #309179
309175 | #309169 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #309172
309174 | #309169 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #309171
309173 | #309169 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #309177
309172 | #309169 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #309171
309171 | #309169 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #309178
309170 | #309169 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #309175 #309180
309169 |  | Feature | <Feature xxx> | Unassigned | Rejected
309107 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: SVD Update of Appendix M Support (INVALIDATED) | Unassigned | Invalid | 0
307992 | #307985 | Story | Integrate AWARE with 8L: Agile Testing | Unassigned | Invalid | 0
307991 | #307985 | Story | Integrate AWARE with 8L: IA Patching and STIGs | Unassigned | Invalid | 0 | #307988
306638 |  | Story | Feature 292824: IETM updates | Unassigned | Invalid | 0
306242 |  | Story | GD Support of Zeta - EAD-9 & FM Support: SA Integration Support-EAD9 testing(part 1) | Unassigned | Invalid | 0
306225 | #306214 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #306220
306224 | #306214 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #306216
306223 | #306214 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
306222 | #306214 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #306216
306221 | #306214 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #306216 #306224
306220 | #306214 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #306217
306219 | #306214 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #306216
306218 | #306214 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #306222
306217 | #306214 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #306216
306216 | #306214 | Story | Feature 306214: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #306223
306215 | #306214 | Story | Feature 306214: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #306220 #306225
306208 |  | Story | GD Support of Zeta - EAD 9/10: HBSS SVD - Update PCR & Start Code Review | Unassigned | Invalid | 0
306100 |  | Story | DT Assist 4 - GIS SME Support for DT Assist 4 Site Final Test Execution (Glen L) [7.4] | Unassigned | Invalid | 0
306085 |  | Story | 19-10 Proposal Support: AWARE (Section 2.6.1.3) - WH and SC Deployment | Unassigned | Invalid | 0
306083 |  | Story | 19-10 Proposal Support: BOE Support | Unassigned | Invalid | 0
306076 |  | Story | 19-10 Proposal Support: EMI (Section 2.3)- BOE Reviews | Unassigned | Invalid | 0
306070 |  | Story | Development: Add a periodic GMAP message to synchronize data | Unassigned | Invalid | 0
306050 |  | Story | 19-10 Proposal Support: EMI (Section 2.3)- BOE Reviews | Unassigned | Invalid | 0
306044 |  | Story | 19-10 Proposal Support: AMS-GS (Section 2.6.1.2) - Database Backup | Unassigned | Invalid | 0
306013 | #306009 | Story | Create IA Posture Assessment Template for Feature and Review with Cyber Team | Unassigned | Invalid | 0
306009 | #216717 | Feature | Implement KMS-RNC interface changes | Unassigned | Rejected
305904 | #297335 | Story | Feature 297335: RDE System Test in VLab of RAN RNC Build (New RDE Environment) | EA 15.1 | Done | 1
305764 | #243424 | Story | Prepare for & attend Group Data TEM | Unassigned | Invalid | 0
305635 | #216598 | Story | Update RNC-RCG Cover Request Failure Handling Design - WF-RAN | Unassigned | Invalid | 0
305634 |  | Task | Kent Tang OOP reminder: | Unassigned | In Development
305633 |  | Task | Dave Corcoran. OOP reminder: 11-27, 12-23, 12-24, 12-26 | Unassigned | In Development
305632 |  | Task | Randy Morton OOP reminder: | Unassigned | In Development
305629 | #305610 | Story | Update RCG Designated Peer Design - WF-RAN | Unassigned | Invalid | 0
305628 | #216637 | Story | Update RCG Key Sharing Triggers Design - WF-RAN | Unassigned | Invalid | 0
305623 |  | Task | Greg OOP reminder: 7/26-8/2 | Unassigned | Invalid
305622 |  | Task | Greg OOP reminder: 7/17-7/24 | PI 16 | New
305621 | #305610 | Story | Feature 305610: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #305616
305620 | #305610 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #305612
305619 | #305610 | Story | Feature 305610: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
305617 | #305610 | Story | Feature 305610 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #305612 #305620
305616 | #305610 | Story | Feature 305610: IA Patching and STIGs | Unassigned | Invalid | 0 | #305613
305615 | #305610 | Story | Feature 305610: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #305612
305614 | #305610 | Story | Feature 305610 Engineering IETM updates | Unassigned | Invalid | 0 | #305618
305613 | #305610 | Story | Feature 305610 IA Posture Assessment | Unassigned | Invalid | 0 | #305612
305612 | #305610 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #305619
305611 | #305610 | Story | Feature 305610: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #305621 #305616
305610 | #216635 | Feature | Improve RCG Designated Peer Selection | Unassigned | Rejected
305609 |  | Task | duplicate | Unassigned | Invalid
305607 |  | Task | Laptops dependents - | Unassigned | Invalid
305603 |  | Task | Jim OOP reminder: | Unassigned | New
305602 |  | Task | Steve OOP reminder: 5/23-5/31 | EA 15.4 | New
305601 |  | Task | Sally OOP reminder: 3/18-3/19 | EA 14.4 | Done
305454 |  | Story | DT Assist 4 - GIS SME Support for DT Assist 4 Site Dry Run (Glen L) [7.2] | Unassigned | Invalid | 0
305411 |  | Story | FY 19 proposals fact finding and proposal close out (Cyber RMF) | Unassigned | Invalid | 0
305410 |  | Story | 19-10 Proposal Support (Cyber RMF) - 7.2 | Unassigned | Invalid | 0
305406 |  | Story | Create/Update Recovery procedures based on design (2) | Unassigned | Invalid | 0
305387 | #251622 | Feature | Windows 10 LAPTOP for ARSTRAT | Unassigned | Rejected
305291 |  | Feature | SME support for CDR & DSN training preparation | Unassigned | Rejected
305214 |  | Story | Test Support for WF Maintenance and MIL STD Development (4) | Unassigned | Invalid | 0
305211 |  | Story | Test Support for WF Maintenance and MIL STD Development (1) | Unassigned | Invalid | 0
305210 |  | Story | Support WF Maintenance and MIL-STD Development (4) | Unassigned | Invalid | 0
305144 |  | Story | 00-P50231E System Drawing Tree – MUOS Ground System - Update for Workstation Expansion | Unassigned | Invalid | 0
305133 |  | Story | 63-P53199T MUOS GS Functional Block Diagram - Needs to be updated for Workstation Expansion | Unassigned | Invalid | 0
305015 | #293371 | Story | RDE BuildForge - Configure BuildForge Connectors for OSSRC Builds | EA 15.4 | Invalid | 0
304972 |  | Story | RTC feature intake | Unassigned | Invalid | 0
304971 |  | Story | Present completed Enterprise ACAS vulnerability management Capability Investigation to IA and System stakeholders and update per comments | Unassigned | Invalid | 0
304970 |  | Story | ROM estimate associated Enterprise ACAS vulnerability management complexity/cost/effort | Unassigned | Invalid | 0
304969 |  | Story | Document Enterprise ACAS vulnerability management security posture and recommended priority | Unassigned | Invalid | 0
304968 |  | Story | Update Enterprise ACAS vulnerability management functional architecture description for proposed architecture | Unassigned | Invalid | 0
304967 |  | Story | Present current MUOS Enterprise ACAS vulnerability management Security Functional architecture and gaps to IA and System stakeholders | Unassigned | Invalid | 0
304966 |  | Story | Perform gap analysis of current MUOS Enterprise ACAS vulnerability management security functional architecture | Unassigned | Invalid | 0
304965 |  | Story | Document current Enterprise ACAS vulnerability management functional architecture | Unassigned | Invalid | 0
304962 |  | Story | Document Enterprise ACAS vulnerability management security control mappings | Unassigned | Invalid | 0
304961 |  | Story | Document Enterprise ACAS vulnerability management capability findings/controls/measures | Unassigned | Invalid | 0
304956 | #396669 | Problem | 974240 / INC000003218093: WH - KMS GCK Rekey Failure - Unable to find Event ID RCG-0201 | EA 15.4 | Approved
304955 | #278834 | Story | FY 19 proposals fact finding and proposal close out (NMS) - 7.2 | Unassigned | Invalid | 0
304953 | #278834 | Story | FY 19 proposals fact finding and proposal close out (NMS) - 7.1 | Unassigned | Invalid | 0
304943 |  | Story | FY 19 proposals fact finding and proposal close out (HAIPE) - 7.2 | Unassigned | Invalid | 0
304932 |  | Task | FY 19 proposals fact finding and proposal close out (F5 Big-IP) 7.2 | Unassigned | Invalid
304931 |  | Task | FY 19 proposals fact finding and proposal close out (HAIPE) - 7.2 | Unassigned | Invalid
304912 |  | Story | Feature 305186: Evaluate AJM Chassis PN# 01-P53220E001, SN# EM201: Evaluate/Initial Troubleshooting | Unassigned | Invalid | 0
304911 |  | Story | Feature 305186: Evaluate AJM Chassis PN# 01-P53220E001, SN# 105: Evaluate/Initial Troubleshooting | Unassigned | Invalid | 0
304803 | #278834 | Task | FY 19 proposals fact finding and proposal close out (Cyber Sustainment) - 7.2 | Unassigned | Invalid
304782 |  | Task | INC000003218092: WH - IETM Update / INC000003218085: WH - RCGS3-AU-RAF - Invalid A7 Key | Unassigned | Done
304691 |  | Story | Place holder for Cyber work to include AWARE/AWARE radio in Ground ATO - 7.1 (INVALIDATED) | Unassigned | Invalid | 0
304209 |  | Story | RDE ClearCase - Identify Non-Build related CC VOBs | Unassigned | Invalid | 0
303938 | #303936 | Story | Convert the informal Analysis Engine Likelihood of Success (LoS) presentation into formal training materials.. | Unassigned | Invalid | 0
303937 | #303936 | Story | Support conversion of the informal Analysis Engine Likelihood of Success (LoS) presentation into formal training materials.. | Unassigned | Invalid | 0
303911 | #293371 | Story | OSSRC Build Testing | EA 15.5 | New | 5
303593 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
303420 | #296189 | Task | Richard P to add the story | Unassigned | Done
303372 | #293371 | Story | RDE ClearCase - Migrate ClearCase Data for OSSRC to RDE region | EA 15.3 | Invalid | 0
303355 |  | Feature | test | Unassigned | Rejected
303336 | #1001062 | Story | RDE ClearCase - Raise Feature Levels of previously identified RAN VOBs and Evaluate Update to Schema | EA 15.4 | Invalid | 0 | #287870
302854 | #293371 | Story | RDE BuildForge - Export BuildForge Projects for Product Build OSSRC | EA 15.2 | Done | 2
302848 | #293371 | Story | RDE BuildForge - Import BuildForge Projects into RDE (BuildForge & Target Product Build) - OSSRC | EA 15.5 | New | 3
302689 | #302643 | Story | Increase single threshold parameter to eight parameters (one per feederlink) | Unassigned | New | 8
302677 | #302663 | Story | Improve Cell Failure Identification in AWARE Waterfall Diagram (web) | Unassigned | Invalid | 0
302676 | #302663 | Story | Improve Cell Failure Identification in AWARE v1 Report | Unassigned | Invalid | 0
302674 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #302669
302673 | #302663 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #302665
302672 | #302663 | Story | Feature 302663: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
302671 | #302663 | Story | Feature 302663: IETM updates for Improvement of Cell Failure Identification in AWARE Report for I-Level (local to AWARE server, not SA dashboard) | Unassigned | Invalid | 0 | #302665
302670 | #302663 | Story | Feature 302663: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #302665 #302673
302669 | #302663 | Story | Feature 302663: IA Patching and STIGs | Unassigned | Invalid | 0 | #302666
302668 | #302663 | Story | Feature 302663: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #302665
302667 | #302663 | Story | Feature 302663: Engineering IETM updates | Unassigned | Invalid | 0 | #302671
302666 | #302663 | Story | Feature 302663: IA Posture Assessment | Unassigned | Invalid | 0 | #302665
302665 | #302663 | Story | Feature Demo – Customer Demo Event - Feature 302663 | Unassigned | Invalid | 0 | #302672
302664 | #302663 | Story | Feature 302663: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #302674 #302669
302654 | #302643 | Story | Feature 302643: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #302649
302653 | #302643 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #302645
302652 | #302643 | Story | <Feature 302643>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
302651 | #302643 | Story | <Feature 302643>:ILS IETM updates | Unassigned | Invalid | 0 | #302645
302650 | #302643 | Story | <Feature 302643> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 8 | #302645 #302653
302649 | #302643 | Story | <Feature 302643>: IA Patching and STIGs | Unassigned | New | 1 | #302646
302648 | #302643 | Story | <Feature 302643>: Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #302645
302647 | #302643 | Story | <Feature 302643> Engineering IETM updates | Unassigned | Invalid | 0 | #302651
302646 | #302643 | Story | Feature 302643: IA Posture Assessment | Unassigned | New | 3 | #302645
302645 | #302643 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #302652
302644 | #302643 | Story | <Feature 302643>: IA Posture Assessment - development input | Unassigned | New | 1 | #302654 #302649
302373 | #302184 | Story | Feature 302184: Prepare and Hold Feature Demo | Unassigned | New | 2
302371 | #302184 | Story | Feature 302184: Create STCD and review with Stakeholders | Unassigned | New | 2
302370 | #302184 | Story | Feature 302184: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
302369 | #302184 | Story | Feature 302184: Create IA Posture Assessment | Unassigned | New | 2
302368 | #302184 | Story | Feature 302184: Create IA Posture Template for Feature | Unassigned | New | 1
302366 | #302184 | Story | Feature 302184: Perform IA Scanning. STIGs, and Patching | Unassigned | New | 2
302360 | #302184 | Story | Feature 302184: Make IETM updates | Unassigned | New | 2
302358 | #302184 | Story | Feature 302184: ILS IETM updates | Unassigned | New | 2
302351 | #302184 | Story | Feature 302184: Support SIT Team with Feature Demo | Unassigned | New | 1
302350 | #302184 | Story | Feature 302184: Execute Required Scans and STIGs | Unassigned | New | 1
302349 | #302184 | Story | Feature 302184: Release Notes Inputs and Training Materials | Unassigned | New | 2
302258 |  | Story | Workstation EXP: updates to Site Drawings parts list | Unassigned | Invalid | 0
301958 |  | Story | Verify RAN IETM Updates (4 of 5) | Unassigned | Invalid | 0
301957 |  | Story | Implement RAN IETM Updates (4 of 5) | Unassigned | Invalid | 0
301956 |  | Story | Verify RAN IETM Updates (2 of 5) | Unassigned | Invalid | 0
301951 |  | Story | Implement RAN IETM Updates (2 of 5) EA 8.4 | Unassigned | Invalid | 0
301885 | #294836 | Story | KG175A Replacement: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB - part 1 | Unassigned | Invalid | 0 | #301872
301883 | #301869 | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #301879
301882 | #301869 | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #301879 #301888
301876 | #294836 | Story | KG175A Replacement: Complete System Operational Verification Test, SOVT (ICM Release by 12/16/2018) | Unassigned | Invalid | 0 | #301879
301872 | #301869 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #301880
301869 |  | Feature | Dummy Feature for Proposal HW/FRCB Deployable Feature | Unassigned | Rejected
301620 |  | Story | Lab - Provide Cross Training for SKL to Lab Support Team | Unassigned | Invalid | 0
301422 | #299984 | Story | Feature 299984: OSS-RC - Fix HSS and CSCF Alarms | PI 15 | Invalid | 0
301417 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #301412
301416 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #301408
301415 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
301414 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #301408
301413 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #301416 #301408
301412 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #301409
301411 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #301408
301410 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #301414
301409 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #301408
301408 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #301415
301407 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #301417 #301412
301252 | #296125 | Story | Scrub MUOSAT CRs and transition to RTC work items where applicable | Unassigned | Invalid | 0
301063 | #270631 | Story | Feature 270631: HBSS FM White Listing | Unassigned | New | 1
300921 | #239677 | Story | Feature 239677: KaDemod RF drawer: Engineering SME review for mechanical changes required to accommodate new part package size and related cables | Unassigned | Invalid | 0
300920 |  | Story | KG175A Replacement: Updated TCT Version Compatability | Unassigned | Invalid | 0
300919 |  | Story | Part 1 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
300912 | #294837 | Story | Feature 294837 KG175A: Drawings Support - Phase 2 (part 2) | Unassigned | Invalid | 0
300908 |  | Story | Part 1 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0
300906 | #294837 | Story | Feature 294837 KG175A: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #300901
300905 | #294837 | Story | Feature Demo - System Test, STCD development and Demo Prep - Feature 294837 KG175A: | Unassigned | Invalid | 0 | #300897
300904 | #294837 | Story | Feature 294837 KG175A: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
300903 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #300897
300902 | #294837 | Story | Feature 294837 KG175A: Part 2 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #300905 #300897
300901 | #294837 | Story | Feature 294837 KG175A: IA Patching and STIGs for GemX | Unassigned | Invalid | 0 | #300898
300900 | #294837 | Story | Feature 294837 KG175A: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #300897
300899 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #300903
300898 | #294837 | Story | Feature 294837 KG175A: IA Posture Assessment for GemX | Unassigned | Invalid | 0 | #300897
300897 | #294837 | Story | Feature Demo - Customer Demo Event - Feature 294837 KG175A | Unassigned | Invalid | 0 | #300904
300896 | #294837 | Story | Feature 294837 KG175A: IA Posture Assessment - development input for GemX | Unassigned | Invalid | 0 | #300906 #300901
300895 |  | Feature | <Feature xxx> | Unassigned | Rejected
300848 |  | Story | SI&T placeholder | Unassigned | Invalid | 0
300846 |  | Story | SI&T placeholder | Unassigned | Invalid | 0
300841 | #294837 | Story | Feature 294837 KG175A: TCT file dev Support - Phase 2 | Unassigned | Invalid | 0
300603 |  | Story | AMS-GS Training: Engineering SME support (ARSTRAT) | Unassigned | Invalid | 0
300573 | #306009 | Story | Feature 306009: Support and advise SME/cross training support | Unassigned | Invalid | 0
300508 |  | Story | Review all Targeted Test Procedures for O-Level | Unassigned | Invalid | 0
299995 | #299984 | Story | Feature 299984: IA Posture Assessment - review of developer input | PI 15 | Invalid | 0 | #299990
299990 | #299984 | Story | Feature 299984: IA Patching and STIGs | PI 15 | Invalid | 0 | #299987
299985 | #299984 | Story | Feature 299984: IA Posture Assessment - development input | PI 15 | Invalid | 0 | #299990 #299995
299304 |  | Story | FY19 Unclassified GDS proposal: Monthly Patching BOE estimates | Unassigned | Invalid | 0
299294 | #245566 | Task | NodeSynchTp_ThresholdExceeded - ADD | Unassigned | Done
299231 |  | Story | RDE CTX GUI needs repair (MUOSAT ClearQuest) | Unassigned | Invalid | 0
298966 |  | Story | GD Support of Zeta - EAD 8 Part 2: Feature Readiness Review-INVALIDATE | Unassigned | Invalid | 0
298964 |  | Story | Improve AWARE IA Posture for IATT: Feature Readiness Review-INVALIDATED | Unassigned | Invalid | 0
298738 |  | Story | Provide evaluation I-level AWARE SA dashboards | Unassigned | Invalid | 0
298733 |  | Story | Feature 244716 Standalone AWARE: Analysis of health/status detection based upon global test Group's CDR flows | Unassigned | Invalid | 0
298419 | #217023 | Feature | GD Support of Zeta - Provide high-fidelity recordings of MUOS channels in support of EMI investigations | Unassigned | Rejected
298418 | #258337 | Story | Update FM whitelist with critical alarms | Unassigned | New | 5
298417 | #258337 | Story | Integrate AMS-GS SNMP v3 with MIB with NetCool | Unassigned | New | 8
298414 |  | Story | EA 9.6 - Recommend Metrics Collection for Revised Metric Plan | Unassigned | Invalid | 0
298391 |  | Story | Call Bank Support Loretta (Sprint 6) | Unassigned | Invalid | 0
298347 |  | Story | Assist with development of procedure recommendation | Unassigned | Invalid | 0
298310 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - Feature 251537: Windows 10 Laptop | Unassigned | Invalid | 0
298045 |  | Story | Remove? | Unassigned | Invalid | 0
298044 |  | Story | Remove? | Unassigned | Invalid | 0
298043 |  | Story | Remove? | Unassigned | Invalid | 0
298041 |  | Story | Feature 298035: EA 9.6 Splunk Data Mining Execution | Unassigned | Invalid | 0
298039 |  | Story | Remove? | Unassigned | Invalid | 0
297977 | #297966 | Story | Satellite Power % Displayed Incorrectly: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #297972
297976 | #297966 | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 297966 | Unassigned | Invalid | 0 | #297968
297975 | #297966 | Story | Satellite Power % Displayed Incorrectly: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
297974 | #297966 | Story | Satellite Power % Displayed Incorrectly:ILS IETM updates | Unassigned | Invalid | 0 | #297968
297973 | #297966 | Story | Satellite Power % Displayed Incorrectly: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #297976 #297968
297972 | #297966 | Story | Satellite Power % Displayed Incorrectly: IA Patching and STIGs | Unassigned | Invalid | 0 | #297969
297971 | #297966 | Story | Satellite Power % Displayed Incorrectly: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #297968
297970 | #297966 | Story | Satellite Power % Displayed Incorrectly: Engineering IETM updates | Unassigned | Invalid | 0 | #297974
297969 | #297966 | Story | Satellite Power % Displayed Incorrectly: IA Posture Assessment | Unassigned | Invalid | 0 | #297968
297968 | #297966 | Story | Feature Demo – Customer Demo Event - Feature 297966 | Unassigned | Invalid | 0 | #297975
297967 | #297966 | Story | Satellite Power % Displayed Incorrectly: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #297972 #297977
297966 | #255693 | Feature | Satellite Power % Displayed Incorrectly on Apportionment Management Screen (TT INC000002899130) | Unassigned | Rejected
297693 | #294837 | Story | Feature 294837 KG175A: Drawings Support - Phase 2 (part 1) | Unassigned | Invalid | 0
297458 |  | Feature | Continue Data Mining Enablement in Splunk | Unassigned | Rejected
297450 | #294595 | Story | Investigate HMS Build Process - Part 1 | Unassigned | Invalid | 0
297339 |  | Story | SME Support for Quest Alarms | Unassigned | Invalid | 0
297335 | #243505 | Feature | RAN Dev Env (RDE) Transition to Production Part 2 | PI 16 - In Progress | Implementing
297177 | #293348 | Story | Address/Incorporate A205 comments received from LM/PMW and submit final package - UX | Unassigned | Invalid | 0
296942 | #287299 | Story | UX Support for LORA Summit | Unassigned | Invalid | 0
296930 |  | Story | AWARE Training: Release Notes Inputs | Unassigned | Invalid | 0
296923 |  | Story | SE Support | Unassigned | Invalid | 0
296922 |  | Story | Place holder for firewall impacts to support new load balancer monitors in story 296403 | Unassigned | Invalid | 0
296878 | #292824 | Story | TFDU Maintenance: Incorporate TFDU SVD Redline Updates from MPC | Unassigned | Invalid | 0
296871 | #292669 | Story | Develop Runtime Checks for TFDU Timing | Unassigned | Invalid | 0
296625 | #262146 | Story | Need SME to run xWFT tests on SN# 1000423 and SN# 1000686 | Unassigned | Invalid | 0
296592 | #244696 | Story | Feature 244696: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
296591 | #244696 | Story | Feature 244696: Prepare and Execute Feature Demo | Unassigned | Invalid | 0
296590 | #244696 | Story | Feature 244696: Create Release Notes and Knowledge Transfer Data for Feature | Unassigned | Invalid | 0
296588 | #244696 | Story | Feature 244696: Create IA Posture Assessment for Feature | Unassigned | Invalid | 0
296587 | #244696 | Story | Feature 244696: Execute final IA Scans and STIGs | Unassigned | Invalid | 0
296586 | #244696 | Story | Feature 244696: Install baseline in VLab, Execute STCD, Verify PCR | Unassigned | Invalid | 0
296585 | #244696 | Story | Feature 244696: Create STCD and review with stakeholders | Unassigned | Invalid | 0
296584 | #244696 | Story | Feature 244696: Create IA Posture Template for feature | Unassigned | Invalid | 0
296583 | #231643 | Story | Feature 231643: Prepare and Execute Feature Demo | Unassigned | Invalid | 0
296578 | #231643 | Story | Feature 231643: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
296577 | #231643 | Story | Feature 231643: ILS IETM Updates for Feature | Unassigned | Invalid | 0
296552 | #231643 | Story | Feature 231643: Create/Update IETMs for Feature | Unassigned | Invalid | 0
296541 | #296537 | Story | Feature 296537 - SCS Patch: Engineering IETM updates | Unassigned | Invalid | 0
296531 | #231643 | Story | Feature 231643: Create Release Notes and Knowledge Transfer Data for Feature | Unassigned | Invalid | 0
296528 | #231643 | Story | Feature 231643: Create IA Posture Assessment for Feature | Unassigned | Invalid | 0
296525 | #231643 | Story | Feature 231643: Execute final IA Scans and STIGs | Unassigned | Invalid | 0
296497 | #231643 | Story | Feature 231643: Install baseline in VLab, Execute STCD, Verify PCR | Unassigned | Invalid | 0
296483 | #231643 | Story | Feature 231643: Create STCD and review with stakeholders | Unassigned | Invalid | 0
296456 |  | Story | Feature 296452: Engineering IETM updates (WL Phase 4 Core/GIS alarms) | Unassigned | Invalid | 0
296403 |  | Story | Placeholder for new load balancer monitors | Unassigned | Invalid | 0
296374 | #293957 | Story | 293957 Identify Operations Procedures Needing Updates | Unassigned | Invalid | 0
296373 | #293957 | Story | 293957 Engineering IETM updates Part 3 | Unassigned | Invalid | 0
296371 | #293957 | Story | 293957 Engineering IETM updates Part 2 | Unassigned | Invalid | 0
296370 | #293957 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
296369 | #293957 | Story | 293957: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
296368 | #293957 | Story | 293957: ILS IETM updates | Unassigned | Invalid | 0
296334 |  | Story | Lab - Maintain Labs - V-Labs Network and Account Administrator - Allen (9.3) | Unassigned | Invalid | 0
296328 | #296248 | Story | Lab – Maintain Labs - Key management and maintenance - Maryam (9.4) | Unassigned | Invalid | 0
296251 | #296228 | Story | Investigate AWARE Traffic SA - A&A | Unassigned | Invalid | 0
296250 | #296228 | Story | Investigate AWARE Traffic SA - Systems | Unassigned | Invalid | 0
296247 | #296228 | Story | Investigate AWARE Traffic SA - SA Dashboards | Unassigned | Invalid | 0
296228 |  | Feature | Investigate AWARE Traffic SA Updates | Unassigned | Rejected
296220 | #264363 | Feature | Scrub existing remaining RAN related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296219 | #262146 | Feature | Prepare and Ship Spares to Support AMS-GS | Unassigned | Rejected
296217 | #264363 | Feature | Scrub existing remaining TOFF related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296213 | #264363 | Feature | Scrub existing remaining A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296211 | #264363 | Feature | Scrub existing remaining SA related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296206 | #268110 | Task | Need more information on Story 258296 prior to Sprint 6.4 planning | Unassigned | Invalid
296182 |  | Story | Update RAN Design Documentation | Unassigned | Invalid | 0
296148 |  | Story | IAVA intake and remediation planning: Estimate remediation effort impact | Unassigned | Invalid | 0
296135 | #264363 | Feature | Scrub existing IETM TOFF related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296134 | #264363 | Feature | Scrub existing IETM A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Rejected
296125 |  | Story | Support PMW Scrub of existing A&A related PCRs in Database and transition to RTC work items where applicable | Unassigned | Invalid | 0
295948 | #217023 | Feature | AMS-GS Phase 2 EAD-11 Deployment and On-Site Integration/Testing | Unassigned | Rejected
295529 | #295518 | Story | Feature 295518: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #295524
295528 | #295518 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #295520
295527 | #295518 | Story | Feature 295518: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
295525 | #295518 | Story | Feature 295518 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #295528 #295520
295524 | #295518 | Story | Feature 295518: IA Patching and STIGs | Unassigned | Invalid | 0 | #295521
295523 | #295518 | Story | Feature 295518: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #295520
295522 | #295518 | Story | Feature 295518 Engineering IETM updates | Unassigned | Invalid | 0 | #295526
295521 | #295518 | Story | Feature 295518 IA Posture Assessment | Unassigned | Invalid | 0 | #295520
295520 | #295518 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #295527
295519 | #295518 | Story | Feature 295518: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #295524 #295529
295463 | #278834 | Story | FY 19 proposals fact finding and proposal close out (ILS) - IETM | Unassigned | Invalid | 0
295456 |  | Story | 950730 INC000002801710: WH- NMF receiving "GTP on ggsn-nw due to PC_INDETERMINATE" on Netcool. | Unassigned | Invalid | 0
295439 |  | Feature | Drawing updates per MPC EAD4.14 | Unassigned | Rejected
295390 | #245566 | Task | SR 965874 - CSR-INC000003123556 for MUOS -NW- MAS-NW BAD CERTIFICATE - REMOVE | Unassigned | Done
295220 |  | Story | Provide AWARE O-Level IETMs: Incorporate comments from review - Part 1 | Unassigned | Invalid | 0
295196 |  | Story | IA Hardening - WannaCry-HLR: Non-Stop Development | Unassigned | Invalid | 0
295189 |  | Story | UNIX - Post Installation tasks associated with Unix servers | Unassigned | Invalid | 0
295096 | #295091 | Story | IAVA intake and remediation planning: Review remediation with System IPT | Unassigned | Invalid | 0
295095 |  | Story | IAVA intake and remediation planning: Estimate remediation effort impact | Unassigned | Invalid | 0
295087 | #295070 | Story | IAVA intake and remediation planning: Review remediation with System IPT | Unassigned | Invalid | 0
295085 |  | Story | IAVA intake and remediation planning: Estimate remediation effort impact | Unassigned | Invalid | 0
294987 | #294980 | Story | TR - Windows Obsolescence Trade Study Phase 3 - Cybersecurity support | Unassigned | Invalid | 0
294986 | #294977 | Story | TR - Windows Obsolescence Trade Study Phase 2 - Cybersecurity support | Unassigned | Invalid | 0
294984 | #241577 | Story | TR - Windows Obsolescence Trade Study Phase 1 - Cybersecurity support | Unassigned | Invalid | 0
294981 | #290868 | Story | SME Support for AWARE PI9 delta capability training | Unassigned | Invalid | 0
294980 | #245898 | Feature | Rejected: TR - Windows Obsolescence Trade Study Phase 3 | Unassigned | Rejected
294979 | #293780 | Story | Feature 293780: JDTA - Eng SME Participation in JDTA Review | Unassigned | Invalid | 0
294977 |  | Task | Rejected: Obsolescence - Windows Obsolescence Trade Study Phase 2 | Unassigned | New
294976 |  | Story | Provide AMS-GS EAD-11 delta capability training | Unassigned | Invalid | 0
294971 |  | Feature | TR - Windows; cybersecurity value/impact analysis, security requirements and architecture definition | Unassigned | Rejected |  | #296518
294970 | #265531 | Story | Add AAA accounts | Unassigned | New | 13
294969 | #265531 | Story | Update FM whitelist for COTS alarms | Unassigned | New | 5
294966 | #238135 | Story | Analyze adding AAA accounts | Unassigned | New | 5
294965 | #238135 | Story | Upgrade SSH to servers as required (assumes SHA2 is supported) | Unassigned | New | 2
294964 | #238135 | Story | Add FM Ping probe to AMS-GS NMF servers | Unassigned | New | 1
294959 |  | Story | Standalone AWARE - Test Groups and Test Call Scenarios: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #294954
294957 |  | Story | Standalone AWARE - Test Groups and Test Call Scenarios: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294956 | #244716 | Task | Standalone AWARE - Test Groups and Test Call Scenarios: AWARE: ILS IETM updates | Unassigned | Invalid |  | #294950
294954 |  | Story | Standalone AWARE - Test Groups and Test Call Scenarios: IA Patching and STIGs | Unassigned | Invalid | 0 | #294951
294952 |  | Story | Standalone AWARE - Test Groups and Test Call Scenarios: Engineering IETM updates | Unassigned | Invalid | 0 | #294956
294948 |  | Feature | <Feature xxx> | Unassigned | Rejected
294922 |  | Feature | TR - KG175A Replacement - I&T - Phase 2 | Unassigned | Rejected
294917 | #241304 | Feature | Obsolescence - KG175A Replacement - I&T - Phase 1 | Unassigned | Rejected |  | #294922
294861 | #294837 | Story | Feature 294837 KG175A: Development Support - Phase 2 | Unassigned | Invalid | 0
294844 |  | Feature | TR - KG175A Replacement - ILS Support - Phase 2 | Unassigned | Rejected
294840 |  | Feature | TR - KG175A Replacement - ILS Support - Phase 1 | Unassigned | Rejected |  | #294844
294837 | #241304 | Feature | Rejected: Ground Obsolescence - KG175A Replacement - Phase 2 | Unassigned | Rejected
294832 |  | Feature | TR - SME Support for KG175A Replacement | Unassigned | Rejected
294830 |  | Story | FY19 Unclassified GDS proposal: System BOE Estimates for FY18 Unclass GDS Proposal-INVALIDATED | Unassigned | Invalid | 0
294718 |  | Story | EA 9.4 Daily Ground Health Check Issues Reporting (Incident, PWI or Trouble Ticket) | Unassigned | Invalid | 0
294717 |  | Story | EA 9.3 Daily Ground Health Check Issues Reporting (Incident, PWI or Trouble Ticket) | Unassigned | Invalid | 0
294715 |  | Story | EA 9.1 Daily Ground Health Check Issues Reporting (Incident, PWI or Trouble Ticket) | Unassigned | Invalid | 0
294707 |  | Story | EA 9.4 Daily Trouble Ticket Prioritization | Unassigned | Invalid | 0
294694 | #293632 | Story | EA 8.3 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
294693 | #293632 | Story | EA 8.2 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
294588 | #262146 | Feature | EPIC 262146: Assess Training Needs, Coordinate, and Deliver Training (Non-AMSGS, Non-AWARE) | Unassigned | Rejected
294572 | #291129 | Story | Feature 291129 OSS-RC NetCool: NetCool Implementation, patching, and Agile Test | PI 14 | Invalid | 0
294563 | #245020 | Story | Feature 245020: ILS IETM updates | Unassigned | Invalid | 0
294562 | #245020 | Story | Feature 245020: Install baseline in VLab, Execute STCD, Verify PCR | Unassigned | Invalid | 0
294561 | #245020 | Story | Feature 245020: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294560 | #245020 | Story | Feature 245020: Create Release Notes and Knowledge Transfer data for Feature | Unassigned | Invalid | 0
294559 | #245020 | Story | Feature 245020: Create IA Posture Assessment for Feature | Unassigned | Invalid | 0
294558 | #245020 | Story | Feature 245020: Create IA Posture Template for Feature | Unassigned | Invalid | 0
294557 | #245020 | Story | Feature 245020: Create STCD and Review with Stakeholders | Unassigned | Invalid | 0
294556 | #245020 | Story | Feature 245020: Create STCD and Review with Stakeholders | Unassigned | Invalid | 0
294555 | #245020 | Story | Feature 245020: Feature Demo Prep and Customer Event | Unassigned | Invalid | 0
294554 | #228282 | Story | Feature 228282: Install baseline in VLab, Execute STCD, Verify PCR | Unassigned | Invalid | 0
294552 | #228282 | Story | Feature 228282: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294547 | #228282 | Story | Feature 228282: Create Release Notes and Knowledge Transfer data for Feature | Unassigned | Invalid | 0
294546 | #228282 | Story | Feature 228282: Create IA Posture Assessment for Feature | Unassigned | Invalid | 0
294545 | #228282 | Story | Feature 228282: Create IA Posture Template for Feature | Unassigned | Invalid | 0
294544 | #228282 | Story | Feature 228282: Create STCD and Review with Stakeholders | Unassigned | Invalid | 0
294543 | #228282 | Story | Feature 228282: Feature Demo Prep and Customer Event | Unassigned | Invalid | 0
294510 | #244686 | Story | Feature Demo Prep and Customer Event | Unassigned | Invalid | 0
294507 | #244686 | Story | Feature 244686: Feature Demo Prep and Feature Demo | Unassigned | Invalid | 0
294488 | #244686 | Story | Feature 244686: Create Release Notes and Training Materials (Netcool) | Unassigned | Invalid | 0
294487 | #244686 | Story | Feature 244686: Install SW Baseline, Execute STCD, and Verify PCR for CGNH module registration (NetCool) | Unassigned | Invalid | 0
294485 | #244686 | Story | Feature 244686: Create Netcool STCD and review with stakeholders | Unassigned | Invalid | 0
294483 | #244686 | Story | Feature 244686: RAN implementation of NetCool probe on Central MP | Unassigned | Invalid | 0
294481 | #244686 | Story | Feature 244686: NetCool implementation of NetCool probe on Central MP | Unassigned | Invalid | 0
294477 | #244686 | Story | Feature 244686: Create IA Posture Assessment Template for Module Provisioning feature and Review with Cyber Team (RAN and NetCool) | Unassigned | Invalid | 0
294476 | #244686 | Story | Feature 244686: Create Intgrated STCD and review with stakeholders | Unassigned | Invalid | 0
294470 | #244686 | Story | Feature 244686: Install SW Baseline, Execute STCD, and Verify PCR for CGNH module registration (Integrated RAN/NetCool) | Unassigned | Invalid | 0
294469 | #244686 | Story | Feature 244686: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294467 | #244686 | Story | Feature 244686: ILS IETM updates | Unassigned | Invalid | 0
294466 | #244686 | Story | Feature 244686: Create IA Posture Assessment | Unassigned | Invalid | 0
294465 | #244686 | Story | Feature 244686: Create Release Notes and Training Materials (RAN) | Unassigned | Invalid | 0
294434 | #294417 | Story | Feature 294417: Review and Verify A204 Conversion Package to HTML5 - Part 2 | Unassigned | Invalid | 0
294433 | #294417 | Story | Feature 294417: Review and Verify A204 Conversion Package to HTML5 - Part 1 | Unassigned | Invalid | 0
294382 | #294363 | Story | Featute 294363: Add Auto Alarm Clear Logic to Netcool rules file for UPS - Development | Unassigned | New | 13
294374 | #294363 | Story | Feature 294363: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #294369
294373 | #294363 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #294365
294372 | #294363 | Story | <Feature 294363>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
294371 | #294363 | Story | Feature 294363: IETM updates for (INC000002393226) Netcool update to autoclear UPS alarms per clear signals listed in IETM | Unassigned | New | 3 | #294365
294370 | #294363 | Story | <Feature 294363> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 5 | #294373 #294365
294369 | #294363 | Story | <Feature 294363>: IA Patching and STIGs | Unassigned | New | 1 | #294366
294368 | #294363 | Story | <Feature 294363>: Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #294365
294367 | #294363 | Story | <Feature 294363> Engineering IETM updates | Unassigned | New | 0 | #294371
294366 | #294363 | Story | Feature 294363: IA Posture Assessment | Unassigned | New | 2 | #294365
294365 | #294363 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #294372
294364 | #294363 | Story | <Feature 294363>: IA Posture Assessment - development input | Unassigned | New | 1 | #294374 #294369
294363 | #216351 | Feature | (INC000002393226) Netcool update to autoclear UPS alarms per clear signals listed in IETM | Unassigned | Approved
294359 | #274014 | Story | PDO Release IETM updates | Unassigned | Invalid | 0
294358 | #274014 | Story | Execute Feature demo prep and Feature Demo of IETM updates | Unassigned | Invalid | 0
294356 | #274014 | Story | Execute STCD for IETM Additions | Unassigned | Invalid | 0
294351 | #302184 | Story | Feature 302184: Install in VLab, Execute STCD, and Verify PCR | Unassigned | New | 3
294350 | #302184 | Story | Implement, Developer test and start review for solution for RANI Admin Account to Expires in 35 days if not used issue | Unassigned | New | 5
294349 |  | Story | Test IETM changes for RNC status after a board replacement procedure is performed | Unassigned | Invalid | 0
294348 |  | Story | Document in IETM changes for RNC status after a board replacement procedure is performed | Unassigned | Invalid | 0
294338 | #274014 | Story | Feature 274014 ILS IETM updates | Unassigned | Invalid | 0
294337 | #294333 | Story | ILS - IETM updates | Unassigned | Invalid | 0
294333 | #216364 | Feature | Add/update IETM alarm recovery procedures for alarms added to whitelist filter in PI-5 and PI-6 (part 2 of 2) | Unassigned | Rejected
294331 | #293348 | Story | Update A205 Package for all items identified as out of date during the A205 review Story 294316 | Unassigned | Invalid | 0
294309 | #272509 | Story | Complete Initial Assessment of PPA UI Cleanup Design | PI 16 | New | 2
294260 |  | Story | Feature 295100: Obsolescence - Create trade study for ET Dehydrator replacement: Create ILS portions of the ET dehydrator study | Unassigned | Invalid | 0
294221 | #216558 | Story | Implement Solution for Data Transferred Over Control TFCIs | Unassigned | Invalid | 0
294218 | #216558 | Story | Analyze Data Transferred Over Control TFCIs | Unassigned | Invalid | 0
294173 | #279306 | Story | Analyze and Design Solution for NPAP Radio Link Issue | Unassigned | Invalid | 0
294172 | #279306 | Story | Implement Solution for NPAP Radio Link Issue | Unassigned | Invalid | 0
294171 |  | Story | Analyze and Design Solution for NPAP Radio Link Issue | Unassigned | Invalid | 0
294170 | #279306 | Story | Feature Demo Prep and Customer event | Unassigned | Invalid | 0
294169 | #279306 | Story | Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294168 | #279306 | Story | Create IA Posture Assessment | Unassigned | Invalid | 0
294167 | #279306 | Story | Create Release Notes and Training Materials | Unassigned | Invalid | 0
294166 | #219764 | Story | Feature Demo Prep and Customer event | Unassigned | Invalid | 0
294165 | #219764 | Story | Create IA Posture Assessment Template for feature and Review with Cyber Team | Unassigned | Invalid | 0
294163 | #219764 | Story | Create STCD and review with stakeholders | Unassigned | Invalid | 0
294162 | #219764 | Story | Install, Execute STCD, and Verify PCR for Feature | Unassigned | Invalid | 0
294161 | #219764 | Story | Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
294160 | #219764 | Story | Create IA Posture Assessment | Unassigned | Invalid | 0
294159 | #219764 | Story | Create Release Notes and Training Materials | Unassigned | Invalid | 0
294155 | #291060 | Story | Create STCD for Feature | Unassigned | New | 2
294061 | #245566 | Feature | Implement alarm severity assignments based on service impact | Unassigned | Draft
293960 | #293957 | Story | 293957 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 1 | Unassigned | Invalid | 0
293959 | #293957 | Story | 293957: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0
293958 | #293957 | Story | 293957 Engineering IETM updates Part 1 | Unassigned | Invalid | 0
293957 |  | Feature | Improve RAN Operations Related IETMs Part 2 | Unassigned | Rejected
293955 | #293940 | Story | 293940 Identify Operations Procedures Needing Updates | Unassigned | Invalid | 0
293954 | #293940 | Story | 293940 Engineering IETM updates Part 3 | Unassigned | Invalid | 0
293953 | #293940 | Story | 293940 Engineering IETM updates Part 2 | Unassigned | Invalid | 0
293952 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) Part 2 | Unassigned | Invalid | 0
293951 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #293946
293950 | #293940 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #293942
293949 | #293940 | Story | 293940: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
293948 | #293940 | Story | 293940: ILS IETM updates | Unassigned | Invalid | 0 | #293942
293947 | #293940 | Story | 293940 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #293942 #293950
293946 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #293943
293945 | #293940 | Story | 293940: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #293942
293944 | #293940 | Story | 293940 Engineering IETM updates Part 1 | Unassigned | Invalid | 0 | #293948
293943 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #293942
293942 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #293949
293941 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #293951 #293946
293940 | #225733 | Feature | Improve RAN Operations Related IETMs Part 1 | Unassigned | Rejected
293920 |  | Task | EA 9.4 Refine Monthly Availability Metrics | Unassigned | Invalid
293916 |  | Task | EA 9.4 Monthly Availability Analysis | Unassigned | Invalid
293912 |  | Story | EA 9.4 - Recommend Metrics Collection for Revised Metric Plan | Unassigned | Invalid | 0
293907 |  | Story | EA 9.4 Weekly TOFF Data Consolidation | Unassigned | Invalid | 0
293900 |  | Task | EA 9.4 Monthly Availability Outcome Recommendation to (MUOS Team) to enhance existing operational process. | Unassigned | Invalid
293897 |  | Task | EA 9.4 Monthly Availability Outcome Recommendation (To Customer) for new business value item | Unassigned | Invalid
293894 |  | Story | EA 9.4 Capture Daily Call Bank Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
293892 |  | Story | EA 9.2 Capture Daily Call Bank Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
293889 |  | Story | EA 9.4 Capture Daily Ground Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
293888 |  | Story | EA 9.3 Capture Daily Ground Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
293885 |  | Story | EA 9.1 Capture Daily Ground Health Check Incidents for TOFF Metrics | Unassigned | Invalid | 0
293873 |  | Story | EA 9.4 Daily Ground Health Check | Unassigned | Invalid | 0
293863 | #229318 | Feature | Define alarm severity assignments based on service impact | Unassigned | Draft
293862 | #229318 | Feature | Define correlation rules & synthesized (virtual) alarms for redundant equipment | Unassigned | Draft
293739 | #293721 | Story | Auto - [Seq. 7] After the new ITLAB E2E server is operational, reconfigure the old server similarly as a backup server. | Unassigned | Invalid | 0
293738 | #293721 | Story | Auto - [Seq. 2] Install and configure the automation SQL database, web server and utilities on the new ITLAB Automation server | Unassigned | Invalid | 0
293721 | #262134 | Feature | Auto - Call – OTA Call Banks Virtual Machines to eliminate laptop platform issues, downtime and missing coverage | Unassigned | Rejected
293681 | #290622 | Story | Update NEDB to include all RGR Equipment | Unassigned | New | 5
293610 | #279283 | Story | Lab - TXO Ericcson - Create TXO process document | EA 14.5 | Done | 3
293466 | #293463 | Story | Feat 293463 IAVA Top 20: Update CCB slides with IAVA status | Unassigned | Invalid | 0
293465 | #293463 | Story | Feat 293463 IAVA Top 20: Estimate remediation effort impact for each IAVA | Unassigned | Invalid | 0
293464 | #293463 | Story | Feat 293463 IAVA Top 20: Review RAR/POA&M relative to "Top 20 IAVA List" | Unassigned | Invalid | 0
293463 | #245560 | Feature | Analyze “Top 20” IAVA List -PI 7.0 Snapshot | Unassigned | Rejected
293452 |  | Story | Support AWARE Phase 3 Proposal Effort - SE-INVALID | Unassigned | Invalid | 0
293450 |  | Problem | SBC drill down display and data defects | Unassigned | Assessing
293392 | #245573 | Feature | INC000002452979: WH - Provisioned P2P and P2N MDR Exceeded | Unassigned | Ready for PO Sync Approval
293371 | #243505 | Feature | RAN Dev Env (RDE) Network Upgrade of MUOS Tools - OSSRC migration | EA 15.5 | Implementing |  | #293375
293338 | #243505 | Feature | SWIT Dev Env (SDE) Create Developer WS VMs | EA 14.5 | Done
293249 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #293244
293247 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
293244 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #293241
293241 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #293240
293239 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #293244 #293249
293171 |  | Story | DT Assist 4 - Support (remote or on site) Final Test Execution and Data Collection at Wahiawa NMF [7.4-7.5] | Unassigned | Invalid | 0
293164 |  | Story | DT Assist 4 - Update Procedures Based on Dry Runs, Hold Final Review of Test Plan/Procedures (Scott, Rich) [7.3] | Unassigned | Invalid | 0
293160 | #276524 | Story | DT Assist 4 - Support (remote or on site) Dry Run Testing at Wahiawa NMF (Bill) | Unassigned | Invalid | 0
293136 | #216598 | Story | Feature Demo Prep and Customer event | Unassigned | Invalid | 0
293133 | #279306 | Story | Create IA Posture Assessment Template for Module Provisioning feature and Review with Cyber Team | Unassigned | Invalid | 0
293132 | #216598 | Story | Create STCD and review with stakeholders | Unassigned | Invalid | 0
293131 | #279306 | Story | Install, Execute STCD, and Verify PCR for Feature | Unassigned | Invalid | 0
293130 | #216598 | Story | Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
293128 | #216598 | Story | Create IA Posture Assessment | Unassigned | Invalid | 0
293127 | #216598 | Story | Create Release Notes and Training Materials | Unassigned | Invalid | 0
293070 |  | Story | Lab - Maintain Labs - NMS, Secure Servers outage debug, recovery and repair - Chris (8.1) | Unassigned | Invalid | 0
293044 | #243505 | Feature | Improve Automated Verification of Physical Hard Drives | Unassigned | Rejected
293022 |  | Story | Evaluate Method to Manage MHAL passwords | Unassigned | Invalid | 0
292936 |  | Story | BackUp - Configure Veritas Netbackup Policy for Disk Arrays | Unassigned | Invalid | 0
292874 | #292862 | Task | CM Release of 63-P53199T Functional Block Diagram | Unassigned | Done
292836 |  | Story | TFDU Maintenance: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #292831
292835 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - Feature 292824: TFDU Maintenance | Unassigned | Invalid | 0
292834 |  | Story | TFDU Maintenance: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
292831 | #292824 | Story | TFDU Maintenance: IA Patching and STIGs | Unassigned | Invalid | 0 | #292827
292825 | #292824 | Story | TFDU Maintenance: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #292831 #292836
292803 |  | Feature | (INC000002393226) Netcool update to autoclear UPS alarms per clear signals listed in IETM | Unassigned | Rejected
292760 |  | Story | System Test - verification of whitelisted alarm recovery procedures (5 of 5) | Unassigned | Invalid | 0
292759 | #294333 | Story | System Test - verification of whitelisted alarm recovery procedures (2 of 2) | Unassigned | Invalid | 0
292758 | #294333 | Story | System Test - verification of whitelisted alarm recovery procedures (1 of 2) | Unassigned | Invalid | 0
292757 | #274014 | Story | System Test - verification of whitelisted alarm recovery procedures (2 of 2) | Unassigned | Invalid | 0
292756 | #274014 | Story | System Test - verification of whitelisted alarm recovery procedures (1 of 2) | Unassigned | Invalid | 0
292742 |  | Story | P7 WL addition: placeholder for TBD procedures | Unassigned | Invalid | 0
292727 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: IA Posture Assessment - review of developer input-INVALIDATED | Unassigned | Invalid | 0
292724 | #292716 | Story | Standalone AWARE IA Posture Improvement in Support of ATO: ILS IETM updates | Unassigned | Invalid | 0 | #292718
292723 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #292718 #292726
292720 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: Engineering IETM updates | Unassigned | Invalid | 0 | #292724
292719 |  | Story | Standalone AWARE IA Posture Improvement in Support of ATO: IA Posture Assessment | Unassigned | Invalid | 0
292680 | #292669 | Story | Feature 292669: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #292675
292679 | #292669 | Story | Feature 292669: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #292671
292677 | #292669 | Story | Feature 292669: ILS IETM updates | Unassigned | Invalid | 0 | #292671
292672 | #292669 | Story | Feature 292669: IA Posture Assessment | Unassigned | Invalid | 0 | #292671
292671 | #292669 | Story | Feature 292669: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #292678
292652 | #294333 | Story | P6 WL addition: RCG "periodic timer has expired <nnnnnn> not in memory" (RCG_00622) | Unassigned | Invalid | 0
292648 | #274014 | Story | P6 WL addition: RNC "FACH/RACH/PACH/UtranCell_InternalResourceUnavailable" (no meaningful event ID) | Unassigned | Invalid | 0
292646 | #274014 | Story | P6 WL addition: RNC "Loss of Signal" (no meaningful event ID) | Unassigned | Invalid | 0
292644 | #274014 | Story | P6 WL addition: GGSN "MASTER on ggsn" (no meaningful event ID) | Unassigned | Invalid | 0
292642 | #294333 | Story | P6 WL addition: TFDU "$STAT,GTF<1¦2>,GPS Receiver Comm Fault" (no meaningful event ID) | Unassigned | Invalid | 0
292640 | #274014 | Story | P5 WL addition: Quest door alarms (no meaningful event ID) | Unassigned | Invalid | 0
292639 | #294333 | Story | P5 WL addition: RNC "SCCP Remote Subsystem Unavailable" (no event ID) | Unassigned | Invalid | 0
292638 | #294333 | Story | P5 WL addition: RNC "MTP3b Link Out of Service" (no event ID) | Unassigned | Invalid | 0
292637 | #294333 | Story | P5 WL addition: RNC "MTP3 Route Set Unavailable" (no event ID) | Unassigned | Invalid | 0
292636 | #274014 | Story | P5 WL addition: RNC "SPM General Problem" (no event ID) | Unassigned | Invalid | 0
292634 | #294333 | Story | P5 WL addition: FCAP101/2 (NMA) "Process Abnormal Termination. Invalid SFRE data received on command line." (SGI_3001) | Unassigned | Invalid | 0
292633 | #294333 | Story | P5 WL addition: RCG platform "cpqHe4FltTolPowerSupplyFailed" (no meaningful event ID) | Unassigned | Invalid | 0
292631 | #245566 | Task | FRB 2018-06 TFDU HW Alarms to Whitelist - ADD | Unassigned | Done
292630 | #274014 | Story | P4 WL addition: Extreme Switch "extremeFanfailed" (no meaningful event ID) | Unassigned | Invalid | 0
292629 | #294333 | Story | P4 WL addition: RNC "UtranCell_NbapMessageFailure" (no event ID) | Unassigned | Invalid | 0
292628 | #274014 | Story | P4 WL addition: RNC "Processor Fault" (no event ID) | Unassigned | Invalid | 0
292626 | #274014 | Story | P4 WL addition: RNC "CchFrameSynch_TimingAdjCtrlFrame" (no event ID) | Unassigned | Invalid | 0
292622 | #274014 | Story | P4 WL addition: RBS "SwitchInternalLink_LinkFault" (no event ID) | Unassigned | Invalid | 0
292621 | #274014 | Story | P4 WL addition: RBS "Processor Fault" (no event ID) | Unassigned | Invalid | 0
292619 | #294333 | Story | P4 WL addition: Provisioning Bridge "bad response code was received while executing a command" (PRVB0111) | Unassigned | Invalid | 0
292617 | #294333 | Story | P4 WL addition: Provisioning Bridge "P2P message could not be rolled back" (PRVB0050) | Unassigned | Invalid | 0
292600 |  | Feature | SR 939279 - INC000002431137: WH- Requesting GD to investigate on the Custom and COTS alarm documents, EVENT ID 6033. | Unassigned | Rejected
292599 | #292588 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #292594
292598 | #292588 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #292590
292597 | #292588 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
292596 | #292588 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #292590
292595 | #292588 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #292598 #292590
292594 | #292588 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #292591
292593 | #292588 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #292590
292592 | #292588 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #292596
292591 | #292588 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #292590
292590 | #292588 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #292597
292589 | #292588 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #292594 #292599
292588 |  | Feature | <Feature xxx> | Unassigned | Rejected
292583 | #280549 | Story | System Test - verification of Quest alarms (2 of 2) | PI 16 | Invalid | 0
292582 | #280549 | Story | System Test - verification of Quest alarms (1 of 2) | PI 16 | Invalid | 0
292572 | #275827 | Story | Feature 275827: System Test - verification of RCG alarms (3 of 3) | Unassigned | Invalid | 0
292570 | #275827 | Story | Feature 275827: System Test - verification of RCG alarms (2 of 3) | Unassigned | Invalid | 0
292568 | #275827 | Story | Feature 275827: System Test - verification of RCG alarms (1 of 3) | Unassigned | Invalid | 0
292565 | #275827 | Story | Feature 275827: RCG Engineering IETM updates (3 of 3) | Unassigned | Invalid | 0
292563 | #275827 | Story | Feature 275827: RCG Engineering IETM updates (2 of 3) | Unassigned | Invalid | 0
292528 |  | Story | System Test - verification of RCG alarms (3 of 3) | Unassigned | Invalid | 0
292527 |  | Story | System Test - verification of RCG alarms (2 of 3) | Unassigned | Invalid | 0
292525 |  | Story | System Test - verification of RCG alarms (1 of 3) | Unassigned | Invalid | 0
292493 |  | Story | System Test - verification of RBS alarms (5 of 5) | Unassigned | Invalid | 0
292484 |  | Story | IETM updates (1 of 5) | Unassigned | Invalid | 0
292480 |  | Story | RBS Engineering IETM updates (5 of 5) | Unassigned | Invalid | 0
292345 | #245437 | Story | Prioritize fixes to Splunk dashboards & infrastructure for OTRR/EAD11 | Unassigned | Invalid | 0
292344 |  | Feature | Prioritize outstanding known problems & determine which to fix for EAD11 | Unassigned | Rejected
292343 |  | Story | System Test - verification of RBS alarms (5 of 5) | Unassigned | Invalid | 0
292333 |  | Story | System Test - verification of SGSN alarms (2 of 2) | Unassigned | Invalid | 0
292329 |  | Story | System Test - verification of RBS alarms (3 of 3) | Unassigned | Invalid | 0
292321 | #238135 | Story | Feature 238135 AMS-GS Phase 2: IA Posture Assessment - review of developer input | Unassigned | New | 2 | #292316
292320 | #238135 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #292312
292319 | #238135 | Story | Feature 238135: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
292317 | #238135 | Story | Feature 238135: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 8 | #292320 #292312
292316 | #238135 | Story | Feature 238135 AMS-GS Phase 2: IA Patching and STIGs | Unassigned | New | 5 | #292313
292315 | #238135 | Story | Feature 238135: Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #292312
292314 | #238135 | Story | Feature 238135: Engineering IETM updates | Unassigned | New | 2 | #292318
292313 | #238135 | Story | Feature 238135 AMS-GS Phase 2: IA Posture Assessment | Unassigned | New | 5 | #292312
292312 | #238135 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #292319
292311 | #238135 | Story | Feature 238135 AMS-GS Phase 2: IA Posture Assessment - development input | Unassigned | New | 2 | #292321 #292316
292310 |  | Feature | <Feature xxx> | Unassigned | Rejected
292152 | #292133 | Story | Assess & provide feedback on ARSTRAT developed dashboards - SE | Unassigned | Invalid | 0
292143 |  | Task | Create Knowledge Management Plan | Unassigned | Invalid
292140 | #292132 | Story | Feature 292132: Assess & provide feedback on ARSTRAT developed dashboards - UX | Unassigned | Invalid | 0
292131 |  | Task | Create Knowledge Management Plan-INVALIDATED | Unassigned | Invalid
292019 | #216598 | Story | Define RCG-RNC Cover Request Failure Handling Changes | Unassigned | Invalid | 0
291998 | #244705 | Story | Define RNC Health Check Alarm/Event Changes | Unassigned | Invalid | 0
291869 | #284459 | Story | Create new batch of Lab PKI | Unassigned | Invalid | 0
291784 |  | Story | GD Support of Zeta - EAD 9/10: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0
291779 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0
291775 |  | Story | GD Support of Zeta - EAD 9/10: IA Posture Assessment | Unassigned | Invalid | 0
291773 |  | Story | GD Support of Zeta - EAD-9 & FM Support: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #291779
291772 |  | Feature | <Feature xxx> | Unassigned | Rejected
291682 | #291671 | Story | AMS-GS Correlate Geolocation outage history: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #291677
291681 | #291671 | Story | Feature Demo – System Test, STCD development and Demo Prep - AMS-GS Correlate Geolocation outage history | Unassigned | New | 5 | #291673
291680 | #291671 | Story | AMS-GS Correlate Geolocation outage history: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
291679 | #291671 | Story | AMS-GS Correlate Geolocation outage history: ILS IETM updates | Unassigned | New | 3 | #291673
291678 | #291671 | Story | AMS-GS Correlate Geolocation outage history Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 5 | #291681 #291673
291677 | #291671 | Story | AMS-GS Correlate Geolocation outage history: IA Patching and STIGs | Unassigned | New | 1 | #291674
291676 | #291671 | Story | AMS-GS Correlate Geolocation outage history: Deployment Notes and Operator Impact Inputs | Unassigned | New | 1 | #291673
291675 | #291671 | Story | AMS-GS Correlate Geolocation outage history: Engineering IETM updates | Unassigned | New | 1 | #291679
291674 | #291671 | Story | AMS-GS Correlate Geolocation outage history: IA Posture Assessment | Unassigned | New | 3 | #291673
291673 | #291671 | Story | Feature Demo – Customer Demo Event - AMS-GS Correlate Geolocation outage history | Unassigned | New | 1 | #291680
291672 | #291671 | Story | AMS-GS Correlate Geolocation outage history: IA Posture Assessment - development input | Unassigned | New | 1 | #291682 #291677
291553 |  | Story | xxx | Unassigned | Invalid | 0
291546 |  | Story | AWARE system integration & test of scheduler & archiver | Unassigned | Invalid | 0
291476 |  | Story | Complete Enhancement 291123 - Ready for 6.3 | Unassigned | Invalid | 0
291334 |  | Story | Design WCDMA performance/status across a region - UX placeholder | Unassigned | Invalid | 0
291315 | #245437 | Feature | Design WCDMA performance/status across a region | Unassigned | Rejected
291140 | #291129 | Story | Feature 291129 OSS-RC NetCool: IA Posture Assessment - review of developer input | PI 14 | Invalid | 0 | #291135
291139 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291131
291138 | #291129 | Story | Feature 291129 OSS-RC NetCool: Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
291137 | #291129 | Story | Feature 291129 OSS-RC NetCool: ILS IETM updates | Unassigned | Invalid | 0 | #291131
291136 | #291129 | Story | Feature 291129 OSS-RC NetCool: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | PI 14 | Invalid | 0 | #291139 #291131
291135 | #291129 | Story | Feature 291129 OSS-RC NetCool: IA Patching and STIGs | Unassigned | Invalid | 0 | #291132
291134 | #291129 | Story | Feature 291129 OSS-RC NetCool: Deployment Notes and Operator Impact Inputs | PI 14 | Invalid | 0 | #291131
291133 | #291129 | Story | Feature 291129 OSS-RC NetCool: Engineering IETM updates | Unassigned | Invalid | 0 | #291137
291132 | #291129 | Story | Feature 291129 OSS-RC NetCool: IA Posture Assessment | PI 14 | Invalid | 0 | #291131
291131 | #291129 | Story | Feature Demo - Customer Demo Event - Feature 291129 OSS-RC NetCool | PI 14 | Invalid | 0 | #291138
291130 | #291129 | Story | Feature 291129 OSS-RC NetCool: IA Posture Assessment - development input | PI 14 | Invalid | 0 | #291140 #291135
291122 | #291111 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #291117
291121 | #291111 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291113
291120 | #291111 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
291119 | #291111 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #291113
291118 | #291111 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #291113 #291121
291117 | #291111 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #291114
291116 | #291111 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #291113
291115 | #291111 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #291119
291114 | #291111 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #291113
291113 | #291111 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #291120
291112 | #291111 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #291117 #291122
291111 |  | Feature | Implement changes for Module rejection of Group Provisioning | Unassigned | Rejected
291108 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291100
291092 | #291084 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #291086
291087 | #306009 | Story | Feature 291084: IA Posture Assessment | Unassigned | Invalid | 0 | #291086
291084 |  | Feature | Implement KMS-RNC interface changes (KMS side) | Unassigned | Rejected
291071 | #291060 | Story | Feature 291060: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #291066
291070 | #291060 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #291062
291069 | #291060 | Story | Feature 291060: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
291068 | #291060 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #291062
291067 | #291060 | Story | Feature 291060 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 5 | #291062 #291070
291066 | #291060 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #291063
291065 | #291060 | Story | Feature 291060: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #291062
291064 | #291060 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #291068
291063 | #291060 | Story | Feature 291060 IA Posture Assessment | Unassigned | New | 2 | #291062
291062 | #291060 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #291069
291061 | #291060 | Story | Feature 291060: IA Posture Assessment - development input | Unassigned | New | 1 | #291071 #291066
291059 | #291048 | Story | Feature 291048: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #291054
291058 | #291048 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291050
291057 | #291048 | Story | Feature 291048: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
291055 | #291048 | Story | Feature 291048 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #291058 #291050
291054 | #291048 | Story | Feature 291048: IA Patching and STIGs | Unassigned | Invalid | 0 | #291051
291053 | #291048 | Story | Feature 291048: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #291050
291052 | #291048 | Story | Feature 291048 Engineering IETM updates | Unassigned | Invalid | 0 | #291056
291051 | #291048 | Story | Feature 291048 IA Posture Assessment | Unassigned | Invalid | 0 | #291050
291050 | #291048 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #291057
291049 | #291048 | Story | Feature 291048: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #291059 #291054
291048 |  | Feature | Implement RNC Support of MAMA2 Message | Unassigned | Rejected
291041 |  | Story | <Feature yyy>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #291037
291040 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291031
291039 |  | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #291031
291038 |  | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
291037 |  | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #291024
291036 |  | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #291035
291035 |  | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #291031
291034 |  | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #291031 #291040
291033 |  | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #291031
291032 |  | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #291031
291031 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #291038 #291029
291030 |  | Story | <Feature yyy>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #291041
291029 |  | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
291028 |  | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #291031
291027 |  | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #291028
291026 |  | Story | <Feature yyy> ILS Create red lines Hardware drawings submitted for IDP | Unassigned | Invalid | 0 | #291023
291025 |  | Story | <Feature yyy> ILS Define Power Consumption Changes for IDP | Unassigned | Invalid | 0 | #291023
291024 |  | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #291032
291023 |  | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #291031
291022 |  | Story | <Feature yyy>: ILS Considerations (non-IETM) | Unassigned | Invalid | 0 | #291031
291019 | #291008 | Story | Feature 291008: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #291014
291018 | #291008 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #291010
291017 | #291008 | Story | Feature 291008: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
291015 | #291008 | Story | Feature 291008 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #291010 #291018
291014 | #291008 | Story | Feature 291008: IA Patching and STIGs | Unassigned | Invalid | 0 | #291011
291013 | #291008 | Story | Feature 291008: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #291010
291012 | #291008 | Story | Feature 291008 Engineering IETM updates | Unassigned | Invalid | 0 | #291016
291011 | #291008 | Story | Feature 291008 IA Posture Assessment | Unassigned | Invalid | 0 | #291010
291010 | #291008 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #291017
291009 | #291008 | Story | Feature 291008: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #291014 #291019
291008 | #225729 | Feature | Implement Extracting Alarm Condition via Log Parsing | Unassigned | Analyzing
291006 | #290995 | Story | Feature 290995: IA Posture Assessment - review of developer input | PI 15 | Invalid | 0 | #291001
291005 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
291004 | #290995 | Story | Feature 290995: Initiate CM PDO Processing for all CI's | PI 15 | Invalid | 0
291003 | #290995 | Story | Feature 290995: IETM Updates for RCG Logging Changes | PI 15 | Invalid | 0 | #290997
291002 | #290995 | Story | Feature 290995 Load in lab, Execute STCD, and Verify Feature | PI 15 | Invalid | 0 | #290997
291001 | #290995 | Story | Feature 290995: IA Patching and STIGs | PI 15 | Invalid | 0 | #290998
291000 | #290995 | Story | Feature 290995: Deployment Notes and Operator Impact Inputs | PI 15 | Invalid | 0 | #290997
290999 | #290995 | Story | Feature 290995 Engineering IETM updates | PI 15 | Invalid | 0 | #291003
290998 | #290995 | Story | Feature 290995 IA Posture Assessment | PI 15 | Invalid | 0 | #290997
290997 | #290995 | Story | Feature Demo – Customer Demo Event | PI 15 | Invalid | 0 | #291004
290996 | #290995 | Story | Feature 290995: IA Posture Assessment - development input | PI 15 | Invalid | 0 | #291001 #291006
290995 |  | Feature | Implement RCG Logging Changes | PI 15 | Rejected
290994 | #290983 | Story | Feature 290983: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #290989
290993 | #290983 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #290985
290992 | #290983 | Story | <Feature 290983>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
290990 | #290983 | Story | <Feature 290983> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #290985 #290993
290989 | #290983 | Story | Feature 290983: IA Patching and STIGs | Unassigned | New | 8 | #290986
290988 | #290983 | Story | <Feature 290983>: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #290985
290987 | #290983 | Story | <Feature 290983> Engineering IETM updates | Unassigned | New | 3 | #290991
290986 | #290983 | Story | Feature 290983: IA Posture Assessment | Unassigned | New | 8 | #290985
290985 | #290983 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #290992
290984 | #290983 | Story | Feature 290983: IA Posture Assessment - development input | Unassigned | New | 2 | #290994 #290989
290981 | #290970 | Story | Feature 290970: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290976
290980 | #290970 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290972
290979 | #290970 | Story | <Feature 290970>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290977 | #290970 | Story | <Feature 290970> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290980 #290972
290976 | #290970 | Story | <Feature 290970>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290973
290975 | #290970 | Story | <Feature 290970>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290972
290974 | #290970 | Story | <Feature 290970> Engineering IETM updates | Unassigned | Invalid | 0 | #290978
290973 | #290970 | Story | Feature 290970: IA Posture Assessment | Unassigned | Invalid | 0 | #290972
290972 | #290970 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290979
290971 | #290970 | Story | <Feature 290970>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290976 #290981
290970 | #225729 | Feature | Investigate RNC tracing/logging improvements | Unassigned | Rejected
290968 | #225729 | Feature | Investigate Extracting Alarm Condition via Log Parsing | Unassigned | Rejected |  | #291008
290964 |  | Task | CM Release of MUOS_IG_GS_SCS_SVD_98-P61749A (Black Workstation) for EAR N (EAD N Candidate) | Unassigned | Invalid
290963 |  | Task | CM Release of MUOS_IG_GS_SCS_OA_SVD_98-P59291M for EAR N (EAD N Candidate) | Unassigned | Invalid
290957 |  | Feature | Analyze changes to RCG logging | PI 15 | Rejected |  | #290995
290953 | #290942 | Story | Feature 290942: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290948
290952 | #290942 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290944
290951 | #290942 | Story | <Feature 290942>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290949 | #290942 | Story | <Feature 290942> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290944 #290952
290948 | #290942 | Story | <Feature 290942>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290945
290947 | #290942 | Story | <Feature 290942>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290944
290946 | #290942 | Story | <Feature 290942> Engineering IETM updates | Unassigned | Invalid | 0 | #290950
290945 | #290942 | Story | Feature 290942: IA Posture Assessment | Unassigned | Invalid | 0 | #290944
290944 | #290942 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290951
290943 | #290942 | Story | <Feature 290942>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290948 #290953
290942 | #225731 | Feature | Implement CDR additions and updates | Unassigned | Rejected
290940 | #290929 | Story | Feature 290929: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #290935
290939 | #290929 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #290931
290938 | #290929 | Story | <Feature 290929>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
290936 | #290929 | Story | <Feature 290929> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #290939 #290931
290935 | #290929 | Story | <Feature 290929>: IA Patching and STIGs | Unassigned | New | 8 | #290932
290934 | #290929 | Story | <Feature 290929>: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #290931
290933 | #290929 | Story | <Feature 290929> Engineering IETM updates | Unassigned | New | 3 | #290937
290932 | #290929 | Story | Feature 290929: IA Posture Assessment | Unassigned | New | 8 | #290931
290931 | #290929 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #290938
290930 | #290929 | Story | <Feature 290929>: IA Posture Assessment - development input | Unassigned | New | 2 | #290935 #290940
290929 | #225731 | Feature | Implement changes to P2P CIT CDR generation | Unassigned | Approved
290928 | #290917 | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290923
290927 | #290917 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290919
290926 | #290917 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290925 | #290917 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290919
290924 | #290917 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290927 #290919
290923 | #290917 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290920
290922 | #290917 | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290919
290921 | #290917 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290925
290920 | #290917 | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290919
290919 | #290917 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290926
290918 | #290917 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290928 #290923
290917 | #225731 | Feature | Implement support for generic CDR format | Unassigned | Rejected
290904 | #290893 | Story | <Feature 290893>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290899
290903 | #290893 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290895
290902 | #290893 | Story | Feature 280893: Initiate CM PDO Processing for all CI's for AWARE PI10 delta capability training | Unassigned | Invalid | 0
290901 | #290893 | Story | Feature 290893: IETM updates for AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290895
290900 | #290893 | Story | Feature 290893: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) for Development of the AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290895 #290903
290899 | #290893 | Story | Feature 290893: IA Patching and STIGs for AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290896
290898 | #290893 | Story | Feature 290893: Deployment Notes and Operator Impact Inputs for AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290895
290897 | #290893 | Story | Feature 290893: Engineering IETM updates for AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290901
290896 | #290893 | Story | <Feature 290893> IA Posture Assessment | Unassigned | Invalid | 0 | #290895
290895 | #290893 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290902
290894 | #290893 | Story | Feature 290893: IA Posture Assessment - development input for AWARE PI10 delta capability training | Unassigned | Invalid | 0 | #290904 #290899
290893 | #242141 | Feature | Develop AWARE PI10 delta capability training | Unassigned | Rejected
290885 | #290880 | Story | Feature 290880: Deployment Notes and Operator Impact Inputs for AWARE PI12 delta capability training | Unassigned | Invalid | 0 | #290882
290879 |  | Story | Feature 290868: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290874
290878 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290870
290877 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290876 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290870
290875 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290878 #290870
290874 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290871
290873 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290870
290872 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290876
290871 |  | Story | Featue 290868: IA Posture Assessment | Unassigned | Invalid | 0 | #290870
290870 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290877
290869 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290879 #290874
290867 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290862
290866 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290858
290865 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290864 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290858
290863 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290866 #290858
290862 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290859
290861 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290858
290860 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290864
290859 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290858
290858 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290865
290857 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290862 #290867
290853 | #290842 | Story | <Feature 290842>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290848
290852 | #290842 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290844
290851 | #290842 | Story | Feature 290842: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290850 | #290842 | Story | Feature 290842: IETM updates for AMS-GS PI10 delta capability training | Unassigned | Invalid | 0 | #290844
290849 | #290842 | Story | Feature 290842: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290844 #290852
290848 | #290842 | Story | Feature 290842: IA Patching and STIGs for AMS-GS PI10 delta capability training | Unassigned | Invalid | 0 | #290845
290847 | #290842 | Story | Feature 290842: Deployment Notes and Operator Impact Inputs for AMS-GS PI10 delta capability training | Unassigned | Invalid | 0 | #290844
290846 | #290842 | Story | Feature 290842: Engineering IETM updates for AMS-GS PI10 delta capability training | Unassigned | Invalid | 0 | #290850
290845 | #290842 | Story | <Feature 290842> IA Posture Assessment | Unassigned | Invalid | 0 | #290844
290844 | #290842 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290851
290843 | #290842 | Story | Feature 290842: IA Posture Assessment - development input for AMS-GS PI10 delta capability training | Unassigned | Invalid | 0 | #290848 #290853
290842 |  | Feature | Develop AMS-GS PI10 delta capability training | Unassigned | Rejected
290841 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290836
290840 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290832
290839 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290838 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290832
290837 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290832 #290840
290836 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290833
290835 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290832
290834 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290838
290833 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290832
290832 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290839
290831 | #290830 | Story | SME Support | Unassigned | Invalid | 0 | #290836 #290841
290828 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290823
290827 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290819
290826 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290825 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290819
290824 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290827 #290819
290823 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290820
290822 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290819
290821 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290825
290820 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290819
290819 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290826
290815 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290810
290814 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290806
290813 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290812 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290806
290811 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290814 #290806
290810 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290807
290809 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290806
290808 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290812
290807 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290806
290806 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290813
290805 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290815 #290810
290800 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290795
290799 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290791
290798 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290797 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290791
290796 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290799 #290791
290795 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290792
290794 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290791
290793 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290797
290792 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290791
290791 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290798
290790 | #290789 | Story | SME Support | Unassigned | Invalid | 0 | #290795 #290800
290789 |  | Feature | Develop AMS-GS FCAPS Good Citizen Part 1 Training | Unassigned | Rejected |  | #290804
290788 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290783
290787 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290779
290786 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290785 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290779
290784 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290779 #290787
290783 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290780
290782 |  | Story | <Feature xxx>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290779
290781 |  | Story | AMS-GS Training: Engineering SME support (WH) | Unassigned | Invalid | 0 | #290785
290780 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #290779
290779 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290786
290778 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290783 #290788
290733 | #290729 | Story | FM Whitelist updates for PI10 (2nd release): Agile Team Test (Install & PCR Verification) | Unassigned | Invalid | 0
290732 | #290729 | Story | FM Whitelist updates for PI10 (2nd release): Identify Whitelist content | Unassigned | Invalid | 0
290731 | #290729 | Story | FM Whitelist updates for PI10 (2nd release): Out-of-cycle/MPC Inputs | Unassigned | Invalid | 0
290730 | #290729 | Story | FM Whitelist updates for PI10 (2nd release): Engineering Whitelist updates | Unassigned | Invalid | 0
290722 |  | Story | Feature 290711: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290717
290721 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290713
290720 |  | Story | Feature 290711: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290719 |  | Story | Feature 290711: ILS IETM updates | Unassigned | Invalid | 0 | #290713
290718 |  | Story | Feature 290711:Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290721 #290713
290717 |  | Story | Feature 290711: IA Patching and STIGs | Unassigned | Invalid | 0 | #290714
290716 |  | Story | Feature 290711: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290713
290715 |  | Story | Feature 290711: Engineering IETM updates | Unassigned | Invalid | 0 | #290719
290714 |  | Story | Feature 290711: IA Posture Assessment | Unassigned | Invalid | 0 | #290713
290713 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290720
290712 |  | Story | Feature 290711: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290722 #290717
290711 | #347073 | Feature | TD 19-10: Deploy AWARE-NMF Connectivity Changes to WH | EA 14.4 | Done
290709 | #244386 | Feature | Integrate FCAPS for AWARE-NMF Connectivity | Unassigned | Rejected
290708 |  | Story | <Feature yyy>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290704
290707 |  | Story | Feature 290711: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290698
290705 |  | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290704 |  | Story | Feat 290687 Conn AWARE: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #290690
290703 |  | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #290702
290702 |  | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #290698
290701 |  | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290698 #290707
290700 |  | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290698
290699 |  | Story | Feature 290711: IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #290713
290698 |  | Story | Feature 290711: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290696 #290705
290697 |  | Story | Feat 290687 Conn AWARE: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290708
290696 |  | Story | Feature 290711: Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
290695 |  | Story | Feature 290711: Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #290698
290690 |  | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #290699
290684 |  | Story | Feat 290673 Global Test Groups: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290679
290683 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290675
290682 |  | Story | Feat 290673 Global Test Groups: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290681 |  | Story | Feat 290673 Global Test Groups: ILS IETM updates | Unassigned | Invalid | 0 | #290675
290680 |  | Story | Feat 290673 Global Test Groups: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290683 #290675
290679 |  | Story | Feat 290673 Global Test Groups: IA Patching and STIGs | Unassigned | Invalid | 0 | #290676
290677 |  | Story | Feat 290673 Global Test Groups: Engineering IETM updates | Unassigned | Invalid | 0 | #290681
290676 |  | Story | Feat 290673 Global Test Groups: IA Posture Assessment | Unassigned | Invalid | 0 | #290675
290675 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290682
290674 |  | Story | Support AWARE On-Site Testing - Global Test Groups: SME Support | Unassigned | Invalid | 0 | #290679 #290684
290671 | #290672 | Story | FM Whitelist updates for PI9 (2nd release): Identify Whitelist content | Unassigned | Invalid | 0
290670 | #290672 | Story | FM Whitelist updates for PI9 (2nd release): Agile Team Test (Install & PCR Verification) | Unassigned | Invalid | 0
290668 | #290672 | Story | FM Whitelist updates for PI9 (2nd release): Out-of-cycle/MPC Inputs | Unassigned | Invalid | 0
290667 | #290672 | Story | FM Whitelist updates for PI9 (2nd release): Engineering Whitelist updates | Unassigned | Invalid | 0
290664 |  | Story | WCDMA Fault Mode Analysis (Phase 2) - SA placeholder | Unassigned | Invalid | 0
290660 |  | Story | WCDMA & Provisioning Fault Mode Analysis (Phase 2) - TOFF placeholder | Unassigned | Invalid | 0
290639 |  | Story | Feature 290638: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290649 #290644
290633 | #290622 | Story | Feature 290622: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #290628
290632 | #290622 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #290624
290631 | #290622 | Story | Feature 290622: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
290629 | #290622 | Story | Feature 290622: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #290624 #290632
290628 | #290622 | Story | Feature 290622: IA Patching and STIGs | Unassigned | New | 8 | #290625
290627 | #290622 | Story | Feature 290622: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #290624
290626 | #290622 | Story | Feature 290622: Engineering IETM updates | Unassigned | New | 3 | #290630
290625 | #290622 | Story | Feature 290622: IA Posture Assessment | Unassigned | New | 8 | #290624
290624 | #290622 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #290631
290623 | #290622 | Story | Feature 290622: IA Posture Assessment - development input | Unassigned | New | 2 | #290628 #290633
290616 | #290605 | Story | Feature 290605: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #290611
290615 | #290605 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #290607
290614 | #290605 | Story | Feature 290605: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
290612 | #290605 | Story | Feature 290605: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #290615 #290607
290611 | #290605 | Story | Feature 290605: IA Patching and STIGs | Unassigned | New | 8 | #290608
290610 | #290605 | Story | Feature 290605: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #290607
290609 | #290605 | Story | Feature 290605: Engineering IETM updates | Unassigned | New | 3 | #290613
290608 | #290605 | Story | Feature 290605: IA Posture Assessment | Unassigned | New | 8 | #290607
290607 | #290605 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #290614
290606 | #290605 | Story | Feature 290605: IA Posture Assessment - development input | Unassigned | New | 2 | #290611 #290616
290474 |  | Story | <Feature 290463>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290469
290473 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290465
290472 |  | Story | <Feature 290463>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290471 |  | Story | <Feature 290463>:ILS IETM updates | Unassigned | Invalid | 0 | #290465
290470 |  | Story | <Feature 290463> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290465 #290473
290469 |  | Story | <Feature 290463>: IA Patching and STIGs | Unassigned | Invalid | 0 | #290466
290468 |  | Story | <Feature 290463>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290465
290467 |  | Story | <Feature 290463> Engineering IETM updates | Unassigned | Invalid | 0 | #290471
290466 |  | Story | <Feature 290463> IA Posture Assessment | Unassigned | Invalid | 0 | #290465
290464 |  | Story | <Feature 290463>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290474 #290469
290461 |  | Story | GD Support of Zeta - EAD 8 Part 2: Update RGR Geolocation Cabinet's Interconnect Diagram - INVALIDATED | Unassigned | Invalid | 0
290429 | #290418 | Story | Feature 290418: IA Posture Assessment - review of developer input | Unassigned | New | 1 | #290424
290428 | #290418 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 2 | #290420
290427 | #290418 | Story | Feature 290418: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
290426 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #290420
290425 | #290418 | Story | <Feature 290418> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #290428 #290420
290424 | #290418 | Story | Feature 290418: IA Patching and STIGs | Unassigned | New | 2 | #290421
290423 | #290418 | Story | Feature 290418: Deployment Notes and Operator Impact Inputs | Unassigned | New | 2 | #290420
290422 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #290426
290421 | #290418 | Story | Feature 290418 IA Posture Assessment | Unassigned | New | 1 | #290420
290420 | #290418 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #290427
290419 | #290418 | Story | Feature 290418: IA Posture Assessment - development input | Unassigned | New | 1 | #290429 #290424
290418 | #216718 | Feature | ETISP implement eRxIM enhancement to prevent narrowband interference mitigation | Unassigned | Ready for System IPT Approval
290354 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
290352 | #216630 | Story | Feature 216630:ILS IETM updates | Unassigned | Invalid | 0
290349 | #216630 | Story | Feature 216630: IA Patching and STIGs | Unassigned | Invalid | 0
290347 | #216630 | Story | Feature 216630 Engineering IETM updates | Unassigned | Invalid | 0
290268 | #257560 | Story | Feature 257560: Update AWARE Design Documentation | EA 14.3 | Done | 2
290140 | #290129 | Story | Feature 290129: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #290135
290139 | #290129 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #290131
290138 | #290129 | Story | Feature 290129: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
290137 | #290129 | Story | Feature 290129: ILS IETM updates | Unassigned | Invalid | 0 | #290131
290136 | #290129 | Story | Feature 290129: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #290131 #290139
290135 | #290129 | Story | Feature 290129: IA Patching and STIGs | Unassigned | Invalid | 0 | #290132
290134 | #290129 | Story | Feature 290129: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #290131
290133 | #290129 | Story | Feature 290129: Engineering IETM updates | Unassigned | Invalid | 0 | #290137
290132 | #290129 | Story | Feature 290129: IA Posture Assessment | Unassigned | Invalid | 0 | #290131
290131 | #290129 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #290138
290130 | #290129 | Story | Feature 290129: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #290140 #290135
290129 | #220361 | Feature | IA Hardening: WannaCry mem101 and mem102 servers (Common_MSServer_SVD_98-P59402M003) | Unassigned | Rejected
290101 |  | Story | xx | Unassigned | Invalid | 0
289988 | #243505 | Feature | TOOLS Team Separate NEDB, PKI and Account Maintenance Plan into different components | Unassigned | Rejected
289907 |  | Task | INC000003027076: WH- SSC PAC and GD lab call automation reporting no service on CONUS F1/F2. | Unassigned | Done
289881 |  | Story | <Feature 289870>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #289876
289880 |  | Story | ILS IETM updates (1 of 5) | Unassigned | Invalid | 0
289879 |  | Story | RBS Engineering IETM updates (5 of 5) | Unassigned | Invalid | 0
289876 |  | Story | <Feature 289870>: IA Patching and STIGs | Unassigned | Invalid | 0 | #289873
289873 |  | Story | <Feature 289870> IA Posture Assessment | Unassigned | Invalid | 0 | #289872
289871 |  | Story | <Feature 289870>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #289881 #289876
289618 | #289607 | Story | <Feature 289607>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #289613
289617 | #289607 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #289609
289616 | #289607 | Story | <Feature 289607>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
289615 | #289607 | Story | <Feature 289607>:ILS IETM updates | Unassigned | Invalid | 0 | #289609
289614 | #289607 | Story | <Feature 289607> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #289617 #289609
289613 | #289607 | Story | <Feature 289607>: IA Patching and STIGs | Unassigned | Invalid | 0 | #289610
289612 | #289607 | Story | <Feature 289607>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #289609
289611 | #289607 | Story | <Feature 289607> Engineering IETM updates | Unassigned | Invalid | 0 | #289615
289610 | #289607 | Story | <Feature 289607> IA Posture Assessment | Unassigned | Invalid | 0 | #289609
289609 | #289607 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #289616
289608 | #289607 | Story | <Feature 289607>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #289618 #289613
289607 |  | Feature | <Feature 289607> | Unassigned | Rejected
289033 | #287910 | Story | Task Analysis- SME Inputs for Draft #3 | Unassigned | Invalid | 0
289027 | #287910 | Story | Task Analysis- Address Comments | Unassigned | Invalid | 0
288877 |  | Story | TR - Workstation EXP: NMF Extreme Switch Additional Updates | Unassigned | Invalid | 0
288853 |  | Task | RCG 0062 "Periodic Timer has Expired..."- ADD | Unassigned | Done
288731 | #216364 | Feature | Non-redundant equipment section of IETM is out of date | Unassigned | Draft
288690 | #288237 | Story | Assess Training Needs EAD 8: WF/RAN Features | Unassigned | Invalid | 0
288491 |  | Story | IA Hardening - WannaCry-HLR: Upgrade Non-Stop | Unassigned | Invalid | 0
288483 | #245566 | Task | INC000002967645 :: AU - Groups unable to read Group Enabled messages through AU - ADD | Unassigned | Done
288363 | #1001062 | Story | RDE Test Product Build with Upgraded ClearCase Features - Prototype Phase 3 | EA 15.5 | New | 3
288223 | #288210 | Story | Feature 288210: Confirm Configuration on Dependent Servers in Pre-SWIT | Unassigned | New | 1
288222 | #288210 | Story | Feature 288210: Configure Raid Server in Pre-SWIT | Unassigned | New | 3
288215 |  | Feature | xx | Unassigned | Rejected
288086 | #266397 | Story | Perform UX Engagement for WCDMA Service Status Dashboards at NCTAMS | Unassigned | Invalid | 0
288054 | #216631 | Story | Feature Demo - System Test, STCD development and Demo Prep - Add an acknowledgement message to the critical GMAP messages (Part 3) | Unassigned | Invalid | 0
288031 | #263333 | Story | Feature Demo - System Test, STCD development and Demo Prep - Module Provisioning Registration with Central GNH Feature (Part 1) | Unassigned | Invalid | 0
288030 | #216631 | Story | Feature Demo - System Test, STCD development and Demo Prep - Add an acknowledgement message to the critical GMAP messages (Part 1) | Unassigned | Invalid | 0
287937 |  | Story | Feature 287931: IA Patching and STIGs | Unassigned | Invalid | 0 | #287934
287931 | #245559 | Feature | Feature 287931: HBSS Deployment Additional Stability Updates Per DISA Documentation and Soak Testing | Unassigned | Rejected
287924 |  | Story | Installation of new servers in RAN Lab Pt 2 | Unassigned | Invalid | 0
287869 |  | Story | Identify Requirements for RAN Backup Tool Upgrade - Part 2 | Unassigned | Invalid | 0
287868 |  | Story | Tools Training for Clear Trigger and ClearQuest Administration - Part 2 | Unassigned | Invalid | 0
287867 |  | Story | Clear Trigger Upgrade requirements - Part 2 | Unassigned | Invalid | 0
287802 |  | Story | RAN EAD 8 Release: Perform IA Scans and STIGs for RAN | Unassigned | Invalid | 0
287734 |  | Story | TD19-10 SOW Definition Proposal Support - A&A (Nadolski)-INVALIDATE | Unassigned | Invalid | 0
287732 |  | Story | IA Hardening - WannaCry Windows: IA Patching and STIGs - SSA_GDSWIN_SVD_98-P55500M (Part 2) - INVALIDATED | Unassigned | Invalid | 0
287731 |  | Story | Improve AWARE IA Posture for IATT: Create 7-day Rollup Reporting - invalidaed | Unassigned | Invalid | 0
287715 |  | Task | GD Support of Zeta - EAD 8 Part 2: Training for HSM, Parts List, and KVM-INVALIDATE | Unassigned | Invalid
287694 | #286492 | Story | WCDMA Fault Mode Analysis System Engineering | Unassigned | Invalid | 0
287574 |  | Story | IA Hardening - WannaCry-HLR: Lab Test of Upgraded WH HLR including STCD | Unassigned | Invalid | 0
287573 |  | Story | IA Hardening - WannaCry-HLR: Upgrade WH HLR (Lab) | Unassigned | Invalid | 0
287572 |  | Story | IA Hardening - WannaCry-HLR: Lab Test of upgraded NW HLR including STCD | Unassigned | Invalid | 0
287317 |  | Story | Test Story: assigned to Mateo - INVALIDATED | Unassigned | Invalid | 0
287316 |  | Story | Test Story: assigned to Mateo-INVALIDATE | Unassigned | Invalid | 0
287315 |  | Story | Test Story- INVALIDATED | Unassigned | Invalid | 0
287314 |  | Story | Test Story: INVALIDATED | Unassigned | Invalid | 0
287307 |  | Feature | RF Alignment: prepare for and perform alignment at NW site | Unassigned | Rejected
287306 |  | Feature | Wahiawa Preventive Maintenance activity: oversee site support and complete report | Unassigned | Rejected
287300 |  | Feature | Preventive Maintenance activity: coordinate during site activity and complete final report (Niscemi) | Unassigned | Rejected
287212 |  | Story | AWARE 1a Fixes: Fix additional scheduler problems found during integration-INVALIDATED | Unassigned | Invalid | 0
287127 | #262244 | Story | IA Hardening - WannaCry Windows: Development Team Test Inputs (HBSS) | Unassigned | Invalid | 0
287076 |  | Story | Provide IEF Document review support | Unassigned | Invalid | 0
286659 |  | Story | Integrate HBSS & AMS-GS UI Server: IETM Updates (MPC only) - INVALIDATED | Unassigned | Invalid | 0
286553 | #290418 | Story | eRxIM automatically disable correction of narrowband interference | Unassigned | New | 5
286541 | #294595 | Story | Investigate HMS Build Process Transfer to MUOS Environment | Unassigned | Invalid | 0
286519 |  | Story | xx | Unassigned | Invalid | 0
286518 |  | Story | xx | Unassigned | Invalid | 0
286510 |  | Story | xx | Unassigned | Invalid | 0
286509 |  | Story | xx | Unassigned | Invalid | 0
285968 | #285967 | Task | test task | Unassigned | Invalid
285962 | #216631 | Story | Feature Demo - System Test, STCD development and Demo Prep - Add an acknowledgement message to the critical GMAP messages (Part 2) | Unassigned | Invalid | 0 | #234543
285954 | #263333 | Story | Feature Demo - System Test, STCD development and Demo Prep - Module Provisioning Registration with Central GNH Feature (Part 2) | Unassigned | Invalid | 0 | #275558
285902 | #278800 | Story | MUOS-5 Test Set Up Analysis - Test Event and Post Analysis | Unassigned | Invalid | 0
285898 |  | Story | MUOS-5 Test Set Up Analysis - Failed Secured Messages | Unassigned | Invalid | 0
285894 | #278800 | Story | MUOS-5 Test Set Up Analysis - Monitoring Tests | Unassigned | Invalid | 0
285893 | #278800 | Story | MUOS-5 - Doppler Unapproved Whitepaper | Unassigned | Invalid | 0
285890 | #278800 | Story | MUOS-5 Test Set Up Analysis - Megahertz Specifications | Unassigned | Invalid | 0
285887 | #278800 | Story | MUOS-5 Test Set Up Analysis - UHF/UE Models | Unassigned | Invalid | 0
285879 |  | Story | SE Support AWARE IETMs | Unassigned | Invalid | 0
285876 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #285871
285875 | #257555 | Story | AWARE O-Level IETMs Part 2 Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #285867
285874 | #257555 | Story | AWARE O-Lebel IETMs Part 2 - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
285873 | #257555 | Story | AWARE O-Level Part 2: ILS IETM updates | Unassigned | Invalid | 0 | #285867
285872 | #257555 | Story | AWARE IETMs Part 2 - Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #285875 #285867
285871 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #285868
285870 | #257555 | Story | AWARE IETMs Part 2: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #285867
285868 | #257555 | Story | AWARE IETM IA Posture Assessment | Unassigned | Invalid | 0 | #285867
285867 | #257555 | Story | AWARE IETMS Part 1 - Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #285874
285866 |  | Story | AWARE ITEMs: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #285876 #285871
285865 |  | Feature | <Feature xxx> | Unassigned | Rejected
285665 |  | Feature | MOT&E Deferred Findings | Unassigned | Rejected
285624 | #279128 | Task | Please update story 279128 | Unassigned | Done
285568 |  | Story | Incorporate AWARE into ground ATO (Radio RMF): Place holder for Cyber work to include AWARE/AWARE radio in Ground ATO - 7.5 | Unassigned | Invalid | 0
285533 |  | Story | AWARE IA Posture Improvement Continuation: IA Patching and STIGs | Unassigned | Invalid | 0 | #285530
285528 |  | Story | AWARE IA Posture Improvement Continuation: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #285538 #285533
285524 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - Configure analysis engine for U2B Int | Unassigned | Invalid | 0 | #285516
285467 |  | Story | PLAN - RMF Step 4 - Create/submit PCRs to address RMF findings and update RMF POAM (21 of 36) EA 6.4 | Unassigned | Invalid | 0
285412 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 2 | Unassigned | Invalid | 0
285411 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 2 | Unassigned | Invalid | 0
285410 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 2 | Unassigned | Invalid | 0
285394 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 1 | Unassigned | Invalid | 0
285393 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 1 | Unassigned | Invalid | 0
285392 |  | Story | Auto - Call - IA STIG requirement analysis - Pt. 1 | Unassigned | Invalid | 0
285168 | #216631 | Story | Feature 216631: Install baseline in VLab, Execute STCD, Verify PCR | Unassigned | Invalid | 0
285161 | #283203 | Story | Test Radios after Factory changes before returning to SSC PAC (3) | Unassigned | Invalid | 0
285141 |  | Story | Release WF Patch | Unassigned | Invalid | 0
285123 |  | Story | Support WF Maintenance and MIL-STD Development (Sprint 4) | Unassigned | Invalid | 0
285082 |  | Story | Improve AWARE IA Posture for IATT: Assess web server ASD STIG (Support IA Assessment) | Unassigned | Invalid | 0
284646 |  | Story | SE Support AWARE IETMs | Unassigned | Invalid | 0
284643 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #284638
284642 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - AWARE LRU IETMs - Part 2 | Unassigned | Invalid | 0 | #284634
284638 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #284635
284636 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #284640
284635 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #284634
284633 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #284643 #284638
284632 |  | Feature | <Feature xxx> | Unassigned | Rejected
284596 |  | Story | GD Support of Zeta - EAD-9 & FM Support: SE Integration Support | Unassigned | Invalid | 0
284593 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #284588
284592 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #284584
284591 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
284590 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #284584
284589 |  | Story | GD Support of Zeta - EAD-9 & FM Support: SA Integration Support - EAD9 testing (part 2) | Unassigned | Invalid | 0 | #284584 #284592
284588 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #284585
284587 |  | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #284584
284586 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #284590
284585 |  | Story | FM Support in PI7: Cyber IA Posture Assistance | Unassigned | Invalid | 0 | #284584
284584 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #284591
284583 |  | Story | GD Support of Zeta - EAD-9 & FM Support: A&A IA Posture Support | Unassigned | Invalid | 0 | #284588 #284593
284569 | #278737 | Story | Research NCTAMS OJT Needs | Unassigned | Invalid | 0
284547 | #283251 | Story | Systems analysis of Issue with PPK Rollover when Additional Radios Are Added to Group | Unassigned | New | 5
284528 | #283251 | Story | Duplicate Issue with PPK Rollover when Additional Radios Are Added to Group | Unassigned | New | 2
284423 | #295439 | Story | Drawing updates per MPC EAD4.14 | Unassigned | Invalid | 0
284340 | #278800 | Story | PLACEHOLDER for points needed for Chris T. | Unassigned | Invalid | 0
284339 | #278800 | Story | PLACEHOLDER for Points needed for Kurt | Unassigned | Invalid | 0
284314 | #297335 | Story | RDE Perform Validation Testing for ICM Release | EA 15.1 | Done | 3
284272 | #1002583 | Story | RDE ClearCase - Update VOB Schema & Feature Level for Prototype VOBs | PI 15 | Invalid | 0
284080 |  | Story | GD Support of Zeta - EAD 8 Part 2: Update NM Common KVM SVD with RGR Rack Info (Relate to #280988) | Unassigned | Invalid | 0
284054 | #268065 | Story | DT Assist 4 - Create Test Procedures - Overflow Part 2 | Unassigned | Invalid | 0
284053 | #268065 | Story | DT Assist 4 - Create Test Procedures - Overflow Part 1 | Unassigned | Invalid | 0
284018 |  | Story | MUOS Workstations will have multiple images to check into ClearCase - will we run out of ClearCase Storage Space for EAD-7 tenatively | Unassigned | Invalid | 0
284013 |  | Story | AZ256CTZBH2D_X101721 - BUILD MACHINE CONSISTENTLY HAS ISSUE WITH NOT BEING ABLE TO WRITE WOR NUMBER to tmpNewWOR.txt | Unassigned | Invalid | 0
284012 |  | Story | Need to finish configuring the other two build machines to make hard drives - been waiting 1 year | Unassigned | Invalid | 0
284009 |  | Story | Build Forge Does Not Send Email to my chris.english@gd-ms.com account when Builds are Done | Unassigned | Invalid | 0
283747 | #283743 | Story | RF Alignment (Northwest): ILS actions to support activity | Unassigned | Invalid | 0
283711 | #266109 | Story | Remove Splunk dependency on Call Banks: UX Review | Unassigned | Invalid | 0
283666 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 283656: HBSS inf201/202 Server Integration | Unassigned | Invalid | 0 | #283658
283590 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - NW Power Down/Up Updates | Unassigned | Invalid | 0 | #283587
283466 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 283456 IETM LoS Improvements | Unassigned | Invalid | 0 | #283458
283452 | #248351 | Story | Feature 248351: Evaluate Service Capacity & Availability Trends - No Traffic | Unassigned | Invalid | 0
283446 | #248351 | Story | Feature 248351: Evaluate Service Capacity & Availability Trends - Cleared Alarms | Unassigned | Invalid | 0
283443 | #248351 | Story | Feature 248351: Evaluate Service Capacity & Availability Trends - xiprnet | Unassigned | Invalid | 0
283442 | #248351 | Story | Feature 248351: Manage Service Level Agreements & Procedures View - No Traffic | Unassigned | Invalid | 0
283433 | #248351 | Story | Feature 248351: Validate & Transform Data Ingestion - xiprnet | Unassigned | Invalid | 0
283432 | #248351 | Story | Feature 248351: Validate & Transform Data Ingestion - Data Absence | Unassigned | Invalid | 0
283392 | #247492 | Story | Feature 247492: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #264452
283283 | #238078 | Story | SIPRNET Process Complete for GD Members | Unassigned | Invalid | 0
283282 | #238078 | Story | MUOS Tools access for GD SIPRNET Staff | Unassigned | Invalid | 0
283281 | #238078 | Story | CAC Process Complete for GD Members | Unassigned | Invalid | 0
283273 | #238078 | Story | Coordinate with GD Security and IT to make sure that GD members have access and accounts for SIPRNET | Unassigned | Invalid | 0
283271 |  | Story | UX Team to complete SIPRNET paperwork | Unassigned | Invalid | 0
283268 |  | Story | Systems Team to complete SIPRNET paperwork | Unassigned | Invalid | 0
283267 | #238078 | Story | Coordinate with PMW to provide PPA, SPLUNK, Geo access to GD SIPRNET Users | Unassigned | Invalid | 0
283265 | #238078 | Story | Coordinate with PMW+Bill Eckler+Kandra Howard to obtain SIPRNET Tokens | Unassigned | Invalid | 0
283264 |  | Story | UX Team to complete CAC paperwork | Unassigned | Invalid | 0
283261 |  | Story | Systems Team to complete CAC paperwork | Unassigned | Invalid | 0
283250 | #204273 | Feature | Review system design against CONOPS of zeroizing | Unassigned | Rejected
283177 |  | Task | xx | Unassigned | Invalid
283176 | #248351 | Story | Feature 248351: Evaluate Service Capacity & Availability Trends - SBC, DSN | Unassigned | Invalid | 0
283175 | #248351 | Story | Feature 248351: Evaluate Service Capacity & Availability Trends | Unassigned | Invalid | 0
283174 | #248351 | Story | Feature 248351: Manage Service Level Agreements & Procedures View - GIS | Unassigned | Invalid | 0
283173 | #248351 | Story | Feature 248351: Manage Service Level Agreements & Procedures View - SBC DSN | Unassigned | Invalid | 0
283170 | #248351 | Story | Feature 248351: Validate & Transform Data Ingestion - CDR | Unassigned | Invalid | 0
283169 | #248351 | Story | Feature 248351: Validate & Transform Data Ingestion - Data Rules | Unassigned | Invalid | 0
283168 | #248351 | Story | Feature 248351: Validate & Transform Data Ingestion - GIS Mapping | Unassigned | Invalid | 0
282754 |  | Story | GD Support of Zeta - EAD 8 Part 2: Scan firewall for site redlines for AMS-GS (Part 2) EA 6.4-INVALIDATE | Unassigned | Invalid | 0
282529 | #281276 | Story | Site Alignment Wireframes V3 (Incorporate Comments + Section 6) | Unassigned | Invalid | 0
282527 | #281276 | Story | Site Alignment Wireframes V2 (Section 5) | Unassigned | Invalid | 0
282511 | #279554 | Story | AMS-GS EAD-7: NAVSOC coordination for EAD-7 | Unassigned | Invalid | 0
282507 |  | Story | NAVSOC coordination for EAD-9 | Unassigned | Invalid | 0
282506 |  | Story | NAVSOC coordination for EAD-8 | Unassigned | Invalid | 0
282505 | #245437 | Story | MUOS Team Knowledge Ramp on UX (Mission and Engagement for PI6) | Unassigned | Invalid | 0
282485 | #272361 | Story | GD Support of Zeta - EAD-TBD: Copy Zeta ISOs into ClearCase | Unassigned | Invalid | 0
282476 |  | Story | Finalize approach for configuring Analysis Engine for U2B Interference | Unassigned | Invalid | 0
282474 |  | Story | Kick off LM support of AE U2B interference effort | Unassigned | Invalid | 0
282466 |  | Story | GD Support of Zeta - EAD 8 Part 2: Complete Enhancement 282454 - Ready for 6.4 | Unassigned | Invalid | 0
282405 |  | Story | Provide AWARE O-Level IETMs: Agile 7-day Test | Unassigned | Invalid | 0
282375 |  | Task | Active TrapRAF CRTXRF: Out of Range - ADD | Unassigned | Done
282360 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 258277 | Unassigned | Invalid | 0
282350 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - INVALID | Unassigned | Invalid | 0
282315 |  | Story | EA 6.5 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282314 |  | Story | EA 6.4 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282312 | #282186 | Story | EA 6.2 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282310 |  | Story | EA 6.5 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282309 |  | Story | EA 6.4 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282308 |  | Story | EA 6.3 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282307 |  | Story | EA 6.2 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282306 |  | Story | EA 6.1 Analyze Spare Radios returned from repair Depot | Unassigned | Invalid | 0
282304 | #282186 | Story | EA 6.4 Call Bank Log Analysis and Issue Support | Unassigned | Invalid | 0
282252 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: Development Team Test Inputs - INVALIDATE | Unassigned | Invalid | 0
282249 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: IA Patching and STIGs - INVALIDATE | Unassigned | Invalid | 0
282244 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: Release Notes Inputs - INVALIDATE | Unassigned | Invalid | 0
282236 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: Engineering IETM updates - INVALIDATE | Unassigned | Invalid | 0
282229 | #282186 | Story | EA 6.3 Call Bank Log Analysis and Issue Support | Unassigned | Invalid | 0
282226 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: IA Posture Assessment - development input - INVALIDATE | Unassigned | Invalid | 0
282155 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: Initiate CM PDO Processing for all CI's - INVALIDATE | Unassigned | Invalid | 0
282102 |  | Task | Major Loss of Signal PC_LOSS_OF_SIGNAL - ADD | Unassigned | Done
282088 | #216364 | Feature | IETM clean-up post-OTRR | Unassigned | Draft
281974 |  | Story | AMS-GS EAD-10 On-Site Integration/Deployment | Unassigned | Invalid | 0
281964 | #279557 | Story | AMS-GS EAD-9 On-Site Integration/Deployment | Unassigned | Invalid | 0
281960 | #279554 | Story | AMS-GS EAD-7: On-Site Integration/Deployment | Unassigned | Invalid | 0
281942 |  | Task | SR 955379/INC000002932208: WH - fcap101-wh-nma AMS Status Adapter Alarm on Netcool. (Remove from whitelist) | Unassigned | Done
281930 |  | Story | RMF Step 5 Checkpoint support (01 of 12 in this feature) | Unassigned | Invalid | 0
281894 | #245566 | Task | INC000002406373 for MUOS -AU - receiving "A PROBE process running on fcaps104-au-fs - ADD | Unassigned | Done
281867 |  | Story | Test AWARE system without Debug Lid and Slice | Unassigned | Invalid | 0
281798 |  | Story | Power Up: Update IETM Redline Procedures for HLR | Unassigned | Invalid | 0 | #283593
281788 | #283243 | Story | Feature 281733: Power Down: SME Update and Consolidate IETM Redline Procedures for RAF/SF/Combined | Unassigned | Invalid | 0 | #283593
281737 | #281733 | Story | Engineering IETM updates | Unassigned | Invalid | 0 | #281741
281641 | #280549 | Story | Knowledge transfer of Quest system experience & expertise (from TOFF/SA to AMS) | PI 16 | Invalid | 0
281287 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #281282
281286 | #281276 | Story | Feature 281276 Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #281278
281285 | #281276 | Story | Feature 281276: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
281284 | #281276 | Story | Feature 281276:ILS IETM updates | Unassigned | Invalid | 0 | #281278
281283 | #281276 | Story | Feature 281276 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #281286 #281278
281282 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #281279
281281 | #281276 | Story | Feature 281276: Release Notes Inputs | Unassigned | Invalid | 0 | #281278
281280 | #281276 | Story | Feature 281276 Engineering IETM updates | Unassigned | Invalid | 0 | #281284
281279 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #281278
281278 | #281276 | Story | Feature 281276 Demo – Customer Demo Event | Unassigned | Invalid | 0 | #281285
281277 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #281282 #281287
281266 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0 | #281261
281265 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #281257
281264 |  | Story | Feature 281255: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
281262 |  | Story | Feature 281255 Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #281265 #281257
281261 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #281258
281260 |  | Story | Feature 281255: Release Notes Inputs | Unassigned | Invalid | 0 | #281257
281258 |  | Story | <Feature xxx> IA Posture Assessment | Unassigned | Invalid | 0 | #281257
281257 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #281264
281256 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #281266 #281261
281255 |  | Feature | IETM replace bad references to sections within the ETI switchover procedure | Unassigned | Rejected
281247 |  | Task | INC000002898029: REQUEST TO ADD NETCOOL ALARM TO WHITELIST FILTER: ETISP1-NW EXCEEDED MILLITRON POWER THRESHOLD AND POWER | Unassigned | Done
281209 | #221231 | Story | Create STCD for Automated Factory Logging Feature | Unassigned | New | 2
281205 |  | Story | DUPLICATE - Provide Systems Support to DT Assist #2 | Unassigned | Invalid | 0
281193 |  | Story | Update All Firewalls With Up-to-Date Version of IA Patches : Patch firewall for IA - INVALIDATED | Unassigned | Invalid | 0
280986 |  | Story | GD Support of Zeta - EAD 8 Part 2: Verify PCR for Common KVM SVD-INVALIDATE | Unassigned | Invalid | 0
280984 |  | Story | GD Support of Zeta - EAD 8 Part 2: Verify PCR for Update RGR Parts List and HSM-INVALIDATED | Unassigned | Invalid | 0
280980 |  | Story | Update RGR Parts List for Common KVM SVD | Unassigned | Invalid | 0
280767 | #280733 | Story | Hands-on skills: work in VLAB to detect, isolate, and resolve incidents (JC) | Unassigned | Invalid | 0
280664 |  | Story | GD Support of Zeta - EAD-6: Install AVHIDS in EAD-6 Build and Update Docs (INVALIDATED) | Unassigned | Invalid | 0
280647 |  | Story | xx | Unassigned | Invalid | 0
280560 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Done | 0 | #280555
280559 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #280551
280558 |  | Story | Feature 280549: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
280557 | #280549 | Story | Feature 280549: ILS IETM updates | PI 16 | Invalid | 0 | #280551
280556 |  | Story | Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #280559 #280551
280555 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Done | 0 | #280552
280554 |  | Story | Feature 280549: Release Notes Inputs | Unassigned | Invalid | 0 | #280551
280553 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #280557
280552 |  | Story | Feature 280549: IA Posture Assessment | Unassigned | Done | 0 | #280551
280551 | #280549 | Story | Feature Demo – Customer Demo Event | PI 16 | Invalid | 0 | #280558
280550 |  | Story | Feature 280549 IA Posture Assessment - development input | Unassigned | Done | 0 | #280560 #280555
280549 | #216364 | Feature | Add/update IETM alarm recovery procedures for CORE/GIS alarms [O-Level - Needs Updates] | PI 17 | Approved
280402 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Done | 0
280399 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Done | 0 | #280396
280397 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Done | 0 | #280401
280394 |  | Story | Feature 280393: IA Posture Assessment - development input | Unassigned | Done | 0 | #280399 #280404
280251 |  | Task | Need the Acceptance Criteria and description for Story: 264602 for Sprint 5.4 - INVALIDATED | Unassigned | Invalid
280020 |  | Story | IA Hardening - WannaCry-HLR: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0
280017 | #280009 | Story | IA Hardening - WannaCry-HLR: ILS IETM updates - INVALIDATED | Unassigned | Invalid | 0 | #280011
280013 | #280009 | Story | IA Hardening - WannaCry-HLR: Engineering IETM updates - INVALIDATED | Unassigned | Invalid | 0 | #280017
279924 | #255693 | Feature | Investigate PPA Database Performance Issues - Short Term Fixes | Unassigned | Rejected
279839 |  | Task | Learn Rollup Reporting-INVALIDATED | Unassigned | Invalid
279766 |  | Story | xx | Unassigned | Invalid | 0
279729 | #262244 | Story | IA Hardening - WannaCry Windows: IA Patching and STIGs - OS_WindowsServer2012_SVD_98-P59852M-98-P55510M | Unassigned | Invalid | 0 | #279727
279725 |  | Story | xx | Unassigned | Invalid | 0 | #279727
279719 |  | Story | xx | Unassigned | Invalid | 0
279642 | #247492 | Story | UX restructuring of ETI Switchover: Engineering IETM updates | Unassigned | Invalid | 0
279641 | #247492 | Story | Feature 247492 UX restructuring of ETISP Switchover: ILS IETM updates | Unassigned | Invalid | 0
279595 |  | Story | 19-10 Proposal Support (Tools) | Unassigned | Invalid | 0
279593 |  | Story | 19-10 Proposal Support (TOFF) | Unassigned | Invalid | 0
279585 |  | Story | 19-10 Proposal Support (HBSS) - Brandon 7.2 | Unassigned | Invalid | 0
279574 |  | Story | 19-10 Proposal Support (A&A Part 3) | Unassigned | Invalid | 0
279570 |  | Story | FY 19 proposals fact finding and proposal close out (UX) | Unassigned | Invalid | 0
279569 |  | Story | FY 19 proposals fact finding and proposal close out (Tools) | Unassigned | Invalid | 0
279568 |  | Story | FY 19 proposals fact finding and proposal close out (TOFF) | Unassigned | Invalid | 0
279566 |  | Story | FY 19 proposals fact finding and proposal close out (System Engr) | Unassigned | Invalid | 0
279564 |  | Story | FY 19 proposals fact finding and proposal close out (SA) | Unassigned | Invalid | 0
279562 |  | Story | FY 19 proposals fact finding and proposal close out (HBSS) | Unassigned | Invalid | 0
279561 |  | Task | FY 19 proposals fact finding and proposal close out (Deployment) | Unassigned | Invalid
279560 |  | Story | FY 19 proposals fact finding and proposal close out (Cyber RMF) | Unassigned | Invalid | 0
279558 |  | Story | FY 19 proposals fact finding and proposal close out (A&A) | Unassigned | Invalid | 0
279557 | #217023 | Feature | AMS-GS EAD-9 On-Site Integration & Deployment Support | Unassigned | Rejected
279554 |  | Feature | AMS-GS EAD-7 On-Site Integration & Deployment Support | Unassigned | Rejected
279552 |  | Story | AMS-GS EAD-6 On-Site Integration & Deployment Support: On-Site Integration & Deployment-INVALIDATED | Unassigned | Invalid | 0
279543 | #248404 | Story | Lab - TXO - SME support for SGSN board replacement procedures | Unassigned | Invalid | 0
279541 | #248404 | Story | Lab - TXO - SME support for ATM board replacement procedures | Unassigned | Invalid | 0
279539 | #248404 | Story | Lab - TXO - SME support for GGSN board replacement procedures | Unassigned | Invalid | 0
279537 | #248404 | Story | Lab - TXO - SME support for CSCF/HSS, GGSN, ATM and SGSN board replacement procedures | Unassigned | Invalid | 0
279457 | #241206 | Feature | Obsolescence: Trade Study - Anti-Jam Modem (AJM) Phase 2 | Unassigned | Rejected
279456 |  | Story | <Feature yyy>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0
279300 | #279290 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #279292
279299 | #279290 | Story | <Feature 279290>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
279297 | #279290 | Story | <Feature 279290> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #279300 #279292
279296 | #279290 | Story | <Feature 279290>: IA Patching and STIGs | Unassigned | New | 8 | #279293
279295 | #279290 | Story | <Feature 279290>: Release Notes Inputs | Unassigned | New | 2 | #279292
279294 | #279290 | Story | <Feature 279290> Engineering IETM updates | Unassigned | New | 3 | #279298
279293 | #279290 | Story | Feature 279290: IA Posture Assessment | Unassigned | New | 8 | #279292
279292 | #279290 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #279299
279291 | #279290 | Story | <Feature 279290>: IA Posture Assessment - development input | Unassigned | New | 2 | #279296
279283 | #248400 | Feature | Lab - TXO Ericsson - Create and update HIGH priority board test procedures for testing Ericsson parts | EA 14.5 | Done
279249 | #216650 | Feature | Communicate Group Provisioning Success/Failure Between RAFs | Unassigned | Rejected
279245 | #216649 | Feature | Reselect Group Owner on Module Failure | Unassigned | Analyzing
279209 | #216605 | Story | Feature Demo – System Test, STCD development and Demo Prep - Resolve rekey issue - KMS leaves keys "in transit" when the HLR fails to provision - Feature 216605 | Unassigned | Invalid | 0 | #279201
279208 | #216605 | Story | KMS Re-key Issue: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
279206 | #216605 | Story | KMS Re-key Issue: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #279209 #279201
279205 | #216605 | Story | KMS Re-key Issue: IA Patching and STIGs | Unassigned | Invalid | 0 | #279202
279204 | #216605 | Story | KMS Re-key Issue: Release Notes Inputs | Unassigned | Invalid | 0 | #279201
279203 | #216605 | Story | KMS Re-key Issue: Engineering IETM updates | Unassigned | Invalid | 0 | #279207
279202 | #216605 | Story | KMS Re-key Issue: IA Posture Assessment | Unassigned | Invalid | 0 | #279201
279201 | #216605 | Story | Feature Demo - Customer Event - Resolve rekey issue - KMS leaves keys "in transit" when the HLR fails to provision - Feature 216605 | Unassigned | Invalid | 0 | #279208
279200 | #216605 | Story | KMS Re-key Issue: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #279205
279199 |  | Feature | Rejected | Unassigned | Rejected
279173 | #279163 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 3 | #279165
279172 | #279163 | Story | Feature 279163: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
279171 | #279163 | Story | Feature 279163: ILS IETM updates | Unassigned | New | 0 | #279165
279170 | #279163 | Story | Feature 279163: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 3 | #279173 #279165
279169 | #279163 | Story | Feature 279163: IA Patching and STIGs | Unassigned | New | 1 | #279166
279168 | #279163 | Story | Feature 279163: Release Notes Inputs | Unassigned | New | 1 | #279165
279167 | #279163 | Story | Feature 279163: Engineering IETM updates | Unassigned | New | 0 | #279171
279166 | #279163 | Story | Feature 279163 IA Posture Assessment | Unassigned | New | 1 | #279165
279165 | #279163 | Story | Feature 279163: Feature Demo – Customer Demo Event | Unassigned | New | 1 | #279172
279164 | #279163 | Story | Feature 279163: IA Posture Assessment - development input | Unassigned | New | 1 | #279169
279132 | #278800 | Story | Review of the B2U frequency spikes/changes | Unassigned | Invalid | 0
279091 |  | Story | AWARE 1a Fixes: Need re-configuration procedure for swapping radios (Part 2)-INVALIDATED | Unassigned | Invalid | 0
279072 |  | Story | Support AWARE Phase 3 Proposal Effort - Test | Unassigned | Invalid | 0
279070 |  | Story | Support AWARE Phase 3 Proposal Effort - IA | Unassigned | Invalid | 0
279069 |  | Story | Support AWARE Phase 3 Proposal Effort -ILS | Unassigned | Invalid | 0
279068 |  | Task | Support AWARE Phase 3 Proposal Effort - A&A | Unassigned | Invalid
279051 |  | Story | <Feature xxx>: IA Posture Assessment - review of developer input | Unassigned | Invalid | 0
278938 |  | Story | <Feature 278928> Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #278930
278937 |  | Story | <Feature 278928>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
278936 |  | Story | Feature 278928: IETM updates for Updating the load balancers in the system to allow ACAS scanning via ssh | Unassigned | Invalid | 0 | #278930
278935 |  | Story | <Feature 278928> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #278938 #278930
278934 |  | Story | <Feature 278928>: IA Patching and STIGs | Unassigned | Invalid | 0 | #278931
278933 |  | Story | <Feature 278928>: Release Notes Inputs | Unassigned | Invalid | 0 | #278930
278932 |  | Story | <Feature 278928> Engineering IETM updates | Unassigned | Invalid | 0 | #278936
278931 |  | Story | <Feature 278928> IA Posture Assessment | Unassigned | Invalid | 0 | #278930
278930 |  | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #278937
278929 |  | Story | <Feature 278928>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #278934
278832 | #278830 | Feature | TD19-03 Proposal Support | Unassigned | Rejected
278828 |  | Story | IETM alarm recovery procedures for CORE/GIS alarms (Quest, part 3) | Unassigned | Invalid | 0
278827 | #280549 | Story | IETM alarm recovery procedures for CORE/GIS alarms | PI 16 | Invalid | 0
278825 | #280549 | Story | IETM alarm recovery procedures for CORE/GIS alarms (Quest, part 1) | PI 16 | Invalid | 0
278791 | #278737 | Story | Create Training Plan for Requested OJT - DSN/Data Connections | Unassigned | Invalid | 0
278789 | #278737 | Story | Create Training Plan for Requested OJT - Call Flow | Unassigned | Invalid | 0
278736 |  | Story | Execute Targeted Functional System Test Event (4) | Unassigned | Invalid | 0
278735 |  | Story | Execute Targeted Functional System Test Event (3) | Unassigned | Invalid | 0
278733 |  | Story | Execute Targeted Functional System Test Event (2) | Unassigned | Invalid | 0
278679 | #278631 | Story | Ericsson HLR/AUC: remove hardware from NW site | Unassigned | Invalid | 0
278670 |  | Story | Ericsson HLR/AUC hardware: SME needed to identify IETM procedures which should be eliminated-INVALIDATED | Unassigned | Invalid | 0
278620 | #278601 | Story | AWARE No Debug Lid/Slice: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #278611
278619 | #278601 | Story | AWARE No Debug Lid/Slice: Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #278611
278618 | #278601 | Story | AWARE No Debug Lid/Slice: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
278617 | #278601 | Story | AWARE No Debug Lid/Slice: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #278604
278616 | #278601 | Story | AWARE No Debug Lid/Slice: Engineering IETM updates | Unassigned | Invalid | 0 | #278615
278615 | #278601 | Story | AWARE No Debug Lid/Slice: ILS IETM updates | Unassigned | Invalid | 0 | #278611
278614 | #278601 | Story | AWARE No Debug Lid/Slice: Agile Team Test (PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #278611 #278620
278613 | #278601 | Story | AWARE No Debug Lid/Slice: Release Notes Inputs | Unassigned | Invalid | 0 | #278611
278612 | #278601 | Story | AWARE No Debug Lid/Slice: IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #278611
278611 | #278601 | Story | AWARE No Debug Lid/Slice: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #278618 #278609
278610 | #278601 | Story | AWARE No Debug Lid/Slice: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #278617
278609 | #278601 | Story | AWARE No Debug Lid/Slice: Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
278608 | #278601 | Story | AWARE No Debug Lid/Slice: Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #278611
278607 | #278601 | Story | AWARE No Debug Lid/Slice: System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #278608
278606 | #278601 | Story | AWARE No Debug Lid/Slice: ILS Create red lines Hardware drawings submitted for IDP | Unassigned | Invalid | 0 | #278603
278605 | #278601 | Story | AWARE No Debug Lid/Slice: ILS Define Power Consumption Changes for IDP | Unassigned | Invalid | 0 | #278603
278604 | #278601 | Story | AWARE No Debug Lid/Slice: IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #278612
278603 | #278601 | Story | AWARE No Debug Lid/Slice: Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #278611
278602 | #278601 | Story | AWARE No Debug Lid/Slice: ILS Considerations (non-IETM) | Unassigned | Invalid | 0 | #278611
278601 |  | Feature | AWARE Prep - Remove Debug Lid/Slice from AWARE Radios (HW/FRCB Deployable Feature) | Unassigned | Rejected
278556 | #278546 | Story | Feature Demo - System Test, STCD development and Demo Prep - AMS-GS Status Page Feature Demo | Unassigned | New | 5 | #278548
278555 | #278546 | Story | AMS-GS Status Page: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
278554 | #278546 | Story | AMS-GS Status Page: ILS IETM updates | Unassigned | New | 3 | #278548
278553 | #278546 | Story | AMS-GS Status Page: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 8 | #278548 #278556
278552 | #278546 | Story | AMS-GS Status Page: IA Patching and STIGs | Unassigned | New | 5 | #278549
278551 | #278546 | Story | AMS-GS Status Page: Release Notes Inputs | Unassigned | New | 1 | #278548
278550 | #278546 | Story | AMS-GS Status Page: Engineering IETM updates | Unassigned | New | 3 | #278554
278549 | #278546 | Story | AMS-GS Status Page: IA Posture Assessment | Unassigned | New | 8 | #278548
278548 | #278546 | Story | Feature Demo - Customer Event - AMS-GS Status Page | Unassigned | New | 1 | #278555
278547 | #278546 | Story | AMS-GS: Status Page: IA Posture Assessment - development input | Unassigned | New | 2 | #278552
278377 | #278361 | Story | AMS-GS Phase 2 - Support of DT-Assist #3: Systems Support GEO | Unassigned | Invalid | 0
278269 | #278165 | Story | Preventive Maintenance (Sicily): Site interface during PM period (Part 2) | Unassigned | Invalid | 0
278143 | #278138 | Story | SME Input Level of Repair Assessment (Post PMW Review) | Unassigned | Invalid | 0
278140 |  | Story | SME Input Level of Repair Assessment (Post PMW Review) | Unassigned | Invalid | 0
278082 | #221231 | Story | PDO Site logging updates | Unassigned | New | 1
278080 | #221231 | Story | Load Baseline in VLab, Execute STCD, Verify PCR | Unassigned | New | 5
278078 |  | Story | Invalid | Unassigned | Invalid | 0
278071 |  | Story | Invalid | Unassigned | Invalid | 0
278031 |  | Story | GD Support of Zeta - EAD-6: Incorporate Account Maintenance redlines for AMS-GS-INVALIDATED | Unassigned | Invalid | 0
277985 | #278601 | Story | Remove Slice/Debug Lid from AWARE IA Documentation | Unassigned | Invalid | 0
277853 |  | Story | Learn Rollup Reporting - INVALIDATED | Unassigned | Invalid | 0
277814 | #231507 | Story | Determine Space Requirements for Data Retention: PPA Provisioning Data | Unassigned | Invalid | 0
277574 | #245561 | Problem | HBSS Updates to NM HW/SW Mapping | Unassigned | Closed
277573 |  | Problem | 98-P52296E003 RevE (5/13/2013) Secure Comms GDS Software Version Description should change references from 98-P54199T NM AV/HIDs to 98-P59854M NM HBSS SVD | Unassigned | Closed
277370 |  | Story | AWARE IA Posture Improvement Continuation: Re-assess ASD STIG | Unassigned | Invalid | 0
277268 |  | Task | Update Tools Upgrade Requirements document with RAN View Storage Info and Configuration | Unassigned | New
277173 | #247492 | Story | Wireframes V2 for non-automated ETISP Switchover | Unassigned | Invalid | 0
277114 |  | Story | Feature 262904: Engineering IETM updates (RNC alarms) | Unassigned | Invalid | 0
277069 |  | Story | HBSS: complete MCO's for 7 additional CI's | Unassigned | Invalid | 0
277057 | #245898 | Feature | Obsolescence - Windows; cybersecurity value/impact analysis, security requirements and architecture definition | Unassigned | Rejected
277049 | #245566 | Task | INC000001925994: SSG-DD-INT1 IPSec tunnel on interface Ethernet 0/0 with tunnel ID 0x2, 0x4, 0x8 received a bad SPI - Remove from Whitelist | Unassigned | Done
277047 | #245566 | Task | INC000001925979: SSG-HQ-INT1 IPSec tunnel on interface Ethernet 0/0 tunnel ID 0x2,0x3,0x6 received a bad SPI - Remove from Whitelist | Unassigned | Done
276933 |  | Story | xx | Unassigned | Invalid | 0
276927 |  | Feature | Develop ACAS site scan operational requirements document to support RMF Step 6 Continuous Monitoring | Unassigned | Rejected
276675 | #262146 | Story | Need SME to evaluate Wildstar PN# WS2P/GDMUOS002, SN# 1000686 | Unassigned | Invalid | 0
276633 | #268065 | Story | DT Assist 4 - Create Test Procedures - Hold Draft Review | Unassigned | Invalid | 0
276630 | #268065 | Story | DT Assist 4 - Create Test Procedures - GIS Fault Insertion | Unassigned | Invalid | 0 | #276633
276629 | #268065 | Story | DT Assist 4 - Create Test Procedures - RBS Fault Insertion | Unassigned | Invalid | 0 | #276633
276628 | #268065 | Story | DT Assist 4 - Create Test Procedures - ET/ETISP Fault Insertion | Unassigned | Invalid | 0 | #276633
276602 | #276592 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #276594
276601 | #276592 | Story | <Feature 276592>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
276599 | #276592 | Story | <Feature 276592> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #276602 #276594
276598 | #276592 | Story | <Feature 276592>: IA Patching and STIGs | Unassigned | Invalid | 0 | #276595
276597 | #276592 | Story | <Feature 276592>: Release Notes Inputs | Unassigned | Invalid | 0 | #276594
276596 | #276592 | Story | <Feature 276592> Engineering IETM updates | Unassigned | Invalid | 0 | #276600
276595 | #276592 | Story | Feature 276592: IA Posture Assessment | Unassigned | Invalid | 0 | #276594
276594 | #276592 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #276601
276593 | #276592 | Story | <Feature 276592>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #276598
276589 |  | Story | Feature 276579: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
276569 | #243505 | Feature | RAN Network Upgrade of MUOS Tools - Final Implementation and Data Migration | Unassigned | Rejected
276513 | #238135 | Story | Support AMS-GS Update PKI Deployment Plan | Unassigned | New | 1
276499 |  | Story | GD Support of Zeta - EAD 8 Part 1: Preliminary AMS-GS Integration Support of Zeta Provided SNMP Traps/Alarms-INVALIDATED | Unassigned | Invalid | 0
276438 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate LMs Low Side ACAS RAR into GD's FINAL Low Side ACAS RAR | Unassigned | Invalid | 0
276436 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate LMs High Side ACAS RAR into GD's FINAL High Side ACAS RAR | Unassigned | Invalid | 0
276435 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate LMs High Side ACAS RAR into GD's INTERIM High Side ACAS RAR | Unassigned | Invalid | 0
276382 | #278601 | Story | Remove Slice/Debug Lid from AWARE drawing/part lists | Unassigned | Invalid | 0
276338 |  | Task | Rejected: Obsolescence: Initial Implementation Plan | Unassigned | Invalid
276333 |  | Task | Rejected: Digital ETI Create MATLAB MUOS modem model | Unassigned | Invalid
276331 |  | Task | Reject: Digital ETI Create software development system | Unassigned | Invalid
276320 | #278601 | Story | Remove References to Radio log collections from AWARE SVD documentation | Unassigned | Invalid | 0
276318 | #278601 | Story | Analyze Results from AWARE Test Rollup for radios without debug lids/slices | Unassigned | Invalid | 0
276316 | #278601 | Story | AWARE Test Rollup for radios without debug Lids/Slice | Unassigned | Invalid | 0
276314 | #278601 | Story | AWARE Test & radios without debug lids/slices | Unassigned | Invalid | 0
276313 | #278601 | Story | Set up radios without debug lids/slices | Unassigned | Invalid | 0
276309 |  | Feature | Rejected | Unassigned | Rejected
276279 |  | Story | Regression Test after change | Unassigned | Invalid | 0
276277 |  | Story | Regression Test before change | Unassigned | Invalid | 0
276236 |  | Story | Feature 276227: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
276235 |  | Story | Feature 276227: ILS IETM updates | Unassigned | Invalid | 0 | #276229
276233 |  | Story | Feature 276227: IA Patching and STIGs | Unassigned | Invalid | 0 | #276230
276230 |  | Story | Feature 276227: IA Posture Assessment | Unassigned | Invalid | 0 | #276229
276228 |  | Story | Feature 276227: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #276233
276202 |  | Story | Feature 276193: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
276201 |  | Story | Feature 276193: ILS IETM updates | Unassigned | Invalid | 0 | #276195
276199 |  | Story | Feature 276193: IA Patching and STIGs | Unassigned | Invalid | 0 | #276196
276196 |  | Story | Feature 276193: IA Posture Assessment | Unassigned | Invalid | 0 | #276195
276194 |  | Story | Feature 276193: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #276199
276183 |  | Story | Feature 276173: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
276182 |  | Story | Feature 276173: ILS IETM updates | Unassigned | Invalid | 0 | #276175
276180 |  | Story | Feature 276173: IA Patching and STIGs | Unassigned | Invalid | 0 | #276176
276176 |  | Story | Feature 276173: IA Posture Assessment | Unassigned | Invalid | 0 | #276175
276174 |  | Story | Feature 276173: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #276180
276124 | #276113 | Story | Bulk Key Management Key Deletion - ILS IETM updates | Unassigned | New | 3
276120 | #257553 | Story | Provide AWARE LRU IETMs - Part 1 & 2 : Release Notes Inputs | Unassigned | Invalid | 0 | #276118
276119 | #276113 | Story | Bulk Key Management Key Deletion - Engineering IETM updates | Unassigned | New | 3
276117 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0
276107 |  | Story | Feature 276098: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
276106 |  | Story | Feature 276098: ILS IETM updates | Unassigned | Invalid | 0 | #276100
276104 |  | Story | Feature 276098: IA Patching and STIGs | Unassigned | Invalid | 0 | #276101
276101 |  | Story | Feature 276098: IA Posture Assessment | Unassigned | Invalid | 0 | #276100
276099 |  | Story | Feature 276098: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #276104
276088 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - Workstation Expansion Phase 2A | Unassigned | Invalid | 0 | #276080
276075 |  | Story | xx | Unassigned | Invalid | 0
276032 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side FINAL ASD STIG RAR into High Side FINAL RMF ASD STIG POAM | Unassigned | Invalid | 0
276031 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side FINAL ASD STIG RAR into Low Side FINAL RMF ASD STIG POAM | Unassigned | Invalid | 0
276030 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side INTERIM ASD STIG RAR into High Side INTERIM RMF ASD STIG POAM | Unassigned | Invalid | 0
276029 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side INTERIM ASD STIG RAR into Low Side INTERIM RMF ASD STIG POAM | Unassigned | Invalid | 0
276028 |  | Story | xx | Unassigned | Invalid | 0
276027 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side FINAL Sever/STIG RAR into High Side FINAL RMF Server/STIG POAM | Unassigned | Invalid | 0
276026 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side FINAL Sever/STIG RAR into Low Side FINAL RMF Server/STIG POAM | Unassigned | Invalid | 0
276025 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side INTERIM Sever/STIG RAR into High Side INTERIM RMF Server/STIG POAM | Unassigned | Invalid | 0
276023 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side INTERIM Sever/STIG RAR into Low Side INTERIM RMF Server/STIG POAM | Unassigned | Invalid | 0
276022 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side DRAFT Sever/STIG RAR into High Side Draft RMF Server/STIG POAM | Unassigned | Invalid | 0
276020 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side DRAFT Sever/STIG RAR into Low Side Draft RMF Server/STIG POAM | Unassigned | Invalid | 0
276019 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side FINAL ACAS RAR into Low Side FINAL RMF ACAS POAM | Unassigned | Invalid | 0
276018 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate High Side FINAL ACAS RAR into High Side FINAL RMF ACAS POAM | Unassigned | Invalid | 0
276016 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Low Side INTERIM ACAS RAR into Low Side INTERIM RMF ACAS POAM | Unassigned | Invalid | 0
275900 | #225729 | Feature | Investigate Ingesting RAN Daily Health Check into Splunk | Unassigned | Rejected
275864 |  | Story | RMF Step 4 - RMF DRAFT POAM artifact generation - Integrate Workbook data into POAM GROUP 5 | Unassigned | Invalid | 0
275855 | #275845 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #275847
275854 | #275845 | Story | <Feature 275845>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
275852 | #275845 | Story | <Feature 275845> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #275855 #275847
275851 | #275845 | Story | <Feature 275845>: IA Patching and STIGs | Unassigned | New | 8 | #275848
275850 | #275845 | Story | <Feature 275845>: Release Notes Inputs | Unassigned | New | 2 | #275847
275849 | #275845 | Story | <Feature 275845> Engineering IETM updates | Unassigned | New | 3 | #275853
275848 | #275845 | Story | Feature 275845: IA Posture Assessment | Unassigned | New | 8 | #275847
275847 | #275845 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #275854
275846 | #275845 | Story | <Feature 275845>: IA Posture Assessment - development input | Unassigned | New | 2 | #275851
275845 | #216550 | Feature | BKM enhancements to reduce human error | Unassigned | Analyzing
275837 |  | Story | Feature 275827: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #275829
275836 |  | Story | Feature 275827: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
275835 | #275827 | Story | Feature 275827: ILS IETM updates | Unassigned | Invalid | 0 | #275829
275834 |  | Story | Feature 275827: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #275829 #275837
275832 |  | Story | Feature 275827: Release Notes Inputs | Unassigned | Invalid | 0 | #275829
275831 | #275827 | Story | Feature 275827: RCG Engineering IETM updates (1 of 3) | Unassigned | Invalid | 0 | #275835
275829 | #275827 | Story | Feature 275827: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #275836
275791 |  | Story | GD Support of Zeta - EAD-6: Review Zeta SDRLs (Keith K.) - INVALIDATED | Unassigned | Invalid | 0
275659 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Generate INTERIM RAR from Workbook GROUP 5 | Unassigned | Invalid | 0
275651 | #275649 | Story | <Feature 275649>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
275642 | #275633 | Story | AMS-GS IETMs: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
275641 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #275635 #318400
275640 |  | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #275643 #275635 #318400
275639 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #275636
275636 |  | Story | <Feature> IA Posture Assessment | Unassigned | Invalid | 0 | #275635 #318400
275634 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #275639
275610 | #262745 | Story | Feature 262745: Engineering IETM updates (Phase 4 NMS alarms) | Unassigned | Invalid | 0
275560 | #263333 | Story | Support SIT Team with Feature Demo for Module Provisioning Registration with Central GNH | Unassigned | Invalid | 0
275558 | #263333 | Story | Feature Demo - Customer Event - Module Provisioning Registration with Central GNH Feature | Unassigned | Invalid | 0
275519 | #255707 | Feature | Need to Describe use of Reprovision button in SAR Edit_Copy in IETM | Unassigned | Rejected
274106 | #274096 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #274098
274105 | #274096 | Story | <Feature 274096>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
274103 | #274096 | Story | <Feature 274096> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #274106 #274098
274102 | #274096 | Story | <Feature 274096>: IA Patching and STIGs | Unassigned | New | 8 | #274099
274101 | #274096 | Story | Feature 274096: Release Notes Inputs | Unassigned | New | 2 | #274098
274100 | #274096 | Story | Feature 274096: Engineering IETM updates | Unassigned | New | 3 | #274104
274099 | #274096 | Story | Feature 274096: IA Posture Assessment | Unassigned | New | 8 | #274098
274098 | #274096 | Story | Feature Demo – Customer Demo Event - Feature 274096 | Unassigned | New | 1 | #274105
274097 | #274096 | Story | Feature 274096: IA Posture Assessment - development input | Unassigned | New | 2 | #274102
274096 | #245569 | Feature | Better Splunk user account 2-factor authentication solution | Unassigned | Draft
274077 | #274067 | Story | Feature Demo – System Test, STCD development and Demo Prep - Splunk Infra SIEM | Unassigned | New | 5 | #274069
274076 | #274067 | Story | Splunk Infra SIEM: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
274075 | #274067 | Story | Splunk Infra SIEM: ILS IETM updates | Unassigned | New | 3 | #274069
274074 | #274067 | Story | Splunk Infra SIEM: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 5 | #274069 #274077
274073 | #274067 | Story | Splunk Infra SIEM: IA Patching and STIGs | Unassigned | New | 5 | #274070
274072 | #274067 | Story | Splunk Infra SIEM: Release Notes Inputs | Unassigned | New | 1 | #274069
274071 | #274067 | Story | Splunk Infra SIEM: Engineering IETM updates | Unassigned | New | 3 | #274075
274070 | #274067 | Story | Splunk Infra SIEM: IA Posture Assessment | Unassigned | New | 5 | #274069
274069 | #274067 | Story | Feature Demo – Customer Demo Event - Splunk Infra SIEM | Unassigned | New | 1 | #274076
274068 | #274067 | Story | Splunk Infra SIEM: IA Posture Assessment - development input | Unassigned | New | 1 | #274073
274067 | #217379 | Feature | Splunk Infra: SIEM Standard Collectors | Unassigned | Approved
274045 | #274035 | Story | Feature Demo – System Test, STCD development and Demo Prep - Splunk Infra Secure SSH | Unassigned | New | 5 | #274037
274044 | #274035 | Story | Splunk Infra Secure SSH: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
274043 | #274035 | Story | Splunk Infra Secure SSH: ILS IETM updates | Unassigned | New | 1 | #274037
274042 | #274035 | Story | Splunk Infra Secure SSH: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 5 | #274045 #274037
274041 | #274035 | Story | Splunk Infra Secure SSH: IA Patching and STIGs | Unassigned | New | 5 | #274038
274040 | #274035 | Story | Splunk Infra Secure SSH: Release Notes Inputs | Unassigned | New | 1 | #274037
274039 | #274035 | Story | Splunk Infra Secure SSH: Engineering IETM updates | Unassigned | New | 1 | #274043
274038 | #274035 | Story | Splunk Infra Secure SSH: IA Posture Assessment | Unassigned | New | 5 | #274037
274037 | #274035 | Story | Feature Demo – Customer Demo Event - Splunk Infra Secure SSH | Unassigned | New | 1 | #274044
274036 | #274035 | Story | Splunk Infra Secure SSH: IA Posture Assessment - development input | Unassigned | New | 2 | #274041
274035 | #217379 | Feature | Splunk Infra: Secure SSH | Unassigned | Approved |  | #273909
274024 |  | Story | Feature 274014: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #274016
274022 |  | Story | Feature 274014: ILS IETM updates | Unassigned | Invalid | 0 | #274016
274021 |  | Story | Feature 274014: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #274016 #274024
274019 |  | Story | Feature 274014: Release Notes Inputs | Unassigned | Invalid | 0 | #274016
274016 |  | Story | Feature 274014: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #274023
274014 | #216364 | Feature | Add/update IETM alarm recovery procedures for alarms added to whitelist filter in PI-5 and PI-6 (part 1 of 2) | Unassigned | Rejected |  | #294333
273972 | #257554 | Story | Provide AWARE O-Level IETMs: IA Posture Assessment | Unassigned | Invalid | 0
273955 |  | Story | Provide AWARE O-Level IETMs: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #273929
273950 |  | Story | Provide AWARE O-Level IETMs: IA Patching and STIGs | Unassigned | Invalid | 0 | #273972
273943 |  | Story | Provide AWARE O-Level IETMs: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #273950
273942 | #273932 | Story | Feature Demo – System Test, STCD development and Demo Prep - Splunk Infra Domain Accounts | Unassigned | New | 5 | #273934
273941 | #273932 | Story | Splunk Infra Domain Accounts: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
273939 | #273932 | Story | Splunk Infra Domain Accounts: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 3 | #273942 #273934
273938 | #273932 | Story | Splunk Infra Domain Accounts: IA Patching and STIGs | Unassigned | New | 5 | #273935
273937 | #273932 | Story | Splunk Infra Domain Accounts: Release Notes Inputs | Unassigned | New | 1 | #273934
273936 | #273932 | Story | Splunk Infra Domain Accounts: Engineering IETM updates | Unassigned | New | 2 | #273940
273935 | #273932 | Story | Splunk Infra Domain Accounts: IA Posture Assessment | Unassigned | New | 5 | #273934
273934 | #273932 | Story | Feature Demo – Customer Demo Event - Splunk Infra Domain Accounts | Unassigned | New | 1 | #273941
273933 | #273932 | Story | Splunk Infra Domain Accounts: IA Posture Assessment - development input | Unassigned | New | 2 | #273938
273932 | #217379 | Feature | Splunk Infra: Domain Account Support & Password Enforcement | Unassigned | Approved |  | #273909
273930 | #257554 | Story | Provide AWARE O-Level IETMs: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
273919 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - Splunk Infra IETM Updates & Sparing Analysis | Unassigned | Invalid | 0 | #273911
273905 | #266537 | Task | David F to update Story 266537 | Unassigned | Done
273850 | #275886 | Story | Give status if MultiHAL Scenarios is less than 5 minutes (Web page indicator and Email Notification) | Unassigned | New | 5
273848 | #275886 | Story | Create a configuration file to be used by the MultiHAL Scheduler and Archive Nightly | Unassigned | New | 5
273844 | #275886 | Story | Archive Nightly: Delete old Log files from the MH_Logs Directories after 2 weeks | Unassigned | New | 2
273839 | #275886 | Story | Move functionality to restart MultiHAL from Process Monitor to MultiHAL Scheduler | Unassigned | New | 5
273806 |  | Story | Feature 273666: Engineering IETM updates (other alarms) | Unassigned | Invalid | 0
273805 |  | Story | Feature 273666: Engineering IETM updates (major alarms) | Unassigned | Invalid | 0
273736 |  | Story | Create IA Posture Assessment for Investigate Module Provisioning Registraion with Central GNH | Unassigned | Invalid | 0
273728 |  | Story | Create Release Notes and Training Materials | Unassigned | Invalid | 0
273709 | #273690 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #273700
273708 | #273690 | Story | <Feature yyy> Completion of Base Electronic System Engineer Plan BESEP (needed 90 days prior to FRCB) | Unassigned | Invalid | 0 | #273700
273707 | #273690 | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
273706 | #273690 | Story | <Feature yyy>: IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #273693
273705 | #273690 | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #273704
273704 | #273690 | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #273700
273703 | #273690 | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #273709 #273700
273702 | #273690 | Story | <Feature yyy>: Release Notes Inputs | Unassigned | Invalid | 0 | #273700
273701 | #273690 | Story | <Feature yyy> IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #273700
273700 | #273690 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #273698 #273707
273699 | #273690 | Story | <Feature yyy>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #273706
273698 | #273690 | Story | <Feature yyy> Test Report, needed 30 days prior to FRCB. | Unassigned | Invalid | 0
273697 | #273690 | Story | <Feature yyy> Complete System Operational Verification Test, SOVT, needed 60 days prior to FRCB | Unassigned | Invalid | 0 | #273700
273696 | #273690 | Story | <Feature yyy> System Operational Verification Test, SOVT, Test Inputs for Feature | Unassigned | Invalid | 0 | #273697
273695 | #273690 | Story | <Feature yyy> ILS Create red lines Hardware drawings submitted for IDP | Unassigned | Invalid | 0 | #273692
273694 | #273690 | Story | <Feature yyy> ILS Define Power Consumption Changes for IDP | Unassigned | Invalid | 0 | #273692
273693 | #273690 | Story | <Feature yyy> IA Patching and STIGs 2nd round for IA Freshness | Unassigned | Invalid | 0 | #273701
273692 | #273690 | Story | <Feature yyy> Completion of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0 | #273700
273691 | #273690 | Story | <Feature yyy>: ILS Considerations (non-IETM) | Unassigned | Invalid | 0 | #273700
273690 |  | Feature | <Feature yyy> HW/FRCB Deployable Feature | Unassigned | Rejected
273689 | #273679 | Story | Feature Demo – System Test, STCD development and Demo Prep - Splunk Infra Fault Management | Unassigned | New | 5 | #273681
273688 | #273679 | Story | Splunk Infra Fault Management: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
273686 | #273679 | Story | Splunk Infra Fault Management: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 8 | #273689 #273681
273685 | #273679 | Story | Splunk Infra Fault Management: IA Patching and STIGs | Unassigned | New | 5 | #273682
273684 | #273679 | Story | Splunk Infra Fault Management: Release Notes Inputs | Unassigned | New | 1 | #273681
273683 | #273679 | Story | Feature 273679: Splunk Infra Fault Management: Engineering IETM updates | Unassigned | New | 5 | #273687
273682 | #273679 | Story | Splunk Infra Fault Management: IA Posture Assessment | Unassigned | New | 1 | #273681
273681 | #273679 | Story | Feature Demo – Customer Demo Event - Splunk Infra Fault Management | Unassigned | New | 1 | #273688
273680 | #273679 | Story | Splunk Infra Fault Management: IA Posture Assessment - development input | Unassigned | New | 2 | #273685
273679 | #217379 | Feature | Splunk Infra Fault Management | Unassigned | Approved
273676 |  | Story | Feature 273666: Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #273668
273674 |  | Story | Feature 273666:ILS IETM updates | Unassigned | Invalid | 0 | #273668
273673 |  | Story | Feature 273666: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #273668 #273676
273671 |  | Story | Feature 273666: Release Notes Inputs | Unassigned | Invalid | 0 | #273668
273670 |  | Story | Feature 273666: Engineering IETM updates (critical alarms) | Unassigned | Invalid | 0 | #273674
273668 |  | Story | Feature 273666: Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #273675
273359 | #281276 | Story | Research Abstractions for Site Alignment Section 6 | Unassigned | Invalid | 0
273179 |  | Task | SNMP Agent Error - REMOVE | Unassigned | Done
273171 |  | Task | INC000002504018: NW - NWTISMUX2 - cp3240CompositeSyncBad - REMOVE | Unassigned | Done
273079 |  | Task | INC000002442391: NW- Following Trap Alarms need to be added onto Whitelist | Unassigned | Done
273075 |  | Task | INC000002397221: WH- hp-Hlr-wh-ADS2, [111] SP clock is not synchronized with system time. | Unassigned | In Development
273071 |  | Task | INC000002324223: AU-AU- Several RNC alarms are not whitelisted - ADD | Unassigned | New
273017 |  | Story | GD Support of Zeta - EAD-7: Re-execute STCD | Unassigned | Invalid | 0
272825 | #232347 | Story | UX will complete all Help sections in the Wizard. | Unassigned | Invalid | 0
272819 |  | Task | PMW - Obtain Vulnerability information from the DIACAP POAM so that GD can ensure completeness of the findings carried over 263 | Unassigned | Invalid
272812 |  | Task | LM - Integrate DRAFT RAR from site data (provided by validator) with DRAFT RAR from GD | Unassigned | Invalid
272734 |  | Story | xx | Unassigned | Invalid | 0
272509 | #388154 | Feature | Design PPA UI Cleanup due to absent CDRs/PM/FM data | PI 16 - Candidate | Approved
272422 | #245437 | Feature | Show WCDMA performance/status across a region | Unassigned | Rejected
272421 | #272411 | Story | Feature Demo Retire Hyperion:– System Test, STCD development and Demo Prep | Unassigned | New | 1 | #272413
272420 | #272411 | Story | Retire Hyperion: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
272418 | #272411 | Story | Retire Hyperion: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 1 | #272421 #272413
272417 | #272411 | Story | Retire Hyperion: IA Patching and STIGs | Unassigned | New | 1 | #272414
272416 | #272411 | Story | Retire Hyperion: Release Notes Inputs | Unassigned | New | 1 | #272413
272415 | #272411 | Story | Feature 272411: Retire Hyperion: Engineering IETM updates | Unassigned | New | 5 | #272419
272414 | #272411 | Story | Retire Hyperion: IA Posture Assessment | Unassigned | New | 1 | #272413
272413 | #272411 | Story | Feature Demo – Customer Demo Event - Retire Hyperion | Unassigned | New | 1 | #272420
272412 | #272411 | Story | Retire Hyperion: IA Posture Assessment - development input | Unassigned | New | 1 | #272417
272411 | #245569 | Feature | Retire Hyperion from MUOS - PM | Unassigned | Approved
272409 | #272399 | Story | Feature Demo PPA UI Cleanup:– System Test, STCD development and Demo Prep | PI 16 | New | 3 | #272401
272408 | #272399 | Story | PPA UI Cleanup: Initiate CM PDO Processing for all CI's | PI 16 | New | 1
272407 | #272399 | Story | Feature 272399: PPA UI Cleanup: IETM Updates | PI 16 | New | 3 | #272401
272406 | #272399 | Story | PPA UI Cleanup: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | PI 16 | New | 5 | #272401 #272409
272405 | #272399 | Story | PPA UI Cleanup: IA Patching and STIGs | PI 16 | New | 1 | #272402
272404 | #272399 | Story | Feature 272399: PPA UI Cleanup: Release Notes Inputs | PI 16 | New | 2 | #272401
272403 | #272399 | Story | PPA UI Cleanup: Engineering IETM updates | PI 16 | New | 3 | #272407
272402 | #272399 | Story | PPA UI Cleanup: IA Posture Assessment | PI 16 | New | 2 | #272401
272401 | #272399 | Story | Feature Demo – Customer Demo Event - PPA UI Cleanup | PI 16 | New | 1 | #272408
272400 | #272399 | Story | PPA UI Cleanup: IA Posture Assessment - development input | PI 16 | New | 1 | #272405
272399 | #388154 | Feature | Implement PPA UI Cleanup due to absent CDRs/PM/FM data | PI 16 | Approved
272398 | #344196 | Story | MUOS Geolocation Support/Maintenance: Remove all legacy GEO nodes from TSM | Unassigned | Invalid | 0
272371 | #272361 | Story | Feature Demo – System Test, STCD development and Demo Prep - GD Support of Zeta | Unassigned | Invalid | 0 | #272363
272370 | #272361 | Story | GD Support of Zeta - EAD TBD: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
272369 | #272361 | Story | GD Support of Zeta - EAD TBD: ILS IETM updates | Unassigned | Invalid | 0 | #272363
272368 | #272361 | Story | GD Support of Zeta - EAD TBD: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #272363 #272371
272367 |  | Story | GD Support of Zeta - EAD TBD: IA Patching and STIGs | Unassigned | Invalid | 0 | #272364
272366 | #272361 | Story | GD Support of Zeta - EAD TBD: Release Notes Inputs | Unassigned | Invalid | 0 | #272363
272365 | #272361 | Story | GD Support of Zeta - EAD TBD: Engineering IETM updates | Unassigned | Invalid | 0 | #272369
272364 | #272361 | Story | GD Support of Zeta - EAD TBD: IA Posture Assessment | Unassigned | Invalid | 0 | #272363
272363 | #272361 | Story | Feature Demo – Customer Demo Event GD Support of Zeta - EAD TBD | Unassigned | Invalid | 0 | #272370
272362 |  | Story | GD Support of Zeta - EAD 10: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #272367
272361 | #217023 | Feature | GD Support of Zeta - EAD 10 High Priority Defect Resolution/UFO Table Updates | Unassigned | Rejected |  | #258337
272324 | #272314 | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 272314 | Unassigned | Invalid | 0 | #272316
272323 | #272314 | Story | Integrate NMS with AWARE: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
272322 | #272314 | Story | Integrate NMS with AWARE: ILS IETM updates | Unassigned | Invalid | 0 | #272316
272321 | #272314 | Story | Integrate NMS with AWARE: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #272316 #272324
272320 | #272314 | Story | Integrate NMS with AWARE: IA Patching and STIGs | Unassigned | Invalid | 0 | #272317
272319 | #272314 | Story | Integrate NMS with AWARE: Release Notes Inputs | Unassigned | Invalid | 0 | #272316
272318 | #272314 | Story | Integrate NMS with AWARE: Engineering IETM updates | Unassigned | Invalid | 0 | #272322
272317 | #272314 | Story | Integrate NMS with AWARE: IA Posture Assessment | Unassigned | Invalid | 0 | #272316
272316 | #272314 | Story | Feature Demo – Customer Demo Event - Feature 272314 | Unassigned | Invalid | 0 | #272323
272315 | #272314 | Story | Integrate NMS with AWARE: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #272320
272314 | #244386 | Feature | Integrate NMS software with AWARE Part 1 | Unassigned | Rejected
272281 |  | Story | Group ID Lookup Enhancements: IA Posture Assessment | Unassigned | Invalid | 0 | #272280
272255 |  | Story | DUPLICATE - WannaCry Samba post PI5 Configuration Items: IA Posture Assessment - development input - GIS | Unassigned | Invalid | 0
272247 |  | Story | Feature Demo – System Test, STCD development and Demo Prep - Feature 272237 | Unassigned | Invalid | 0 | #272239
272246 |  | Story | Feature 272237: Initiate CM PDO Processing for all CI's | Unassigned | Done | 0
272245 |  | Story | Feature TBD: IETM updates for Problem 272237 | Unassigned | Invalid | 0 | #272239
272244 |  | Story | Feature 272237: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #272247 #272239
272243 |  | Story | Feature 272237: IA Patching and STIGs | Unassigned | Done | 0 | #272240
272242 |  | Story | Feature 272237: Release Notes Inputs | Unassigned | Done | 0 | #272239
272241 |  | Story | Feature TBD: Engineering IETM updates for Problem 272237 | Unassigned | New | 3 | #272245
272240 |  | Story | Feature 272237: IA Posture Assessment | Unassigned | Done | 0 | #272239
272239 |  | Story | Feature Demo – Customer Demo Event - Feature 272237 | Unassigned | Invalid | 0 | #272246
272238 |  | Story | Feature 272237: IA Posture Assessment - development input | Unassigned | Done | 0 | #272243
272232 |  | Story | Feature Demo - System Test, STCD development and Demo Prep - WannaCry Samba post PI5 Configuration Items-INVALIDATED | Unassigned | Invalid | 0 | #272224
272231 |  | Story | INVALID WannaCry Samba post PI5 Configuration Items: Initiate CM PDO Processing for all CI's - HLR | Unassigned | Invalid | 0
272229 |  | Story | INVALID WannaCry Samba post PI5 Configuration Items: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) - HLR | Unassigned | Invalid | 0 | #272232 #272224
272228 |  | Story | INVALID WannaCry Samba post PI5 Configuration Items: IA Patching and STIGs - HLR | Unassigned | Invalid | 0
272223 |  | Story | INVALID WannaCry Samba post PI5 Configuration Items: IA Posture Assessment - development input - HLR | Unassigned | Invalid | 0 | #272228
272111 | #272101 | Story | Feature Demo – System Test, STCD development and Demo Prep: Prevent unauthorized users from running real time Splunk searches | Unassigned | New | 5 | #272103
272110 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
272109 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches:ILS IETM updates | Unassigned | New | 3 | #272103
272108 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #272111 #272103
272107 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches: IA Patching and STIGs | Unassigned | New | 8 | #272104
272106 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches: Release Notes Inputs | Unassigned | New | 2 | #272103
272105 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches Engineering IETM updates | Unassigned | New | 3 | #272109
272104 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches IA Posture Assessment | Unassigned | New | 8 | #272103
272103 | #272101 | Story | Feature Demo – Customer Demo Event: Prevent unauthorized users from running real time Splunk searches | Unassigned | New | 1 | #272110
272102 | #272101 | Story | Prevent unauthorized users from running real time Splunk searches: IA Posture Assessment - development input | Unassigned | New | 2 | #272107
272101 | #217043 | Feature | Prevent unauthorized users from running real time Splunk searches | Unassigned | Draft
271886 |  | Feature | Temporary feature to get stories to link to 254401 | Unassigned | Rejected
271884 | #271874 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #271876
271883 | #271874 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
271882 | #271874 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #271876
271881 | #271874 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #271876 #271884
271880 | #271874 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #271877
271879 | #271874 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #271876
271878 | #271874 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #271882
271877 | #271874 | Story | <Feature> IA Posture Assessment | Unassigned | Invalid | 0 | #271876
271876 | #271874 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #271883
271875 | #271874 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #271880
271874 |  | Feature | <Feature> | Unassigned | Rejected
271873 | #271863 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #271865
271872 | #271863 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
271871 | #271863 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #271865
271870 | #271863 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #271865 #271873
271869 | #271863 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #271866
271868 | #271863 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #271865
271867 | #271863 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #271871
271866 | #271863 | Story | <Feature> IA Posture Assessment | Unassigned | Invalid | 0 | #271865
271865 | #271863 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #271872
271864 | #271863 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #271869
271863 |  | Feature | <Feature> | Unassigned | Rejected
271607 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
271603 | #271600 | Story | Update Documentation/Plan for FM Whitelist Phases and Review Process | Unassigned | Invalid | 0
271599 | #271549 | Story | Prepare Training Materials for "Specialist" Role | Unassigned | Invalid | 0
271574 | #265600 | Task | Dan to send sharepoint link to Anjalee and Terri | Unassigned | Done
271394 |  | Task | PMW/Validator to provide GD/LM guidance from SCA for conducting RAR Risk Assessment | Unassigned | Invalid
271352 | #216718 | Feature | Determine best gain reduction to reduce Hadamard transform clipping | Unassigned | Approved
270860 |  | Story | AWARE 1a Fixes: Clean-up SVD Redlines (5.2) - DUPLICATE | Unassigned | Invalid | 0
270812 |  | Task | Preliminary AWARE alarm information for the "Implement AWARE Alarms/Events" Feature (#265267) | Unassigned | Invalid
270707 | #270631 | Story | Feature 270631: HBSS FM SVD Updates | Unassigned | New | 5
270705 | #270631 | Story | Feature 270631: HBSS FM Configuration on ePO Servers | Unassigned | New | 3
270703 | #270631 | Story | Feature 270631: HBSS FM MIB Rules Design | Unassigned | New | 3
270702 | #270631 | Story | Feature 270631: HBSS Integrate SIEM with HBSS | Unassigned | New | 3
270694 |  | Task | Preliminary AWARE alarm information for the "Implement AWARE Alarms/Events" Feature (#265267) | Unassigned | Invalid
270641 | #270631 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #270633
270640 | #270631 | Story | Feature 270631: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
270639 | #270631 | Story | Feature 270631:ILS IETM updates | Unassigned | New | 3 | #270633
270638 | #270631 | Story | Feature 270631: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 8 | #270641 #270633
270637 | #270631 | Story | Feature 270631: IA Patching and STIGs | Unassigned | New | 3 | #270634
270636 | #270631 | Story | Feature 270631: Release Notes Inputs | Unassigned | New | 2 | #270633
270635 | #270631 | Story | Feature 270631: Engineering IETM updates | Unassigned | New | 3 | #270639
270634 | #270631 | Story | Feature 270631: IA Posture Assessment | Unassigned | New | 3 | #270633
270633 | #270631 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #270640
270632 | #270631 | Story | Feature 270631: IA Posture Assessment - development input | Unassigned | New | 2 | #270637
270480 |  | Story | Investigate RNC status after a board replacement procedure is performed | Unassigned | Invalid | 0
270371 | #270361 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #270363
270370 | #270361 | Story | <Feature 270361>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
270369 | #270361 | Story | Feature 270361: IETM updates for RNC - RNH sends cellAvailableInd to GNH when op_state is disabled | Unassigned | Invalid | 0 | #270363
270368 | #270361 | Story | <Feature 270361> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #270371 #270363
270367 | #270361 | Story | <Feature 270361>: IA Patching and STIGs | Unassigned | Invalid | 0 | #270364
270366 | #270361 | Story | <Feature 270361>: Release Notes Inputs | Unassigned | Invalid | 0 | #270363
270365 | #270361 | Story | <Feature 270361> Engineering IETM updates | Unassigned | Invalid | 0 | #270369
270364 | #270361 | Story | RNC - RNH sends cellAvailableInd: IA Posture Assessment | Unassigned | Invalid | 0 | #270363
270363 | #270361 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #270370
270362 | #270361 | Story | <Feature 270361>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #270367
270356 | #270346 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | New | 5 | #270348
270355 | #270346 | Story | <Feature 270346>: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
270353 | #270346 | Story | <Feature 270346> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | New | 13 | #270356 #270348
270352 | #270346 | Story | <Feature 270346>: IA Patching and STIGs | Unassigned | New | 8 | #270349
270351 | #270346 | Story | <Feature 270346>: Release Notes Inputs | Unassigned | New | 2 | #270348
270350 | #270346 | Story | <Feature 270346> Engineering IETM updates | Unassigned | New | 3 | #270354
270349 | #270346 | Story | RNC: GSLN Preemption: IA Posture Assessment | Unassigned | New | 8 | #270348
270348 | #270346 | Story | Feature Demo – Customer Demo Event | Unassigned | New | 1 | #270355
270347 | #270346 | Story | <Feature 270346>: IA Posture Assessment - development input | Unassigned | New | 2 | #270352
270064 | #270055 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
270063 | #270055 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #270057
270062 | #270055 | Story | <Feature xxx> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #270065 #270057
270061 | #270055 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #270058
270059 | #270055 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #270063
270058 | #270055 | Story | Update Count-C Usage: IA Posture Assessment | Unassigned | Invalid | 0 | #270057
269872 | #267955 | Task | Add Acceptance Criteria - 267955 | Unassigned | Done
269870 | #234556 | Task | Please add acceptance criteria - 234556 | Unassigned | Done
269328 |  | Story | Evaluate Field Failure from NW | Unassigned | Invalid | 0
269308 | #216568 | Story | Evaluate Cover Rekey Failure Handling | Unassigned | Invalid | 0
269165 |  | Task | PMW/Validator to review FINAL RAR | Unassigned | Invalid
269163 |  | Task | PMW/Validator to review INTERIM RAR | Unassigned | Invalid
269162 |  | Task | PMW/Validator to review DRAFT RAR | Unassigned | Invalid
269157 |  | Task | PMW/Validator to validate INTERIM POAM (generated by GD from the INTERIM RARs) | Unassigned | Invalid
269153 |  | Task | PMW/Validator to review and update draft RAR for the DIACAP POAM findings covering the delta STIG checks | Unassigned | Invalid
269133 |  | Task | PMW (Brian Fredericks)- Linux ACAS Laptop high side workbook creation and analysis | Unassigned | Invalid
269129 |  | Task | PMW/Validator review of ACAS results for workbooks & associated RAR developed from the ACAS Scans for all Component Groups (both low & high side) | Unassigned | Invalid
269109 |  | Story | AWARE to NMF: Update functional block diagram with WH AWARE connectivity to NMF-INVALIDATED | Unassigned | Invalid | 0
269102 |  | Story | AWARE 1a Fixes: Update & install AWARE server and VM with patches-INVALIDATED | Unassigned | Invalid | 0
269101 |  | Story | AMS-GS Phase 1: Prep Work for AMS-GS Deployment - INVALIDATE | Unassigned | Invalid | 0
269100 |  | Story | AWARE to NMF: Update AWARE server SVD VLAN connection for NMF connection-INVALIDATED | Unassigned | Invalid | 0
269099 |  | Story | AWARE to NMF: VLAB integration of connectivity-INVALIDATED | Unassigned | Invalid | 0
269098 |  | Story | AWARE to NMF: Integrate firewall changes in VLAB-INVALIDATED | Unassigned | Invalid | 0
269097 |  | Story | AWARE to NMF: Update WH firewall config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269096 |  | Story | AWARE to NMF: Update switch config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269095 |  | Story | AWARE to NMF: Update router config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269094 |  | Story | AWARE to NMF: Update functional block diagram with WH AWARE connectivity to NMF-INVALIDATED | Unassigned | Invalid | 0
269093 |  | Story | AWARE to NMF: Update NEBD to include IP updates for WH sites-INVALIDATED | Unassigned | Invalid | 0
269092 |  | Story | AWARE 1a Fixes: Update & install AWARE server and VM with patches-INVALIDATED | Unassigned | Invalid | 0
269091 |  | Story | AMS-GS Phase 1: Prep Work for AMS-GS Deployment-INVALIDATED | Unassigned | Invalid | 0
269090 |  | Story | AWARE to NMF: Update AWARE server SVD VLAN connection for NMF connection-INVALIDATED | Unassigned | Invalid | 0
269089 |  | Story | AWARE to NMF: VLAB integration of connectivity-INVALIDATED | Unassigned | Invalid | 0
269088 |  | Story | AWARE to NMF: Integrate firewall changes in VLAB-INVALIDATED | Unassigned | Invalid | 0
269087 |  | Story | AWARE to NMF: Update WH firewall config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269086 |  | Story | AWARE to NMF: Update switch config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269085 |  | Story | AWARE to NMF: Update router config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269084 |  | Story | AWARE to NMF: Update functional block diagram with WH AWARE connectivity to NMF-INVALIDATED | Unassigned | Invalid | 0
269083 |  | Story | AWARE to NMF: Update NEBD to include IP updates for WH sites-INVALIDATED | Unassigned | Invalid | 0
269082 |  | Story | AWARE 1a Fixes: Update & install AWARE server and VM with patches-INVALIDATED | Unassigned | Invalid | 0
269081 |  | Story | AMS-GS Phase 1: Prep Work for AMS-GS Deployment-INVALIDATED | Unassigned | Invalid | 0
269080 |  | Story | AWARE to NMF: Update AWARE server SVD VLAN connection for NMF connection-INVALIDATED | Unassigned | Invalid | 0
269079 |  | Story | AWARE to NMF: VLAB integration of connectivity-INVALIDATED | Unassigned | Invalid | 0
269078 |  | Story | AWARE to NMF: Integrate firewall changes in VLAB-INVALIDATED | Unassigned | Invalid | 0
269077 |  | Story | AWARE to NMF: Update WH firewall config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269076 |  | Story | AWARE to NMF: Update switch config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269075 |  | Story | AWARE to NMF: Update router config for AWARE NMF connectivity-INVALIDATED | Unassigned | Invalid | 0
269073 |  | Story | AWARE to NMF: Update NEBD to include IP updates for WH sites-INVALIDATED | Unassigned | Invalid | 0
268937 |  | Story | Feature 263009: Update SVDs for required third party software needed for workstations. | Unassigned | Invalid | 0
268928 |  | Story | Feature263009: Create Windows XP VM image | Unassigned | Invalid | 0
268870 | #318983 | Story | Auto - Call - MultiHAL's state machine debug log is empty [MUOSAT-00114] | Unassigned | Invalid | 0
268866 | #318983 | Story | Auto - Call - Fix AA_BB Retry condition behavior [MUOSAT-00134] | Unassigned | Invalid | 0
268855 | #253448 | Story | Auto - Call - MultiHAL Browser display should show last-known waveform version numbers for all radios [MUOSAT-00096] | Unassigned | Invalid | 0
268843 |  | Story | TR - Workstation Expansion: Identify Necessary Third Party Software | Unassigned | Invalid | 0
268842 | #216601 | Story | Provide NMS Support for OSSRC Interface Reliability Demo | Unassigned | Invalid | 0
268829 | #262134 | Story | Provide RAN Support to Lab Users | Unassigned | Invalid | 0
268785 | #263333 | Story | Install, Execute STCD, and Verify PCR for CGNH module registration | Unassigned | Invalid | 0
268752 |  | Feature | Investigate the addition of a CDR triggered by the UE's ranging message | Unassigned | Rejected
268712 |  | Story | Not needed (duplicate) | Unassigned | Invalid | 0
268707 | #245573 | Feature | Investigate how to detect when UE is gone and release resources | Unassigned | Analyzing
268624 |  | Story | RMF: Convert MFR POAM items from EAD1-EAD4 to RMF POAM - part 2 | Unassigned | Invalid | 0
268572 |  | Story | Call Bank Log Analysis and Issue Support | Unassigned | Invalid | 0
268515 |  | Feature | Reject: Maintain Call Banks Strings | Unassigned | Rejected
268472 |  | Story | RMF: Convert MFR POAM items from EAD1-EAD4 to RMF POAM | Unassigned | Invalid | 0
268448 | #265929 | Story | RTL testing performed in GD lab | Unassigned | Invalid | 0
268382 |  | Feature | Coordinate and complete non feature IETM content for EAD 6 | Unassigned | Rejected
268276 | #268266 | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0 | #268268
268275 | #268266 | Story | Workstation Expansion Phase 2: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
268274 | #268266 | Story | Workstation Expansion Phase 2: ILS IETM updates | Unassigned | Invalid | 0 | #268268
268273 | #268266 | Story | Workstation Expansion Phase 2: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #268276 #268268
268272 | #268266 | Story | Workstation Expansion Phase 2: IA Patching and STIGs | Unassigned | Invalid | 0 | #268269
268271 | #268266 | Story | Workstation Expansion Phase 2: Release Notes Inputs | Unassigned | Invalid | 0 | #268268
268270 | #268266 | Story | Workstation Expansion Phase 2: Engineering IETM updates | Unassigned | Invalid | 0 | #268274
268269 | #268266 | Story | Workstation Expansion Phase 2: IA Posture Assessment | Unassigned | Invalid | 0 | #268268
268268 | #268266 | Story | Feature Demo – Customer Demo Event | Unassigned | Invalid | 0 | #268275
268267 | #268266 | Story | Workstation Expansion Phase 2: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #268272
268266 | #246826 | Feature | Workstation Expansion Phase 2B | Unassigned | Rejected
268237 |  | Story | Support ILS coordinate, plan, and establish site alignment activity for 2018 - INVALIDATED | Unassigned | Invalid | 0
268210 |  | Story | Post Deployment Redlines for SVD, etc. - INVALIDATED | Unassigned | Invalid | 0
268206 |  | Story | Develop & Support ADNS Testing w/SSC PAC - INVALIDATED | Unassigned | Invalid | 0
268205 |  | Story | AMS-GS Phase 1: Deployment Support | Unassigned | Invalid | 0
268199 |  | Story | Develop & Support ADNS Testing between GD VLAB and SSC PAC | Unassigned | Invalid | 0
268140 |  | Story | Fix Prod Rack Radio - INVALIDATED | Unassigned | Invalid | 0
268112 |  | Story | A&A ScrumMaster Housekeeping (EA 6.5) | Unassigned | Invalid | 0
268111 |  | Story | A&A ScrumMaster Housekeeping - PI 07 | Unassigned | Invalid | 0
268110 |  | Story | A&A ScrumMaster Housekeeping - PI 06 | Unassigned | Invalid | 0
268109 |  | Story | A&A ScrumMaster Housekeeping (EA 6.2) | Unassigned | Invalid | 0
268105 | #268097 | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0 | #268100
268104 | #268097 | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0 | #268103
268103 | #268097 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #268099
268102 | #268097 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #268099
268101 | #268097 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #268099
268100 | #268097 | Story | <Feature> IA Posture Assessment | Unassigned | Invalid | 0 | #268099
268099 | #268097 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #241247
268098 | #268097 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #268105
268097 |  | Feature | <Feature ...> | Unassigned | Rejected
268096 |  | Feature | Adjust RRC Delay Responses | Unassigned | Rejected
268074 |  | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
268073 |  | Story | <Feature xxx>: IA Patching and STIGs | Unassigned | Invalid | 0
268072 |  | Story | <Feature xxx> Engineering IETM updates | Unassigned | Invalid | 0
268071 |  | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0
268070 |  | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0
268069 |  | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0
268068 |  | Story | <Feature> IA Posture Assessment | Unassigned | Invalid | 0
268067 |  | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0
268066 |  | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0
268041 |  | Story | V-Lab Power Up - Chris M. (5.1) | Unassigned | Invalid | 0
267946 |  | Story | GD Support of Zeta - EAD 7: Zeta User Guide Updates - INVALIDATED | Unassigned | Invalid | 0
267898 | #262134 | Feature | Not needed | Unassigned | Rejected
267884 | #262134 | Feature | Not needed. | Unassigned | Rejected
267814 | #267777 | Story | Featute 267777: Add Auto Alarm Clear Logic and Event IDs to Netcool rules file for TFDU - Development | Unassigned | New | 13
267786 | #267777 | Story | Feature 267777: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
267785 | #267777 | Story | Feature 267777: IA Patching and STIGs | Unassigned | New | 1 | #267780
267784 | #267777 | Story | Feature 267777: Engineering IETM updates | Unassigned | New | 3 | #267783
267783 | #267777 | Story | Feature 267777: ILS IETM updates | Unassigned | New | 3 | #267779
267782 | #267777 | Story | Feature 267777: Development Team Test Inputs | Unassigned | New | 5 | #267779
267781 | #267777 | Story | Feature 267777: Release Notes Inputs | Unassigned | New | 1 | #267779
267780 | #267777 | Story | Feature 267777: IA Posture Assessment | Unassigned | New | 1 | #267779
267779 | #267777 | Story | Feature Demo - Feature 267777 | Unassigned | New | 5 | #241247
267778 | #267777 | Story | Feature 267777: IA Posture Assessment - development input | Unassigned | New | 1 | #267785
267777 | #216351 | Feature | Add Auto Alarm Clear Logic and Event IDs to Netcool rules file for TFDU | Unassigned | Approved
267673 | #267568 | Feature | Provide Recommendations Based on Pareto Outcomes | Unassigned | Rejected
267669 | #267568 | Feature | Communicate Pareto Outcomes | Unassigned | Rejected
267665 | #267568 | Feature | Conduct Monthly Pareto Analysis | Unassigned | Rejected
267657 | #267568 | Feature | Conduct Weekly Consolidation of TOFF Data | Unassigned | Rejected
267611 |  | Feature | Add Auto Alarm Clear Logic to Netcool rules file for TFDU | Unassigned | Rejected
267608 | #267568 | Feature | Report Health Check Issues | Unassigned | Rejected
267594 | #267568 | Feature | Identify Health Check Issues | Unassigned | Rejected
267558 | #217152 | Feature | Implement Long Term Metrics Collection and Reporting Approach | Unassigned | Rejected
267486 |  | Story | A&A ScrumMaster Housekeeping (EA 6.1) | Unassigned | Invalid | 0
267465 | #262371 | Story | Perform ILS activities for NW De-ice | Unassigned | Invalid | 0
267325 | #225731 | Feature | Investigate Incorrect Generation of P2P Collection Interval Timeout CDRs | Unassigned | Approved
267297 |  | Task | LM - Site configuration delta report, based on ACAS results | Unassigned | Invalid
267296 |  | Task | LM - ACAS Analsysis based Draft, Interim and Final RAR Generation (High Side) | Unassigned | Invalid
267295 |  | Task | LM - ACAS Analysis based Draft, Interim and Final RAR Generation (Low Side) | Unassigned | Invalid
267292 |  | Task | xx | Unassigned | Invalid
267271 | #216649 | Feature | Investigate Failure of PDRs to Reestablish After Reset | Unassigned | Analyzing
267203 |  | Task | Test Feature | Unassigned | Invalid
267143 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
267142 |  | Story | Feature Demo – System Test, STCD development and Demo Prep | Unassigned | Invalid | 0
267101 |  | Task | create story boards | Unassigned | Invalid
267097 | #269354 | Story | Tools Team Sprint 4.5 Support | Unassigned | Invalid | 0
267024 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: Development and SVD Updates | Unassigned | New | 5
266999 |  | Story | <Feature yyy> ILS Development of Installation Design Plan IDP (red lines Hardware drawings submitted), needed 90 days prior to FRCB; | Unassigned | Invalid | 0
266983 | #262146 | Story | Need SME to evaluate VME PN# 01-P51759E002, SN# 110 (Duplicate of 242038) | Unassigned | Invalid | 0
266982 | #262146 | Story | Need SME to evaluate workstation PN# 01-P59186M001, SN# 2UA4212L7P (Duplicate of 239687) | Unassigned | Invalid | 0
266981 | #262146 | Story | Need SME to evaluate Digi Passport Console Server PN# 70002258, SN# W04601351 (Duplicate of 213825) | Unassigned | Invalid | 0
266979 | #262146 | Story | Need resource assigned to complete repair - SR Ref 833168 ( tied to 213825) - FRACAS G2368 - (Placeholder) | Unassigned | Invalid | 0
266977 | #262146 | Story | Need resource assigned to complete repair - SR Ref 817145 ( tied to 232506) - FRACAS G2326 (Placeholder) | Unassigned | Invalid | 0
266975 | #262146 | Story | Need resource assigned to complete repair - SR Ref 817138 ( tied to 232506) - FRACAS G2325 (Placeholder) | Unassigned | Invalid | 0
266962 | #266953 | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
266960 | #266953 | Story | <Feature yyy> Engineering IETM updates | Unassigned | Invalid | 0 | #266959
266959 | #266953 | Story | <Feature yyy>:IETM updates (Template for HW/FRCB Deployable Feature) | Unassigned | Invalid | 0 | #266955
266958 | #266953 | Story | <Feature yyy> Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #266955
266957 | #266953 | Story | <Feature yyy>: Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #266955
266955 | #266953 | Story | Feature Demo – Customer Demo Event - <Feature yyy> | Unassigned | Invalid | 0 | #266962
266954 | #266953 | Story | <Feature yyy>: IA Posture Assessment - Define Patch and STIG Requirements | Unassigned | Invalid | 0
266953 |  | Feature | <Feature yyy> HW/FRCB Deployable Feature | Unassigned | Rejected
266942 | #247198 | Task | BArry to update the acceptance criteria 247198 | Unassigned | Done
266927 |  | Story | Training: AWARE 3-day roll-up reporting | Unassigned | Invalid | 0
266781 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
266780 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: IA Patching and STIGs | Unassigned | New | 8 | #266775
266779 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: Engineering IETM updates | Unassigned | New | 3 | #266778
266778 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: ILS IETM updates | Unassigned | New | 3 | #266774
266777 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: Development Team Test Inputs | Unassigned | New | 3 | #266774
266776 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: Release Notes Inputs | Unassigned | New | 2 | #266774
266775 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: IA Posture Assessment | Unassigned | New | 8 | #266774
266774 | #266772 | Story | Feature Demo- for DMZ SIPRNET Router Changes from DISA | Unassigned | New | 5 | #241247
266773 | #266772 | Story | DMZ SIPRNET Router Changes from DISA: IA Posture Assessment - development input | Unassigned | New | 2 | #266780
266772 | #243424 | Feature | DMZ SIPRNET Router Changes from DISA | Unassigned | Analyzing
266428 | #266419 | Story | Additional AWARE 1a Fixes: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
266427 | #266419 | Story | Additional AWARE 1a Fixes: IA Patching and STIGs | Unassigned | Invalid | 0 | #266422
266426 | #266419 | Story | Additional AWARE 1a Fixes: Engineering IETM updates | Unassigned | Invalid | 0 | #266425
266425 | #266419 | Story | Additional AWARE 1a Fixes: ILS IETM updates | Unassigned | Invalid | 0 | #266421
266424 | #266419 | Story | Additional AWARE 1a Fixes: Development Team Test Inputs | Unassigned | Invalid | 0 | #266421
266423 | #266419 | Story | Additional AWARE 1a Fixes: Release Notes Inputs | Unassigned | Invalid | 0 | #266421
266422 | #266419 | Story | Additional AWARE 1a Fixes: IA Posture Assessment | Unassigned | Invalid | 0 | #266421
266421 | #266419 | Story | Feature Demo - Customer Event - Additional AWARE 1a Fixes | Unassigned | Invalid | 0 | #241247
266420 | #266419 | Story | Additional AWARE 1a Fixes: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #266427
266419 |  | Feature | Placeholder: Fix additional AWARE Phase 1a items | Unassigned | Rejected
266406 |  | Story | System Test: Add/update IETM alarm recovery procedures for ET LBIP alarms | Unassigned | Invalid | 0
266405 |  | Story | System Test: Add/update IETM alarm recovery procedures for ET TFDU alarms | Unassigned | Invalid | 0
266399 | #243511 | Feature | SME Support for OPLAN Gap Analysis | Unassigned | Rejected
266390 |  | Story | RMF ASD STIG assess: 98-P59418M NM OSS-RC Interface - Analysis | Unassigned | Invalid | 0
266209 | #267558 | Story | Identify CRM data to automatically pull into metrics spreadsheet | Unassigned | Invalid | 0
266207 | #267558 | Story | Create tools to import CRM incident data into incident spreadsheet | Unassigned | Invalid | 0
266203 | #243427 | Feature | DMZ SIPRNET Router Interface Changes from DISA **OBSOLETE | Unassigned | Rejected
266198 | #243505 | Story | Stabilize Veritas backup system - Part 3 | Unassigned | Invalid | 0
266163 | #232017 | Story | RBS: As a Release Manager, I need the RBS load module release process implemented in the new incremental build process | Unassigned | New | 5
266160 | #232017 | Story | RBS:: As a Release Manager I need to extract the logic from Buildforge for creating RBS load module release Package | Unassigned | New | 5
266156 | #232017 | Story | RBS: As a Release Manager I need to extract the logic from Buildforge for creating RBS load module release Package | Unassigned | New | 5
266118 | #266109 | Story | Remove Splunk dependency on Call Banks: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
266117 | #266109 | Story | Remove Splunk dependency on Call Banks: IA Patching and STIGs | Unassigned | Invalid | 0 | #266112
266116 | #266109 | Story | Remove Splunk dependency on Call Banks: Engineering IETM updates | Unassigned | Invalid | 0 | #266115
266115 | #266109 | Story | Feature 266109: Remove Splunk dependency on Call Banks: IETM updates | Unassigned | Invalid | 0 | #266111
266114 | #266109 | Story | Remove Splunk dependency on Call Banks: Development Team Test Inputs | Unassigned | Invalid | 0 | #266111
266113 | #266109 | Story | Feature 266109: Remove Splunk dependency on Call Banks: Release Notes Inputs | Unassigned | Invalid | 0 | #266111
266112 | #266109 | Story | Remove Splunk dependency on Call Banks: IA Posture Assessment | Unassigned | Invalid | 0 | #266111
266111 | #266109 | Story | Feature Demo - Remove Splunk dependency on Call Banks | Unassigned | Invalid | 0 | #241247
266110 | #266109 | Story | Remove Splunk dependency on Call Banks: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #266117
266078 | #224658 | Story | Update Samba version on NMS CIs | Unassigned | Invalid | 0
266076 |  | Story | xx | Unassigned | Invalid | 0
266074 |  | Story | xx | Unassigned | Invalid | 0
266072 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations INTERIM POAM artifact generation - Integrate Workbook data into POAM GROUP 4 | Unassigned | Invalid | 0
266067 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations DRAFT POAM artifact generation - Integrate Workbook data into POAM GROUP 4 | Unassigned | Invalid | 0
266066 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations DRAFT POAM artifact generation - Integrate Workbook data into POAM GROUP 3 | Unassigned | Invalid | 0
266061 |  | Story | xx | Unassigned | Invalid | 0
266058 |  | Story | xx | Unassigned | Invalid | 0
266057 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Generate FINAL RAR from Workbook GROUP 1 | Unassigned | Invalid | 0
266026 | #262983 | Task | LM Compare site configurations using ACAS scan results | Unassigned | Invalid
265982 | #247890 | Story | Feature Demo- for Feature 247890 | Unassigned | Invalid | 0
265965 |  | Story | V-Lab Power Up - Chris (5.1) | Unassigned | Invalid | 0
265915 | #265531 | Story | Enable COTS Alarms and integrate into NetCool | Unassigned | New | 8
265856 | #265848 | Story | Feature 265848: Engineering IETM updates | Unassigned | Invalid | 0 | #265855
265855 | #265848 | Story | Feature 265848:ILS IETM updates | Unassigned | Invalid | 0 | #265850
265780 |  | Story | Confirm Laptop can install radio files (Unvalidated) | Unassigned | Invalid | 0
265776 | #264321 | Story | Placeholder of 4 of 4 points for UX | Unassigned | Invalid | 0
265775 | #264321 | Story | Placeholder of 2 of 4 points for UX | Unassigned | Invalid | 0
265748 |  | Story | xx | Unassigned | Invalid | 0
265742 |  | Story | xx | Unassigned | Invalid | 0
265677 | #265531 | Story | AMS-GS NMS SVD Updates | Unassigned | New | 5
265618 | #233338 | Story | Enhance the "alarm tracker" tool to automate daily snapshots against current white/black lists - Preliminary work | Unassigned | New | 0
265610 |  | Story | Feature Demo - Customer Event - ETT SVD Release - INVALID | Unassigned | Invalid | 0
265580 |  | Feature | Release AWARE Phase 1a Fixes | Unassigned | Rejected
265571 | #261491 | Story | 6.2 STR RMF Step 4 - RMF Security Assessment Report (SAR) artifact generation (GD support to Validator) - Stretch Story (2 of 2) | Unassigned | Invalid | 0
265570 | #261491 | Story | 6.1 STR RMF Step 4 - RMF Security Assessment Report (SAR) artifact generation (GD support to Validator) - Stretch Story (1 of 2) | Unassigned | Invalid | 0
265569 |  | Story | 5.3 STR RMF Step 4 - RMF Security Assessment Report (SAR) artifact generation (GD support to Validator) - Stretch Story for Sprint 3 | Unassigned | Invalid | 0
265566 |  | Story | xx | Unassigned | Invalid | 0
265565 |  | Story | xx | Unassigned | Invalid | 0
265564 |  | Story | xx | Unassigned | Invalid | 0
265562 |  | Story | xx | Unassigned | Invalid | 0
265561 |  | Story | xx | Unassigned | Invalid | 0
265560 |  | Story | xx | Unassigned | Invalid | 0
265559 |  | Story | xx | Unassigned | Invalid | 0
265558 |  | Story | xx | Unassigned | Invalid | 0
265557 |  | Story | xx | Unassigned | Invalid | 0
265556 |  | Story | xx | Unassigned | Invalid | 0
265555 |  | Story | xx | Unassigned | Invalid | 0
265554 |  | Story | xx | Unassigned | Invalid | 0
265553 |  | Story | xx | Unassigned | Invalid | 0
265552 |  | Story | xx | Unassigned | Invalid | 0
265551 |  | Story | xx | Unassigned | Invalid | 0
265550 |  | Story | xx | Unassigned | Invalid | 0
265549 |  | Story | xx | Unassigned | Invalid | 0
265548 |  | Story | xx | Unassigned | Invalid | 0
265535 |  | Story | xx | Unassigned | Invalid | 0
265533 |  | Story | xx | Unassigned | Invalid | 0
265532 |  | Story | xx | Unassigned | Invalid | 0
265530 |  | Story | xx | Unassigned | Invalid | 0
265529 |  | Story | xx | Unassigned | Invalid | 0
265527 |  | Story | xx | Unassigned | Invalid | 0
265526 |  | Story | xx | Unassigned | Invalid | 0
265525 |  | Story | xx | Unassigned | Invalid | 0
265524 |  | Story | xx | Unassigned | Invalid | 0
265520 |  | Story | xx | Unassigned | Invalid | 0
265519 |  | Story | xx | Unassigned | Invalid | 0
265518 |  | Story | xx | Unassigned | Invalid | 0
265516 |  | Story | xx | Unassigned | Invalid | 0
265515 |  | Story | xx | Unassigned | Invalid | 0
265509 |  | Story | xx | Unassigned | Invalid | 0
265508 |  | Story | xx | Unassigned | Invalid | 0
265507 |  | Story | xx | Unassigned | Invalid | 0
265503 |  | Story | xx | Unassigned | Invalid | 0
265500 |  | Story | xx | Unassigned | Invalid | 0
265499 |  | Story | xx | Unassigned | Invalid | 0
265498 |  | Story | xx | Unassigned | Invalid | 0
265497 |  | Story | xx | Unassigned | Invalid | 0
265496 |  | Story | xx | Unassigned | Invalid | 0
265493 |  | Story | xx | Unassigned | Invalid | 0
265490 |  | Story | xx | Unassigned | Invalid | 0
265489 |  | Story | xx | Unassigned | Invalid | 0
265488 |  | Story | xx | Unassigned | Invalid | 0
265487 |  | Story | xx | Unassigned | Invalid | 0
265486 |  | Story | xx | Unassigned | Invalid | 0
265485 |  | Story | xx | Unassigned | Invalid | 0
265484 |  | Story | xx | Unassigned | Invalid | 0
265483 |  | Story | xx | Unassigned | Invalid | 0
265482 |  | Story | xx | Unassigned | Invalid | 0
265481 |  | Story | xx | Unassigned | Invalid | 0
265480 |  | Story | xx | Unassigned | Invalid | 0
265478 |  | Story | xx | Unassigned | Invalid | 0
265476 |  | Story | xx | Unassigned | Invalid | 0
265475 |  | Story | xx | Unassigned | Invalid | 0
265474 |  | Story | xx | Unassigned | Invalid | 0
265473 |  | Story | xx | Unassigned | Invalid | 0
265472 |  | Story | xx | Unassigned | Invalid | 0
265471 |  | Story | xx | Unassigned | Invalid | 0
265470 |  | Story | xx | Unassigned | Invalid | 0
265468 |  | Story | xx | Unassigned | Invalid | 0
265467 |  | Story | xx | Unassigned | Invalid | 0
265466 |  | Story | xx | Unassigned | Invalid | 0
265459 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate and deliver unclassified maintenance POAM to customer | Unassigned | Invalid | 0
265458 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate Operations/Management RAR into RMF POAM | Unassigned | Invalid | 0
265453 |  | Story | RMF Step 4 - RMF Plan of Action and Mitigations (POAM) artifact generation - Integrate validators site visit results ino POAM | Unassigned | Invalid | 0
265431 | #267558 | Story | Define metrics database platform for long term use | Unassigned | Invalid | 0
265430 | #267558 | Story | Work with PMW-146 to add fields needed for metrics spreadsheet to ITSM | Unassigned | Invalid | 0
265429 | #267558 | Story | Create tools to import call bank data into Incident spreadsheet or database | Unassigned | Invalid | 0
265428 | #267558 | Story | Create tools to import daily log collection into database | Unassigned | Invalid | 0
265427 | #267558 | Story | Automate Metric report creation | Unassigned | Invalid | 0
265426 | #267558 | Story | Create first cut of long term metrics infrastructure | Unassigned | Invalid | 0
265424 | #267558 | Story | Identify metrics DB fields | Unassigned | Invalid | 0
265377 | #216631 | Story | Feature 216631: Add an acknowledgement message to the critical GMAP messages. - ILS IETM updates | Unassigned | Invalid | 0
265376 |  | Story | Feature 219443: Add/update IETM alarm recovery procedures for RBS alarms - IA Posture Assessment - development input | Unassigned | Invalid | 0
265375 |  | Story | Feature 219443: Add/update IETM alarm recovery procedures for RBS alarms -: IA Posture Assessment | Unassigned | Invalid | 0
265373 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms - Engineering IETM updates | Unassigned | Invalid | 0
265372 |  | Story | Feature 219443: Add/update IETM alarm recovery procedures for RBS alarms - Release Notes Inputs | Unassigned | Invalid | 0
265371 |  | Story | Feature 219443: Add/update IETM alarm recovery procedures for RBS alarms - IA Patching and STIGs | Unassigned | Invalid | 0
265369 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms - IA Posture Assessment - development input | Unassigned | Invalid | 0
265368 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms - IA Posture Assessment | Unassigned | Invalid | 0
265367 |  | Story | Feature 219438: Add/update IETM alarm recovery procedures for CORE/GIS alarms - Release Notes Inputs | Unassigned | Invalid | 0
265366 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms - IA Patching and STIGs | Unassigned | Invalid | 0
265365 |  | Story | Feature 219438: Add/update IETM alarm recovery procedures for CORE/GIS alarms - Development Team Test Inputs | Unassigned | Invalid | 0
265364 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms:ILS IETM updates | Unassigned | Invalid | 0
265363 |  | Story | Add/update IETM alarm recovery procedures for CORE/GIS alarms - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
265360 |  | Story | Complete Add/update IETM alarm recovery procedures for RNC alarms - Release Notes Inputs | Unassigned | Invalid | 0
265358 |  | Story | Feature 262904: Create Release Notes and Training Inputs | Unassigned | Invalid | 0
265357 | #233847 | Story | Feature 233847: Review ETISP & ERS whitelisted alarms (47 Alarms Total) | Unassigned | New | 13
265355 | #216567 | Story | Feature 216567: Improve RCG IA Posture for GD Controlled SW - ILS IETM updates | Unassigned | Invalid | 0
265354 | #216567 | Story | Feature 216567: Improve RCG IA Posture for GD Controlled SW - Engineering IETM updates | Unassigned | Invalid | 0
265350 | #246191 | Story | Support Ka-band robustness SUT switching: IA Posture Assessment - development input | Unassigned | Invalid | 0
265349 | #246191 | Story | Support Ka-band robustness SUT switching: IA Posture Assessment | Unassigned | Invalid | 0
265348 | #246191 | Story | Support Ka-band robustness SUT switching: IA Patching and STIGs | Unassigned | Invalid | 0
265343 | #233862 | Story | Feature 233862: Add/update IETM alarm recovery procedures for ET LBIP alarms - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
265339 | #216569 | Story | Feature 216569: Complete Testing and Release of Quest Box FM Alarm Updates - Engineering IETM updates | Unassigned | Invalid | 0
265333 | #265324 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #265328
265332 | #265324 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #265331
265331 | #265324 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #265326
265330 | #265324 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #265326
265329 | #265324 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #265326
265328 | #265324 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #265326
265327 | #265324 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #265333
265326 | #265324 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0
265325 | #241246 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0 | #241249
265324 |  | Feature | <Feature ...> | Unassigned | Rejected
265268 |  | Feature | Provide Connectivity between AWARE and NMF Network | Unassigned | Rejected
265267 | #244386 | Feature | Implement Alarms/Events in AWARE | Unassigned | Rejected
265227 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Meet with stakeholders for SCA/Validator feedback on workbooks, draft RAR and on data currency. Meeting in March | Unassigned | Invalid | 0
265222 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate Ops/Mgmt RAR into GD final RAR | Unassigned | Invalid | 0
265221 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate Stakeholder feedback into GD final RAR | Unassigned | Invalid | 0
265216 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation - Integrate LMs ACAS RAR into GD's final RAR | Unassigned | Invalid | 0
265188 |  | Story | Docs for Connected AWARE WH FRCB: Verify and release AWARE ETT site alignment updates | Unassigned | Invalid | 0
265066 |  | Task | LM - Create Draft POAM entries for the open findings in the ACAS RAR. | Unassigned | Invalid
265065 |  | Task | LM - Identify and document ACAS based device configuration discrepancies list. This will be an artifact provided to Ray Cendana (and onwards to the SCA). | Unassigned | Invalid
265064 |  | Task | LM - Create Final ACAS Analysis based RAR to be provided to Ray Cendana for validation. | Unassigned | Invalid
265061 |  | Task | LM - Create the ACAS Analysis based draft RAR and provide to Ray Cendana for his use during the site visit 1/22-2/1. The RAR will be in two parts – a low side RAR portion and a high side RAR portion. | Unassigned | Invalid
264977 |  | Story | xx | Unassigned | Invalid | 0
264976 |  | Story | xx | Unassigned | Invalid | 0
264972 |  | Story | xx | Unassigned | Invalid | 0
264971 |  | Story | xx | Unassigned | Invalid | 0
264970 |  | Story | xx | Unassigned | Invalid | 0
264969 |  | Story | xx | Unassigned | Invalid | 0
264964 |  | Story | xx | Unassigned | Invalid | 0
264963 |  | Story | xx | Unassigned | Invalid | 0
264962 |  | Story | xx | Unassigned | Invalid | 0
264961 |  | Story | xx | Unassigned | Invalid | 0
264960 |  | Story | xx | Unassigned | Invalid | 0
264959 |  | Story | xx | Unassigned | Invalid | 0
264958 |  | Story | xx | Unassigned | Invalid | 0
264957 |  | Story | xx | Unassigned | Invalid | 0
264956 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation Story 5 of 5 | Unassigned | Invalid | 0
264955 |  | Story | xx | Unassigned | Invalid | 0
264954 |  | Story | xx | Unassigned | Invalid | 0
264953 |  | Story | xx | Unassigned | Invalid | 0
264952 |  | Story | RMF Step 4 - RMF Risk Assessment Report (RAR) artifact generation Story 1 of 5 | Unassigned | Invalid | 0
264925 |  | Story | xx | Unassigned | Invalid | 0
264924 |  | Story | xx | Unassigned | Invalid | 0
264923 |  | Story | xx | Unassigned | Invalid | 0
264921 |  | Story | xx | Unassigned | Invalid | 0
264920 |  | Story | xx | Unassigned | Invalid | 0
264919 |  | Story | xx | Unassigned | Invalid | 0
264918 |  | Story | xx | Unassigned | Invalid | 0
264916 |  | Story | xx | Unassigned | Invalid | 0
264913 | #247890 | Story | TR - Workstation Performance: Anti Virus | Unassigned | Invalid | 0
264825 | #241577 | Story | TR - Hardware Architecture Selection | Unassigned | Invalid | 0
264625 |  | Story | AWARE 1a Fixes: ILS IETM updates-INVALIDATED | Unassigned | Invalid | 0
264604 |  | Story | Install the AWARE 1b subsystem in the WH RAF - Rich (site week 1 activity) - INVALIDATED | Unassigned | Invalid | 0
264602 |  | Story | AMS-GS Phase 1: Post Deployment Drawing Redlines - INVALIDATED | Unassigned | Invalid | 0
264595 | #264586 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264590
264594 | #264586 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264593
264593 | #264586 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264588
264592 | #264586 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264588
264591 | #264586 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264588
264590 | #264586 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264588
264589 | #264586 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264595
264588 | #264586 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264587
264587 | #264586 | Story | RNC ITEM Slide 2: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264586 |  | Feature | Add/update IETM alarm recovery procedures for RNC alarms (slide 2) | Unassigned | Rejected
264585 | #220766 | Story | eRxIM: Engineering IETM updates | Unassigned | Invalid | 0
264584 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): IA Patching and STIGs | Unassigned | Invalid | 0 | #264579
264583 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): Engineering IETM updates | Unassigned | Invalid | 0 | #264582
264582 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): ILS IETM updates | Unassigned | Invalid | 0 | #264577
264581 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): Development Team Test Inputs | Unassigned | Invalid | 0 | #264577
264580 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): Release Notes Inputs | Unassigned | Invalid | 0 | #264577
264579 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): IA Posture Assessment | Unassigned | Invalid | 0 | #264577
264578 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264584
264577 | #264575 | Story | Feature Demo - IETM recovery procedures for NMS alarms (Part 4) | Unassigned | Invalid | 0 | #264576
264576 | #264575 | Story | IETM recovery procedures for NMS alarms (Part 4): Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264575 | #216364 | Feature | IETM alarm recovery procedures for NMS alarms (Part 3 of 3) [Non-O-Level] | Unassigned | Analyzing
264571 | #264562 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264566
264567 | #264562 | Story | IETM: OTA-FT fails on WH RAF power outage: Release Notes Inputs | Unassigned | Invalid | 0 | #264564
264566 | #264562 | Story | IETM: OTA-FT fails on WH RAF power outage: IA Posture Assessment | Unassigned | Invalid | 0 | #264564
264565 | #264562 | Story | IETM: OTA-FT fails on WH RAF power outage: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264571
264563 | #264562 | Story | IETM: OTA-FT fails on WH RAF power outage: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264561 | #216578 | Story | ETISP snapshot: IA Patching and STIGs | Unassigned | Invalid | 0
264560 | #216578 | Story | ETISP snapshot: ILS IETM updates | Unassigned | Invalid | 0
264559 |  | Story | Feature 233865 IA Patching and STIGs | Unassigned | Invalid | 0 | #264541
264558 | #264549 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #264553
264557 |  | Story | eRiXM: Engineering IETM updates | Unassigned | Invalid | 0
264553 | #264549 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264551
264552 |  | Story | eRiXM: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264558
264551 | #264549 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264550
264550 | #264549 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264549 |  | Feature | <Feature ...> | Unassigned | Rejected
264548 | #233865 | Story | Feature 233865: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264559
264547 |  | Story | Feature 233865: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264546 | #264537 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264541
264545 |  | Story | Feature 233865: Engineering IETM updates | Unassigned | Invalid | 0
264544 |  | Story | Feature 233865:ILS IETM updates | Unassigned | Invalid | 0 | #251929
264543 |  | Story | Feature 233865 Development Team Test Inputs | Unassigned | Invalid | 0 | #251929
264542 |  | Story | Feature 233865: Release Notes Inputs | Unassigned | Invalid | 0 | #251929
264541 |  | Story | Feature 233865: IA Posture Assessment | Unassigned | Invalid | 0 | #251929
264540 | #264537 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264546
264539 |  | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264538
264538 | #264537 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264537 |  | Feature | <Feature ...> | Unassigned | Rejected
264536 | #262895 | Story | RNC-RBS Netcool rules: IA Patching and STIGs | Unassigned | New | 1
264535 | #262895 | Story | RNC-RBS Netcool rules: Engineering IETM updates | Unassigned | New | 3
264534 | #262895 | Story | RNC-RBS Netcool rules: ILS IETM updates | Unassigned | New | 3
264533 | #262895 | Story | RNC-RBS Netcool rules: Development Team Test Inputs | Unassigned | New | 5
264531 | #262895 | Story | RNC-RBS Netcool rules: Release Notes Inputs | Unassigned | New | 2
264530 | #262895 | Story | RNC-RBS Netcool rules: IA Posture Assessment | Unassigned | New | 2
264529 | #262895 | Story | RNC-RBS Netcool rules: IA Posture Assessment - development input | Unassigned | New | 1
264528 | #262895 | Story | Feature Demo- for RNC-RBS Netcool rules | Unassigned | New | 5
264527 | #262895 | Story | RNC-RBS Netcool rules: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
264526 | #264517 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #264521
264525 | #264517 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264524
264524 | #264517 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264519
264523 | #264517 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264519
264522 | #264517 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264519
264521 | #264517 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264519
264520 | #264517 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264526
264519 | #264517 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264518
264518 | #264517 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264517 |  | Feature | <Feature ...> | Unassigned | Rejected
264501 | #262982 | Story | ETISP ETI_1131: ILS IETM updates | Unassigned | Invalid | 0
264498 | #262982 | Story | ETISP ETI_1131: IA Patching and STIGs | Unassigned | Invalid | 0 | #264493
264497 | #264489 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264496
264496 | #264489 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264491
264495 | #264489 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264491
264494 | #262982 | Story | ETISP ETI_1131: Release Notes Inputs | Unassigned | Invalid | 0 | #264491
264493 | #264489 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264491
264492 | #264489 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264498
264491 | #264489 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264490
264490 | #264489 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264489 |  | Feature | <Feature ...> | Unassigned | Rejected
264488 |  | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0
264487 | #262982 | Story | ETISP ETI_1131: IA Posture Assessment | Unassigned | Invalid | 0
264486 | #262982 | Story | ETISP ETI_1131: IA Posture Assessment - development input | Unassigned | Invalid | 0
264485 | #262982 | Story | Feature Demo- for ETISP ETI_1131 | Unassigned | Invalid | 0
264484 | #262982 | Story | ETISP ETI_1131: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264483 |  | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0
264482 | #216578 | Story | ETISP snapshot: Release Notes Inputs | Unassigned | Invalid | 0
264481 | #216578 | Story | ETISP snapshot: IA Posture Assessment | Unassigned | Invalid | 0
264480 | #216578 | Story | ETISP snapshot: IA Posture Assessment - development input | Unassigned | Invalid | 0
264479 | #216578 | Story | Feature Demo- for ETISP snapshot | Unassigned | Invalid | 0
264477 | #216578 | Story | ETISP snapshot: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264475 | #264466 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #264470
264474 | #264466 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264473
264473 | #264446 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264468
264472 | #264466 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264468
264471 | #264466 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264468
264470 | #264466 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264468
264469 | #264466 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264475
264468 | #264466 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264467
264467 | #264466 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264466 |  | Feature | <Feature ...> | Unassigned | Rejected
264452 | #247492 | Story | Feature 247492 ETISP Switchover: IA Patching and STIGs | Unassigned | Invalid | 0
264450 | #247492 | Story | UX restructuring of ETI switchover: Development Team Test Inputs | Unassigned | Invalid | 0
264449 | #247492 | Story | Feature 247492 UX restructuring of ETI switchover: Release Notes Inputs | Unassigned | Invalid | 0
264448 | #264439 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #264443
264447 | #264439 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264446
264446 | #264439 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264441
264445 | #264439 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264441
264444 | #264439 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264441
264443 | #264439 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264441
264442 | #264439 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264448
264441 | #264439 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264440
264440 | #264439 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264439 |  | Feature | <Feature ...> | Unassigned | Rejected
264438 |  | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0
264437 | #247492 | Story | Feature 247492 ETI switchover: IA Posture Assessment | Unassigned | Invalid | 0
264436 | #247492 | Story | Feature 247492 UX restructuring of ETI switchover: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #283392
264435 | #250449 | Story | Lab-WCTB Maintenance Training | Unassigned | New | 2
264434 | #247492 | Story | Feature Demo- for Feature 247492 UX restructuring of ETI switchover | Unassigned | Invalid | 0
264432 | #250449 | Story | Lab-WCTB Maintenance Training | Unassigned | New | 2
264431 | #264422 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264426
264430 | #264422 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264429
264429 | #264422 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264424
264428 | #264422 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264424
264427 | #264422 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264424
264426 | #264422 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264424
264425 | #264422 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264431
264424 | #264422 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264423
264423 | #264422 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264422 |  | Feature | <Feature ...> | Unassigned | Rejected
264421 | #250449 | Story | Lab-WCTB Maintenance Training | Unassigned | New | 2
264420 | #247492 | Story | Feature 247492 ETI switchover: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264419 | #250449 | Story | Lab-WCTB Maintenance Training | Unassigned | New | 2
264417 | #250449 | Story | Lab-WCTB Maintenance Training | Unassigned | New | 2
264416 | #264407 | Story | Feature XXXXXX IA Patching and STIGs | Unassigned | Invalid | 0 | #264411
264415 | #264407 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264414
264414 | #264407 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264409
264413 | #264407 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264409
264412 | #264407 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264409
264411 | #264407 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264409
264410 | #264407 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264416
264409 | #264407 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264408
264408 | #264407 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264407 |  | Feature | <Feature ...> | Unassigned | Rejected
264404 |  | Story | Reliability Block Diagrams SME input-INVALIDATED | Unassigned | Invalid | 0
264403 | #262134 | Story | Reliability Block Diagrams SME input | Unassigned | Invalid | 0
264391 |  | Story | Feature 219443: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264390 | #264381 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264385
264389 | #264381 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264388
264388 | #264381 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264383
264387 | #264381 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264383
264386 | #264381 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264383
264385 | #264381 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264383
264384 | #264381 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264390
264383 | #264381 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264382
264382 | #264381 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264381 |  | Feature | <Feature ...> | Unassigned | Rejected
264371 |  | Story | Feature 262904: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264364 | #256679 | Story | Placeholder for SIT Story points | Unassigned | Invalid | 0
264360 |  | Story | Feature 283880: ILS IETM updates (1 of 5) | Unassigned | Invalid | 0
264354 | #264345 | Story | Feature xxx IA Patching and STIGs | Unassigned | Invalid | 0 | #264349
264353 | #264345 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264352
264352 | #264345 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264347
264351 | #264345 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264347
264350 | #264345 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264347
264349 | #264345 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264347
264348 | #264345 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264354
264347 | #264345 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264346
264346 | #264345 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264345 |  | Feature | <Feature ...> | Unassigned | Rejected
264344 |  | Story | Feature 219438: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264343 | #245566 | Feature | Assess the need & viability of software level monitoring, alarms, and recovery procedures | Unassigned | Draft
264336 | #262146 | Story | Test Verifications required for non- feature IETM work | Unassigned | Invalid | 0
264333 | #264324 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #264328
264332 | #264324 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #264331
264331 | #264324 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #264326
264330 | #264324 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #264326
264329 | #264324 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #264326
264328 | #264324 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #264326
264327 | #264324 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #264333
264326 | #264324 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #264325
264325 |  | Story | Feature 219438: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
264324 |  | Feature | <Feature ...> | Unassigned | Rejected
264321 | #264319 | Feature | Remove Splunk dependency on Call Banks (design enabler) | Unassigned | Rejected
264276 | #263333 | Story | Feature 263333: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0 | #290337
264274 | #263333 | Story | Feature 263333:ILS IETM updates | Unassigned | Invalid | 0
264272 | #262134 | Story | Feature 263333:- Feature Demo | Unassigned | Invalid | 0
264271 | #232019 | Story | Verify New OSSRC CIB System Build Result | Unassigned | New | 3
264270 | #220187 | Story | Verify Integrated CIB System Build Result | Unassigned | Invalid | 0
264269 | #232017 | Story | Verify New RBS CIB System Build Result | Unassigned | New | 2
264200 |  | Story | delete | Unassigned | Invalid | 0
264193 | #247890 | Story | Feature 247890: Release Notes Inputs | Unassigned | Invalid | 0
264178 |  | Story | Lab Tax - INVALIDATED | Unassigned | Invalid | 0
264137 |  | Story | delete - duplicate | Unassigned | Invalid | 0
264134 | #263333 | Story | xx - RAN EAD 8 Release: Perform IA Patching, Scans, and STIGs based on outcome of Posture Template Review | Unassigned | Invalid | 0
264013 |  | Story | Feature 251537: Engineering IETM updates | Unassigned | Invalid | 0
263901 | #265924 | Story | Lab - SCS Power Up - Allen (4.5) | Unassigned | Invalid | 0
263764 |  | Feature | Test Feature | Unassigned | Rejected
263763 | #263754 | Story | Feature 263009 IA Patching and STIGs | Unassigned | Invalid | 0 | #263758
263762 | #263754 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #263761
263761 | #263754 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #263756
263760 | #263754 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #263756
263759 | #263754 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #263756
263758 | #263754 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #263756
263757 | #263754 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #263763
263756 | #263754 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #263755
263755 | #263754 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
263667 | #263658 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #263665
263666 | #263658 | Story | <Feature xxx> IA Patching and STIGs | Unassigned | Invalid | 0 | #263662
263665 | #263658 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #263660
263664 | #263658 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #263660
263663 | #263658 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #263660
263662 | #263658 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #263660
263661 | #263658 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #263666
263660 | #263658 | Story | Feature Demo- for <Feature xxx> | Unassigned | Invalid | 0 | #263659
263659 | #263658 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
263658 |  | Feature | <Feature ...> | Unassigned | Rejected
263648 | #263639 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #263642
263647 | #263639 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #263642
263646 | #263639 | Story | <Feature xxx> IA Patching and STIGs | Unassigned | Invalid | 0 | #263643
263645 | #263639 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #263642
263644 | #263639 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #263648
263643 | #263639 | Story | <Feature xxx>: IA Posture Assessment | Unassigned | Invalid | 0 | #263642
263642 | #263639 | Story | Feature Demo- | Unassigned | Invalid | 0 | #263640
263641 | #263639 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #263646
263640 | #263639 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
263639 |  | Feature | <Feature ...> | Unassigned | Rejected
263509 |  | Story | Support Analysis of AMS-GS FCAPS | Unassigned | Invalid | 0
263508 |  | Story | Support Analysis of AMS-GS FCAPS - INVALIDATED | Unassigned | Invalid | 0
263392 | #247890 | Story | TR - FOUO Workstation EXP: GSN | Unassigned | Invalid | 0
263344 |  | Story | TR - Workstation EXP: Add new workstations to FM | Unassigned | Invalid | 0
263288 | #263244 | Story | Investigate RNC Board Failures | Unassigned | Invalid | 0
263287 |  | Story | Investigate RNC Board Failures | Unassigned | Invalid | 0
263272 | #263263 | Story | CDR Delivery Dashboard: Engineering IETM updates | Unassigned | New | 3 | #263270
263271 | #263263 | Story | CDR Delivery Dashboard: IA Patching and STIGs | Unassigned | New | 1 | #263267
263270 | #263263 | Story | CDR Delivery Dashboard: ILS IETM updates | Unassigned | New | 3 | #263265
263269 | #263263 | Story | CDR Delivery Dashboard: Development Team Test Inputs | Unassigned | New | 3 | #263265
263268 | #263263 | Story | CDR Delivery Dashboard: Release Notes Inputs | Unassigned | New | 2 | #263265
263267 | #263263 | Story | CDR Delivery Dashboard: IA Posture Assessment | Unassigned | New | 8 | #263265
263266 | #263263 | Story | CDR Delivery Dashboard: IA Posture Assessment - development input | Unassigned | New | 1 | #263271
263265 | #263263 | Story | Feature Demo - CDR Delivery Dashboard | Unassigned | New | 5 | #263264
263264 | #263263 | Story | CDR Delivery Dashboard: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
263263 | #245437 | Feature | Create Splunk Dashboard(s) and Indicators to Monitor CDR Data Delivery to Gather Baseline Metrics | Unassigned | Approved
263256 | #263247 | Story | PM Delivery Dashboard: Engineering IETM updates | Unassigned | New | 3 | #263254
263255 | #263247 | Story | PM Delivery Dashboard: IA Patching and STIGs | Unassigned | New | 1 | #263251
263254 | #263247 | Story | PM Delivery Dashboard: ILS IETM updates | Unassigned | New | 3 | #263249
263253 | #263247 | Story | PM Delivery Dashboard: Development Team Test Inputs | Unassigned | New | 3 | #263249
263252 | #263247 | Story | PM Delivery Dashboard: Release Notes Inputs | Unassigned | New | 2 | #263249
263251 | #263247 | Story | PM Delivery Dashboard: IA Posture Assessment | Unassigned | New | 8 | #263249
263250 | #263247 | Story | PM Delivery Dashboard: IA Posture Assessment - development input | Unassigned | New | 1 | #263255
263249 | #263247 | Story | Feature Demo - PM Delivery Dashboard | Unassigned | New | 5 | #263248
263248 | #263247 | Story | PM Delivery Dashboard: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
263247 | #218503 | Feature | Create Splunk Dashboard(s) and Indicators to Monitor PM Data Delivery to Gather Baseline Metrics | Unassigned | Approved
263164 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: Engineering IETM updates | Unassigned | Invalid | 0 | #263162
263163 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: IA Patching and STIGs | Unassigned | Invalid | 0 | #263159
263162 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: ILS IETM updates | Unassigned | Invalid | 0 | #263157
263161 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: Development Team Test Inputs | Unassigned | Invalid | 0 | #263157
263160 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: Release Notes Inputs | Unassigned | Invalid | 0 | #263157
263159 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: IA Posture Assessment | Unassigned | Invalid | 0 | #263157
263158 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #263163
263157 | #263155 | Story | Feature Demo - Splunk Infra: Guaranteed Data Delivery | Unassigned | Invalid | 0 | #263156
263156 | #263155 | Story | Splunk Infra: Guaranteed Data Delivery: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
263155 | #217379 | Feature | Improve Splunk FM data reliability | Unassigned | Rejected
263153 | #263144 | Story | Deduplicate FM data in Splunk index: Engineering IETM updates | Unassigned | New | 0 | #263151
263152 | #263144 | Story | Deduplicate FM data in Splunk index: IA Patching and STIGs | Unassigned | New | 1 | #263148
263151 | #263144 | Story | Deduplicate FM data in Splunk index: ILS IETM updates | Unassigned | New | 0 | #263146
263150 | #263144 | Story | Deduplicate FM data in Splunk index: Development Team Test Inputs | Unassigned | New | 3 | #263146
263149 | #263144 | Story | Deduplicate FM data in Splunk index: Release Notes Inputs | Unassigned | New | 2 | #263146
263148 | #263144 | Story | Deduplicate FM data in Splunk index: IA Posture Assessment | Unassigned | New | 8 | #263146
263147 | #263144 | Story | Deduplicate FM data in Splunk index: IA Posture Assessment - development input | Unassigned | New | 2 | #263152
263146 | #263144 | Story | Feature Demo - Deduplicate FM data in Splunk index | Unassigned | New | 5 | #263145
263145 | #263144 | Story | Deduplicate FM data in Splunk index: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
263144 | #245408 | Feature | Deduplicate FM data in Splunk index | Unassigned | Ready for System IPT Approval
263136 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Engineering IETM updates | PI 14 | Invalid | 0 | #263134
263135 | #263127 | Story | Change Intersite Status so That "No News=Bad News": IA Patching and STIGs | PI 14 | Invalid | 0 | #263131
263134 | #263127 | Story | Change Intersite Status so That "No News=Bad News": ILS IETM updates | PI 14 | Invalid | 0 | #263129
263133 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Development Team Test Inputs | PI 14 | Invalid | 0 | #263129
263132 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Release Notes Inputs | PI 14 | Invalid | 0 | #263129
263131 | #263127 | Story | Change Intersite Status so That "No News=Bad News": IA Posture Assessment | PI 14 | Invalid | 0 | #263129
263130 | #263127 | Story | Change Intersite Status so That "No News=Bad News": IA Posture Assessment - development input | PI 14 | Invalid | 0 | #263135
263129 | #263127 | Story | Feature Demo - Change Intersite Status so That "No News=Bad News" | PI 14 | Invalid | 0 | #263128
263128 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Initiate CM PDO Processing for all CI's | PI 14 | Invalid | 0
263127 | #219598 | Feature | Change Intersite Status so That "No News=Bad News" | PI 14 | Rejected
263085 | #245408 | Feature | Indexing all/more FM data into Splunk | Unassigned | Rejected
263064 | #224658 | Story | IA Hardening - WannaCry Samba: Update Samba version on CIs | Unassigned | Invalid | 0
263036 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: Engineering IETM updates | Unassigned | New | 1 | #263034
263035 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: IA Patching and STIGs | Unassigned | New | 8 | #263031
263034 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: ILS IETM updates | Unassigned | New | 1 | #263029
263033 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: Development Team Test Inputs | Unassigned | New | 3 | #263029
263032 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: Release Notes Inputs | Unassigned | New | 2 | #263029
263031 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: IA Posture Assessment | Unassigned | New | 8 | #263029
263030 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: IA Posture Assessment - development input | Unassigned | New | 2 | #263035
263029 | #263027 | Story | Feature Demo - Implement "Best Practices" Updates from Splunk Training | Unassigned | New | 5 | #263028
263028 | #263027 | Story | Implement "Best Practices" Updates from Splunk Training: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
263027 | #217379 | Feature | Implement "Best Practices" Updates from Splunk Training | Unassigned | Draft
263026 | #217379 | Feature | Analyze/Propose "Best Practices" Updates from Splunk Training | Unassigned | Draft
262994 | #262985 | Story | Distribute AWARE Alarms/Events to NMS: Engineering IETM updates | Unassigned | Invalid | 0
262993 | #262985 | Story | Distribute AWARE Alarms/Events to NMS: IA Patching and STIGs | Unassigned | Invalid | 0
262992 | #262985 | Story | Feature 262985: IETM Updates for Distribution of AWARE Alarms/Events to NMS | Unassigned | Invalid | 0
262991 |  | Story | Distribute AWARE Alarms/Events to NMS: Development Team Test Inputs | Unassigned | Invalid | 0
262989 | #262985 | Story | Distribute AWARE Alarms/Events to NMS: IA Posture Assessment | Unassigned | Invalid | 0
262988 |  | Story | Distribute AWARE Alarms/Events to NMS: IA Posture Assessment - development input | Unassigned | Invalid | 0
262982 | #245567 | Feature | ETISP enhance ETI_1131 alarm to indicate which board is not locked | Unassigned | Rejected
262965 | #262956 | Story | Implement FCAPS for Splunk: Engineering IETM updates | Unassigned | Invalid | 0 | #262963
262964 | #262956 | Story | Implement FCAPS for Splunk: IA Patching and STIGs | Unassigned | Invalid | 0 | #262960
262963 | #262956 | Story | Implement FCAPS for Splunk: ILS IETM updates | Unassigned | Invalid | 0 | #262958
262962 | #262956 | Story | Implement FCAPS for Splunk: Development Team Test Inputs | Unassigned | Invalid | 0 | #262958
262961 | #262956 | Story | Implement FCAPS for Splunk: Release Notes Inputs | Unassigned | Invalid | 0 | #262958
262960 | #262956 | Story | Implement FCAPS for Splunk: IA Posture Assessment | Unassigned | Invalid | 0 | #262958
262959 | #262956 | Story | Implement FCAPS for Splunk: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262964
262958 | #262956 | Story | Feature Demo - Implement FCAPS for Splunk | Unassigned | Invalid | 0 | #262957
262957 | #262956 | Story | Implement FCAPS for Splunk: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262956 | #217379 | Feature | Implement FCAPS for Splunk | Unassigned | Rejected
262954 |  | Story | Increase Splunk Licensing to Support More Data: Engineering IETM updates | Unassigned | Invalid | 0 | #262952
262953 |  | Story | Increase Splunk Licensing to Support More Data: IA Patching and STIGs | Unassigned | Invalid | 0 | #262949
262951 | #262945 | Story | Update STCD, Execute STCD | Unassigned | Invalid | 0 | #262947
262948 |  | Story | Increase Splunk Licensing to Support More Data: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262953
262944 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: Engineering IETM updates | Unassigned | Invalid | 0 | #262942
262943 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: IA Patching and STIGs | Unassigned | Invalid | 0 | #262939
262942 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: ILS IETM updates | Unassigned | Invalid | 0 | #262937
262941 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: Development Team Test Inputs | Unassigned | Invalid | 0 | #262937
262940 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: Release Notes Inputs | Unassigned | Invalid | 0 | #262937
262939 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: IA Posture Assessment | Unassigned | Invalid | 0 | #262937
262938 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262943
262937 | #262935 | Story | Feature Demo - Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback | Unassigned | Invalid | 0 | #262936
262936 | #262935 | Story | Splunk Cell/SBC Status - Address EAD-3 & Splunk Operator Training Feedback: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262934 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Training Operator Feedback: Engineering IETM updates | Unassigned | Invalid | 0 | #262932
262933 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: IA Patching and STIGs | Unassigned | Invalid | 0 | #262929
262932 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: ILS IETM updates | Unassigned | Invalid | 0 | #262927
262931 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: Development Team Test Inputs | Unassigned | Invalid | 0 | #262927
262930 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: Release Notes Inputs | Unassigned | Invalid | 0 | #262927
262929 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: IA Posture Assessment | Unassigned | Invalid | 0 | #262927
262928 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262933
262927 | #262925 | Story | Feature Demo - Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback | Unassigned | Invalid | 0 | #262926
262926 | #262925 | Story | Splunk Feederlink Status - Address EAD-3 & Splunk Operator Training Feedback: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262905 | #233865 | Story | Add Auto Alarm Clear Logic to Netcool rules file for TFDU | Unassigned | Invalid | 0
262895 | #216351 | Feature | Add alarm event IDs and Auto Alarm Clear Logic to NetCool rules file for RNC and RBS | Unassigned | Approved
262872 | #245575 | Feature | SCS Software and SODD Updates (INC000002189087 & INC000002189130) for telemetry algorithm update and mnemonic algorithm redefine | Unassigned | Rejected
262864 | #224658 | Story | IA Hardening - WannaCry Samba: ILS IETM updates | Unassigned | Invalid | 0 | #262859
262857 |  | Story | delete | Unassigned | Invalid | 0
262820 | #221231 | Story | Auto Logging: Perform IA Scans and STIGs based on Cyber Teams input | Unassigned | New | 1 | #249082
262813 | #221231 | Story | Auto Logging: Create IA Posture Assesment Template | Unassigned | New | 1
262775 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): Engineering IETM updates | Unassigned | Invalid | 0 | #262773
262774 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): IA Patching and STIGs | Unassigned | Invalid | 0 | #262770
262773 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): ILS IETM updates | Unassigned | Invalid | 0 | #262768
262772 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): Development Team Test Inputs | Unassigned | Invalid | 0 | #262768
262771 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): Release Notes Inputs | Unassigned | Invalid | 0 | #262768
262770 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): IA Posture Assessment | Unassigned | Invalid | 0 | #262768
262769 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262774
262768 | #262766 | Story | Feature Demo - IETM recovery procedures for NMS alarms (Part 3) | Unassigned | Invalid | 0 | #262767
262767 | #262766 | Story | IETM recovery procedures for NMS alarms (Part 3): Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262766 | #216364 | Feature | IETM alarm recovery procedures for NMS alarms (Part 2 of 3) [Non-O-Level] | Unassigned | Analyzing
262764 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): Engineering IETM updates | Unassigned | Invalid | 0 | #262762
262763 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): IA Patching and STIGs | Unassigned | Invalid | 0 | #262759
262762 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): ILS IETM updates | Unassigned | Invalid | 0 | #262757
262761 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): Development Team Test Inputs | Unassigned | Invalid | 0 | #262757
262760 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): Release Notes Inputs | Unassigned | Invalid | 0 | #262757
262759 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): IA Posture Assessment | Unassigned | Invalid | 0 | #262757
262758 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262763
262757 | #262755 | Story | Feature Demo - Customer Event - IETM recovery procedures for NMS alarms (Part 2) | Unassigned | Invalid | 0 | #262756
262756 | #262755 | Story | IETM recovery procedures for NMS alarms (Part 2): Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262755 | #216364 | Feature | IETM alarm recovery procedures for NMS alarms (Part 1 of 3) [Non-O-Level] | Unassigned | Analyzing
262754 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): Engineering IETM updates | Unassigned | Invalid | 0 | #262752
262753 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): IA Patching and STIGs | Unassigned | Invalid | 0 | #262749
262752 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): ILS IETM updates | Unassigned | Invalid | 0 | #262747
262751 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): Development Team Test Inputs | Unassigned | Invalid | 0 | #262747
262749 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): IA Posture Assessment | Unassigned | Invalid | 0 | #262747
262748 | #262745 | Story | IETM recovery procedures for NMS alarms (Part 1): IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262753
262738 |  | Story | FM whitelist updates for PI5: IA Posture Assessment | Unassigned | Invalid | 0 | #262736
262731 |  | Story | Update IETM to provide routine task to clean up disk space on NMS FOUO database servers | Unassigned | Invalid | 0
262722 | #346561 | Story | Part 3 - Triage lab/site data | Unassigned | Invalid | 0
262708 | #262707 | Story | FM whitelist updates for high-side alarms (quick pass): Initiate CM PDO Processing for all CI's | Unassigned | Done | 0
262634 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: Engineering IETM updates | Unassigned | New | 3 | #262632
262633 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: IA Patching and STIGs | Unassigned | New | 1 | #262629
262632 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: ILS IETM updates | Unassigned | New | 3 | #262627
262631 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: Development Team Test Inputs | Unassigned | New | 3 | #262627
262630 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: Release Notes Inputs | Unassigned | New | 2 | #262627
262629 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: IA Posture Assessment | Unassigned | New | 8 | #262627
262628 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: IA Posture Assessment - development input | Unassigned | New | 1 | #262633
262627 | #262625 | Story | Feature Demo - Prevent Operators from Updating GD Defined Splunk Dashboards | Unassigned | New | 5 | #262626
262626 | #262625 | Story | Prevent Operators from Updating GD Defined Splunk Dashboards: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
262625 | #217043 | Feature | Prevent Operators from Updating GD Defined Splunk Dashboards | Unassigned | Draft
262579 | #245718 | Feature | Rejected: TR - TPM CRL workflow replacement (Deployment) | Unassigned | Rejected
262567 |  | Story | Invalid | Unassigned | Invalid | 0
262562 |  | Story | Rejected: TR - TPM Unix patching workflow replacement (Deployment) | Unassigned | Invalid | 0
262529 |  | Story | AWARE 1a Fixes: Support AWARE & WF 8H Integration (Part 2) | Unassigned | Invalid | 0
262505 |  | Task | Reject: TR - TPM windows patching workflow replacement (deployment) | Unassigned | New
262440 |  | Story | xx | Unassigned | Invalid | 0 | #262438
262439 |  | Story | xx | Unassigned | Invalid | 0 | #262435
262438 |  | Story | xx | Unassigned | Invalid | 0 | #262433
262437 |  | Story | xx | Unassigned | Invalid | 0 | #262433
262436 |  | Story | xx | Unassigned | Invalid | 0 | #262433
262435 |  | Story | xx | Unassigned | Invalid | 0 | #262433
262434 |  | Story | IA Hardening - WannaCry: Block SMB: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #262439
262433 |  | Story | Feature Demo - Customer Event - IA Hardening - WannaCry: Block SMB | Unassigned | Invalid | 0
262432 |  | Story | IA Hardening - WannaCry: Block SMB: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
262431 |  | Story | Delete | Unassigned | Invalid | 0
262413 |  | Story | xx | Unassigned | Invalid | 0
262346 |  | Feature | Coordinate and conduct NW Deice / Furnace Troubleshooting and Replace Motor Connectors | Unassigned | Rejected
262251 | #262244 | Story | IA Hardening - WannaCry Windows: ILS IETM updates | Unassigned | Done | 0 | #262246
262247 |  | Story | xx | Unassigned | Invalid | 0 | #279714
262239 | #248241 | Story | Provide AWARE Connectivity Consultation | Unassigned | Invalid | 0
262190 | #243505 | Feature | Tools Support - PI 6 | Unassigned | Rejected
262189 |  | Feature | Tools Support - PI 5 | Unassigned | Rejected
262122 |  | Story | V-Lab Power Up - Glen (5.1) - INVALID | Unassigned | Invalid | 0
262109 | #262579 | Story | TR - CRL Update Application\Tool: IETM | Unassigned | Invalid | 0
262106 | #262579 | Story | TR - CRL Update Application\Tool: Create CI | Unassigned | Invalid | 0
262102 | #262579 | Story | Feature Demo - CRL Update Application\Tool CI | Unassigned | Invalid | 0
262101 | #262579 | Story | CRL Update Application\Tool CI: Release Briefing | Unassigned | Invalid | 0
262100 | #262579 | Story | CRL Update Application\Tool CI: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
262098 | #262579 | Story | CRL Update Application\Tool CI: ILS IETM updates - checklist | Unassigned | Invalid | 0
262096 | #262579 | Story | CRL Update Application\Tool CI: IA Posture Assessment and MFR | Unassigned | Invalid | 0
262094 | #262579 | Story | CRL Update Application\Tool CI:IA Posture Assessment - development input | Unassigned | Invalid | 0
262075 | #262579 | Story | CRL Update Application\Tool CI Initiate CM PDO Processing for CI | Unassigned | Invalid | 0
262030 | #216552 | Feature | RMF Step 3&4 - PMW/Validator tasks to support RMF Accreditation | Unassigned | Rejected
261994 | #318303 | Story | Windows 10 LAPTOP CI: create SECRET\AJM LAPTOP Image | Unassigned | Invalid | 0
261963 |  | Story | Windows 10 LAPTOP CI: Release Briefing | Unassigned | Invalid | 0
261960 |  | Story | Windows 10 LAPTOP CI: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
261942 |  | Story | xx | Unassigned | Invalid | 0
261940 |  | Story | xx | Unassigned | Invalid | 0
261899 | #262562 | Story | Feature Demo - Linux Patching CI | Unassigned | Invalid | 0
261898 |  | Story | Linux Patching CI: Release Briefing | Unassigned | Invalid | 0
261897 | #262562 | Story | Linux Patching CI: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
261896 | #262562 | Story | Linux Patching CI: ILS IETM updates - checklist | Unassigned | Invalid | 0
261894 | #262562 | Story | Linux Patching CI: IA Posture Assessment and MFR | Unassigned | Invalid | 0
261892 | #262562 | Story | Linux Patching CI:IA Posture Assessment - development input | Unassigned | Invalid | 0
261890 | #262562 | Story | Linux Patching CI: Initiate CM PDO Processing for CI | Unassigned | Invalid | 0
261885 | #262562 | Story | TR - Linux Patching: IETM | Unassigned | Invalid | 0
261883 | #262562 | Story | TR - Linux Patching: Create CI | Unassigned | Invalid | 0
261831 | #261787 | Story | TR - Workstation Performance: IETM R&R pages for hardware z820 | Unassigned | Invalid | 0
261810 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
261802 | #261787 | Story | TR - Workstation Performance: GEO SECRET Enclave switch impacts | Unassigned | Invalid | 0
261787 | #246826 | Feature | Workstation performance phase 2 | Unassigned | Rejected
261784 | #262134 | Feature | System Test - ILS development work for Non-feature IETM Updates | Unassigned | Rejected
261782 | #261787 | Story | TR - Workstation Performance: update FM impacts | Unassigned | Invalid | 0
261781 | #261787 | Story | TR - Workstation Performance: update SAN201\202 ACLs | Unassigned | Invalid | 0
261767 | #261787 | Story | TR - Workstation Performance: Functional Block Diagram | Unassigned | Invalid | 0
261765 | #261787 | Story | TR - Workstation Performance: NEDB updates | Unassigned | Invalid | 0
261749 | #247890 | Story | TR - Workstation Performance: NMF extreme switch impacts | Unassigned | Invalid | 0
261738 |  | Story | TR - Workstation Performance: NMF Router impacts | Unassigned | Invalid | 0
261730 | #247890 | Story | TR - Workstation Performance: update AAA/DNS | Unassigned | Invalid | 0
261719 | #233862 | Story | Create Alarm/Event Id's for all White Listed Alarms | Unassigned | Invalid | 0
261698 |  | Story | Work with SIT to support LBIP IETM Feature Demo | Unassigned | Invalid | 0
261694 | #267777 | Story | Feature 267777: Investigate/Test LBIP Alarm/Event IDs mapped to NetCool | Unassigned | New | 5
261690 | #262134 | Story | Work with ILS to review and verify RNC IETM Content | Unassigned | Invalid | 0
261687 | #219442 | Story | Work with SIT to support Feature Demo | Unassigned | Invalid | 0
261686 | #219442 | Story | Provide Training material and Release Notes for RNC IETM updates | Unassigned | Invalid | 0
261679 |  | Story | Feature 262904: Create IA Posture Assessment | Unassigned | Invalid | 0
261677 |  | Story | Create IA Posture for RTT Release | Unassigned | Invalid | 0
261676 |  | Story | Feature 262904: Execute STCD for RTT Changes | Unassigned | Invalid | 0
261675 |  | Story | Add RNC Alarm/Event IDs to NetCool whitelist | Unassigned | Invalid | 0
261665 | #220766 | Story | Review ILS Human Error IETM content and verify PCR | Unassigned | Invalid | 0
261664 | #216575 | Story | Test ETISP IETM changes | Unassigned | Done | 0
261538 | #256828 | Story | Identify RAN IETM Changes | Unassigned | Invalid | 0
261492 | #216552 | Feature | RMF Step 4 - RMF System Level Continuous Monitoring (SLCM) Strategy artifact updates (GD support to PMW-146) | Unassigned | Analyzing
261491 | #216552 | Feature | RMF Step 4 - RMF Security Assessment Report (SAR) artifact generation (GD support to Validator) | Unassigned | Rejected
261485 | #262562 | Story | TR - Linux Patching: SVD | Unassigned | Invalid | 0
261481 | #262562 | Story | TR - Linux Patching: Create CI | Unassigned | Invalid | 0
261456 | #216552 | Feature | RMF Step 3 - Complete RMF Step 3 Assessment Plan | Unassigned | Rejected
261411 | #262505 | Story | TR - Windows Patching: drawing impacts | Unassigned | Invalid | 0
261368 | #228829 | Task | Run tests once pspi's are complete | Unassigned | Done
261367 | #228829 | Task | Create pspi based on the NMS profiles | Unassigned | Done
261364 | #228829 | Task | Get profiles generated from NMS | Unassigned | Done
261216 | #243505 | Feature | Improve customer access to configuration and data management databases | Unassigned | Rejected
261168 | #262505 | Story | Windows patching CI: Release Briefing | Unassigned | Invalid | 0
261167 | #262505 | Story | Windows Patching CI: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
261162 | #262505 | Story | Windows patching CI: ILS IETM updates - checklist | Unassigned | Invalid | 0
261160 | #262505 | Story | Windows Patching CI: IA Posture Assessment and MFR | Unassigned | Invalid | 0
261159 |  | Story | Feature Demo - Windows patching CI | Unassigned | Invalid | 0
261156 | #262505 | Story | Windows Patching CI: : IA Posture Assessment - development input | Unassigned | Invalid | 0
261153 | #262505 | Story | Windows Patching CI: Initiate CM PDO Processing for CI | Unassigned | Invalid | 0
261146 | #262505 | Story | TR - Windows Patching: IETM | Unassigned | Invalid | 0
261143 | #262505 | Story | TR - Windows Patching: SVD | Unassigned | Invalid | 0
261142 | #262505 | Story | TR - Windows Patching: Create CI | Unassigned | Invalid | 0
260938 |  | Story | Docs for Connected AWARE WH FRCB: Continue to incorporate AWARE installation redlines into the site alignment procedure | Unassigned | Invalid | 0
260775 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) - ExtremeSW (High Side) | Unassigned | Invalid | 0
260651 |  | Story | Improve AWARE IA Posture for IATT: ILS IETM updates-INVALIDATED | Unassigned | Invalid | 0 | #260645
260649 |  | Story | Improve AWARE IA Posture for IATT: IA Patching and STIGs-INVALIDATE | Unassigned | Invalid | 0 | #260646
260647 |  | Story | Improve AWARE IA Posture for IATT: Engineering IETM updates-INVALIDATED | Unassigned | Invalid | 0 | #260651
260581 |  | Feature | Test Feature for Amy McKee | Unassigned | Rejected
260348 |  | Story | Develop recommendations for expansion & "rollout" of specialist role | Unassigned | Invalid | 0
260345 |  | Story | Incorporate task analysis results into LCSP (identified in NetOps/CONOPS study) | Unassigned | Invalid | 0
260343 |  | Story | Identify frequency & duration of tasks to be performed by new specialist and floor lead roles (identified in NetOps/CONOPS study) | Unassigned | Invalid | 0
260337 |  | Story | Identify tasks to be performed by new specialist and floor lead roles (identified in NetOps/CONOPS study) | Unassigned | Invalid | 0
260327 |  | Story | Update new NCTAMS Roles description of responsibilities, qualifications, and KSAs | Unassigned | Invalid | 0
260320 |  | Story | Review new NCTAMS Roles description of responsibilities, qualifications, and KSAs | Unassigned | Invalid | 0
260317 |  | Story | Create new NCTAMS Roles description of responsibilities, qualifications, and KSAs | Unassigned | Invalid | 0
260314 |  | Feature | Definition of new roles identified in NetOps/CONOPS study | Unassigned | Rejected
259557 | #217026 | Feature | Improve group data/multicast suitability: WF Buffering Improvements Implementation | Unassigned | Approved |  | #232525
259323 | #235558 | Task | Create Proof of Concept | Unassigned | New
259238 |  | Story | AMS-GS SVD Reference to IETM Procedure for MAC learning - INVALIDATED | Unassigned | Invalid | 0
259005 |  | Story | Need to track and account for intake hours going forward to allocate our time appropriately. Should discuss with Steve a plan going forward. LOE. | Unassigned | Done | 0
258701 | #258692 | Story | High BLER: ILS IETM updates | Unassigned | Invalid | 0 | #258695
258700 | #258692 | Story | High BLER: Development Team Test Inputs | Unassigned | Invalid | 0 | #258695
258699 | #258692 | Story | High BLER: IA Patching and STIGs | Unassigned | Invalid | 0 | #258696
258698 | #258692 | Story | High BLER: Release Notes Inputs | Unassigned | Invalid | 0 | #258695
258697 | #258692 | Story | High BLER: Engineering IETM updates | Unassigned | Invalid | 0 | #258701
258696 | #258692 | Story | High BLER: IA Posture Assessment | Unassigned | Invalid | 0 | #258695
258695 | #258692 | Story | Feature Demo- High BLER | Unassigned | Invalid | 0 | #258693
258694 | #258692 | Story | High BLER: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #258699
258693 | #258692 | Story | High BLER: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
258616 | #245566 | Story | Add TFDU alarm event IDs to Netcool rules file | Unassigned | Invalid | 0
258590 | #245566 | Story | Add clear alarm mapping to Netcool rules file | Unassigned | Invalid | 0
258588 | #262146 | Story | IETM Release for ET Switchover Imidaite Site Updates | Unassigned | Invalid | 0
258573 | #262134 | Story | Repair WDEs to support BKM users | Unassigned | Done | 5
258383 | #255621 | Task | Support Tasks for Eric | Unassigned | Done
258380 | #219442 | Story | Create Health Check script proof of concept for collecting PMD and NTP data | Unassigned | Invalid | 0
258379 | #219442 | Story | update the “hc” script for moshell | Unassigned | Invalid | 0
258375 |  | Story | Train and Certify a MUOS SIPRNET "Trusted Agent" | Unassigned | Invalid | 0
258356 |  | Story | AMS-GS Training: ILS IETM updates | Unassigned | Invalid | 0 | #258350
258355 |  | Story | AMS-GS Training: Development Team Test Inputs | Unassigned | Invalid | 0 | #258350
258354 |  | Story | AMS-GS Training: IA Patching and STIGs | Unassigned | Invalid | 0 | #258351
258353 |  | Story | AMS-GS Training: Release Notes Inputs | Unassigned | Invalid | 0 | #258350
258351 |  | Story | AMS-GS Training: IA Posture Assessment | Unassigned | Invalid | 0 | #258350
258350 |  | Story | Feature Demo- AMS-GS Training | Unassigned | Invalid | 0 | #258348
258349 |  | Story | AMS-GS Training: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #258354
258348 | #258347 | Story | AMS-GS Training: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
258346 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: ILS IETM updates | Unassigned | New | 3 | #258340
258345 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: Development Team Test Inputs | Unassigned | New | 3 | #258340
258344 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: IA Patching and STIGs | Unassigned | New | 8 | #258341
258343 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: Release Notes Inputs | Unassigned | New | 2 | #258340
258342 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: Engineering IETM updates | Unassigned | New | 3 | #258346
258341 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: IA Posture Assessment | Unassigned | New | 8 | #258340
258340 | #258337 | Story | Feature Demo- AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7 | Unassigned | New | 5 | #258338
258339 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: IA Posture Assessment - development input | Unassigned | New | 2 | #258344
258338 | #258337 | Story | AMS-GS Alarm Distribution & Fault Recovery Procedures - PI7: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
258308 | #367689 | Problem | SR 931715 - INC 000002212519 - FOUO Workstation Internet Explorer connection to Lantronix SLC16 console server Web page fails after certificate presentation | PI 16 | Approved
258305 | #217023 | Feature | Rejected | Unassigned | Rejected
258295 |  | Story | GD Support of Zeta - EAD 8: Development Team Test Inputs - INVALIDATED | Unassigned | Invalid | 0
258294 |  | Story | GD Support of Zeta - EAD 8 Part 2: IA Patching and STIGs-INVALIDATED | Unassigned | Invalid | 0 | #258291
258289 |  | Story | GD Support of Zeta - EAD 8 Part 2: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #258294
258286 |  | Story | GD Support of Zeta - EAD 7: ILS IETM updates | Unassigned | Invalid | 0 | #258280
258285 |  | Story | GD Support of Zeta - EAD 7: Agile Team Test (Unit Test, Install, PCR Verification, STCD Dev & Test) | Unassigned | Invalid | 0 | #258280
258284 |  | Story | GD Support of Zeta - EAD 7: IA Patching and STIGs (Provided by Zeta) | Unassigned | Invalid | 0 | #258281
258283 |  | Story | GD Support of Zeta - EAD 7: Release Notes Inputs | Unassigned | Invalid | 0 | #258280
258282 |  | Story | GD Support of Zeta - EAD 7: Engineering IETM updates | Unassigned | Invalid | 0 | #258286
258281 |  | Story | GD Support of Zeta - EAD 7: IA Posture Assessment | Unassigned | Invalid | 0 | #258280
258280 |  | Story | Feature Demo- Customer Demo Event - Feature 258277 | Unassigned | Invalid | 0 | #258278
258279 |  | Story | GD Support of Zeta - EAD 7: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #258284
258278 |  | Story | GD Support of Zeta - EAD 7: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
258272 | #258263 | Story | AMS-GS Alarm Distribution: ILS IETM updates | Unassigned | Invalid | 0 | #258266
258271 | #258263 | Story | AMS-GS Alarm Distribution: Development Team Test Inputs | Unassigned | Invalid | 0 | #258266
258270 | #258263 | Story | AMS-GS Alarm Distribution: IA Patching and STIGs | Unassigned | Invalid | 0 | #258267
258269 | #258263 | Story | AMS-GS Alarm Distribution: Release Notes Inputs | Unassigned | Invalid | 0 | #258266
258268 | #258263 | Story | AMS-GS Alarm Distribution: Engineering IETM updates | Unassigned | Invalid | 0 | #258272
258267 | #258263 | Story | AMS-GS Alarm Distribution: IA Posture Assessment | Unassigned | Invalid | 0 | #258266
258266 | #258263 | Story | Feature Demo- AMS-GS Alarm Distribution | Unassigned | Invalid | 0 | #258264
258265 | #258263 | Story | AMS-GS Alarm Distribution: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #258270
258264 | #258263 | Story | AMS-GS Alarm Distribution: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
258263 |  | Feature | AMS-GS Phase 2: Implement/test AMS-GS Alarm Distribution - PI6 | Unassigned | Rejected
258255 | #258246 | Story | GD Support of Zeta - EAD-6: ILS IETM updates | Unassigned | Invalid | 0 | #258249
258253 |  | Story | GD Support of Zeta - EAD-6: IA Patching and STIGs Support - INVALIDATED | Unassigned | Invalid | 0
258251 |  | Story | GD Support of Zeta - EAD-6: Engineering IETM updates - INVALIDATED | Unassigned | Invalid | 0
258238 |  | Story | Update AWARE IATT document - INVALIDATED | Unassigned | Invalid | 0
258225 | #262145 | Story | Update EMP to address MCP and MUOS Agile Process Document | Unassigned | Invalid | 0
258129 |  | Task | Test 1 | Unassigned | Invalid
257560 | #242141 | Feature | TD 19-10 Finalize AWARE Design Documentation | EA 14.4 | Done
257559 |  | Feature | Incorporate AWARE Alarms/Events into NetCool | Unassigned | Rejected
257558 |  | Feature | Distribute AWARE Alarms/Events to NMS | Unassigned | Rejected
257555 |  | Feature | Provide AWARE O-Level IETMs - Part 2 | Unassigned | Rejected
257549 | #244386 | Feature | Analysis of Integration of AWARE Test Logs into SA | Unassigned | Rejected
257548 | #216593 | Feature | Analyze Proposed Mobility Changes | Unassigned | Rejected
257547 | #216592 | Feature | Analyze Proposed Resource Allocation Changes | Unassigned | Rejected
257325 | #245572 | Story | RTT Updates for Health Check Procedure | Unassigned | Invalid | 0
256995 | #219623 | Story | Perform Feature Demo | Unassigned | Invalid | 0
256991 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) inf202-wh-nma | Unassigned | Invalid | 0
256990 |  | Story | xx | Unassigned | Invalid | 0
256988 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) lan201-wh-nma | Unassigned | Invalid | 0
256986 |  | Story | xx | Unassigned | Invalid | 0
256978 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) inf202-wh-nma (High Side) | Unassigned | Invalid | 0
256974 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) prxylb202-wh-nma - High Side | Unassigned | Invalid | 0
256970 |  | Story | xx | Unassigned | Invalid | 0
256902 | #219381 | Feature | Analyze MUOS Component Failover Mechanisms | Unassigned | Rejected
256886 |  | Task | PMW/Validator to review and finalize the initial unclassified DRAFT POAM. GD to provide unclassified draft POAM maintenance file to PMW/Validator. | Unassigned | Invalid
256884 | #262029 | Task | GD/LM to generate workbooks for all Operational, Management, and Technical security control assessments, and associated Draft RAR for review | Unassigned | Invalid
256882 | #225733 | Feature | Analyze Repair-Replace Procedures | Unassigned | Rejected
256877 |  | Task | LM & GD to post all ASD STIG Workbooks & Associated RARs for review for All ASD STIG workbook & RAR | Unassigned | Invalid
256872 | #225733 | Feature | Analyze Repair-Replace Process | Unassigned | Rejected
256871 |  | Task | LM & GD to post Workbook & Associated RAR post for review for All Component Group STIGS (both low & high side) workbook & associated RAR | Unassigned | Invalid
256864 |  | Task | LM - Post workbooks & associated RAR developed from the ACAS Scans for all Component Groups (both low & high side) | Unassigned | Invalid
256863 |  | Task | LM - Create RMF POAM based on the analysis being performed in PI4 & PI5 | Unassigned | Invalid
256831 |  | Feature | Identify RBS IETM Changes | Unassigned | Rejected
256709 | #262145 | Story | AMS-GS activities continue to drain HBSS development capacity | Unassigned | Invalid | 0
256707 | #262145 | Story | McAfee removal tool expires quarterly | Unassigned | Implementing | 0
256515 |  | Story | test story 2 | Unassigned | Invalid | 0
256496 |  | Feature | Need to Describe use of Reprovision button in SAR Edit_Copy in IETM | Unassigned | Rejected
256460 |  | Story | Test Story | Unassigned | Invalid | 0
256333 |  | Story | Feature 244024: Remove Legacy Alt Geo: HW/SW Mapping | Unassigned | Invalid | 0
256096 | #245564 | Feature | Assess Early AWARE Phase 1 Operation | Unassigned | Rejected
256095 |  | Feature | Multi-Site AWARE Design Analysis | Unassigned | Rejected
256094 |  | Feature | Multi-Site AWARE Radio Equipment Plan | Unassigned | Rejected
256065 |  | Story | Scrum Master - DII Sprint Commitment | Unassigned | Invalid | 0
255774 |  | Story | RMF Step 3 – Review ASD STIG results for deployed applications (JBOSS scripts) | Unassigned | Invalid | 0
255768 | #261463 | Story | RMF Step 3 – Review ASD STIG results for deployed applications (F5 BIG_IP scripts) | Unassigned | Invalid | 0
255703 |  | Task | RMF Step 3 - Tech Assessment Support (Analysis)-Windows 2003-NMS (Apache) (High) Workbook | Unassigned | Invalid
255702 |  | Story | xx | Unassigned | Invalid | 0
255700 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis)- TFDU - NTP (High) Workbook | Unassigned | Invalid | 0
255547 |  | Story | Adjucation documentation for MOTE_S30 | Unassigned | Invalid | 0
255541 |  | Story | Adjucation documentation for MOTE_S23 | Unassigned | Invalid | 0
255537 |  | Story | Adjucation documentation for MOTE_S19 | Unassigned | Invalid | 0
255518 |  | Story | Adjucation documentation for MOTE_E24 | Unassigned | Invalid | 0
255517 |  | Story | Adjucation documentation for MOTE_E23 | Unassigned | Invalid | 0
255513 |  | Story | Adjucation documentation for MOTE_E18 | Unassigned | Invalid | 0
255511 |  | Story | Adjucation documentation for MOTE_E15 | Unassigned | Invalid | 0
255500 |  | Story | Adjucation documentation for MOTE_S30 | Unassigned | Invalid | 0
255499 |  | Story | Adjucation documentation for MOTE_S29 | Unassigned | Invalid | 0
255497 |  | Story | Adjucation documentation for MOTE_S27 | Unassigned | Invalid | 0
255496 |  | Story | Adjucation documentation for MOTE_S25 | Unassigned | Invalid | 0
255494 |  | Story | Adjucation documentation for MOTE_S23 | Unassigned | Invalid | 0
255493 |  | Story | Adjucation documentation for MOTE_S22 | Unassigned | Invalid | 0
255490 |  | Story | Adjucation documentation for MOTE_S19 | Unassigned | Invalid | 0
255487 |  | Story | Adjucation documentation for MOTE_S16 | Unassigned | Invalid | 0
255485 |  | Story | Adjucation documentation for MOTE_S14 | Unassigned | Invalid | 0
255483 |  | Story | Adjucation documentation for MOTE_S09 | Unassigned | Invalid | 0
255479 |  | Story | Adjucation documentation for MOTE_S04 | Unassigned | Invalid | 0
255478 |  | Story | Adjucation documentation for MOTE_E37 | Unassigned | Invalid | 0
255477 |  | Story | Adjucation documentation for MOTE_E36 | Unassigned | Invalid | 0
255476 |  | Story | Adjucation documentation for MOTE_E34 | Unassigned | Invalid | 0
255475 |  | Story | Adjucation documentation for MOTE_E30 | Unassigned | Invalid | 0
255474 |  | Story | Adjucation documentation for MOTE_E27 | Unassigned | Invalid | 0
255473 |  | Story | Adjucation documentation for MOTE_E26 | Unassigned | Invalid | 0
255471 |  | Story | Adjucation documentation for MOTE_E24 | Unassigned | Invalid | 0
255469 |  | Story | Adjucation documentation for MOTE_E22 | Unassigned | Invalid | 0
255466 |  | Story | Adjucation documentation for MOTE_E18 | Unassigned | Invalid | 0
255465 |  | Story | Adjucation documentation for MOTE_E16 | Unassigned | Invalid | 0
255458 |  | Story | Adjucation documentation for MOTE_E08 | Unassigned | Invalid | 0
255457 |  | Story | Adjucation documentation for MOTE_E07 | Unassigned | Invalid | 0
255456 |  | Story | Adjucation documentation for MOTE_E06 | Unassigned | Invalid | 0
255455 |  | Story | Adjucation documentation for MOTE_E05 | Unassigned | Invalid | 0
255452 |  | Story | Adjucation documentation for MOTE_S29 | Unassigned | Invalid | 0
255450 |  | Story | Adjucation documentation for MOTE_S27 | Unassigned | Invalid | 0
255449 |  | Story | Adjucation documentation for MOTE_S25 | Unassigned | Invalid | 0
255446 |  | Story | Adjucation documentation for MOTE_S22 | Unassigned | Invalid | 0
255440 |  | Story | Adjucation documentation for MOTE_S16 | Unassigned | Invalid | 0
255438 |  | Story | Adjucation documentation for MOTE_S14 | Unassigned | Invalid | 0
255436 |  | Story | Adjucation documentation for MOTE_S09 | Unassigned | Invalid | 0
255432 |  | Story | Adjucation documentation for MOTE_S04 | Unassigned | Invalid | 0
255431 |  | Story | Adjucation documentation for MOTE_E37 | Unassigned | Invalid | 0
255430 |  | Story | Adjucation documentation for MOTE_E36 | Unassigned | Invalid | 0
255429 |  | Story | Adjucation documentation for MOTE_E34 | Unassigned | Invalid | 0
255428 |  | Story | Adjucation documentation for MOTE_E30 | Unassigned | Invalid | 0
255427 |  | Story | Adjucation documentation for MOTE_E27 | Unassigned | Invalid | 0
255426 |  | Story | Adjucation documentation for MOTE_E26 | Unassigned | Invalid | 0
255423 |  | Story | Adjucation documentation for MOTE_E23 | Unassigned | Invalid | 0
255422 |  | Story | Adjucation documentation for MOTE_E22 | Unassigned | Invalid | 0
255418 |  | Story | Adjucation documentation for MOTE_E16 | Unassigned | Invalid | 0
255417 |  | Story | Adjucation documentation for MOTE_E15 | Unassigned | Invalid | 0
255411 |  | Story | Adjucation documentation for MOTE_E08 | Unassigned | Invalid | 0
255410 |  | Story | Adjucation documentation for MOTE_E07 | Unassigned | Invalid | 0
255409 |  | Story | Adjucation documentation for MOTE_E06 | Unassigned | Invalid | 0
255408 |  | Story | Adjucation documentation for MOTE_E05 | Unassigned | Invalid | 0
255220 | #219442 | Story | Update RAN IETMS to use new Procedures | Unassigned | Invalid | 0
255194 |  | Feature | Test Feature Summary, if found please close | Unassigned | Rejected
255192 |  | Feature | Test Feature Summary, if found please close | Unassigned | Rejected
255179 |  | Story | xx | Unassigned | Invalid | 0
255167 |  | Story | RMF Step 3 - General clean-up of the SP Supplement - part 1 | Unassigned | Invalid | 0
255165 |  | Story | RMF Step 3 - General clean-up of the SP Supplement - part 1 | Unassigned | Invalid | 0
254926 |  | Story | GD Support of Zeta - EAD-9 & FM Support: AMS-GS Geo Switch IA Findings - post EAD4 | Unassigned | Invalid | 0
254731 | #261463 | Story | RMF ASD STIG assess: JBOSS scripts (Cyber RMF needs by EA 5.1) | Unassigned | Invalid | 0
254725 | #261463 | Story | RMF ASD STIG assess: AAA scripts (Cyber RMF needs by EA 5.1) | Unassigned | Invalid | 0
254719 | #261463 | Story | RMF ASD STIG assess: IPWorks Element Manager scripts (Cyber RMF needs by EA 5.1) | Unassigned | Invalid | 0
254717 | #261463 | Story | RMF ASD STIG assess: F5 BIG_IP scripts (Cyber RMF needs by EA 5.1) - INVALIDATED | Unassigned | Invalid | 0 | #255768
254112 |  | Story | Update Recovery for RAN Alarms - Part 1 | Unassigned | Invalid | 0
254098 |  | Story | Provide Inputs to SE team for Recommendation | Unassigned | Invalid | 0
253980 | #232017 | Story | RDE Investigate UCM - Base ClearCase Interface | Unassigned | New | 3
253871 | #245560 | Feature | CI IA Hardening: 98-P59402M, NM Microsoft Windows 2003 Server, SVD | Unassigned | Rejected
253838 | #245560 | Feature | CI IA Hardening: 98-P54190T, NM Ericsson Multi Mediation, SVD | Unassigned | Rejected
253656 |  | Story | Add IETM procedures for white list alarms and update list of COTS alarms as needed (ET TFDU) | Unassigned | Invalid | 0
253396 | #241503 | Task | Document the process | Unassigned | Done
253395 | #241503 | Task | Establish recurring review of common CIs set to release within an EAR, Identify CI Owner | Unassigned | Done
253393 | #241503 | Task | Extract from RTC the Feature ID, EAR and EAD, Merge into CI Spreadsheet | Unassigned | Done
253392 | #241503 | Task | Use Feature Query stored in CQ to extract CI's and merge into common spreadsheet | Unassigned | Done
253390 | #241503 | Task | Update Scrum Master's Query and Upload into RTC, Communicate this to Mike Diaz | Unassigned | Done
253389 | #241503 | Task | Show Scrum Masters how to open a PCR, assign a llinked event with the FN Number | Unassigned | Done
253388 | #241503 | Task | Communicate that each Scrum Master needs to define their CI for each feature by 10/30/17 | Unassigned | Done
253256 |  | Task | VOBs need to be locked and unlocked before and after full backups | Unassigned | In Development
253241 |  | Story | xx | Unassigned | Invalid | 0
253223 |  | Story | RMF Step 3 – Review ASD STIG results for deployed applications – Part 2 (story 2 of 2 this sprint) | Unassigned | Invalid | 0
253216 | #246825 | Story | Determine prioritized minimum essential capabilities list for dashboards & reports to enable priority 2 & 1 users - Sprint 5 | Unassigned | Done | 0
252687 | #252677 | Story | MSISDN GDS: Story that captures remaining Story Pts for the feature | Unassigned | Invalid | 0
252685 | #252677 | Story | MSISDN GDS Development Team Test Inputs | Unassigned | Invalid | 0 | #252680
252684 | #252677 | Story | MSISDN GDS IA Patching and STIGs | Unassigned | Invalid | 0 | #252681
252683 | #252677 | Story | MSISDN GDS: Release Notes Inputs | Unassigned | Invalid | 0 | #252680
252682 | #252677 | Story | MSISDN GDS: Engineering IETM updates | Unassigned | Invalid | 0 | #252686
252681 | #252677 | Story | MSISDN GDS: IA Posture Assessment and MFR content | Unassigned | Invalid | 0 | #252680
252680 | #252677 | Story | Feature Demo - MSISDN GDS | Unassigned | Invalid | 0 | #252678
252679 | #252677 | Story | MSISDN GDS: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #252684
252678 | #252677 | Story | MSISDN GDS: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
252677 | #219668 | Feature | MSISDN Lookup when Function=GDS | Unassigned | Rejected
252556 | #233862 | Story | Reviews of LBIP IETM - Customer Collaboration (ET LBIP) | Unassigned | Invalid | 0
252400 | #221210 | Story | Investigate methods needed to make selected ETI data available to NMF operator and Splunk | Unassigned | Invalid | 0
252397 | #221210 | Story | ETI define how to use data for situational awareness of ranked issues 11 - 14 | Unassigned | Invalid | 0
252395 | #221210 | Story | ETI define how to use data for situational awareness of ranked issues 6 - 10 | Unassigned | Invalid | 0
252376 |  | Story | HBSS Development IETM Generation Part 1 | Unassigned | Invalid | 0
252370 | #221210 | Story | ETI define how to use data for situational awareness of ranked issues 1 - 5 | Unassigned | Invalid | 0
252253 |  | Story | RMF ASD STIG - Update 3 STIGS (Allen- 1 STIG) | Unassigned | Invalid | 0
252252 | #219403 | Story | Strategy and Implementation of Report Optimizations in Splunk: Test Splunk deployment with new structure | Unassigned | Invalid | 0
252249 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Nester- 1 STIG) | Unassigned | Invalid | 0
252248 |  | Story | RMF ASD STIG - Update 3 STIGS (Michael - 1 STIG) | Unassigned | Invalid | 0
252236 | #231220 | Task | EPIC TASK WILL BE BROKEN DOWN LMT - Develop & track validation feedback regarding Wahiawa Hawaii *RMF POAM, *ACAS workbook & RaR, *Stig workbook & RaR, *ASD Stig workbook & RaR | Unassigned | Invalid
252235 |  | Task | LMT & GD - Develop & publish RaR guidance document and how to perform analysis document | Unassigned | Invalid
252229 |  | Task | LM - Perform high side windows firewall workbook creation and analysis for all Windows Devices (Mark Muzzio) | Unassigned | Invalid
252225 |  | Task | LM - Perform high side ACAS scan for Wahiawa Hawaii data & create necessary component workbooks | Unassigned | Invalid
252220 |  | Task | PMW - Linux ACAS Laptop low side workbook creation and analysis | Unassigned | Invalid
252217 |  | Task | PMW - Linux ACAS laptop high side workbook creation and analysis | Unassigned | Invalid
252216 |  | Task | Test Task1 | Unassigned | Invalid
252205 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Chris- 1 STIG) | Unassigned | Invalid | 0
252204 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Jonathan- 1 STIG) | Unassigned | Invalid | 0
252201 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Nestor - 1 STIG) | Unassigned | Invalid | 0
252200 | #250456 | Story | Auto - Eggplant training - Batch 2 | Unassigned | Invalid | 0
252189 |  | Story | RMF Step 3 – Review ASD STIG results for deployed applications – Part 5 | Unassigned | Invalid | 0
252188 |  | Story | RMF Step 3 – Review ASD STIG results for deployed applications – Part 4 (PLACEHOLDER) | Unassigned | Invalid | 0
252169 | #242815 | Story | Release ILS AWARE Laptop CIs | Unassigned | Invalid | 0
252166 |  | Story | RMF ASD STIG - Update 3 STIGS (Dean - 1 STIG) | Unassigned | Invalid | 0
252165 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Tim - 1 STIG) | Unassigned | Invalid | 0
252163 |  | Story | Story has been marked as invalid ad a more concise story has been created to replace it - RMF ASD STIG - Update 3 STIGS (Tony - 1 STIG) | Unassigned | Invalid | 0
252159 | #232388 | Story | V-Lab TLE Update | Unassigned | Invalid | 0
252158 | #262134 | Story | IA Scan Study (BLOCKED) | Unassigned | Invalid | 0
252141 |  | Story | Analyze nodes / CI to Determine What needs to be ??? | Unassigned | Invalid | 0
252132 |  | Story | Develop Test Procedures For TXO RNC/RBS Board Testing (Part 2) | Unassigned | Invalid | 0
252120 |  | Story | Compare Actionable alarms with IETM | Unassigned | Invalid | 0
252111 |  | Story | Story marked as invalid, as a more concise story has replaced this one - RMF ASD STIG - Update 3 STIGS (Tim - 1 STIG) | Unassigned | Invalid | 0
252110 |  | Story | Story marked as invalid, as a more concise story has replaced this one - RMF ASD STIG - Update 3 STIGS (Michael - 1 STIG) | Unassigned | Invalid | 0
252108 |  | Story | Story marked as invalid, as a more concise story has replaced this one - RMF ASD STIG - Update 3 STIGS (Nestor - 1 STIG) | Unassigned | Invalid | 0
252107 | #248046 | Story | Colloborate & Support UX on KM inputs | Unassigned | Invalid | 0
252095 |  | Story | RMF ASD STIG - I.A. Review of STIGs (for DII & SA#2 teams) | Unassigned | Invalid | 0
252092 |  | Story | Invalid | Unassigned | Invalid | 0
252076 |  | Story | xx | Unassigned | Invalid | 0
252064 |  | Story | xx | Unassigned | Invalid | 0
252020 | #252010 | Story | delete | Unassigned | Invalid | 0
252019 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252013
252018 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252013
252017 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252014
252016 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252013
252015 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252019
252014 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252013
252013 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252011
252012 | #252010 | Story | delete | Unassigned | Invalid | 0 | #252017
252011 | #252010 | Story | delete | Unassigned | Invalid | 0
252010 |  | Feature | delete | Unassigned | Rejected
251995 | #248945 | Story | Write and deliver updated ROM | Unassigned | Invalid | 0
251993 | #248945 | Story | Resolve Roll Up and FOUO DMZ issue | Unassigned | Invalid | 0
251940 |  | Feature | Analyze Call Banks Use in MUOS Network Management | Unassigned | Rejected
251918 | #262146 | Story | Verify IETM PCR 303207, 311863 and 311779 | Unassigned | Invalid | 0
251819 |  | Story | Trouble Ticket Support (PI 4.3) | Unassigned | Invalid | 0
251752 |  | Story | SME to Evaluate/Repair AJMs - Repair Units (assume 2) - INVALIDATED | Unassigned | Invalid | 0
251748 |  | Story | SME to Evaluate/Repair AJMs - Test Units (assume 2) - INVALIDATED | Unassigned | Invalid | 0
251746 |  | Story | Support AWARE Scanning and Planning approach (EA 4.4) | Unassigned | Invalid | 0
251731 |  | Story | Docs for Connected AWARE WH FRCB: Include AWARE alignment spreadsheet for Release | Unassigned | Invalid | 0
251724 |  | Story | AMS-GS Phase 1 Deployment - PI4 - duplicate story 234556 created by Jessica K | Unassigned | Invalid | 0
251716 | #251706 | Story | <Feature xxx> Story that captures remaining Story Pts for the feature | Unassigned | Invalid | 0
251715 | #251706 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #251709
251714 | #251706 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #251709
251713 | #251706 | Story | <Feature xxx> IA Patching and STIGs | Unassigned | Invalid | 0 | #251710
251712 | #251706 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #251709
251711 | #251706 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #251715
251710 | #251706 | Story | Material and Administrative Changes to Support Cyber DT Assist Event : IA Posture Assessment and MFR content | Unassigned | Invalid | 0 | #251709
251709 | #251706 | Story | Feature Demo- | Unassigned | Invalid | 0 | #251707
251708 | #251706 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #251713
251707 | #251706 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
251706 | #216552 | Feature | Material and Administrative Changes to Support Cyber DT Assist Event | Unassigned | Rejected
251695 |  | Story | Invalid | Unassigned | Invalid | 0
251693 |  | Story | Develop & Support ADNS Testing Support between GD Lab & SSC PAC (LOE for PI4.3) | Unassigned | Invalid | 0
251685 | #220187 | Story | Provide V&V of Newly Tooled RBS Build Tools (BLOCKED) | Unassigned | Invalid | 0
251679 |  | Story | Invalid | Unassigned | Invalid | 0
251678 |  | Story | Develop and Support ADNS testing between GD VLAB and SSC PAC (LOE PI4 .3) | Unassigned | Invalid | 0
251673 |  | Story | Develop and Support ADNS testing between GD VLAB and SSC PAC (LOE PI4 .1) | Unassigned | Invalid | 0
251563 |  | Story | Review Zeta SDRLs | Unassigned | Invalid | 0
251560 |  | Story | Review Zeta SDRLs | Unassigned | Invalid | 0
251504 |  | Story | Develop & Support ADNS Testing Support between GD Lab & SSC PAC | Unassigned | Invalid | 0
251469 |  | Story | ILS work for ETISP Create alarms for human error IETM | Unassigned | Invalid | 0
251383 |  | Story | Develop & Support ADNS Testing Support between GD Lab & SSC PAC | Unassigned | Invalid | 0
251334 | #251324 | Story | <Feature xxx> Story that captures remaining Story Pts for the feature | Unassigned | Invalid | 0
251333 | #251324 | Story | <Feature xxx>:ILS IETM updates | Unassigned | Invalid | 0 | #251327
251332 | #251324 | Story | <Feature xxx> Development Team Test Inputs | Unassigned | Invalid | 0 | #251327
251331 | #251324 | Story | <Feature xxx> IA Patching and STIGs | Unassigned | Invalid | 0 | #251328
251330 | #251324 | Story | <Feature xxx>: Release Notes Inputs | Unassigned | Invalid | 0 | #251327
251329 | #251324 | Story | <Feature xxx>: Engineering IETM updates | Unassigned | Invalid | 0 | #251333
251328 | #251324 | Story | <Feature KAP TEST>: IA Posture Assessment and MFR content | Unassigned | Invalid | 0 | #251327
251327 | #251324 | Story | Feature Demo - | Unassigned | Invalid | 0 | #251325
251326 | #251324 | Story | <Feature xxx>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #251331
251325 | #251324 | Story | <Feature xxx>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
251324 |  | Feature | <Feature KAP TEST> | Unassigned | Rejected
251286 | #251276 | Story | <Feature 251276> Story that captures remaining Story Pts for the feature | Unassigned | New | 0
251285 | #251276 | Story | Splunk Dashboard ILS IETM updates | Unassigned | Done | 3 | #251279
251284 | #251276 | Story | Feature 251276: Development Team Test Inputs | Unassigned | New | 3 | #251279
251283 | #251276 | Story | Feature 251276: IA Patching and STIGs | Unassigned | New | 8 | #251280
251282 | #251276 | Story | Feature 251276: Release Notes Inputs | Unassigned | New | 2 | #251279
251281 | #251276 | Story | Feature 251276: Engineering IETM updates | Unassigned | New | 3 | #251285
251280 | #251276 | Story | Improve effectiveness of Splunk dashboard navigation: IA Posture Assessment and MFR content | Unassigned | New | 8 | #251279
251279 | #251276 | Story | Feature Demo - Feature 251276 | Unassigned | New | 5 | #251277
251278 | #251276 | Story | Feature 251276: IA Posture Assessment - development input | Unassigned | New | 2 | #251283
251277 | #251276 | Story | Feature 251276: Initiate CM PDO Processing for all CI's | Unassigned | New | 1
251276 | #219668 | Feature | Improve effectiveness of Splunk dashboard navigation | Unassigned | Approved
251248 | #246191 | Story | Support Ka-band robustness SUT switching: IA Posture Assessment | Unassigned | Invalid | 0
250992 |  | Story | HBSS Test Remaining HIPS installs in SWIT. | Unassigned | Invalid | 0
250949 | #259557 | Story | Test Improve group data/multicast suitability: WF buffering improvements (PCR 16183) | Unassigned | New | 5
250873 |  | Story | RMF Step 3 - Review ASD STIG results for deployed applications - part 3 | Unassigned | Invalid | 0
250820 | #219438 | Story | As a ggsn SME, provide routing engine replacement procedures to the site level operators so that they can recover from a faulty ggsn routing engine board. | Unassigned | Invalid | 0
250818 |  | Task | Rejected: TR _ SIEM investigate data Flow from FOUO to SECRET | Unassigned | New
250616 | #259557 | Story | Test Issue - Develop group buffering improvements in WF (PCR 16183) | Unassigned | Invalid | 0
250426 | #250422 | Task | Populate program backlog | Unassigned | Invalid
250425 | #250422 | Task | Create a roadmap | Unassigned | Invalid
250424 | #250422 | Task | Create a program vision | Unassigned | Invalid
250423 | #250422 | Task | Configure program environment | Unassigned | Invalid
250422 |  | Task | Not valid Delete | Unassigned | Invalid
250320 |  | Story | CSO to revise Spare Inventory Report to correct additional issues (Fitch work) | Unassigned | Invalid | 0
250255 | #221231 | Story | Feature Demo - Customer Event - Auto Factory Logging | Unassigned | New | 5
250169 |  | Story | TR - Detailed Plan for KG175A replacement | Unassigned | Invalid | 0
250118 |  | Task | TR - Planning and Provisioning | Unassigned | Invalid
249856 |  | Story | Aware 1b - Run additional scans/stigs | Unassigned | Invalid | 0
249854 |  | Story | Aware 1b - Analyze results of additional scans/stigs | Unassigned | Invalid | 0
249834 | #243410 | Story | PCR MUOSD00311821 NMS KG-175A HAIPEs - TT INC000002168406 GD to Comply with Security Bulletin: ALCOMS 126/17 and 129/167 | Unassigned | Invalid | 0
249832 | #243410 | Story | PCR MUOSD00311820 SSA Operations KG-175A HAIPEs - TT INC000002168406 GD to Comply with Security Bulletin: ALCOMS 126/17 and 129/167 | Unassigned | Invalid | 0
249831 | #243410 | Story | PCR MUOSD00311819 GIS KG-175A HAIPEs - TT INC000002168406 GD to Comply with Security Bulletin: ALCOMS 126/17 and 129/167 | Unassigned | Invalid | 0
249401 | #262145 | Story | LOE is not tracked consistently by each team (some reduce velocity and some create story points), so metrics could be off | Unassigned | Invalid | 0
249400 | #262145 | Story | A person on MUOS was assigned more than 8 points in a sprint. Later, when they said they couldn't complete the work, they were told they had to complete it. | Unassigned | Invalid | 0
249397 |  | Story | It appears as though we are micro-managing agile by adding more and more process | Unassigned | Done | 0
249350 | #245573 | Feature | UE Ka Doppler Model | Unassigned | Draft
249334 | #243511 | Feature | MUOS-5 RRT Validity | Unassigned | Rejected
249086 | #219454 | Story | PM Delivery Dashboard: Cyber Considerations | Unassigned | Invalid | 0
249084 | #219454 | Story | PM Delivery Dashboard: ILS Considerations | Unassigned | Invalid | 0
249082 | #221231 | Story | Auto Logging: Create IA Posture Assessment | Unassigned | New | 5
249076 | #221231 | Story | Rework SW change to eliminate IA concern | Unassigned | New | 13
249055 | #219751 | Story | Decouple Splunk Dashboard Queries from Hardcoded Indices: ILS IETM updates | Unassigned | Invalid | 0 | #238178
249051 | #219403 | Story | Strategy and Implementation of Report Optimizations in Splunk: ILS IETM updates | Unassigned | Invalid | 0 | #249055 #249068 #249053
249050 |  | Story | Fix even more Cat 1 finding | Unassigned | Invalid | 0
249038 |  | Story | Prepare and execute RFR test | Unassigned | Invalid | 0
249017 |  | Story | xx | Unassigned | Invalid | 0
249003 |  | Story | <Feature xxx> Story that captures remaining Story Pts for the feature | Unassigned | Invalid | 0
248684 |  | Feature | Old | Unassigned | Rejected
248680 | #248352 | Story | <Feature yyy>:ILS IETM updates | Unassigned | Invalid | 0 | #248355
248675 | #248352 | Story | <Feature yyy> Development Team Test Inputs | Unassigned | Invalid | 0 | #248355
248662 | #248352 | Story | <Feature yyy> IA Patching and STIGs and Risk Management Framework (RMF) Security Plan (SP) Supplement, and initial IA Posture assessment, needed 100 days prior to FRCB | Unassigned | Invalid | 0 | #248661
248661 | #248352 | Story | <Feature yyy>: IA Posture Assessment and MFR needed 30 days prior to FRCB | Unassigned | Invalid | 0 | #248355
248659 | #248352 | Story | <Feature yyy>: Release Notes Inputs | Unassigned | Invalid | 0 | #248355
248658 | #248352 | Story | <Feature yyy>: Engineering IETM updates | Unassigned | Invalid | 0 | #248680
248657 | #248352 | Story | <Feature yyy>: IA Posture Assessment - development input | Unassigned | Invalid | 0 | #248662
248655 | #248352 | Story | <Feature yyy>: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
248556 |  | Feature | Delete | Unassigned | Rejected
248455 | #241246 | Story | <Feature xxx>: Perform Iterative Implementation, Integration, development Testing including updating design | Unassigned | Invalid | 0 | #241249 #247204
248438 |  | Feature | Plan, coordinate, execute depot activities to support AMS-GS, AWARE deployments | Unassigned | Rejected
248414 | #241246 | Story | <Feature xxx> Document Initial capability specification and detailed design to start Implementation | Unassigned | Invalid | 0 | #243678 #317816 #248455
248355 | #248352 | Story | <Feature yyy>: Feature Demo | Unassigned | Invalid | 0 | #248655
248352 |  | Feature | <Feature yyy> (New HW, FRCB) OBE | Unassigned | Rejected
248250 | #219668 | Feature | Index Other CDR Types: MAS, SGSN, etc. | Unassigned | Rejected
248249 | #246827 | Feature | Speed up PM/CDR/FM data receipt (Research) | Unassigned | Analyzing
248248 | #245408 | Feature | Deduplicate FM data in Splunk index | Unassigned | Rejected
248240 |  | Feature | Assess Value of Improvements to AWARE | Unassigned | Rejected
248124 | #221627 | Story | Test Issue - OTA: Waveform unexpectedly stores joined_to_group in LKS during automated calls (PCR 16172) | Unassigned | Invalid | 0
248123 | #221627 | Story | Analyze, Develop, and Release Issue - OTA: Waveform unexpectedly stores joined_to_group in LKS during automated calls (PCR 16172) | Unassigned | Invalid | 0
248121 |  | Story | Delete | Unassigned | Invalid | 0
248120 | #221627 | Story | Test Issue - OTA: Periodic Rach Ranging did not apply correctly in a corner case (PCR 16174) | Unassigned | Invalid | 0
248119 | #221627 | Story | Analyze, Develop, and Release Issue - OTA: Periodic Rach Ranging did not apply correctly in a corner case (PCR 16174) | Unassigned | Invalid | 0
248117 |  | Story | Delete me | Unassigned | Invalid | 0
248061 | #246065 | Feature | TOFF Issue Analysis | Unassigned | Rejected
248038 | #216688 | Story | Test Issue - 384K DCH power is fluctuating 4 dB in an AWGN channel (PCR 16158) | Unassigned | Invalid | 0
248037 | #216688 | Story | Analyze, Develop, and Release Issue - 384K DCH power is fluctuating 4 dB in an AWGN channel (PCR 16158) | Unassigned | Invalid | 0
248035 | #216688 | Story | Test Issue - Transit IMSI permission granted but the WF goes OOS 3 to 4 times before completing registration (PCR 16156) | Unassigned | Invalid | 0
248034 | #216688 | Story | Analyze, Develop, and Release Issue - Transit IMSI permission granted but the WF goes OOS 3 to 4 times before completing registration (PCR 16156) | Unassigned | Invalid | 0
248032 | #216688 | Story | Test Issue - Transmit IMSI Denied causes the WF to continuously loop through acquisition (PCR 16155) | Unassigned | Invalid | 0
248031 | #216688 | Story | Analyze, Develop, and Release Issue - Transmit IMSI Denied causes the WF to continuously loop through acquisition (PCR 16155) | Unassigned | Invalid | 0
247991 | #225731 | Feature | Analyze CDRs for Improvements | Unassigned | Rejected |  | #290942
247914 | #247907 | Story | Pareto all CDR error/problem causes: Release Briefing | Unassigned | Invalid | 0
247913 | #247907 | Story | Pareto all CDR error/problem causes: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
247912 | #247907 | Story | Pareto all CDR error/problem causes: ILS IETM updates - checklist | Unassigned | Invalid | 0
247911 | #247907 | Story | Pareto all CDR error/problem causes: IA Posture Assessment and MFR | Unassigned | Invalid | 0
247910 | #247907 | Story | Pareto all CDR error/problem causes: Feature Demo | Unassigned | Invalid | 0
247909 | #247907 | Story | Pareto all CDR error/problem causes: IA Posture Assessment - development input | Unassigned | Invalid | 0
247908 | #247907 | Story | Pareto all CDR error/problem causes: Initiate CM PDO Processing for CI <CI name> | Unassigned | Invalid | 0
247907 | #219670 | Feature | Pareto all CDR error/problem causes | Unassigned | Rejected
247897 | #247890 | Story | Workstation performance issues: Release Briefing | Unassigned | Invalid | 0
247896 | #247890 | Story | Feature 247890: Engineering IETM updates | Unassigned | Invalid | 0
247895 | #247890 | Story | Feature 247890: ILS IETM updates | Unassigned | Invalid | 0
247894 | #247890 | Story | Feature 247890: IA Posture Assessment | Unassigned | Invalid | 0
247893 | #247890 | Story | Feature 247890 Development Team Test Inputs | Unassigned | Invalid | 0
247892 | #247890 | Story | Feature 247890: IA Posture Assessment - development input | Unassigned | Invalid | 0
247891 | #247890 | Story | Feature 247890: Initiate CM PDO Processing for CI workstation | Unassigned | Invalid | 0
247890 | #246826 | Feature | Workstation performance phase 1 | Unassigned | Rejected
247889 |  | Feature | Workstation performance issues with Firefox & Splunk | Unassigned | Rejected
247839 | #344196 | Story | MUOS Geolocation Support/Maintenance: Remove Geo SW (GSSC application) from the workstation | Unassigned | Invalid | 0
247830 |  | Task | Rejected: TR - Sentinel SIEM application replacement | Unassigned | Invalid
247742 | #247718 | Feature | Review & Comment Operational Command CONOPS document (draft 1.2 8/3/2017) | Unassigned | Rejected
247735 | #247718 | Feature | Review & Comment ITSM Help Desk CONOPS document (released 11/1/2016) | Unassigned | Rejected
247701 |  | Story | Remove Legacy Alt Geo: IA Posture Assessment - development input | Unassigned | Invalid | 0
247699 |  | Feature | delete | Unassigned | Rejected
247621 |  | Story | Cyber Sustain Spare - duplicate | Unassigned | Invalid | 0
247516 | #247513 | Story | Feature Demo - Retire SA Data from PPA | Unassigned | Invalid | 0
247513 | #217406 | Feature | Stop CDR/PM/FM Data ingest into PPA database (Implement) | Unassigned | Rejected
247492 | #228636 | Feature | Implement UX restructuring of ETI switchover procedure and NMF FOUO workstation case 3 IA posture improvement | Unassigned | Rejected
247487 | #247492 | Story | UX restructuring of ETI switchover procedure define design details | Unassigned | Invalid | 0
247474 | #258337 | Story | New FM MIB needed to Support Load Balancer v13 | Unassigned | New | 0
247439 |  | Task | Reject: TR - MUOS Intrusion Detection System (IDS) replacement | Unassigned | New
247438 |  | Story | TLSDD needs to be updated to reflect updates for AMS-GS updates to Geolocation | Unassigned | Invalid | 0
247322 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS Key Management | Unassigned | Invalid | 0
247321 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS Network_LB | Unassigned | Invalid | 0
247320 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS ExtremeSwitch | Unassigned | Invalid | 0
247319 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS Network_Router | Unassigned | Invalid | 0
247318 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS Firewall_Network | Unassigned | Invalid | 0
247316 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI Account Maintenance Plan | Unassigned | Invalid | 0
247314 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI Tectia | Unassigned | Invalid | 0
247313 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI PKI | Unassigned | Invalid | 0
247312 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI AAA/DNS | Unassigned | Invalid | 0
247311 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI SAN | Unassigned | Invalid | 0
247310 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI RAID | Unassigned | Invalid | 0
247309 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI Backup Archive (TSM) | Unassigned | Invalid | 0
247308 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI TPM | Unassigned | Invalid | 0
247307 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI GS Windows 2012 Server | Unassigned | Invalid | 0
247305 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI NMS Windows 2012 Server | Unassigned | Invalid | 0
247302 |  | Story | HBSS Prepare For Deployment: Initiate CM PDO Processing for CI HBSS | Unassigned | Invalid | 0
247222 |  | Story | delete | Unassigned | Invalid | 0
247221 |  | Story | delete | Unassigned | Invalid | 0
247220 |  | Story | delete | Unassigned | Invalid | 0
247219 |  | Story | delete | Unassigned | Invalid | 0
247218 |  | Story | delete | Unassigned | Invalid | 0
247217 |  | Story | delete | Unassigned | Invalid | 0
247216 |  | Story | delete | Unassigned | Invalid | 0
247215 |  | Feature | delete | Unassigned | Rejected
247213 | #265531 | Story | <Feature 238135>: Release Briefing | Unassigned | New | 1
247212 |  | Story | <Feature 238135>: ILS Considerations (non-IETM) | Unassigned | Invalid | 0
247211 | #265531 | Story | <Feature 238135>: ILS IETM updates | Unassigned | New | 3
247210 | #265531 | Story | Feature 265531: IA Posture Assessment and MFR | Unassigned | New | 5
247209 | #265531 | Story | Feature Demo: AMS-GS Phase 2 Integrate NMS software for the AMS-GS servers - Part 2 | Unassigned | New | 5
247208 | #265531 | Story | Feature 238135: IA Posture Assessment - development input | Unassigned | New | 3
247207 |  | Story | delete | Unassigned | Invalid | 0
247206 |  | Feature | delete | Unassigned | Rejected
247204 | #241246 | Story | <Feature xxx>: MFR 3 – CSE Performs initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #241248
247200 |  | Feature | AMS-GS Phase 2 Decomposition - Drops for DT-Assist and TechEval | Unassigned | Rejected
247186 |  | Story | delete | Unassigned | Invalid | 0
247185 |  | Story | delete | Unassigned | Invalid | 0
247184 |  | Story | delete | Unassigned | Invalid | 0
247183 |  | Story | delete | Unassigned | Invalid | 0
247182 |  | Story | delete | Unassigned | Invalid | 0
247181 |  | Story | delete" | Unassigned | Invalid | 0
247180 | #265531 | Story | Feature 238135: Initiate CM PDO Processing for CI <CI name> | Unassigned | New | 1
247179 |  | Feature | delete | Unassigned | Rejected
247169 | #344196 | Story | MUOS Geolocation Support/Maintenance: Move GEO 201 AMS-GS SVD into Extreme Switch SVD | Unassigned | Invalid | 0
247108 | #221090 | Story | Correcting Labels on Congestion Management Dashboards | Unassigned | Invalid | 0
247099 | #245437 | Story | SA Help and IETM Updates for Intersite Connectivity "No News =Unknown" | Unassigned | Invalid | 0
247097 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Update Intersite Connectivity Dashboards | PI 14 | Invalid | 0
247087 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Enabler: Investigate Approach for Ping Probe Alarms | PI 14 | Invalid | 0
247082 | #263127 | Story | Change Intersite Status so That "No News=Bad News": Enabler: Investigate Approach for BGP Alarms | PI 14 | Invalid | 0
246970 | #246012 | Feature | Implementation of incident management workflow for MUOS | Unassigned | Rejected
246585 |  | Task | TR - TPM CRL workflow replacement (study) | Unassigned | New
246327 | #216631 | Story | PLAN - RAN EAD 8 Release: Execute all Required Scans and STIGs for critical GMAP messages Feature | Unassigned | Invalid | 0 | #246321
246321 | #216631 | Story | Create IA Posture Assesment for critical GMAP messages Feature | Unassigned | Invalid | 0
246312 | #216556 | Story | Create Release Notes and Knowledge Transfer Data | Unassigned | New | 1
246302 | #216556 | Story | Create IA Posture Assesment for AddMe GSL Improvements Feature | Unassigned | New | 3
246203 |  | Story | Calibrate New Tray | Unassigned | Invalid | 0
246179 | #221627 | Story | WF PCR 16174 [Part1 analysis/implement] Update initial and periodic ranging to support OTA with KA doppler. | Unassigned | Invalid | 0
246165 |  | Story | ETISP/ETI - Help with SW Integration with FW on ETISP | Unassigned | Invalid | 0
246159 | #245718 | Task | Reject: TR - TPM Unix patching workflow replacement (Study) | Unassigned | Invalid
246156 | #245718 | Task | Reject: TR - TPM windows patching workflow replacement (study) | Unassigned | Invalid
246132 | #216556 | Story | Release AddMe GSL Improvements Feature | Unassigned | New | 3
246130 | #216556 | Story | Perform all required IA Scans and Stigs for AddMe GSL Improvements Feature | Unassigned | New | 2
246121 | #216556 | Story | Implement Solution for Add-Me GSL expiration during active call | Unassigned | Implementing | 3
246091 |  | Feature | AMS-GS Phase 1 Deployment and On-Site Integration/Testing - PI5 | Unassigned | Rejected
246083 |  | Feature | Delete | Unassigned | Rejected
246078 |  | Feature | AMS-GS Phase 2: Analyze FCAPS Changes with Zeta | Unassigned | Rejected
246077 | #246012 | Feature | Understand industry best practices and how to adopt better practices | Unassigned | Approved
246049 | #262145 | Story | Develop Program Level Retrospective Metrics for I&A | Unassigned | New | 3
246048 | #262145 | Story | Establish WIP Metrics | Unassigned | New | 5
245928 |  | Story | Feature <xxx>: Training Identified | Unassigned | Invalid | 0
245919 | #261824 | Story | Provide PPA Training (BLOCKED) | Unassigned | Invalid | 0
245887 | #232210 | Story | Remove ERS VLab Bypass | Unassigned | Invalid | 0
245885 |  | Story | Execute Deployment Plan - Build New AWARE Production Rack | Unassigned | Invalid | 0
245880 |  | Story | Teardown current AWARE Production Rack and take to Depo for Shipping | Unassigned | Invalid | 0
245815 |  | Task | Rejected: TR - Update the GemX application | Unassigned | Invalid
245756 |  | Story | As a SME support for oss-rc and netcool, I will ensure that Ericsson ggsn alarm for the routing engine displays on the operation view as a minor. | Unassigned | Invalid | 0
245755 | #245437 | Task | GGSN Routing Engine Alarms - Update FM Whitelist | Unassigned | Done
245753 |  | Task | Rejected: Create digital ETI software development system | Unassigned | Invalid
245718 |  | Task | TR - Windows Obsolescence TPM | Unassigned | Invalid
245687 | #216662 | Feature | TR - DSN-Gateway System Requirements Review/System Functional Review (SRR/SFR) | Unassigned | Rejected
245555 |  | Task | Rejected: Digital ETI create MATLAB MUOS modem model | Unassigned | Invalid
245471 |  | Story | <Feature >: | Unassigned | Invalid | 0
245470 |  | Story | <Feature >: | Unassigned | Invalid | 0
245469 |  | Story | <Feature >: | Unassigned | Invalid | 0
245468 |  | Story | <Feature >: | Unassigned | Invalid | 0
245467 |  | Story | <Feature >: | Unassigned | Invalid | 0
245466 |  | Story | <Feature >: | Unassigned | Invalid | 0
245465 |  | Story | <Feature >: | Unassigned | Invalid | 0
245443 | #245402 | Feature | Develop Availability Model to Support WCDMA Service Management Metrics | Unassigned | Rejected
245428 | #245408 | Feature | Indexing all/more FM data into Splunk | Unassigned | Rejected
245335 |  | Feature | AMS-GS Phase 1 Release/Deployment | Unassigned | Rejected
245328 | #245063 | Feature | Perform Robustness & Reliability WCDMA Targeted Testing | Unassigned | Rejected
245322 | #245063 | Feature | Perform Robustness & Reliability FCAPS Targeted Testing | Unassigned | Rejected
245300 | #245063 | Feature | Create Robustness & Reliability FCAPS Test Plan | Unassigned | Rejected
245299 | #245063 | Feature | Create Robustness & Reliability WCDMA Test Plan | Unassigned | Rejected
244750 | #245569 | Story | Hyperion SVD redlines from site 8/17 | Unassigned | Invalid | 0
244739 |  | Story | Reject: Unsupported versions of McAfee Virus Enterprise and McAfee Common Framework for Windows XP | Unassigned | Invalid | 0
244724 |  | Feature | Deploy global test Groups and call scenarios | Unassigned | Rejected
244721 |  | Feature | Analyze Use of Test Groups by SA | Unassigned | Rejected
244719 |  | Feature | Create Test Call Scenarios using Global Test Groups | Unassigned | Rejected
244700 |  | Feature | Implement Module GNH to Central GNH Alarm/Event Interface | Unassigned | Rejected
244682 | #225731 | Feature | Add Generation of Group BLER CDR by RNC | Unassigned | Analyzing
244678 | #225731 | Feature | Add Generation of PTP BLER CDR by RNC | Unassigned | Analyzing
244677 |  | Feature | Update AWARE Installation Drawings | Unassigned | Rejected
244456 | #343253 | Story | Feature 343253:: Increase Disk Drive Spares in RAID Array | Unassigned | New | 3
244455 | #343253 | Story | RAID Array Fault Reporting to Netcool | Unassigned | New | 13
243886 |  | Story | Feature Demo - Display Operational Capability (Up/Down Status) of Each SBC (Implementation) | Unassigned | Invalid | 0
243678 | #241246 | Story | <Feature xxx>: Provide Deployment Notes and Operator Impact Inputs | Unassigned | Invalid | 0 | #241249
243385 | #243505 | Story | Investigate usage of SMART DRIVE parameters to do pro-active health check of Build Machine Hard Disks | Unassigned | Invalid | 0
242966 | #216722 | Story | i | Unassigned | Invalid | 0
242963 |  | Story | Create AWARE Release Notes | Unassigned | Invalid | 0
242961 |  | Story | Regression Test Final AWARE Image | Unassigned | Invalid | 0
242960 |  | Task | Reject: Update AWARE SVD and other Document | Unassigned | Invalid
242956 |  | Story | Analyze and Fix IA Cat1 findings | Unassigned | Invalid | 0
242880 |  | Task | delete | Unassigned | Invalid
242750 |  | Task | Rejected: Scrum Master tasks | Unassigned | Invalid
242452 |  | Feature | Rejected: Develop NMS tech refresh plan to support long term plan | Unassigned | Rejected
242431 | #262145 | Feature | Usage of RTC Problem work items instead of CQ PCRs (Phase 1 Feasibility only) | Unassigned | Rejected
242247 |  | Story | Rejected: Integrate AMS-GS with DMZ Load Balancer v13 | Unassigned | Invalid | 0
242124 |  | Story | xx | Unassigned | Invalid | 0
242065 |  | Task | Rejected: Obsolescence: Digital ETI Ugrade Sub-Strategy | Unassigned | Invalid
241866 | #245563 | Story | Test the Polatis after it has been replaced. | Unassigned | Invalid | 0
241847 |  | Story | Reject: AMS-GS: IETM Support | Unassigned | Invalid | 0
241818 |  | Story | Coordinate to get VPSI / PWM rep account on GD SIPRNET workstation in SEL - delete | Unassigned | Invalid | 0
241577 | #245898 | Feature | Rejected: Obsolescence - Windows Obsolescence Trade Study Phase 1 | Unassigned | Rejected
241567 | #241577 | Story | TR - Virtual Environment, Hypervisor, section of MUOS VM Trade Study | Unassigned | Invalid | 0
241344 |  | Task | TR - Windows Obsolescence Initial Implementation Plan | Unassigned | Invalid
241252 | #241246 | Story | <Feature xxx>: Develop IETMs and Perform Development Testing | Unassigned | Invalid | 0 | #241249
241251 |  | Story | <Feature yyy>: verify PCRs | Unassigned | Invalid | 0
241250 | #241246 | Story | <Feature xxx>: MFR 3 – CSE Completes Final CAP | Unassigned | Invalid | 0 | #241249
241249 | #241246 | Story | <Feature xxx>- Prep and Perform Feature Demo – Customer Demo Event | Unassigned | Invalid | 0
241248 | #241246 | Story | <Feature xxx>: MFR 3 - Dev Team Supports Initial Cybersecurity Assessment | Unassigned | Invalid | 0 | #317820
241247 | #216601 | Story | Feature 216601: Improve NMS to OSS-RC Interface Reliability - Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
241246 |  | Feature | <Feature xxx> Template | Unassigned | Rejected
241187 | #232210 | Story | Aware Site Mech & RF Install | Unassigned | Invalid | 0
241079 | #343253 | Story | Feature 343253: IETM Update for Database Restoration | Unassigned | New | 13
241078 | #343253 | Story | Feature 343253: IETM Enhancements for RAID Array Drive Replacement | Unassigned | New | 13
241077 | #343253 | Story | Redlines for AV/HIDS SVD | Unassigned | New | 8
241076 | #343253 | Story | Redlines for RAID Array SVD (Array Spares) | Unassigned | New | 8
241034 | #241029 | Task | Pilot dashboard tabs | Unassigned | Done
240494 | #216430 | Story | Feature Demo - SA - Enter a Group ID/Name and View Provisioning Data | Unassigned | Done | 2 | #216430
240351 |  | Story | CQ PCR has old/outdated data fields when moving PCRs to verifying state. | Unassigned | Invalid | 0
240042 | #216556 | Story | Create STCD for Addme GSL Improvements Feature | Unassigned | New | 1
239788 |  | Story | ASD STIG needs to be done for the RCG - Cyber team - duplicate | Unassigned | Invalid | 0
239190 |  | Story | Auto - AWARE: Debug the IncFailed option of AWARE's CELL_ADVANCE feature | Unassigned | Invalid | 0
239186 | #234347 | Story | Create RBDs | Unassigned | Invalid | 0
239140 | #262146 | Feature | Assess ILS Lifetime Buys | Unassigned | Done
239123 | #262145 | Feature | Develop Program Controls | Unassigned | Rejected
239118 |  | Feature | Define Consistent Usage of Program Board during PI planning | Unassigned | Rejected
238855 |  | Story | Add 'replacement SN' field to CRM note | Unassigned | Invalid | 0
238798 | #233365 | Story | IA scan and analysis of R2.1 SCS Workstation | Unassigned | Invalid | 0 | #249085
238647 | #232010 | Story | DITL - Work with IA team to harden laptop for DITL NIPRNET testing | Unassigned | Invalid | 0
238556 |  | Story | Investigate whether RAF Load Balancer Failovers meet failover requirements | Unassigned | Invalid | 0
238189 |  | Feature | MUOS Feature | PI 16 | Rejected
238123 | #238135 | Story | AMS-GS DNS Updates to Remove Extra IP Addresses | Unassigned | New | 3
238110 |  | Task | (deleted) | Unassigned | Invalid
237602 | #239123 | Story | Update Agile/RTC Processes to Account for ETC needed for Monthly Program Reports | Unassigned | Invalid | 0
237177 |  | Story | HBSS NMS Windows 2012 Patches and STIGs Supporting FRCB IA Posture Assessment | Unassigned | Invalid | 0
237050 | #235787 | Story | Identify new network file sharing software for the lab/tools network environment and install it | Unassigned | Invalid | 0
237049 | #235787 | Story | Prioritize fixing the tools before they break/fail, instead of just working around the problems | Unassigned | Invalid | 0
237047 | #235787 | Story | Track and quantify the failure rate for deliveries and builds | Unassigned | Invalid | 0
236933 | #221695 | Story | Enhance SA for GDS registration failures, GEMX Networking, & Ping Probes (Enabler) | Unassigned | New | 2
236863 | #231457 | Story | Socialize OTAP performance improvement approach with customer stakeholders | Unassigned | Invalid | 0
236862 | #231457 | Story | Perform trade study to choose OTAP performance | Unassigned | Invalid | 0
236833 | #231507 | Story | Define system design for ability to search PPA provisioning data | Unassigned | Invalid | 0
236824 | #226024 | Story | As a tester I need a U2B BLER test system to that I can verify performance with new RxIM algorithms | Unassigned | New | 5
236822 |  | Story | As a Systems Engineer I need to define which data must be collected to identify, isolate and recover common ETI issues and failures | Unassigned | Invalid | 0
236807 |  | Story | HBSS FRCB IDP Tables | Unassigned | Invalid | 0
236804 |  | Story | HBSS IDP Tables and CIs in support of FRCB | Unassigned | Invalid | 0
236799 |  | Story | Complete restructure of strategy/sub-strategy | Unassigned | Invalid | 0
236794 |  | Story | As a Systems Engineer I need to add ET upgrades to strategy so obsolescence work is defined and prioritized | Unassigned | Invalid | 0
236790 |  | Story | Map MOT&E findings to the Strategies | Unassigned | Invalid | 0
236789 | #236564 | Story | Put MOT&E findings into the 4 categories | Unassigned | Invalid | 0
236774 | #245561 | Story | HBSS Support app201 HIPS Transitiion | Unassigned | Invalid | 0
236762 |  | Story | As a Systems Engineer I need an ETI tech refresh strategy to define needed epics | Unassigned | Invalid | 0
236707 | #262145 | Story | Need to determine what options and/or improvements should be made to limit the amount of duplicate work being tracked in RTC vs. CQ | Unassigned | Invalid | 0
236704 | #239314 | Story | Need to investigate time and money into our infrastructure (build machines, test automation, cross training, process definition, metrics, etc), Need a Tools Roadmap | Unassigned | Invalid | 0
236698 | #262145 | Story | Need to assess what we plan to do for PI level System Demos and in particular upcoming PI 3 | Unassigned | Invalid | 0
236675 | #239316 | Story | Update Roles for PO, PM | Unassigned | Invalid | 0
236608 |  | Story | Verify changes to the network status reporting. | Unassigned | Invalid | 0
236607 | #231643 | Story | Implement changes to the network status reporting. | Unassigned | Invalid | 0
236440 | #221134 | Story | Submit Zeta test report (30 days prior to deployment) (need for FRCB) (classed and unclassed) | Unassigned | Invalid | 0
236435 | #219503 | Story | Transition Activities Sprint 3.2 | Unassigned | Invalid | 0
236431 | #219503 | Story | Router SVD and review | Unassigned | Invalid | 0
236358 | #217041 | Feature | Standard Operating Procedure and Manual for SIPRNET Access | Unassigned | Approved
236165 | #245573 | Feature | Implement Transmit Timing and Frequency Control in the GS as defined in M1.2 and M1.3 of the CAI ICD Addm 6 | Unassigned | Rejected
236031 | #216606 | Story | Investigate New RNC Alarm/Event Mechanism, Part 1 | Unassigned | Invalid | 0
235842 | #245563 | Story | HBSS TR NMS SIEM new EMC RAID hardware secret enclave - INVALIDATED | Unassigned | Invalid | 0
235809 | #289988 | Story | Separate NEDB, PKI and Account Maintenance Plan into different components | Unassigned | Invalid | 0
235808 | #235787 | Story | Upgrade other build servers to Windows Server 2008 R2 - duplicate | Unassigned | Invalid | 0
235806 |  | Story | Install Rational Suite on NMS Windows 7 Development Machine - duplicate | Unassigned | Invalid | 0
235805 | #235787 | Story | Upgrade GTS build servers to Server 2008 R2 | Unassigned | Invalid | 0
235718 | #220031 | Story | IA Posture assessment for SGSN | Unassigned | Invalid | 0
235669 | #235673 | Story | S2-Bob LOE Inc3 | Unassigned | Invalid | 0
235657 | #234568 | Story | LOE for Waveform support | Unassigned | Invalid | 0
235637 | #243511 | Story | GD Personnel to be at site for Northwest power down starting 8/21/17. | Unassigned | Invalid | 0
235590 |  | Story | xx | Unassigned | Invalid | 0
235580 | #226025 | Story | Stretch: ETISP - eRxIM STCD dev | Unassigned | Invalid | 0
235579 | #235271 | Story | Aware site HW and RF install - Val | Unassigned | Invalid | 0
235577 | #221134 | Story | Create AMS-GS STCD | Unassigned | Invalid | 0
235571 | #221695 | Story | Enhance SA for GDS registration failures | Unassigned | New | 5
235570 | #259557 | Story | Analyze, Develop, and Release Issue - Develop group buffering improvements in WF (PCR 16183) | Unassigned | New | 8 | #250949
235569 | #221251 | Story | Update documents/review issues to seek approval to deliver scripts to the sites. | Unassigned | New | 3
235562 |  | Story | Reject: Make sure GNL requests correct data usage on addme group addition. | Unassigned | Invalid | 0
235560 | #220529 | Story | Delete entries in the statistic storage table in MHAL's database that are incorrect. | Unassigned | New | 2
235559 | #220529 | Story | Create and integrate a function that overwrites statstic analysis data points in the MHAL database. | Unassigned | New | 3
235558 | #216660 | Story | Create a background task within the MHAL browser interface for proof of concept. | Unassigned | New | 3
235554 |  | Story | Stretch: Test PCR | Unassigned | Invalid | 0
235553 |  | Story | Reject: Verify GNL asking for correct data usage on addme group addition. | Unassigned | Invalid | 0
235550 | #221695 | Story | Enhance SA for GDS registration failures, GEMX Networking, & Ping Probes (Enabler) | Unassigned | New | 3
235549 | #216607 | Story | Secret NMF - HAIPE201 Single Point of Failure (Enabler) | Unassigned | Invalid | 0
235543 |  | Story | Establish baseline without eRxIM with test vector (thermal noise) | Unassigned | Invalid | 0
235541 |  | Story | Measure eRxIM performance using Test Vector #4 | Unassigned | Invalid | 0
235540 | #226025 | Story | Update test plan for expanded lab test | Unassigned | Invalid | 0
235538 | #232248 | Story | Debug Certificate Issue | Unassigned | Invalid | 0
235537 | #216607 | Story | Secret NMF - HAIPE201 Single Point of Failure (Enabler) | Unassigned | Invalid | 0
235534 |  | Story | Enhance SA for GDS registration failures (rejected) | Unassigned | Invalid | 0
235533 |  | Story | GIS Firewall log analysis (rejected) | Unassigned | Invalid | 0
235532 | #221251 | Story | Review/Test all updated scripts in V-Lab to get ready for System Demo | Unassigned | New | 5
235531 | #221251 | Story | Develop/Test bash scripts for switch log collections | Unassigned | New | 3
235527 |  | Story | Reject: Keep GSL up during addme expiration on listener leg while call is still active. | Unassigned | Invalid | 0
235526 |  | Story | Reject: Generate AMS-GS SVD to support deployment 1. include refs to zeta SVDs 2. to include sequencing of install AV/HIDS, HW drive, etc. | Unassigned | Invalid | 0
235523 | #216660 | Story | Install and integrate gems within the MHAL web server | Unassigned | New | 2
235521 |  | Task | Rejected: DITL Prep 2nd week of 3.3 | Unassigned | Invalid
235520 |  | Story | Reject: Test PCR | Unassigned | Invalid | 0
235519 |  | Story | Reject: Verify addme expiration on listener leg still receive data 100% reliably. | Unassigned | Invalid | 0
235516 | #221695 | Story | Enhance SA for GDS registration failures, GEMX Networking, & Ping Probes (Enabler) | Unassigned | New | 5
235515 | #221694 | Story | Check Site GIS Firewall Logs For Exceptions (Enabler) | Unassigned | Invalid | 0
235514 |  | Story | Reject: Implement and developer test PCR | Unassigned | Invalid | 0
235513 |  | Task | Reject: Analyze MIL-STD issue | Unassigned | Invalid
235511 |  | Story | Reject: AMS-GS Disposition zeta cdrls w/ cm and subcontracts | Unassigned | Invalid | 0
235510 |  | Story | Reject: Need detailed AMS-GS integration on-ramp sequence from Zeta. | Unassigned | Invalid | 0
235506 | #234568 | Task | Check GIS Firewall logs for exceptions sprint 3 | Unassigned | Done
235504 | #232248 | Story | Install MAS and other Java Environment on Development Web Server | Unassigned | Invalid | 0
235500 | #221694 | Story | GIS Firewall log analysis | Unassigned | Invalid | 0
235498 | #220031 | Story | SGSN STCD execution and PCR verification | Unassigned | Invalid | 0
235497 | #221251 | Story | Fix date/time issue in SGSN scripts | Unassigned | New | 1
235491 |  | Story | Every 10 minutes, rnc check for each GNL make sure still establish. If it went away, then re-establish. | Unassigned | Invalid | 0
235490 |  | Story | From Anthony Silva. T400 IETM update for faulted DGS600 card. | Unassigned | Invalid | 0
235489 |  | Story | Risk Reduction: Final Integration Build | Unassigned | Invalid | 0
235488 |  | Story | delete me | Unassigned | Invalid | 0
235484 |  | Story | delete me | Unassigned | Invalid | 0
235483 |  | Story | delete me | Unassigned | Invalid | 0
235480 |  | Task | Delete me | Unassigned | Invalid
235478 |  | Story | Review R3.1C TACLANE IETM Updates (verify update incorporated correctly.) | Unassigned | Invalid | 0
235477 |  | Task | Rejected: Implement and developer test PCR | Unassigned | Invalid
235476 |  | Story | Rejected: Analyze MIL-STD issue | Unassigned | Invalid | 0
235469 |  | Story | ETISP - Update ETISP L3 test procedures | Unassigned | Invalid | 0
235468 |  | Story | ETISP - FW integration with sw | Unassigned | Invalid | 0
235465 | #221694 | Story | Check GIS Firewall logs for exceptions (enabler) | Unassigned | Invalid | 0
235463 | #220766 | Story | ETISP - eRxIM STCD execute | Unassigned | Invalid | 0
235454 |  | Story | Rejected: MAS-OOS Load Balancer Release | Unassigned | Invalid | 0
235452 | #221251 | Story | Remove all expect scripts out of the Auto Logging Delivery package | Unassigned | New | 2
235451 | #221251 | Story | Stretch: Remove TPM SVD out of the Auto Logging Delivery package | Unassigned | New | 1
235436 | #245318 | Story | GDS profiles for OTA GDS testing | Unassigned | Invalid | 0
235434 |  | Story | delete me | Unassigned | Invalid | 0
235423 |  | Story | Analyze MIL-STD issue, MIL-STD TC 04_101 (PCR16146) | Unassigned | Invalid | 0
235276 | #216722 | Feature | Install lab AWARE hardware | Unassigned | Rejected
235248 | #293721 | Story | Auto - [Seq. 6] Modify MultiHAL to use the new Windows Domain on the new E2E Automation Server. | Unassigned | Invalid | 0
235245 | #293721 | Story | Auto - [Seq. 5] Create a new Windows Domain on the new E2E Automation Server and VMs | Unassigned | Invalid | 0 | #235248
235240 | #232079 | Story | Auto - [SPIKE] Evaluate and identify scope of work | Unassigned | Invalid | 0
235202 | #293721 | Story | Auto - [Seq. 3] Configure E2E Automation Cisco switches with VLANs for each new VM (ITLAB) | Unassigned | Invalid | 0
235200 | #221218 | Story | UX review of B2U and U2B site alignment procedures | Unassigned | Invalid | 0
235197 | #293721 | Story | Auto - [Seq. 4] Migrate the E2E Automation laptops/desktops to VMs | Unassigned | Invalid | 0
235196 | #293721 | Story | Auto - [Seq. 1] Update new ITLAB E2E Automation server with the same OS and base configuration as the new WDE Automation server | Unassigned | Invalid | 0 | #235197 #235202
234919 | #238135 | Story | AMS-GS Update PKI Deployment Plan | Unassigned | Invalid | 0
234909 | #221218 | Story | Analyze Site Alignment Procedure Manipulation of ETISP Configuration Files | Unassigned | Invalid | 0
234805 |  | Story | I/A / Cyber Team needs to do ASD STIG for RCG - duplicate | Unassigned | Invalid | 0
234798 |  | Story | Sprint 2 - Vendors, HMS, DMR and Team - Brian | Unassigned | Invalid | 0
234752 | #262145 | Story | Define how MUOS uses LOE and what metrics are needed | Unassigned | New | 5
234708 |  | Story | LOE Allen SP? | Unassigned | Invalid | 0
234707 |  | Story | R2.1 IETM PCR Verifications -NAVSOC T501/T500 related | Unassigned | Invalid | 0
234698 |  | Story | LOE 3.1 | Unassigned | Invalid | 0
234697 |  | Story | LOE 3.1 | Unassigned | Invalid | 0
234696 |  | Story | LOE 3.1 | Unassigned | Invalid | 0
234686 | #234683 | Feature | Backfill PI 3 RMF assessment activities that were to be performed by ISSEs (no longer on MUOS as of 8/1/2017) | Unassigned | Rejected
234679 | #234683 | Feature | Backfill PI 3 RMF assessment activities that were to be performed by IA Validator (no longer on MUOS as of 8/1/2017) | Unassigned | Rejected
234676 | #234683 | Feature | Backfill PI 3 RMF assessment activities that were to be performed by ISSO (no longer on MUOS as of 8/1/2017) | Unassigned | Rejected
234598 | #216597 | Story | Review changes - Detect when the RNC GCK misalignment continues after GCK refresh and either switch to the backup PDR/RCG or stop cover keystream requests | Unassigned | Invalid | 0
234596 | #216597 | Story | Implement and unit test - Detect when the RNC GCK misalignment continues after GCK refresh and either switch to the backup PDR/RCG or stop cover keystream requests | Unassigned | Invalid | 0
234594 | #216597 | Story | Investigate - Detect when the RNC GCK misalignment continues after GCK refresh and either switch to the backup PDR/RCG or stop cover keystream requests | Unassigned | Invalid | 0
234590 | #246787 | Story | LOE 3.1 | Unassigned | Done | 0
234589 |  | Story | LOE 3.4 | Unassigned | Invalid | 0
234588 |  | Story | LOE 3.3 | Unassigned | Invalid | 0
234587 |  | Story | LOE 3.2 | Unassigned | Invalid | 0
234586 |  | Story | LOE 3.1 | Unassigned | Invalid | 0
234585 |  | Story | LOE 3.4 | Unassigned | Invalid | 0
234584 |  | Story | LOE 3.3 | Unassigned | Invalid | 0
234583 |  | Story | LOE 3.2 | Unassigned | Invalid | 0
234582 |  | Story | LOE 3.1 | Unassigned | Invalid | 0
234572 | #216568 | Story | Identify modules that need be be changed for failure handling GCK Rekey between NMS ,RCG,OSSRC and RNC | Unassigned | Invalid | 0
234567 | #216568 | Story | Investigate GCK Rekey failure between NMS , OSSRC and RNC | Unassigned | Invalid | 0
234559 |  | Story | GD Send AMS-GS Equipment (cables, labels, etc) | Unassigned | Invalid | 0
234557 | #219764 | Story | Feature Demo - RNC - Maintain Established GNLs | Unassigned | Invalid | 0 | #219764
234553 | #216565 | Story | Feature Demo for Call Stability Improvements ID'd in Inc1 | Unassigned | Invalid | 0 | #216565
234548 | #216556 | Story | Feature Demo - Perform Demo for RNC AddMe GSL Improvements Feature | Unassigned | New | 1 | #216556
234543 | #216631 | Story | Feature Demo - Customer Event - Add an acknowledgement message to the critical GMAP messages | Unassigned | Invalid | 0 | #216631
234540 |  | Feature | EAD-2 Deployment Work through Gov't CCB | Unassigned | Rejected
234514 | #216721 | Story | CM PDO Processing - ETISP Memory Leak CIs | Unassigned | Done | 1
234513 | #243505 | Story | As an engineer I need to be able to flag Stories as Expedited or Fixed Date so that I can organize my Kanban properly to account for these specialized kinds of stories | Unassigned | New | 0
234369 |  | Feature | Prevent generation of TS information through data correlation - Release and Test | Unassigned | Rejected
234335 | #243505 | Feature | IT Lab Upgrade for RAN | Unassigned | Rejected
234237 | #250467 | Story | (SVD update) PKI - RCG instructions missing steps to remove obsolete CRL | Unassigned | Invalid | 0
233883 |  | Story | Need SME to evaluate LBIP 01400017, SN# AL151775550 - INVALIDATED | Unassigned | Invalid | 0
233881 | #216598 | Story | Review changes to add additional granularity to error codes between RCG and RNC | Unassigned | Invalid | 0
233880 |  | Story | Need SME to evaluate LBIP 01400017, SN# AL081609626 - INVALIDATED | Unassigned | Invalid | 0
233879 |  | Story | Review changes to refresh GCK ID when RNC detects it may have stale key data | Unassigned | Invalid | 0
233872 |  | Story | Hold review for IA patches we do not own yet Feature 216566 | Unassigned | Invalid | 0
233856 |  | Feature | IETM procedures for CRITICAL ET alarms - TFDU | Unassigned | Rejected
233847 | #216351 | Feature | Add alarm summary text for ETISP & ERS whitelist alarms which currently have no summary | Unassigned | Draft
233828 | #282088 | Story | Evaluate current whitelist (ET/FEP), alarms indeterminate and unassigned severities | Unassigned | New | 5
233805 |  | Feature | IETM procedures for MAJOR ET alarms - ETISPW | Unassigned | Rejected
233801 |  | Feature | IETM procedures for CRITICAL ET alarms - ETISPW | Unassigned | Rejected
233745 |  | Feature | Test Feature for Training Purposes | Unassigned | Rejected
233718 | #220078 | Feature | Enable FACH switching with PtX established while NOT congested | Unassigned | Analyzing
233717 | #220078 | Feature | Enable FACH switching for IP UM/streaming services | Unassigned | Analyzing
233642 |  | Story | Evaluate current whitelist, identify changes that need to be implemented | Unassigned | Invalid | 0
233607 |  | Feature | MUOS Feature - delete | Unassigned | Rejected
233576 |  | Story | Correct the SCS switch configuration linespeed on the port connected to the HAIPE | Unassigned | Invalid | 0
233569 |  | Story | Correct the mtu configuration so that it is permanently set on the rtlogic servers in the RAF | Unassigned | Invalid | 0
233499 | #217798 | Feature | AMS-GS R3.1.C GD CIs Needed for EAD2 | Unassigned | Rejected
233492 |  | Story | HBSS POAM Review of existing AV/HIDS | Unassigned | Invalid | 0
233425 |  | Story | Correct HQ red switch configuration and procedure for bench installation of spare switch. | Unassigned | Invalid | 0
233406 |  | Story | RCG SVD | Unassigned | Invalid | 0
233383 |  | Story | EA 3.5 Paul Tools Support | Unassigned | Invalid | 0
233359 |  | Feature | REJECTED - Define Short Term Analysis Engine Mitigation Strategy | Unassigned | Rejected
233275 | #232019 | Story | OSSRC: As a Developer, I want to be able to provide a patch build for test before delivery, so that I can iterate testing of my changes independently | Unassigned | New | 2
233274 | #232017 | Story | RBS: As a Developer, I want to be able to provide a patch build for test before delivery, so that I can iterate testing of my changes independently 5.1 candidate | Unassigned | New | 2
233272 | #232019 | Story | OSSRC: As a Builder, I want to build each CI on the command line, so that I can implement a continuous integration build mechanism | Unassigned | New | 2
233254 |  | Story | EA 3.4 Paul Tools Support | Unassigned | Invalid | 0
233253 |  | Story | EA 3.3 Paul Tools Support | Unassigned | Invalid | 0
233252 |  | Story | EA 3.2 Paul Tools Support | Unassigned | Invalid | 0
233251 |  | Story | EA 3.1 Paul Tools Support | Unassigned | Invalid | 0
233246 | #232019 | Story | OSSRC: As a Developer, I want a simple mechanism that will build everything, so that I can focus on implementation rather than on building | Unassigned | Implementing | 2
233244 | #232019 | Story | OSSRC: As a Developer, I want an easy mechanism to Deliver changes to the Build, so that I can focus on fixing my next PCR | Unassigned | New | 2
233235 | #238135 | Story | PKI Document, Syntax error in A.6.3 (updating SSH keys) for Series J routers. | Unassigned | New | 1
233234 |  | Story | Site visit to NCTAMS NMF for discussions and observation of day-to-day operations | Unassigned | Invalid | 0
233110 |  | Feature | Whitelist Updates, pass 2: Core/GIS and related subsystems | Unassigned | Rejected
233104 |  | Feature | Whitelist Updates, pass 2: RAN and related subsystems | Unassigned | Rejected
233100 |  | Feature | Whitelist Updates, pass 2: ET and related subsystems | Unassigned | Rejected
233008 |  | Feature | Alarm Analysis & Whitelist Filter Implementation, pass 2: NMS (FOUO side) | Unassigned | Rejected
233000 |  | Feature | Alarm Analysis, pass 2: RAN and related subsystems | Unassigned | Rejected
232994 |  | Feature | Alarm Analysis, pass 2: ET and related subsystems | Unassigned | Rejected
232804 |  | Story | John EA 3.4 Tool Support | Unassigned | Invalid | 0
232803 |  | Story | John EA 3.3 Tool Support | Unassigned | Invalid | 0
232802 |  | Story | John EA 3.2 Tool Support | Unassigned | Invalid | 0
232800 |  | Story | Nick EA 3.4 Tool Support | Unassigned | Invalid | 0
232799 |  | Story | Nick EA 3.3 Tool Support | Unassigned | Invalid | 0
232797 |  | Story | Nick EA 3.2 Tool Support | Unassigned | Invalid | 0
232796 | #245561 | Story | R2.1 Site Deployment Impacts to NM AAA 98-P54188T SVD | Unassigned | Invalid | 0
232795 |  | Story | Eric EA 3.4 Tool Support | Unassigned | Invalid | 0
232793 |  | Story | Eric EA 3.3 Tool Support | Unassigned | Invalid | 0
232792 |  | Story | Eric EA 3.2 Tool Support | Unassigned | Invalid | 0
232790 |  | Story | Eric EA 3.1 Tool Support | Unassigned | Invalid | 0
232788 |  | Story | John EA 3.1 Tool Support | Unassigned | Invalid | 0
232778 | #217152 | Feature | Call Bank Metrics Improvements | Unassigned | Approved
232653 |  | Story | MUOSD00306839 INC000000261214: HQ - SWI-HQ - Unable to login | Unassigned | Invalid | 0
232649 |  | Story | MUOSD00289005 SPAS00000142531 IETM: A lock learning procedure is needed for IETM | Unassigned | Invalid | 0
232525 | #217026 | Feature | Improve group data/multicast suitability: application performance testing of WF buffering improvements | Unassigned | Ready for System IPT Approval
232521 | #217026 | Feature | Improve group data/multicast suitability: implement WF buffering improvements | Unassigned | Rejected
232496 | #245561 | Story | HBSS System Demo Report in Support of FRCB | Unassigned | Invalid | 0
232446 | #245561 | Story | IETM routine task to check HBSS backups are still making it all the way to tape | Unassigned | Invalid | 0
232443 | #245561 | Story | Cleanup Backup_Archive logs for HBSS | Unassigned | Invalid | 0
232366 | #217632 | Feature | Research Better Map Visualization Capability | Unassigned | Approved
232365 |  | Feature | Pass 2 FM whitelist updates for ET/ETISP/etc alarms (analysis) | Unassigned | Rejected
232354 | #229255 | Feature | Provide repository for site support personnel identifying service interruptions or outages per CI | Unassigned | Analyzing
232341 | #210216 | Feature | Improve NMS Build Robustness | Unassigned | Rejected
232323 | #232209 | Story | Remove ipworks servers and hostname procedures from IETM, PKI, and Account Maintenance documentation | Unassigned | New | 5
232317 | #232209 | Story | Update drawings, parts list and hardware software maps to remove ipworks servers. | Unassigned | New | 13
232309 | #232209 | Story | Transition the ipworks server DHCP functions to a supportable device | Unassigned | New | 8
232277 | #232209 | Story | Update NMS equipment (SIEM, FM Ping Probe, AAA, AV HIDS, PPA/EMA) to remove IPworks server functions | Unassigned | New | 8
232275 | #232209 | Story | Update switch ports to ipworks servers. | Unassigned | New | 2
232263 | #232209 | Story | Disable IPworks servers and perform UE test call function | Unassigned | New | 2
232248 | #227708 | Feature | Update document and train to prevent generation of TS information through data correlation | Unassigned | Rejected
232221 | #232209 | Story | Transition the ipworks server rac and lac dns functions to a supportable device | Unassigned | New | 8
232217 | #232209 | Story | Transition the ipworks server apn dns functions to a supportable device | Unassigned | New | 13
232212 | #232210 | Story | Reject: Determine what to deploy with the AWARE radios to the site. | Unassigned | Invalid | 0
232209 | #243511 | Feature | Transition the ipworks server dns and dhcp functions to a supportable device to reduce foot print and increase efficiency | Unassigned | Draft | 0
232204 |  | Story | xx | Unassigned | Invalid | 0
232203 |  | Story | RMF ASD STIG assess: spare 1 | Unassigned | Invalid | 0
232201 |  | Story | RMF ASD STIG assess: spare 2 | Unassigned | Invalid | 0
232197 |  | Story | RMF ASD STIG assess: spare 3 | Unassigned | Invalid | 0
232189 |  | Story | RMF ASD STIG assess: spare 4 | Unassigned | Invalid | 0
232181 |  | Story | RMF ASD STIG assess: 98-P59418M NM OSS-RC Interface | Unassigned | Invalid | 0
232078 | #280393 | Story | Site Maintainer depot level procedure for NAVSOC Juniper J-series routers is incomplete for FIPS software and configuration installation | Unassigned | Invalid | 0
232022 | #234568 | Story | Call Barring | Unassigned | Invalid | 0
232021 |  | Task | LOE Stability Inc3 (duplicate of 234568) | Unassigned | Invalid
232016 | #225732 | Feature | Improve the capturing of OSS-RC alarms by Fault Management | PI 15 | Rejected |  | #291129
231578 |  | Story | Add TFDU alarms to whitelist | Unassigned | Invalid | 0
231567 |  | Feature | Perform ADNS Testing between GD Vlab and SSC Pacific Labs | Unassigned | Rejected
231531 |  | Feature | Call Stability Improvements INC4 | Unassigned | Rejected
231524 |  | Story | (Re-) Define Scope for NetOps analysis | Unassigned | Invalid | 0
231508 | #231494 | Feature | Implement Ability to Search Provisioning Data | Unassigned | Rejected
231490 | #216707 | Feature | *DELETE ME* Enhance SA for GDS Registration Failures (Enabler - Continued) | Unassigned | Rejected
231470 |  | Story | delete | Unassigned | Invalid | 0
231469 |  | Story | Delete | Unassigned | Invalid | 0
231458 | #217036 | Feature | Implement OTAP Performance Improvements | Unassigned | Rejected
231457 | #217036 | Feature | System Design for OTAP Performance | Unassigned | Rejected
230795 | #219762 | Story | ASD STIG Questionaire IA Evaluation for RNC and RBS- delete | Unassigned | Invalid | 0
230756 | #220766 | Story | ASD ETISP STIG IA Evaluation EAD3.0 | Unassigned | Invalid | 0 | #235714
230746 |  | Story | ASD RTT STIG Questionaire IA Evaluation - delete | Unassigned | Invalid | 0
230415 |  | Story | **DELETE ME* | Unassigned | Invalid | 0
230414 |  | Story | **DELETE ME** | Unassigned | Invalid | 0
230120 | #216469 | Story | BKM: Test - Create Feature STCD - Delete | Unassigned | Invalid | 0
230118 |  | Story | BKM: Order final CD with max number of keys for system demo - delete | Unassigned | Invalid | 0
230117 |  | Feature | MUOS enabler Feature Template | Unassigned | Rejected
230051 | #216547 | Feature | Laptop XP eradication | Unassigned | Rejected
228688 |  | Feature | Add Group Audit and Group Provisioning Troubleshooting Detail to IETM | Unassigned | Rejected
228609 | #232019 | Story | OSSRC: As a Release Manager, I want to release OSSRC build artifacts using MUOS build prototype | Unassigned | New | 5
228608 | #232017 | Story | RBS: As a Release Manager, I want to release RBS build artifacts using MUOS build prototype 5.1 candidate | Unassigned | New | 5
228435 | #220530 | Story | (Break down the feature.) Translate MHAL'S nightly archive to Ruby. | Unassigned | Invalid | 0
228351 | #221231 | Story | Rsync work to achieve auto logging story. | Unassigned | Done | 3
228258 | #217377 | Story | Static IP STCD regression after PPA is installed. | Unassigned | Invalid | 0
228237 |  | Story | Create Account Maintenance password update procedure for the SCS Black workstation user | Unassigned | Invalid | 0
228197 |  | Story | Verity IETM PCR 308165 | Unassigned | Invalid | 0
228024 |  | Story | xx | Unassigned | Invalid | 0
228021 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) - Part 5 (PLACEHOLDER) | Unassigned | Invalid | 0
228020 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) - Part 4 (PLACEHOLDER) | Unassigned | Invalid | 0
228018 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) - Part 6 (PLACEHOLDER) | Unassigned | Invalid | 0
228014 |  | Story | RMF Step 4 - placeholder | Unassigned | Invalid | 0
228010 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) Sprint 3 - Part 1 | Unassigned | Invalid | 0
227925 |  | Story | RMF Step 3 - On Site Tech Assessment - Sprint 2 - GD Rep 3 (Sally) - delete | Unassigned | Invalid | 0
227924 |  | Story | RMF Step 3 - On Site Tech Assessment - Sprint 1 - GD Rep 5 (Sally) - delete | Unassigned | Invalid | 0
227921 |  | Story | RMF Step 3 - On Site Tech Assessment - Sprint 1 - GD Rep 2 (Craig) -delete | Unassigned | Invalid | 0
227916 |  | Story | RMF Step 3 – eMASS testing of the tools used for SAR and POAM - part 2 - delete | Unassigned | Invalid | 0
227824 |  | Feature | (IETM) PtX Inactivity Timeout controls in PPA are unclear | Unassigned | Rejected
227607 |  | Story | Tim's Story: Code, unit test, and review the changes on the RCG and RNC. PCR309692 | Unassigned | Invalid | 0
227601 | #219157 | Feature | Obtain Government approval to operate MUOS Transec Controller (MTC) and classified Anti-Jam modem in GD's Scottsdale lab (moved from LM SIL) | Unassigned | Analyzing
227273 |  | Story | Obtain AWARE IA Stakeholder Approval for remote NMF | Unassigned | Invalid | 0
227096 | #226080 | Feature | IA Hardening: NMS Solaris DNSEM Component | Unassigned | Rejected
226973 | #216594 | Feature | Update Leap Second Script | Unassigned | Rejected
226856 |  | Feature | Enhance RNC VLAB log capture | Unassigned | Rejected
226280 |  | Feature | R2.1 Release completion and support | Unassigned | Rejected
226025 | #216718 | Feature | eRxIM CONUS interference mitigation lab test | Unassigned | Rejected
226024 | #216718 | Feature | Investigate rebuilding U2B BLER test system (Enabler) | Unassigned | Approved
225944 |  | Feature | Execution Environment Improvements for Phase 2 | Unassigned | Rejected
225451 | #217806 | Story | VLAB Execute Client Roll Out Plan ( for Secondary MGS Adapter) | Unassigned | Invalid | 0
225361 | #225355 | Task | Need to rebuild Cisco Splunk indexer in CVI LAB | Unassigned | Invalid
225358 | #225355 | Task | Need to rebuild Cisco vCenter in CVI LAB | Unassigned | Invalid
225355 | #242452 | Story | Complete research for VM infrastructure | Unassigned | Invalid | 0
225322 | #217151 | Story | FY 18 Roadmap update with IDS Trade Study data | Unassigned | Invalid | 0
225317 |  | Task | Rejected: TR - IDS trade study | Unassigned | Invalid
225288 | #217151 | Story | FY 18 Roadmap update with load Balancer data | Unassigned | Invalid | 0
225284 | #217151 | Story | FY 18 Roadmap update with IASC Router data | Unassigned | Invalid | 0
225270 | #217151 | Story | FY 18 Roadmap update with NMF KG175a data | Unassigned | Invalid | 0
225262 |  | Story | FY 18 Roadmap update with NMF Trade Study data | Unassigned | Invalid | 0
225260 | #242452 | Story | FY18 Load Balancer study cost Estimates | Unassigned | Invalid | 0
225259 | #242452 | Story | FY18 IASC Router replacement cost estimates | Unassigned | Invalid | 0
225258 | #217151 | Story | FY18 KG175 replacement cost estimates | Unassigned | Invalid | 0
225178 | #216649 | Feature | Investigate NMS-Central GNH Interface Lockup | Unassigned | Rejected
225075 | #233365 | Story | R2.1 - Update NAVSOC Firewalls With Latest Patches - Part 2 | Unassigned | Invalid | 0
224990 | #226280 | Story | SR Disposition for R2.1/R3.1. Generate SRs for 2.5 | Unassigned | Invalid | 0
224984 |  | Task | RAN Build Request | Unassigned | Invalid
224975 |  | Story | EAR 2.5 Release Manager Tasks | Unassigned | Invalid | 0
224918 | #223934 | Story | Test returned parts after vendor repair (ILS Depot LOE/Sprint 2) | Unassigned | Invalid | 0
224799 |  | Story | Complete AMS-GS sparing analysis | Unassigned | Invalid | 0
224797 | #224483 | Story | ILS Supply Support LOE work | Unassigned | Invalid | 0
224553 | #220361 | Feature | IA Hardening - WannaCry: Additional WannaCry patching beyond initial 2 IAVAs covered under Feature 222893 | Unassigned | Rejected
224480 |  | Story | Assess and recommend additional lifetime buy items (w ILS Team) | Unassigned | Invalid | 0
224166 | #217809 | Story | Team PCR Reviews Part 2 | Unassigned | Invalid | 0
224119 |  | Story | xx | Unassigned | Invalid | 0
224040 |  | Story | CSO Support for TD 18-03 proposal | Unassigned | Invalid | 0
224031 | #224017 | Story | Upload of CSR log to LM site (CSO LOE) | Unassigned | Invalid | 0
224029 | #224017 | Story | Execute Debriefs (CSO LOE) | Unassigned | Invalid | 0
224026 | #224017 | Story | Manage RA's on CSR log (CSO LOE work) | Unassigned | Invalid | 0
223987 |  | Story | xx | Unassigned | Invalid | 0
223984 |  | Feature | HBSS VLAB Early SVD Integration Phase II | Unassigned | Rejected
223976 | #217806 | Story | VLAB Execute Client Roll Out Plan ( For SIEM DB Servers ) | Unassigned | Invalid | 0
223974 | #217806 | Story | VLAB Execute Client Roll Out Plan ( for SIEM Servers ) | Unassigned | Invalid | 0
223969 | #217806 | Story | VLAB Execute Client Roll Out Plan ( for Secondary FM Server ) | Unassigned | Invalid | 0
223968 | #217806 | Story | VLAB Execute Client Roll Out Plan ( for Primary MGS Adapter) | Unassigned | Invalid | 0
223925 | #245567 | Feature | FOUO Backup Archive Performance and Disk Usage | Unassigned | Rejected
223831 |  | Feature | HBSS PCR Completion Phase I PI 3 Feature | Unassigned | Rejected
223664 | #214605 | Task | Resolve Outstanding Level 1 MUOSESTR Tickets | Unassigned | Done
223593 | #245569 | Story | INC000000236383: TT # 167426 - WH - Modify Satellite Mapping. | Unassigned | Invalid | 0
223590 |  | Story | Complete Quest Box FM Alarm RAF and SF NEDB, parts list, and hardware software map updates | Unassigned | Invalid | 0
223306 | #225714 | Feature | Add an acknowledgement/retry mechanism for the GNH router messages, Part 2 | Unassigned | Rejected
223299 |  | Feature | Improve Inter-RNC Status Tracking Completion | Unassigned | Rejected
223297 |  | Feature | AddMe GSL Improvements for Increment 2 Completion | Unassigned | Rejected
223168 |  | Feature | Implement Call Stability Improvements Identified in Increment 1 Completion | Unassigned | Rejected
223163 |  | Feature | Investigate Additional Provisioning Issues Completion | Unassigned | Rejected
223161 |  | Feature | Rejected: Perform IAVA for Owned Software Completion | Unassigned | Rejected
223156 |  | Story | Strategic Roadmap Swimlane 4 (Planning and Provisioning) needs final PI#2 cost and schedule data | Unassigned | Invalid | 0
223155 |  | Story | Strategic Roadmap Swimlane 3 (Warfighter Services) needs final PI#2 cost and schedule data | Unassigned | Invalid | 0
223154 |  | Story | Strategic Roadmap Swimlane 2 (WCDMA) needs final PI#2 cost and schedule data | Unassigned | Invalid | 0
223141 | #233365 | Story | IA scan and analysis for NAVSOC firewalls | Unassigned | Invalid | 0
222900 |  | Story | Reject | Unassigned | Invalid | 0
222898 | #221248 | Story | Delete me. | Unassigned | Invalid | 0
222779 |  | Story | AMS-GS R3.1.C MCR Support- Convert to Excel via TCRA | Unassigned | Invalid | 0
222776 | #216556 | Story | Implement solution for Add-Me GSL Max Data Usage | Unassigned | Implementing | 5
222769 |  | Story | VLAB Test Training | Unassigned | Invalid | 0 | #204312
222768 | #216565 | Story | Test changes identified for PCR301357 | Unassigned | Invalid | 0
222765 | #231531 | Story | Test changes identified for PCR305110 | Unassigned | Invalid | 0
222764 | #216565 | Story | Test changes identified for PCR298986 | Unassigned | Invalid | 0
222605 | #218902 | Story | Complete V-Lab Like Site analysis, make recommendations | PI 16 | New | 5 | #222606
222604 | #218902 | Story | Analyze the RAN to identify differences between the VLAB and Site | PI 16 | New | 8
222602 | #218902 | Story | Lab - VLab Like Site - Analyze NMS and Situational Awareness to identify differences | PI 16 | New | 8
222600 | #218902 | Story | Analyze Core/GIS to identify differences between the VLAB and Site | PI 16 | New | 8
222571 | #219766 | Story | Feature Demo - RNC Module Registration | Unassigned | Invalid | 0 | #219766
222569 | #220349 | Story | Connect RSC to RSC Safe | Unassigned | New | 1
222568 | #220349 | Story | Complete internal Cabling of MTC in RSC safe | Unassigned | New | 3
222567 | #220349 | Story | Decommission RSC | Unassigned | New | 2
222562 | #233365 | Story | System Demo for NAVSOC R2.1 IA | Unassigned | Invalid | 0
222560 | #249388 | Story | Develop Scripts/Process for detecting system outages | Unassigned | Invalid | 0
222559 | #219158 | Story | Auto - [Seq. 6] Develop V-Lab Call Automation Plan | Unassigned | New | 5
222544 | #219158 | Story | Auto - [Seq. 7] Analysis of V-Lab Call Automation specific to Core or NMS installs/outages | Unassigned | New | 5
222543 | #219158 | Story | Auto - [Seq. 8] V-Lab Call Automation Analysis | Unassigned | New | 5 | #222566
222513 | #220349 | Story | Resolve MTC Key issue with COMSEC office | Unassigned | Invalid | 0
222266 |  | Story | V-lab auto roll up for WDEs | Unassigned | Invalid | 0
222219 | #231531 | Story | Implement changes identified PCR 301357 in Increment 1 | Unassigned | Invalid | 0
222217 | #216642 | Story | Implement changes to add an ack mechanism for GNH Router messages | Unassigned | Invalid | 0
222211 | #245575 | Story | (not approved) OAS File Server Configuration | Unassigned | Invalid | 0
222210 |  | Feature | Delete me | Unassigned | Rejected
222208 | #216710 | Feature | TACLANE IETM Updates for R3.1C - Finish in Inc 3 | Unassigned | Rejected
222180 |  | Story | SA for GDS registration failures | Unassigned | Invalid | 0
222179 | #216660 | Story | Design state machine for MHAL browser interface | Unassigned | New | 1
222178 | #216660 | Story | Design, implement and test browser interface code for text/email notifications. | Unassigned | New | 5
222172 | #216556 | Story | Execute STCD and verify PCRs for AddMe GSL Improvements Feature | Unassigned | New | 2
222165 | #223306 | Story | Implement changes to add an retry mechanism for GNH Router messages | Unassigned | Invalid | 0
222155 | #219400 | Story | FM whitelist for ET alarms part 3 | Unassigned | Invalid | 0
222149 | #216598 | Story | Test changes to refresh Common_GK ID when RNC detects that it has stale key data | Unassigned | Invalid | 0
222148 | #216598 | Story | Implement changes to refresh GCK ID | Unassigned | Invalid | 0
222146 | #231531 | Story | Implement changes identified PCR 305110 in Increment 1 | Unassigned | Invalid | 0
222140 | #220766 | Story | Integrate ETISP eRxIm FW & SW | Unassigned | Invalid | 0
222137 | #233365 | Story | T500 load IA release & soak test | Unassigned | Invalid | 0
222131 | #233365 | Story | T500/T501 STCD execution Chris | Unassigned | Invalid | 0
222107 | #216598 | Story | Analyze changes to refresh GCK ID when RNC detects it may have stale key data | Unassigned | Invalid | 0
222106 |  | Story | SA for GDS registration failures | Unassigned | Invalid | 0
222089 | #216660 | Story | Create MHAL Browser interface background job that analyses call function data. | Unassigned | New | 5
222053 | #222893 | Story | Deleted. | Unassigned | Invalid | 0
222041 | #216660 | Story | Research how to send text notifications on a private network. | Unassigned | New | 3
222036 | #216565 | Story | Implement changes identified PCR 298986 in Increment 1 | Unassigned | Invalid | 0
222033 | #216598 | Story | Implement changes to add additional granularity to error codes between RCG and RNC | Unassigned | Invalid | 0
222023 | #219764 | Story | Implement changes for GNLs being setup at reboot. | Unassigned | Invalid | 0
221984 | #216642 | Story | Analyze adding an ack/retry mechanism for GNH Router messages | Unassigned | Invalid | 0
221973 |  | Story | Delete me. | Unassigned | Invalid | 0
221958 |  | Story | DELETE | Unassigned | Invalid | 0
221939 |  | Story | VM System Design for SPLUNK Phase 2 | Unassigned | Invalid | 0
221927 | #250473 | Story | AU RBS 10 issue | Unassigned | Invalid | 0
221915 | #221251 | Story | Wrap-up autologging activities to release current scripts to the sites | Unassigned | Invalid | 0
221701 | #221698 | Story | Complete IA Freshness Process | Unassigned | Invalid | 0
221698 | #205310 | Feature | Complete IA Freshness Process Definition and Roll-Out to GD Team | Unassigned | Rejected
221695 | #216707 | Feature | Enhance SA for GDS Registration Failures (Enabler) | Unassigned | Approved
221694 | #216625 | Feature | Check Site GIS Firewall Logs For Exceptions (Enabler) | Unassigned | Rejected
221660 | #216469 | Story | BKM: ILS IETM Updates for Bulk Key Loading | Unassigned | Invalid | 0
221603 |  | Feature | Complete SMEs & leader ConOps interviews | Unassigned | Rejected
221454 | #217040 | Feature | Create Plan for SA and FM Tactical Architectural Roadmap | Unassigned | Rejected
221418 | #220944 | Feature | Release and prepare for Deployment EAD2 | Unassigned | Rejected
221394 | #221383 | Story | FY18 System Optimization Proposal: Splunk SIEM System Design & Engineering Estimate | Unassigned | Invalid | 0
221393 | #221383 | Story | FY18 System Optimization Proposal: NMF integrated call banks System Design & Engineering Estimate | Unassigned | Invalid | 0
221392 | #221383 | Story | FY18 System Optimization Proposal: Provisioning Common User Interface System Design & Engineering Estimate | Unassigned | Invalid | 0
221388 | #221383 | Story | FY18 System Optimization Proposal: Digital RAN Prototype Design & Engineering Estimate | Unassigned | Invalid | 0
221386 |  | Story | FY18 System Optimization Proposal: VM Infrastructure System Design & Engineering Estimate | Unassigned | Invalid | 0
221377 | #221383 | Story | FY18 System Optimization Proposal: FOUO Direct Link to Scottsdale System Design & Engineering Estimate | Unassigned | Invalid | 0
221344 | #221383 | Story | FY18 System Optimization Proposal: HBSS (FOUO) System Design & Engineering Estimate | Unassigned | Invalid | 0
221313 | #210216 | Feature | Implement Continuous Integration Build for RCG | Unassigned | Rejected
221307 | #210216 | Feature | Implement Continuous Integration Build for RTT | Unassigned | Rejected
221274 | #217272 | Feature | Train MUOS SMEs in use of Splunk for ingesting and analyzing logs | Unassigned | Rejected
221269 | #219533 | Feature | Consolidated tech refresh plan for FY18 through FY21 | Unassigned | Rejected
221251 | #219384 | Feature | Stretch: Automate Factory Logging - Complete TPM SVD updates to install expect (Continue from PI2) | Unassigned | Approved
221248 | #219384 | Feature | Reject: Automate Factory Logging - Complete Vlab system demo for INC2 | Unassigned | Rejected
221244 | #219384 | Feature | Automate Factory Logging - Complete IETM updates for Automated Factory Logging | Unassigned | Approved
221234 | #219384 | Feature | Automate Factory Logging - Complete PDO and release. | Unassigned | Rejected
221231 | #219384 | Feature | Automate ETISP Log Collection | Unassigned | Approved
221215 | #216716 | Feature | ETI switchover procedure add NAVSOC notices | Unassigned | Rejected
221210 | #217358 | Feature | ETI define how to use data for situational awareness and recovery procedures | Unassigned | Rejected
221209 |  | Story | Define common system issues with root cause in the ETI (Enabler) | Unassigned | Invalid | 0
221148 |  | Feature | Reject: SCS updates for MUOS-5 Rev L OOH | Unassigned | Rejected
221147 | #219668 | Feature | Call Log by Transaction (MSISDN Lookup) | Unassigned | Rejected
220953 | #221156 | Story | Release EAD 1 Obtain Release Approvals | Unassigned | Done | 8
220890 |  | Story | AMS-GS R3.1.C Perform Final IA Scan -delete | Unassigned | Invalid | 0
220882 | #220042 | Story | Enable eggplant software on workstation | Unassigned | Invalid | 0
220871 | #217379 | Feature | Splunk Phase 2 Infrastructure - No Hardware Dependency: Unresolved IA Findings | Unassigned | Approved
220870 | #217379 | Feature | Splunk Infra: IETM Updates | Unassigned | Rejected
220869 | #217379 | Feature | Splunk Infra: Secure SSH | Unassigned | Rejected
220868 | #217379 | Feature | Splunk Infra: SIEM | Unassigned | Rejected
220866 | #217379 | Feature | Splunk Infra: Domain Account Support | Unassigned | Rejected
220864 | #217379 | Feature | Splunk Phase 2 Infrastructure - No Hardware Dependency: Backup/Archive/Restore | Unassigned | Rejected
220863 | #217379 | Feature | Splunk Infra: Fault Management | Unassigned | Rejected
220862 | #217379 | Feature | Splunk Infra: Guaranteed Data Delivery | Unassigned | Rejected
220777 | #217460 | Feature | ETISP configuration utility TPM batch files | Unassigned | Rejected
220774 |  | Feature | ETISP configuration utility lab test | Unassigned | Rejected
220770 |  | Feature | ETISP configuration utility automates editing ETI switchover property values | Unassigned | Rejected
220769 |  | Feature | ETISP configuration utility picks up property values from existing installation | Unassigned | Rejected
220765 |  | Feature | eRxIM integrate software | Unassigned | Rejected
220764 |  | Feature | eRxIM integrate firmware | Unassigned | Rejected
220652 |  | Feature | Add/update IETM alarm recovery procedures for high-side alarms | Unassigned | Rejected
220647 |  | Feature | FM whitelist updates | Unassigned | Rejected
220625 | #219384 | Feature | Automate Factory Logging - Scheduler | Unassigned | Approved
220621 | #219384 | Feature | Automate Factory Logging - Complete Extreme Switch Log Collection scripts | Unassigned | Approved
220618 | #219384 | Feature | Automate Factory Logging - Analysis Reports | Unassigned | Approved
220613 | #219384 | Feature | Automate Factory Logging - Password Management | Unassigned | Approved
220511 |  | Feature | Improve IA Posture for Static IP CI's | Unassigned | Rejected
220373 |  | Story | xx | Unassigned | Invalid | 0
220372 |  | Story | RMF - POAM Items review | Unassigned | Invalid | 0
220371 |  | Story | RMF Step 3 - Develop Assessment Tracking Tool | Unassigned | Invalid | 0
220369 |  | Story | RMF - Plan tool design for the RAR clean up tool - delete | Unassigned | Invalid | 0
220368 |  | Task | LM - Develop the RAR to SAR tool | Unassigned | Invalid
220367 |  | Task | RMF - Plan tool design for the RAR to SAR tool | Unassigned | Invalid
220366 |  | Story | RMF Step 3 - VPSI (Anderson) Plan tool for Assessment Tracking for Step 3 - delete | Unassigned | Invalid | 0
220363 |  | Story | RMF Step 3 - Tech Assessment Support (Analysis) - Part 7 | Unassigned | Invalid | 0
220362 |  | Task | RMF Step 2 - PMW-146 - Update SP in eMASS After Step 2 Checkpoint Review | Unassigned | Invalid
220348 | #230787 | Task | RMF Step 2 - Post Step 2 Checkpoint - update eMASS | Unassigned | Invalid
220347 |  | Task | RMF Step 2 - Post Step 2 Checkpoint - update ISCM | Unassigned | Invalid
220324 | #216446 | Story | RMF Step 3 - Update eMASS with SP Supplement updates | Unassigned | Invalid | 0
220322 | #216446 | Story | RMF Step 3 - Review SP Supplement update | Unassigned | Invalid | 0
220321 | #216446 | Story | RMF Step 3 - Update SP Supplement for new capabilities | Unassigned | Invalid | 0
220320 |  | Story | RMF Step 3 - General clean-up of the SP Supplement - part 2 | Unassigned | Invalid | 0
220317 |  | Feature | SCS SW Updates | Unassigned | Rejected
220315 |  | Feature | Reject: R2.1 - Update SCS Software for NAVSOC | Unassigned | Rejected
220288 | #221405 | Story | (Inc2) RMF Step 3 – Update the SP Supplement (TO BE DELETED...covered by other stories under RMF] | Unassigned | Invalid | 0
220242 | #219691 | Feature | Static IP system demo for work done in Increment 1 | Unassigned | Rejected
220153 | #219691 | Feature | CDR/PM Data Reliablility - Periodically cleanup SCS messages system demo for work completed in Increment 1 | Unassigned | Rejected
220151 |  | Feature | MUOS Change Process ( MCP ) Section Updates | Unassigned | Rejected
220147 | #219691 | Feature | SGSN system demo for work completed in increment 1 | Unassigned | Rejected
220144 | #219691 | Feature | RTT system demo for work completed in increment 1 | Unassigned | Rejected
220142 | #219691 | Feature | Win XP -NMS IA Hardening system demo for work completed in increment 1 | Unassigned | Rejected
220065 |  | Story | RMF Step 3 – Create Workbook Analysis How-To Documents | Unassigned | Invalid | 0
220064 |  | Story | xx | Unassigned | Invalid | 0
220061 |  | Story | RMF Step 3 – eMASS testing of the tools used for SAR and POAM - part 1 - delete | Unassigned | Invalid | 0
220055 |  | Story | RMF Step 3 – Technical Controls - Delta STIGs Assessment at Site - delete | Unassigned | Invalid | 0
220052 |  | Story | RMF Step 3 – Assessment Execution performed off site for Operational Category Controls - delete | Unassigned | Invalid | 0
220051 |  | Story | RMF Step 3 – Assessment execution performed off-site for Management Category Controls - delete | Unassigned | Invalid | 0
220050 |  | Story | (Inc2) RMF Step 3 – Tools Development for POAM, RAR, SAR, Assessment Tracking Tool [TO BE DELETED...replaced by stories 220366 - 220373] | Unassigned | Invalid | 0
220046 |  | Story | (Inc2) RMF Step 2 – Checkpoint Review completion [TO BE DELETED...covered by 220364 and 220365] | Unassigned | Invalid | 0
220045 |  | Story | (Inc2) RMF Step 2 – eMASS updates and review for SP Controls (DELETE) | Unassigned | Invalid | 0
220044 |  | Story | (Inc2) RMF Step 2 – Post Step 2 Checkpoint Review Actions (DELETE) | Unassigned | Invalid | 0
220026 | #222554 | Story | System Demo for Auto Factory Logging for work completed in Increment 1 | Unassigned | Done | 3
220024 | #219691 | Feature | SPLUNK Demo for work completed in Increment 1 | Unassigned | Rejected
220023 | #219691 | Feature | RAN - Group Demo for work done in increment 1 | Unassigned | Rejected
219896 | #216572 | Story | Finish R3.1C TACLANE IETM Updates | Unassigned | Invalid | 0
219803 | #239315 | Story | Define 90 day IA requirement and integrate within Agile process | Unassigned | Done | 1
219770 |  | Feature | TPM update for new ETISP release | Unassigned | Rejected
219767 |  | Feature | Improve RNC/RBS Field Support for Phase 1 | Unassigned | Rejected
219760 | #245573 | Feature | Investigate Zombie Issues | Unassigned | Rejected
219745 | #218379 | Feature | Add 2 HMTs to the SWIT lab RNC2 string | Unassigned | Rejected
219671 | #219670 | Feature | SBC Degraded Status | Unassigned | Rejected
219615 |  | Feature | RT Logic Tech Refresh Updates needed for deployment to NAVSOC | Unassigned | Rejected
219587 |  | Story | AMS-GS Final IA Scanning on DB and UI Servers | Unassigned | Invalid | 0
219537 | #217406 | Feature | Create Splunk Dashboard(s) and Indicators to Monitor CDR Data Delivery to Gather Baseline Metrics | Unassigned | Rejected
219518 | #216554 | Story | Test any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219516 | #216554 | Story | Implement any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219514 | #220243 | Story | Test any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219501 |  | Story | Delete | Unassigned | Invalid | 0
219475 | #216558 | Story | Install, Execute STCD, and Verify PCR for Feature | Unassigned | Invalid | 0
219474 |  | Story | Implement any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219462 | #218503 | Feature | Evaluate the usefulness of the types of data PM collects | Unassigned | Rejected
219461 | #218503 | Feature | Update PM to track its memory usage (in order to help diagnose its out-of-memory errors) | Unassigned | Rejected
219460 | #218503 | Feature | Improve PM database connectivity | Unassigned | Rejected
219454 | #218503 | Feature | Create Splunk Dashboard(s) and Indicators to Monitor PM Data Delivery to Gather Baseline Metrics | Unassigned | Rejected
219449 | #225178 | Story | Test any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219446 | #225178 | Story | Implement any changes identified by the analysis stories in this feature | Unassigned | Invalid | 0
219444 |  | Feature | Add/update IETM alarm recovery procedures for RCG alarms | Unassigned | Rejected
219441 |  | Feature | Add/update IETM alarm recovery procedures for FOUO NMS alarms | Unassigned | Rejected
219440 |  | Feature | Add/update IETM alarm recovery procedures for ETISP alarms | Unassigned | Rejected
219439 |  | Feature | IETM procedures for CRITICAL ET alarms - ETISPD | Unassigned | Rejected
219418 | #219598 | Feature | Change Intersite Status so That "No News=Bad News" | Unassigned | Rejected
219411 | #217379 | Feature | Splunk Infra- Case Study for Data Model Strategy | Unassigned | Rejected
219399 |  | Feature | Alarm Analysis, pass 2: Core/GIS and related subsystems | Unassigned | Rejected
219135 | #216466 | Story | STIG MM12 STIG Assessment | Unassigned | Invalid | 0
219134 | #216466 | Story | Verify final SCAP scan on MM12 | Unassigned | Invalid | 0
219133 | #216466 | Story | STIG MM12 and run initial SCAP scan | Unassigned | Invalid | 0
219132 | #216466 | Story | STIG MM12 per findings from initial SCAP scan | Unassigned | Invalid | 0
219131 | #216466 | Story | Solaris NMS MM12 VLAB regression testing | Unassigned | Invalid | 0
219130 | #216467 | Story | Update Generic UNIX STIG SVD on how to apply latest STIGs | Unassigned | Invalid | 0
218396 |  | Story | Test changes for GNLs being setup at reboot | Unassigned | Invalid | 0
218361 | #217799 | Story | Create STCD for Increment 1: Cyber - NMS Windows Workstation XP Updates - delete | Unassigned | Invalid | 0
218360 | #217799 | Story | 98-P59408M_Windows_Workstation_SVD, Load Point 3.21 migration for remaining SWIT hosts - delete | Unassigned | Invalid | 0
218356 | #216458 | Story | STIG Regression Test OSS-RC in VLab | Unassigned | Invalid | 0
218355 | #216458 | Story | Verify final SCAP scan on OSS-RC | Unassigned | Invalid | 0
218354 | #216458 | Story | STIG OSS-RC and run initial SCAP scan | Unassigned | Invalid | 0
218353 | #216457 | Story | STIG Regression Test FM in VLab | Unassigned | Invalid | 0
218352 | #216457 | Story | Verify final SCAP scan on FM | Unassigned | Invalid | 0
218351 | #216457 | Story | STIG FM per findings from initial SCAP scan | Unassigned | Invalid | 0
218350 | #216457 | Story | STIG FM and run initial SCAP scan | Unassigned | Invalid | 0
218349 | #227096 | Story | STIG Regression Test IPWorks in VLab | Unassigned | Invalid | 0
218348 | #227096 | Story | Verify final SCAP scan on IPWorks | Unassigned | Invalid | 0
218347 | #227096 | Story | STIG IPWorks per findings from initial SCAP scan | Unassigned | Invalid | 0
218346 | #216442 | Story | STIG IPWorks and run initial SCAP scan | Unassigned | Invalid | 0
218345 | #216496 | Story | Verify final SCAP scan on EMA11 | Unassigned | Invalid | 0
218344 | #216496 | Story | STIG EMA11 per findings from initial SCAP scan | Unassigned | Invalid | 0
218343 | #216496 | Story | STIG EMA11 and run initial SCAP scan | Unassigned | Invalid | 0
218342 |  | Story | Assess feasibility of non-cyber teams doing portions of their own IA hardening | Unassigned | Invalid | 0
218341 | #216459 | Story | Verify final SCAP scan on MM11 | Unassigned | Invalid | 0
218340 | #216459 | Story | STIG MM11 per findings from initial SCAP scan | Unassigned | Invalid | 0
218339 | #216459 | Story | STIG MM11 and run initial SCAP scan | Unassigned | Invalid | 0
218338 | #216466 | Story | Verify final ACAS scan on MM12 | Unassigned | Invalid | 0
218337 | #216466 | Story | Patch MM12 per findings from initial ACAS scan | Unassigned | Invalid | 0
218336 | #216466 | Story | Patch MM12 with latest Critical Patch Update (CPU) and run initial ACAS scan | Unassigned | Invalid | 0
218335 | #216453 | Story | Reevaluate IA posture from R3.1 Solaris items coming out of build & brief PWM 146 IA | Unassigned | Invalid | 0
218334 |  | Story | Train cyber team on using new ACAS 5.x laptop | Unassigned | Invalid | 0
218331 | #216496 | Story | STIG Regression Test EMA11 in VLab | Unassigned | Invalid | 0
218322 | #216467 | Story | Perform IA hardening on a per server basis for CIs using Solaris 9 or 10. | Unassigned | Invalid | 0
218321 | #217799 | Story | WinXP-NMS: STIG 1 Implementation (Part 2) - delete | Unassigned | Invalid | 0
218320 | #230051 | Story | SCAP scan and assessment for ILS Laptop with Windows 10 | Unassigned | Invalid | 0
218319 | #230051 | Story | Verify ILS Laptop WIN10 STIG Hardening | Unassigned | Invalid | 0
218317 |  | Story | For Cyber: Investigate cross-domain accreditation | Unassigned | Invalid | 0
218316 | #230051 | Story | ILS Tool Laptop SVD Integration Testing | Unassigned | Invalid | 0
218314 |  | Story | AMS-GS R3.1C - Prepare and Submit FRCB IA Analysis Workbook Inputs (30 calendar days prior to deployment) | Unassigned | Invalid | 0
218313 | #216471 | Story | AMS-GS R3.1C - Prepare and Submit FRCB C&A Inputs (100 calendar days prior to deployment) | Unassigned | Invalid | 0
218311 | #217799 | Story | WinXP-NMS: STIG 1 Regression Test - delete | Unassigned | Invalid | 0
218310 | #217799 | Story | WinXP-NMS: STIG 1 Verification - delete | Unassigned | Invalid | 0
218309 | #230051 | Story | Apply Patches to ILS Laptop running Windows 10 | Unassigned | Invalid | 0
218308 | #217799 | Story | WinXP-NMS: XP STIG 1 - delete | Unassigned | Invalid | 0
218306 | #216532 | Story | Fix NW IASS internal switches and NW IASS IR routers to disable unused interfaces | Unassigned | Invalid | 0
218305 | #230051 | Story | IETM execution on the ILS Laptop | Unassigned | Invalid | 0
218304 | #216664 | Story | IA Scan/STIG for GIS Load Balancers - MAS Out of Sync | Unassigned | Invalid | 0
218303 | #216475 | Story | RMF Step 2: Convert 2nd 50% DIACAP POAM CAT I items to RMF RAR | Unassigned | Invalid | 0
218302 | #216448 | Story | RMF Step 2: Convert 2nd 50% DIACAP POAM CAT II items to RMF RAR | Unassigned | Invalid | 0
218301 |  | Story | RMF Step 4: Continue Dev work on "RMF Munging tool" | Unassigned | Invalid | 0
218300 |  | Story | xx | Unassigned | Invalid | 0
218299 | #216448 | Story | RMF Step 2: Review site documents for management category controls | Unassigned | Invalid | 0
218298 | #216459 | Story | Update EMM SVD on how to apply latest patches | Unassigned | Invalid | 0
218296 | #217799 | Story | WinXP-NMS: STIG 1 Implementation (Part 1) - delete | Unassigned | Invalid | 0
218295 |  | Story | xx | Unassigned | Invalid | 0
218294 | #230051 | Story | Misc ILS: Sparing Analysis, etc | Unassigned | Invalid | 0
218293 | #230051 | Story | Win 10 Laptop SVD initial release | Unassigned | Invalid | 0
218292 | #230051 | Story | ILS Tool Laptop SVD related IETM | Unassigned | Invalid | 0
218291 | #230051 | Story | ETT Laptop SVD Updates & Integration Testing | Unassigned | Invalid | 0
218290 | #230051 | Story | MTC/AJM Laptop SVD Updates and Integration Testing | Unassigned | Invalid | 0
218289 | #230051 | Story | IETM Updates for Win 10 Laptop | Unassigned | Invalid | 0
218287 | #221100 | Story | IETM Procedure to Renew Splunk License | Unassigned | Invalid | 0
218286 |  | Story | Static IP - IA scan and assessment report - NMS | Unassigned | Invalid | 0
218285 |  | Story | IA scan and assessment report - Static IP - Firewall | Unassigned | Invalid | 0
218284 |  | Story | IA scan and assessment report - Static IP - DNSDHCP | Unassigned | Invalid | 0
218283 |  | Story | Static IP - IA scan and assessment report - GGSN | Unassigned | Invalid | 0
218282 |  | Story | IA scan and assessment report - Static IP - MAS | Unassigned | Invalid | 0
218281 |  | Story | 3_IA Perform IA scans and provide report & PCR on GGSN | Unassigned | Invalid | 0
218280 | #216441 | Story | Update RTLogic T500/501 with latest patches | Unassigned | Invalid | 0
218279 | #216448 | Story | RMF Step 2: Update MS project plan for RMF transition | Unassigned | Invalid | 0
218278 | #216448 | Story | RMF Step3: Create RMF POA&M Items based on RAR Recommendations | Unassigned | Invalid | 0
218277 | #216448 | Story | RMF Step 3: SCA-Validator (VPSI) to Generate SAP for RMF management controls | Unassigned | Invalid | 0
218276 | #216448 | Story | RMF Step 3: SCA Validator (VPSI) - Define assessment scope for the SAP Management Controls | Unassigned | Invalid | 0
218275 | #216448 | Story | RMF Step 2: Convert1st 50% DIACAP POAM CAT II items to RMF RAR | Unassigned | Invalid | 0
218274 | #216475 | Story | RMF Step 2: Convert 1st 50% DIACAP POAM CAT I items to RMF RAR | Unassigned | Invalid | 0
218273 |  | Story | HBSS - Complete IA scans for Windows 2012 R2 configurations specific to HBSS | Unassigned | Invalid | 0
218272 |  | Story | HBSS - Complete IA scans for network gear used by HBSS | Unassigned | Invalid | 0
218271 |  | Story | HBSS - Complete IA Scans for Deployable HBSS | Unassigned | Invalid | 0
218270 |  | Story | Generate Draft IAVM/Patching process for AGILE | Unassigned | Invalid | 0
218269 | #216485 | Story | Scans for MGM Red Hat updates | Unassigned | Invalid | 0
218268 |  | Story | Deleted. | Unassigned | Invalid | 0
218267 |  | Story | Prepare IA Workbook and Test Report | Unassigned | Invalid | 0
218264 |  | Story | RMF Step 5: Complete Security Plan (SP) for RMF Step 5 | Unassigned | Invalid | 0
218262 |  | Story | BKM: Regression tests - Scan and Manual checks to verify - delete | Unassigned | Invalid | 0
218258 | #223306 | Story | Test changes to add an ack/retry mechanism for GNH Router messages | Unassigned | Invalid | 0
218094 |  | Task | Fix default gateway for the MUOS Management network interface | Unassigned | Invalid
218093 |  | Task | Tectia Updates Review (Chris) | Unassigned | Invalid
218092 |  | Task | Update draft Client Roll Out Plan (if necessary) | Unassigned | Invalid
218091 |  | Task | Update Client Roll Out Plan draft procedures | Unassigned | Invalid
218090 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218089 |  | Task | Update Client Roll Out Plan draft procedures | Unassigned | Invalid
218088 |  | Task | Configure emulation NCDOC server to MUOS HBSS roll up | Unassigned | Invalid
218087 |  | Task | Build ePO application including initial configuration (components, packages, system tree, policies, tasks) | Unassigned | Invalid
218086 |  | Task | Install HBSS Servers | Unassigned | Invalid
218085 |  | Task | Tectia Updates Review (Ken) | Unassigned | Invalid
218084 |  | Task | Patch epo201/202 (NMS 2012 OS SVD) | Unassigned | Invalid
218083 |  | Task | Patch epo200 (HBSS SVD) | Unassigned | Invalid
218082 |  | Task | Patch epo201/202 (NMS 2012 OS SVD) | Unassigned | Invalid
218081 |  | Task | Tectia Updates Review (Jim) | Unassigned | Invalid
218080 |  | Task | Update Tectia to support new servers | Unassigned | Invalid
218079 |  | Task | Complete WinZip installation | Unassigned | Invalid
218078 |  | Task | HBSS SVD updates draft for HBSS Backup/Archive | Unassigned | Invalid
218077 |  | Task | TPM SVD updates for HBSS Backup/Archive | Unassigned | Invalid
218076 |  | Task | Update Client Roll Out Plan draft procedures | Unassigned | Invalid
218075 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218074 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218073 |  | Task | Update with correct version of McAfee Agent for Linux (5.0.3) | Unassigned | Invalid
218072 |  | Task | Install HBSS interconnects | Unassigned | Invalid
218071 |  | Task | Build epo200-wh-nma | Unassigned | Invalid
218070 |  | Task | Configure account used by NCDOC to access the HBSS database | Unassigned | Invalid
218069 |  | Task | Test restoration procedure | Unassigned | Invalid
218068 |  | Task | Write draft HBSS SVD VM Java installation content | Unassigned | Invalid
218067 |  | Task | Change HIP policy to deploy in un-enabled state | Unassigned | Invalid
218066 |  | Task | Verify co-existance of RAID manager Java version with MUOS standard Java version | Unassigned | Invalid
218065 |  | Task | Patch epo200 (HBSS SVD) | Unassigned | Invalid
218064 |  | Task | Patch epo201/202 (NMS 2012 OS SVD) | Unassigned | Invalid
218063 |  | Task | Build epo201-wh-nma | Unassigned | Invalid
218062 |  | Task | Analyze PCR 308897 for Tectia HBSS SVD updates for Backup/Archive | Unassigned | Invalid
218061 |  | Task | Procedure changes to account for not being able to connect a USB drive to hosts at site | Unassigned | Invalid
218060 |  | Task | Patch epo200 (HBSS SVD) | Unassigned | Invalid
218059 |  | Task | Tectia Updates Review (Mark) | Unassigned | Invalid
218058 |  | Task | Troubleshoot ePO Shortcut Problem | Unassigned | Invalid
218057 |  | Task | Configure registered server on HBSS for roll up | Unassigned | Invalid
218056 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218055 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218054 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218053 |  | Task | Configure user account used by NCDOC for rollup | Unassigned | Invalid
218052 |  | Task | Transfer VM architecture/implementation details to Steve - Steve's Time | Unassigned | Invalid
218051 |  | Task | Update draft HBSS SVD procedures (if necessary) | Unassigned | Invalid
218050 |  | Task | Update Client Roll Out Plan draft procedures | Unassigned | Invalid
218049 |  | Task | Patch epo201/202 (NMS 2012 OS SVD) | Unassigned | Invalid
218048 |  | Task | Patch epo200 (HBSS SVD) | Unassigned | Invalid
218047 |  | Task | Configure IP address on emulation server for NCDOC | Unassigned | Invalid
218046 |  | Task | Build epo202-wh-nma | Unassigned | Invalid
218045 |  | Task | Complete script installation on the TPM server | Unassigned | Invalid
218044 |  | Task | Install HBSS RAID & SANs | Unassigned | Invalid
218043 |  | Task | Patch epo200 (HBSS SVD) | Unassigned | Invalid
218042 |  | Task | Patch epo201/202 (NMS 2012 OS SVD) | Unassigned | Invalid
218041 |  | Task | Identify RAID manager host platform | Unassigned | Invalid
218040 |  | Task | Update Client Roll Out PLan draft procedures | Unassigned | Invalid
218039 |  | Task | Update Client Roll Out Plan draft procedure | Unassigned | Invalid
218038 |  | Task | Fix console restriction registration item | Unassigned | Invalid
218037 |  | Task | Update Client Roll Out Plan draft procedure | Unassigned | Invalid
218036 |  | Task | Update Client Roll Out Plan draft procedure | Unassigned | Invalid
218035 |  | Task | Transfer VM architecture/implementation details to Steve - Jim's Time | Unassigned | Invalid
218034 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218033 |  | Task | Tectia Updates Refview (Mike McD) | Unassigned | Invalid
218032 |  | Task | Update Client Roll Out Plan draft procedure | Unassigned | Invalid
218031 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218030 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218029 |  | Task | Deploy to SWIT hosts | Unassigned | Invalid
218028 |  | Task | Knowledge Transfer ePO 5.3 vs. ePO 4,6 - Jim's time | Unassigned | Invalid
218027 |  | Task | Resolve PCR 308897 For Tectia HBSS SVD updates for Backup/Archive | Unassigned | Invalid
218026 |  | Task | VM disk volume updates (to add backup drive) | Unassigned | Invalid
218025 |  | Task | Tectia Updates Review (Steve) | Unassigned | Invalid
218024 |  | Task | Config TSM Client as required to handle large file sizes | Unassigned | Invalid
218023 |  | Task | Draft SVD Instructions for certificate install/upgrade ePO | Unassigned | Invalid
218022 |  | Task | Verify Correct Linux Agent version is installed in VM image | Unassigned | Invalid
218021 |  | Task | RAID SVD updates | Unassigned | Invalid
218020 |  | Task | Roll out MA, VSE, HIPS to servers targeted by the Client Roll Out Plan | Unassigned | Invalid
218019 |  | Task | Update Client Roll Out Plan draft procedure | Unassigned | Invalid
218018 |  | Task | Update draft HBSS SVD procedures (if necessary) | Unassigned | Invalid
218017 |  | Task | Create Deployable VM | Unassigned | Invalid
218016 |  | Task | Knowledge transfer ePO 5.3 vs. ePO 4.6 - Steve's time | Unassigned | Invalid
218015 | #245561 | Story | Debug app201 in SWIT | Unassigned | Invalid | 0
218014 |  | Story | ROM Dedicated Operator Console | Unassigned | Invalid | 0
218013 | #245561 | Story | GS Key Management PCR work and send to review | Unassigned | Invalid | 0
218011 | #245561 | Story | Network configuration fixes supporting VLAB | Unassigned | Invalid | 0
218010 |  | Story | (dup) RAID SVD Updates for Disk Drive Changes | Unassigned | Invalid | 0
218009 |  | Story | Execute Enforcement Mode transition | Unassigned | Invalid | 0
218008 | #245561 | Story | PCR MUOSD00299484 SAN Switch Account Maintenance Document Updates for SECRET (IETM) | Unassigned | Invalid | 0
218007 | #245561 | Story | PCR MUOSD00297672 GS FW TR HBSS PCR ePO Server impacts to GS firewalls to allow ePO access external DMZ firewalls (fw203/204) - HBSS Phase 2 | Unassigned | Invalid | 0
218006 |  | Story | PCR MUOSD00299839 NMS TR HBSS SQL impacts to HW/SW Mapping | Unassigned | Invalid | 0
218005 |  | Story | PCR MUOSD00299756 NMS TR HBSS ePO Server impacts to PKI Deployment Plan | Unassigned | Invalid | 0
218004 | #245561 | Story | PCR MUOSD00304553 NMS TR HBSS Imacts to AV/HIDS SVD for McAfee ePO 4.6.8 Removal | Unassigned | Invalid | 0
218003 |  | Story | Restore backup to stand-alone physical server from tape | Unassigned | Invalid | 0
218002 | #217806 | Story | Configure and test roll up server emulation | Unassigned | Invalid | 0
218001 |  | Story | Implement RAID Manager in a non-Workstation solution | Unassigned | Invalid | 0
218000 | #245561 | Story | Deploy VSE to Windows Server 2012 hosts | Unassigned | Invalid | 0
217999 | #245561 | Story | Deploy McAfee Agent to Windows Server 2003 hosts | Unassigned | Invalid | 0
217998 |  | Story | Official V-Lab Feature build | Unassigned | Invalid | 0
217997 | #217806 | Story | Complete feature checklist and review | Unassigned | Invalid | 0
217996 |  | Story | Open firewall rules to allow CRL server access from ePO servers | Unassigned | Invalid | 0
217995 | #245561 | Story | Deployable VM | Unassigned | Invalid | 0
217994 | #245561 | Story | Tectia Updates Resolve PCR | Unassigned | Invalid | 0
217993 | #245561 | Story | Fix sftp problem on backup drive (Steve) | Unassigned | Invalid | 0
217992 | #245561 | Story | Tectia Updates PCR work and send to review | Unassigned | Invalid | 0
217991 | #217814 | Story | Deploy HBSS | Unassigned | Invalid | 0
217990 |  | Story | Verify HBSS PCRs | Unassigned | Invalid | 0
217989 |  | Story | PCR MUOSD00299814 TR NME-13 Add Secret EMC RAID array to cabinet | Unassigned | Invalid | 0
217988 |  | Story | PCR MUOSD00299360 NMS SAN Switch: Update the SECRET Enclave SAN Switches to Support HBSS/SAN/RAID | Unassigned | Invalid | 0
217986 |  | Story | PCR TBD Learn Mode Conops PCR | Unassigned | Invalid | 0
217985 | #245561 | Story | PCR MUOSD00299934 IETM TR HBSS ePO Server impacts to IETM | Unassigned | Invalid | 0
217984 | #245561 | Story | PCR MUOSD00304665 Change firewall configuration for Interim HBSS solution to support Rollup Server | Unassigned | Invalid | 0
217983 | #245561 | Story | Deploy MA to Windows 2003 hosts Roll Out Plan Update | Unassigned | Invalid | 0
217982 | #245561 | Story | Network configuration updates (switches, routers, firewalls, etc.) | Unassigned | Invalid | 0
217981 |  | Story | Incorporate fixes to deployable VM | Unassigned | Invalid | 0
217980 |  | Story | Complete network changes to close off Interim HBSS | Unassigned | Invalid | 0
217979 |  | Story | Deploy APS | Unassigned | Invalid | 0
217978 |  | Story | Deploy RSD | Unassigned | Invalid | 0
217976 |  | Story | V-Lab mechanical drawing updates | Unassigned | Invalid | 0
217975 | #245561 | Story | File Configuration Management | Unassigned | Invalid | 0
217974 | #245561 | Story | Deploy McAfee Agent to Windows Server 2012 hosts | Unassigned | Invalid | 0
217973 | #245561 | Story | Test backup of D: and E: on Drive E: or D: | Unassigned | Invalid | 0
217972 | #245561 | Story | Deploy VSE to Windows XP hosts | Unassigned | Invalid | 0
217971 | #245561 | Story | WIN2003 NMS - SWIT SME Regression Testing - Cox | Unassigned | Invalid | 0
217970 | #245561 | Story | Deploy VSE to Windows XP hosts Roll Out Plan documentation updates | Unassigned | Invalid | 0
217969 | #217814 | Story | Validate Roll Up Server Configuration in VLAB | Unassigned | Invalid | 0
217967 |  | Story | PCR MUOSD00299851 TR HBSS RAID/SAN Update WH site interconnect for NME10,11 to NME13 | Unassigned | Invalid | 0
217966 | #245561 | Story | PCR MUOSD00296759 IETM: Need to add SAN switch replacement procedure to IETM (SPAS00000142600) | Unassigned | Invalid | 0
217965 |  | Story | PCR MUOSD00304612 Add epo200/201/202 to GS Windows 2012 SVD | Unassigned | Invalid | 0
217962 | #245561 | Story | Certificates for ePO | Unassigned | Invalid | 0
217961 |  | Story | PCR 299325 HBSS ePO Server impacts to TPM | Unassigned | Invalid | 0
217959 | #217814 | Story | Transition from adaptive to enforcement mode | Unassigned | Invalid | 0
217958 | #245561 | Story | PCR 301753 HBSS ePO Server impacts to faciligty interconnect drawings | Unassigned | Invalid | 0
217957 | #245561 | Story | Deploy HIPS to Linux hosts in SWIT | Unassigned | Invalid | 0
217956 | #245561 | Story | Change backup processing due to disk volume changes in SWIT | Unassigned | Invalid | 0
217955 | #245561 | Story | Deploy HIPS to Windows XP hosts | Unassigned | Invalid | 0
217954 | #245561 | Story | Resolve SQL Access error | Unassigned | Invalid | 0
217953 | #245561 | Story | GS Key Management PCR Completion | Unassigned | Invalid | 0
217952 | #245561 | Story | HBSS SVD Documentation for roll up server | Unassigned | Invalid | 0
217950 |  | Story | Evaluation options for implementation of dedicated HBSS console | Unassigned | Invalid | 0
217949 | #217814 | Story | On-site customer support during Enforcement Mode transition | Unassigned | Invalid | 0
217948 |  | Story | PCR MUOSD00299813 TR NME-11 Add ethernet and fiber connections to NME-13 Secret SAN/RAID | Unassigned | Invalid | 0
217947 | #245561 | Story | PCR MUOSD00299480 SAN Switch IETM Updates (SECRET) | Unassigned | Invalid | 0
217946 |  | Story | HBSS RAID Related IETM Work | Unassigned | Invalid | 0
217945 | #245561 | Story | PCR MUOSD00299782 NMS TR HBSS ePO Server impacts to MUOS GS Functional Block Diagram | Unassigned | Invalid | 0
217944 |  | Story | PCR MUOSD00298187 ILS TR HBSS ePO impacts to MUOS Ground System Account Maintenance Plan | Unassigned | Invalid | 0
217943 | #245561 | Story | Complete Configuration Management of McAfee Components and Starter VM Image | Unassigned | Invalid | 0
217942 | #245561 | Story | Tectia Updates Reviews | Unassigned | Invalid | 0
217941 |  | Story | Complete RAID Manager Work | Unassigned | Invalid | 0
217940 |  | Story | STIG epo201/202 | Unassigned | Invalid | 0
217939 | #217806 | Story | Use draft HBSS/TSM/TPM SVD to build backup/archive | Unassigned | Invalid | 0
217938 | #245561 | Story | HBSS March patches | Unassigned | Invalid | 0
217937 | #223984 | Story | Execute draft HBSS Client Roll Out Plan (Phase II) | Unassigned | Invalid | 0
217936 | #245561 | Story | Jim to transfer VM architecture/implementation details to Steve | Unassigned | Invalid | 0
217935 |  | Story | Update HBSS SVD for adaptive mode configuration | Unassigned | Invalid | 0
217934 |  | Story | Deploy VSE to Linux hosts in SWIT | Unassigned | Invalid | 0
217933 | #245561 | Story | Deploy McAfee Agent to Solaris hosts | Unassigned | Invalid | 0
217931 |  | Story | PCR 310629 Add epo201/202 to NMS Windows 2012 SVD | Unassigned | Invalid | 0
217930 |  | Story | PCR 299738 HBSS ePO Server impacts to NME-10 (HBSS ePO Server 1 - SECRET) | Unassigned | Invalid | 0
217929 |  | Story | PCR 299740 HBSS ePO Server impacts to NME-11 (HBSS ePO Server 2 - SECRET) | Unassigned | Invalid | 0
217928 |  | Story | PCR 299858 ePO Server impacts to DL360 SCD | Unassigned | Invalid | 0
217927 | #217806 | Story | VLAB Execute Client Roll Out Plan (for GDS Servers) | Unassigned | Invalid | 0
217926 | #245561 | Story | Update RAID SVD due to disk volume changes | Unassigned | Invalid | 0
217925 | #245561 | Story | Update disk volume configuration in SWIT due to restore issues | Unassigned | Invalid | 0
217924 | #245561 | Story | Deploy MA to Windows XP hosts Roll Out Plan documentation updates | Unassigned | Invalid | 0
217923 |  | Story | Investigate PKI for SSL on RAID Manager | Unassigned | Invalid | 0
217922 |  | Story | Create HBSS Virus Scan Enterprise 8.8 On-Access Process Policies | Unassigned | Invalid | 0
217921 | #245561 | Story | Roll up server configuration for VLAB | Unassigned | Invalid | 0
217920 |  | Story | Finalize building RAID in VLAB | Unassigned | Invalid | 0
217919 | #245561 | Story | PCR MUOSD00299485 Add SAN Switch SSH Host Key Re-Generation Procedure to PKI Deployment Document (IETM) | Unassigned | Invalid | 0
217918 | #245561 | Story | PCR MUOSD00299563 TR NMS SIEM new EMC RAID hardware SECRET Enclave | Unassigned | Invalid | 0
217917 |  | Story | HBSS IETM Work | Unassigned | Invalid | 0
217916 |  | Story | PCR MUOSD00306332 HBSS Support for Splunk Clients | Unassigned | Invalid | 0
217915 |  | Story | PCR MUOSD00304562 Remove/replace Interim HBSS Solution | Unassigned | Invalid | 0
217914 |  | Story | GS Key Management PCR Verification VLAB | Unassigned | Invalid | 0
217913 | #245561 | Story | PCR 299933 HBSS ePO Server impacts to A211 (Sparing Requirements) | Unassigned | Invalid | 0
217912 | #245561 | Story | Deploye VSE to Windows Server 2003 hosts in SWIT | Unassigned | Invalid | 0
217911 | #245561 | Story | HBSS April 2017 patches | Unassigned | Invalid | 0
217910 | #245561 | Story | Configure HBSS ePO server to support roll up | Unassigned | Invalid | 0
217909 | #245561 | Story | Deploy HIPS to Windows Server 2012 hosts in SWIT | Unassigned | Invalid | 0
217908 | #217806 | Story | IETM PCR and Training Development and review | Unassigned | Invalid | 0
217907 |  | Story | Official V-Lab install readiness review | Unassigned | Invalid | 0
217906 | #245561 | Story | Deploy HIPS to Solaris hosts | Unassigned | Invalid | 0
217905 |  | Story | Regression test hosts | Unassigned | Invalid | 0
217904 |  | Story | PCR 299742 HBSS ePO Server impactgs to NME-14 (Connect LAN205/207 to I/O panel - Secret) | Unassigned | Invalid | 0
217903 |  | Story | PCR 299744 HBSS ePO Server impacts to NME-15 (Connect LAN 206/208 to I/O panel - Secret) | Unassigned | Invalid | 0
217902 | #245561 | Story | Fix sftp problem on backup drive (Ken) | Unassigned | Invalid | 0
217900 |  | Story | Develop selected option for dedicated HBSS console | Unassigned | Invalid | 0
217899 |  | Story | On-site custimer support during Adaptive Mode transition | Unassigned | Invalid | 0
217898 |  | Story | Execute Adaptive Mode transition | Unassigned | Invalid | 0
217897 |  | Story | PCR MUOSD00299806 TR HBSS RAID/SAN Update SF/NMF interconnect diagram for NME10,11 to NME13 | Unassigned | Invalid | 0
217896 |  | Story | PCR MUOSD00299792 Update DNS to Include SECRET EMC RAID | Unassigned | Invalid | 0
217894 |  | Story | PCR MUOSD00299944 IETM TR HBSS SQL impacts to IETM | Unassigned | Invalid | 0
217893 |  | Story | PCR MUOSD00298074 NMS FM TR HBSS ePO Server impacts to FM | Unassigned | Invalid | 0
217892 | #245561 | Story | PCR MUOSD00299746 NMS TR HBSS ePO Server impacts to NM HW/SW Mapping | Unassigned | Invalid | 0
217891 |  | Story | PCR MUOSD00299753 NMS GS KEY TR HBSS ePO Server impacts to NM GS_KeyMgmt | Unassigned | Invalid | 0
217890 |  | Story | PCR MUOSD00299757 NMS AAA TR HBSS ePO Server impacts to AAA | Unassigned | Invalid | 0
217889 |  | Story | PCR MUOSD00299971 NMS TR HBSS ePO Server impacts to NM CSCI | Unassigned | Invalid | 0
217888 | #245561 | Story | PCR MUOSD00305773 Change Switch Configurations for Interim HBSS Solution to support NCDOC rollup server | Unassigned | Invalid | 0
217887 | #245561 | Story | Roll Out Plans Updates for Sprint 3 | Unassigned | Invalid | 0
217886 |  | Story | Create procedure to restore backup to a VM | Unassigned | Invalid | 0
217885 | #245561 | Story | Deploy MA and VSE to Linux hosts in SWIT | Unassigned | Invalid | 0
217884 | #245561 | Story | Emulated NCDOC server configuration | Unassigned | Invalid | 0
217883 |  | Story | Steve to do scratch install of VM | Unassigned | Invalid | 0
217881 | #245561 | Story | Deploy MA to Windows XP hosts | Unassigned | Invalid | 0
217880 | #217814 | Story | Site Support by Team Members (Sprint 4) | Unassigned | Invalid | 0
217879 |  | Story | (dup) Windows 2003 IA Patching SWIT Regression Tests | Unassigned | Invalid | 0
217878 |  | Story | PCR MUOSD00299811 TR NME-10 Add ethernet and fiber connections to NME-13 Secret SAN/RAID | Unassigned | Invalid | 0
217877 |  | Story | PCR MUOSD00299805 TR NME-13 HW/SW Mapping Doc updates for HBSS/RAID/SAN | Unassigned | Invalid | 0
217876 |  | Story | PCR TBD Develop HBSS Training Plan (HBSS Phase 2) | Unassigned | Invalid | 0
217875 |  | Story | PCR MUOSD00299854 ILS TR HBSS SQL impacts to Account Maintenance Plan | Unassigned | Invalid | 0
217874 | #245561 | Story | Complete backup script including changes | Unassigned | Invalid | 0
217873 |  | Story | STIG epo200 | Unassigned | Invalid | 0
217871 |  | Story | Execute draft HBSS Client Roll Out Plan (Phase I) | Unassigned | Invalid | 0
217869 |  | Story | PCR 299747 HBSS ePO Server impacts to Tectia | Unassigned | Invalid | 0
217866 | #217814 | Story | Migrate interim HBSS managed hosts to MUOS HBSS | Unassigned | Invalid | 0
217865 |  | Story | Deploy OAM | Unassigned | Invalid | 0
217864 |  | Story | Deploy ACCM | Unassigned | Invalid | 0
217863 | #245561 | Story | Jim to help Steve with ePO 5.3 variations rwt ePO 4.6.8 | Unassigned | Invalid | 0
217862 | #245561 | Story | Deploy HIPS to Windows Server 2003 hosts in SWIT | Unassigned | Invalid | 0
217861 |  | Story | Update HBSS SVD due to disk volume changes | Unassigned | Invalid | 0
217860 | #245561 | Story | Debug siem203/204 in SWIT | Unassigned | Invalid | 0
217859 | #245561 | Story | Fix VLab RAID and configure it for HBSS | Unassigned | Invalid | 0
217858 |  | Story | Integrate FM with HBSS | Unassigned | Invalid | 0
217857 | #217814 | Story | Complete IETM and training material contents in conjunction with deployment activities | Unassigned | Invalid | 0
217855 | #245561 | Story | PCR MUOSD00299724 Add New SECRET EMC RAID to the NEDB | Unassigned | Invalid | 0
217854 |  | Story | PCR MUOSD00299973 NMS TR HBSS ePO Server impacts to FCAPS IDD | Unassigned | Invalid | 0
217853 | #245561 | Story | PCR MUOSD00305782 Change load balancer configuration for Interim HBSS solution to support NCDOC rollup server | Unassigned | Invalid | 0
217852 |  | Story | PCR MUOSD00303052 NMS TR Create content for HBSS SVD - Phase 2 | Unassigned | Invalid | 0
217851 | #245561 | Story | Network Configuration in VLab for NCDOC Roll Up Server | Unassigned | Invalid | 0
217850 | #245561 | Story | TSM SVD updates for HBSS Backup/Archive | Unassigned | Invalid | 0
217849 | #245561 | Story | V-Lab HBSS Hardware Installation | Unassigned | Invalid | 0
217848 | #245561 | Story | Deploy MA to Linux Update Client Roll Out Plan draft procedure | Unassigned | Invalid | 0
217842 | #217838 | Story | HBSS July patches | Unassigned | Invalid | 0
217841 |  | Story | Feature development testing/integration plan updates | Unassigned | Invalid | 0
217840 |  | Story | Unexpected problems to be resolved | Unassigned | Invalid | 0
217839 |  | Story | HBSS Client Roll Out Phase I (MA, VSE, HIPS) SWIT | Unassigned | Invalid | 0
217838 |  | Feature | HBSS IA Completion | Unassigned | Rejected
217837 | #217806 | Story | HBSS Official V-Lab Feature Test Roll Out and Learning Mode Plan | Unassigned | Invalid | 0
217836 |  | Story | HBSS Windows 2012 STIGS for HBSS servers | Unassigned | Invalid | 0
217835 |  | Story | HBSS Workstation for NMS OPS | Unassigned | Invalid | 0
217834 |  | Story | HBSS DMZ Secret Enclave | Unassigned | Invalid | 0
217832 | #217806 | Story | HBSS Build "golden" deployable VM | Unassigned | Invalid | 0
217828 |  | Story | HBSS RAID Manager | Unassigned | Invalid | 0
217827 |  | Story | HBSS Backup/Archive Development | Unassigned | Invalid | 0
217826 |  | Feature | HBSS SIEM Integration for HBSS | Unassigned | Rejected
217824 |  | Story | SVD Documentation Updates | Unassigned | Invalid | 0
217823 | #217838 | Story | HBSS STIGS | Unassigned | Invalid | 0
217821 | #217814 | Story | HBSS Post-Deployment adaptive/enforcement mode transitions and monitoring | Unassigned | Invalid | 0
217820 |  | Story | HBSS Knowledge Transfer for Team Changes | Unassigned | Invalid | 0
217819 |  | Feature | HBSS Adaptive and Enforcement Mode Transition and Monitoring | Unassigned | Rejected
217818 |  | Story | Deploy McAfee Agent to Linux hosts | Unassigned | Invalid | 0
217816 | #245561 | Story | HBSS Prepare for Client Roll Out | Unassigned | Invalid | 0
217815 |  | Story | HBSS OS patching | Unassigned | Invalid | 0
217814 |  | Feature | HBSS Support Deployment | Unassigned | Rejected
217813 |  | Story | Restore Backups | Unassigned | Invalid | 0
217812 | #217814 | Story | HBSS Back out interim HBSS (SWIT) | Unassigned | Invalid | 0
217811 |  | Feature | HBSS Remote dedicated HBSS console in OPS | Unassigned | Rejected
217810 |  | Story | HBSS Roll Up Server Integration (SWIT) | Unassigned | Invalid | 0
217808 |  | Feature | HBSS Adaptive Mode Transition and Monitoring (SWIT) | Unassigned | Rejected
217806 |  | Feature | HBSS Feature Official V-Lab Feature PCR verification | Unassigned | Rejected
217799 | #216489 | Feature | Feature: WinXP - NMS STIGing - delete | Unassigned | Rejected
217636 |  | Story | List Terminals Impacted by AWARE Failures | Unassigned | Invalid | 0
217634 | #217632 | Story | Allow User to Choose a Region and Filter Results | Unassigned | Invalid | 0
217633 |  | Story | Center the Map on the User Selected Satellite Beam Overlay | Unassigned | Invalid | 0
217631 |  | Story | Define User Preferences Administration | Unassigned | Invalid | 0
217629 |  | Story | Research Stories Related to SA by COCOM | Unassigned | Invalid | 0
217628 |  | Story | Allow User to View Performance of Similar Groups | Unassigned | Invalid | 0
217627 |  | Story | Planned Resource Usage of Future Point in Time | Unassigned | Invalid | 0
217626 |  | Story | Allow User to Conduct Contingency Planning | Unassigned | Invalid | 0
217625 |  | Story | Indication for Multiple Data Sources Produce Stale Data | Unassigned | Invalid | 0
217624 |  | Story | Indication for Intervals with Suspect Data | Unassigned | Invalid | 0
217623 |  | Story | Analyze Past Performance to Determine Future Needs | Unassigned | Invalid | 0
217622 |  | Story | Support Op Planning Assessments | Unassigned | Invalid | 0
217621 |  | Story | Indicate if Sympathetic Congestion is On/Off | Unassigned | Invalid | 0
217620 |  | Story | Allow user to Resume Operations after Inactivity Timeout | Unassigned | Invalid | 0
217619 |  | Story | Research Stories Related to Provisioned Object Reports | Unassigned | Invalid | 0
217618 |  | Story | Get pre-decoded data from Storygen to the user screens | Unassigned | Invalid | 0
217617 |  | Story | Get all five VMs working in Mitre NERVE | Unassigned | Invalid | 0
217616 |  | Story | Research Stories Related to NCTAMS Daily/Weekly Checklists | Unassigned | Invalid | 0
217615 |  | Story | Research Stories Related to Shift Changes | Unassigned | Invalid | 0
217614 |  | Story | Update Configuration of NCTAMS Ops Floor | Unassigned | Invalid | 0
217613 |  | Story | Reduce the Number of Applications Needed for SA | Unassigned | Invalid | 0
217611 | #216379 | Story | Analyze PCR- changes to CE router needed for intersite connectivity | Unassigned | Invalid | 0
217610 | #245569 | Story | Analyze PCR- changes to FM needed for inter-site connectivity | Unassigned | Done | 8
217609 | #216379 | Story | Analyze PCR- changes to PM needed for inter-site connectivity | Unassigned | Invalid | 0
217608 | #216379 | Story | Analyze PCR- changes to the decoder needed for inter-site connectivity | Unassigned | Invalid | 0
217607 |  | Story | Install storygen in V-Lab | Unassigned | Invalid | 0
217606 | #217632 | Feature | Upgrade to Better Map Visualization Capability | Unassigned | Analyzing
217605 | #245569 | Story | Update IETM pages for Terminal Provisioning Template, Terminal Provisioning and User Services Provisioning with new screens and rules. | Unassigned | Invalid | 0
217604 | #245569 | Story | Update DB Connect to its latest version | Unassigned | Invalid | 0
217603 | #216379 | Story | Implement PCR - FM changes for intersite connectivity | Unassigned | Invalid | 0
217602 | #216379 | Story | Implement PCR - PM changes for intersite connectivity | Unassigned | Invalid | 0
217601 | #216379 | Story | Implement PCR - Decoder changes for intersite connectivity | Unassigned | Invalid | 0
217600 | #216379 | Story | Implement PCR - CE Router for intersite connectivity | Unassigned | Invalid | 0
217599 | #216379 | Story | Review and Resolve PCR for CE Router | Unassigned | Invalid | 0
217598 | #216379 | Story | Verify PCR for CE Router and Build | Unassigned | Invalid | 0
217597 | #245569 | Story | (Enabler) Identify security patches for Apache HTTP server | Unassigned | Invalid | 0
217596 | #245569 | Story | (Enabler) Initial IA vulnerability scan of Apache HTTP server | Unassigned | Invalid | 0
217595 | #245569 | Story | (Enabler) Identify how to fix the vulnerabilities not addressed by the vendor | Unassigned | Invalid | 0
217594 |  | Story | As the CRL Web Server, I can implement available security patches so that MUOS IA obligations are satisfied | Unassigned | Invalid | 0
217593 |  | Story | As the CRL Web Server, I can implement available STIGs so that MUOS IA obligations are satisfied | Unassigned | Invalid | 0
217591 | #245569 | Story | (Enabler) Final IA vulnerability scan of Apache HTTP server | Unassigned | Invalid | 0
217590 | #245569 | Story | Measurements of Splunk Performance with HBSS monitoring software installed | Unassigned | Invalid | 0
217587 | #245569 | Story | NMS HW/SW Mapping is missing AV/HIDS software for Splunk servers | Unassigned | Invalid | 0
217583 |  | Story | P2P Call Completion Metrics Over Time | Unassigned | Invalid | 0
217582 |  | Story | Group Call Completion Metrics Over Time | Unassigned | Invalid | 0
217581 | #245569 | Story | WIN2003 NMS - SWIT SME Regression Testing - Blake | Unassigned | Invalid | 0
217580 | #245569 | Story | WIN2003 NMS - SWIT SME Regression Testing - Black | Unassigned | Invalid | 0
217579 | #245569 | Story | PPA User Services Provisioning is missing initialization for status | Unassigned | Invalid | 0
217573 | #219747 | Story | (Placeholder) Implement AWARE Remote Access for Factory Support | Unassigned | Invalid | 0
217571 | #219747 | Story | (Placeholder) Implement AWARE Remote Access for Factory Support | Unassigned | Invalid | 0
217565 | #221090 | Story | SBC Mitigation Group Table Incorrectly Displays NaN for DTI | Unassigned | Invalid | 0
217564 | #221090 | Story | SBC Mitigation Count of Data Rates is incorrect | Unassigned | Invalid | 0
217563 | #221090 | Story | SBC Mitigation Group Data Table is empty | Unassigned | Invalid | 0
217562 | #245569 | Story | Finish Update regular expression for new subnets | Unassigned | Invalid | 0
217561 | #245569 | Story | Finish Disable the IPWORKS DNS push | Unassigned | Invalid | 0
217560 | #245569 | Story | Finish Remove the interface associated with the DNS push from the Provisioning Bridge | Unassigned | Invalid | 0
217559 |  | Story | Resolve PCR for Parts List updates (Firefox on the SECRET Enclave NMF Workstations) | Unassigned | Invalid | 0
217375 |  | Feature | Feature: SIEM Phase 2 - delete | Unassigned | Rejected
217153 |  | Feature | Evaluate existing Trouble Ticket system and alternatives for opportunities to reduce mean time to restore in response to service incidents. | Unassigned | Rejected
217039 | #245573 | Feature | Waveform Changes to improve PtN Mobility | Unassigned | Approved
216969 | #216631 | Story | Feature 216631: Initiate CM PDO Processing for all CI's | Unassigned | Invalid | 0
216762 |  | Feature | HBSS Backup/Archive Development | Unassigned | Rejected
216761 |  | Feature | HBSS RAID Manager | Unassigned | Rejected
216760 | #245561 | Story | HBSS Roll Up Server Integration (SWIT) | Unassigned | Invalid | 0
216759 |  | Feature | HBSS Client Roll Out Phase I (MA, VSE, HIPS) SWIT | Unassigned | Rejected
216758 | #245561 | Story | Deploy McAfee Agent to Linux hosts | Unassigned | Invalid | 0
216757 |  | Story | Restore Backups | Unassigned | Invalid | 0
216755 |  | Feature | HBSS V-Lab Early SVD Integration Feature | Unassigned | Rejected
216754 |  | Feature | HBSS Client Roll Out Phase II Feature | Unassigned | Rejected
216753 |  | Story | HBSS OS patching | Unassigned | Invalid | 0
216752 |  | Story | HBSS PCR Completion Phase I Feature | Unassigned | Invalid | 0
216751 | #245561 | Story | HBSS PCR Completion Phase II | Unassigned | Invalid | 0
216750 | #245561 | Story | HBSS Back out interim HBSS (SWIT) | Unassigned | Invalid | 0
216749 | #245561 | Story | HBSS Windows 2012 STIGS for HBSS servers | Unassigned | Invalid | 0
216747 |  | Feature | HBSS Official V-Lab scratch install for formal feature test | Unassigned | Rejected
216746 |  | Feature | HBSS Official V-Lab Feature PCR verification | Unassigned | Rejected
216745 |  | Feature | HBSS Official V-Lab Feature Test Roll Out and Learning Mode Plan | Unassigned | Rejected
216744 |  | Feature | HBSS Enforcement Mode Transition and Monitoring | Unassigned | Rejected
216743 |  | Feature | HBSS Adaptive Mode Transition and Monitoring (SWIT) | Unassigned | Rejected
216742 |  | Feature | HBSS Official V-Lab Feature Test Preparation | Unassigned | Rejected
216741 |  | Feature | FRCB Document PCR Development | Unassigned | Rejected
216740 | #234511 | Feature | HBSS Support Deployment | Unassigned | Rejected
216739 |  | Feature | HBSS Post-Deployment adaptive/enforcement mode transitions and monitoring | Unassigned | Rejected
216738 |  | Feature | HBSS Workstation for NMS OPS | Unassigned | Rejected
216737 |  | Feature | HBSS Remote dedicated HBSS console in OPS | Unassigned | Rejected
216736 |  | Story | HBSS IA Scanning - HBSS | Unassigned | Invalid | 0
216735 |  | Feature | HBSS Knowledge Transfer for Team Changes | Unassigned | Rejected
216734 |  | Feature | HBSS SIEM Integration for HBSS | Unassigned | Rejected
216733 | #245561 | Story | HBSS STIGS | Unassigned | Invalid | 0
216732 |  | Feature | Unexpected problems to be resolved | Unassigned | Rejected
216704 |  | Story | Update GEMx Software to latest version. | Unassigned | Invalid | 0
216677 | #219384 | Feature | Rejected Feature: Automate Factory Logging - Complete ETISP Auto Factory Log Collection Scripts | Unassigned | Rejected
216676 | #219384 | Feature | Automate Factory Logging - Complete MUOS Application Server Log Collection scripts | Unassigned | Approved
216654 | #217042 | Feature | Enable access to ADNS HAIPEs in TIS Firewall policies (baseline config & update ICD) | Unassigned | Rejected
216651 | #243511 | Feature | Provide automated testing of the Group provisioning so that I can identify and isolate infrequent errors to improve reliability. | Unassigned | Draft
216644 | #225714 | Feature | Add an acknowledgement/retry mechanism for the Group related inter-module messages so that lost messages do not result in incorrect Group behavior. | Unassigned | Rejected
216643 |  | Feature | Add an acknowledgement/retry mechanism for the Group related inter-load module messages. | Unassigned | Rejected
216642 | #225714 | Feature | Add an acknowledgement/retry mechanism for the GNH router messages, Part 1 | Unassigned | Rejected
216637 | #216635 | Feature | Add additional RCG Key Sharing Triggers. | Unassigned | Rejected
216636 |  | Feature | Improve RCG Cover Error Reporting to RNC | Unassigned | Rejected
216629 |  | Feature | Add the coordination of Group count and version information between the RNCs. | Unassigned | Rejected
216628 |  | Feature | Reduce the complexity and non-value added operations of the Group provisioning functionality to reduce the likelyhood of provisioning errors. | Unassigned | Rejected
216627 |  | Feature | ETISP support install update while running | Unassigned | Rejected
216621 | #245574 | Feature | UE Cannot Initiate PtP services or Perform Re-Authentication when a Site has Lost Network Communication with a Switching Facility. | Unassigned | Analyzing
216603 | #245561 | Story | Finalize Load Balancer Updates for HBSS Configs and SVD | Unassigned | Invalid | 0
216602 | #216588 | Feature | Static IP: Remove Original IP Addresses | Unassigned | Analyzing
216599 | #216719 | Feature | Improve RCG Field Support in Phase 1 | Unassigned | Rejected
216597 | #216635 | Feature | RNC Uses Backup PDR/RCG When Cover Requests Fail | Unassigned | Rejected
216596 |  | Feature | Detect, Isolate, and Manage Faults for RAN | Unassigned | Rejected
216595 |  | Feature | Deleted: Improve RNC/RBS Field Support | Unassigned | Rejected
216579 |  | Feature | ETISP configuration utility automates editing ETI switchover property values | Unassigned | Rejected
216578 | #232256 | Feature | ETI improve fault isolation with ETISP U2B snapshots | Unassigned | Rejected
216577 | #217460 | Feature | Analyze use of ETISP configuration utility for site alignment | Unassigned | Rejected
216573 |  | Feature | Analyze RCG-RNC Interface Issues | Unassigned | Rejected
216565 |  | Feature | Implement Call Stability Improvements Identified in Increment 1 | Unassigned | Rejected
216560 |  | Feature | Air Interface Improvements for Phase 1 | Unassigned | Rejected
216559 |  | Feature | Call Establishment Improvements for Phase 1 | Unassigned | Rejected
216558 | #245573 | Feature | Data Transferred Over Control TFCIs | Unassigned | Rejected
216557 |  | Feature | Call Release Improvements for Phase 1 | Unassigned | Rejected
216556 | #245573 | Feature | AddMe GSL Improvements | Unassigned | Approved
216553 |  | Feature | Bulk Key Destruction [TO BE DELETED...this feature is combined into one of the other Bulk Key Management features] | Unassigned | Rejected
216546 | #245560 | Feature | Convert from IAVM spreadsheet to CQ-IA database | Unassigned | Rejected
216545 | #216467 | Story | Solaris PCR cleanup | Unassigned | Invalid | 0
216540 | #226080 | Feature | IA Hardening: Ancillary-GEO Component Group | Unassigned | Rejected
216539 | #226080 | Feature | IA Hardening: ETISP Console Server Component Group | Unassigned | Rejected
216538 | #226080 | Feature | IA Hardening: GIS Console Server Component Group | Unassigned | Rejected
216537 | #226080 | Feature | IA Hardening: GTS Console Server Component Group | Unassigned | Rejected
216536 | #226080 | Feature | IA Hardening: DSNGW Component Group | Unassigned | Rejected
216535 | #226080 | Feature | IA Hardening: ET Discrete Component Group | Unassigned | Rejected
216534 | #226080 | Feature | IA Hardening: ET-FEP Component Group | Unassigned | Rejected
216533 | #226080 | Feature | IA Hardening: GEO Extreme Switch Component Group | Unassigned | Rejected
216532 | #226080 | Feature | IA Hardening: GIS Extreme Switch Component Group | Unassigned | Rejected
216531 | #226080 | Feature | IA Hardening: GTS Extreme Switch Component Group | Unassigned | Rejected
216530 | #226080 | Feature | IA Hardening: NMS Extreme Switch Component Group | Unassigned | Rejected
216529 | #226080 | Feature | IA Hardening: TNA Extreme SW Component Group | Unassigned | Rejected
216528 | #226080 | Feature | IA Hardening: GGSN Component Group | Unassigned | Rejected
216527 | #226080 | Feature | IA Hardening: HLR Component Group | Unassigned | Rejected
216526 | #226080 | Feature | IA Hardening: HLR Console Servers (Windows) Component Group | Unassigned | Rejected
216525 | #226080 | Feature | IA Hardening: HLR Internals - Linux Component Group | Unassigned | Rejected
216524 | #226080 | Feature | IA Hardening: KVM Component Group | Unassigned | Rejected
216523 | #226080 | Feature | IA Hardening: Linux-Ericsson Component Group | Unassigned | Rejected
216522 | #226080 | Feature | IA Hardening: Linux RCG Component Group | Unassigned | Rejected
216521 | #226080 | Feature | IA Hardening: Linux T500 Component Group | Unassigned | Rejected
216520 | #226080 | Feature | IA Hardening: Load Balancer F5 Component Group | Unassigned | Rejected
216519 | #226080 | Feature | IA Hardening: Misc ATM Switch Component Group | Unassigned | Rejected
216518 | #226080 | Feature | IA Hardening: FMS Component Group | Unassigned | Rejected
216517 | #226080 | Feature | IA Hardening: LBIP Component Group | Unassigned | Rejected
216516 | #226080 | Feature | IA Hardening: Misc Polatis Optical Switch Component Group | Unassigned | Rejected
216515 | #226080 | Feature | IA Hardening: Misc Printer Component Group | Unassigned | Rejected
216514 | #226080 | Feature | IA Hardening: Misc SAN-ARCM Component Group | Unassigned | Rejected
216513 | #226080 | Feature | IA Hardening: Misc SAN-RAID Component Group | Unassigned | Rejected
216512 | #226080 | Feature | IA Hardening: Misc SAN-Switch Component Group | Unassigned | Rejected
216511 | #226080 | Feature | IA Hardening: Misc - Security Manager Component Group | Unassigned | Rejected
216510 | #226080 | Feature | IA Hardening: Misc-Tape_Drive Component Group | Unassigned | Rejected
216509 | #226080 | Feature | IA Hardening: Misc-TFDU Component Group | Unassigned | Rejected
216508 | #226080 | Feature | IA Hardening: Misc-UPS Component Group | Unassigned | Rejected
216507 | #226080 | Feature | IA Hardening: NIDS-GIS Component Group | Unassigned | Rejected
216506 | #226080 | Feature | IA Hardening: NIDS-GTS Component Group | Unassigned | Rejected
216505 | #226080 | Feature | IA Hardening: NIDS-NMS Component Group | Unassigned | Rejected
216504 | #226080 | Feature | IA Hardening: RBS Component Group | Unassigned | Rejected
216503 | #226080 | Feature | IA Hardening: RNC Component Group | Unassigned | Rejected
216502 | #226080 | Feature | IA Hardening: Router-GIS Component Group | Unassigned | Rejected
216501 | #226080 | Feature | IA Hardening: Router-GTS Component Group | Unassigned | Rejected
216500 | #226080 | Feature | IA Hardening: Router-NMS Component Group | Unassigned | Rejected
216499 | #226080 | Feature | IA Hardening: Router-RCG Component Group | Unassigned | Rejected
216498 | #226080 | Feature | IA Hardening: SGSN Component Group | Unassigned | Rejected
216497 | #226080 | Feature | IA Hardening: Solaris-GTS Component Group | Unassigned | Rejected
216496 | #226080 | Feature | IA Hardening: NMS Solaris EMA Component | Unassigned | Rejected
216495 | #226080 | Feature | IA Hardening: SSG20 Component Group | Unassigned | Rejected
216494 | #226080 | Feature | IA Hardening: TFDU Component Group | Unassigned | Rejected
216492 | #226080 | Feature | IA Hardening: WinXP-ERS Component Group | Unassigned | Rejected
216490 | #226080 | Feature | IA Hardening: WinXP-ILSLaptop Component Group | Unassigned | Rejected
216488 | #226080 | Feature | IA Hardening: Win7-NMS Component Group | Unassigned | Rejected
216487 |  | Feature | IA Hardening: Firewall-ALL Component Group | Unassigned | Rejected
216468 | #216467 | Story | Solaris Component Patching | Unassigned | Invalid | 0
216467 | #226080 | Feature | IA Hardening: Solaris Update | Unassigned | Rejected
216466 | #226080 | Feature | IA Hardening: NMS Solaris MM12 Component | Unassigned | Rejected
216465 | #216466 | Story | Solaris-NMS MM12 Patching | Unassigned | Invalid | 0
216464 | #216459 | Story | IA Hardening: NMS Solaris MM11 Patching | Unassigned | Invalid | 0
216463 | #216457 | Story | Solaris-NMS FMxxx Patching | Unassigned | Invalid | 0
216462 | #227096 | Story | IA Hardening: NMS Solaris DNSEM (IPworks) Patching | Unassigned | Invalid | 0
216461 | #216496 | Story | Solaris-NMS EMA11 Patching | Unassigned | Invalid | 0
216460 | #216458 | Story | Solaris-NMS OSS-RC Patching | Unassigned | Invalid | 0
216459 | #226080 | Feature | IA Hardening: NMS Solaris MM11 Component | Unassigned | Rejected
216458 | #226080 | Feature | IA Hardening: NMS Solaris OSS-RC Component Group | Unassigned | Rejected
216457 | #226080 | Feature | IA Hardening: NMS Solaris FMxxx Component Group | Unassigned | Rejected
216456 | #216496 | Story | Solaris-NMS EMA11 STIGing | Unassigned | Invalid | 0
216455 | #227096 | Story | IA Hardening: NMS Solaris DNSEM (IPworks) STIGing | Unassigned | Invalid | 0
216448 |  | Story | RMF Accreditation - Step 2-3 (Increment 2) [IGNORE, WILL BE DELETED EVENTUALLY] | Unassigned | Invalid | 0
216446 |  | Feature | (Inc3) RMF Accreditation - Step 3 - delete | Unassigned | Rejected
216444 | #216552 | Feature | (Inc5) RMF Accreditation - Step 5 (Increment 5) | Unassigned | Rejected
216441 | #216549 | Feature | Feature: Integrate, release, and deploy RT Logic IA release - delete | Unassigned | Rejected
216437 | #219681 | Feature | Compare Congestion Indicators and AARM Thresholds Over Time | Unassigned | Draft
216436 | #219681 | Feature | Allow CSSE to View Average MPR Over Time | Unassigned | Rejected
216435 | #219670 | Feature | Correlate Failures with Usage Metrics to Prioritize Work | Unassigned | Rejected
216434 | #219670 | Feature | CDR Failures Organized by Type- WCDMA Failures | Unassigned | Rejected
216433 | #219670 | Feature | Estimate Operational Impact of SBC Failures | Unassigned | Rejected
216429 | #219681 | Feature | Allow Help Desk to Determine if Cause is Congestion | Unassigned | Rejected
216428 | #219681 | Feature | Allow Help Desk to Determine Active Congestion Mitigations | Unassigned | Rejected
216427 | #216367 | Feature | Allow Help Desk to Determine Service Status for a Troubled Caller | Unassigned | Rejected
216425 | #216367 | Feature | Display Which Terminals Are/Were in a Group | Unassigned | Rejected
216424 | #216367 | Feature | List Active Terminals in a Group and Last Location | Unassigned | Rejected
216423 | #217588 | Feature | Detect DSN Interface Congestion | Unassigned | Rejected
216421 | #219681 | Feature | List Terminals Impacted by Congestion Mitigation/Preemption | Unassigned | Rejected
216420 | #217635 | Feature | Display Provisioning Status | Unassigned | Rejected
216419 | #217632 | Feature | Visualize Beam Movement on Map | Unassigned | Rejected
216418 | #216374 | Feature | Provide Graphical Display of Notching | Unassigned | Rejected
216417 | #216374 | Feature | Ability to See Aggregate Notching on a Call | Unassigned | Rejected
216416 | #216374 | Feature | RAN Mask Percentage Over Time for Single UE | Unassigned | Rejected
216415 | #219681 | Feature | Allow EMI Manager to Correlate RTWP with Congestion Mitigation | Unassigned | Rejected
216414 | #216374 | Feature | Collect and Characterize EMI Reports | Unassigned | Rejected
216413 | #216374 | Feature | Monitor Trends in RAN Notching | Unassigned | Rejected
216412 | #216374 | Feature | Understand EMI Restrictions in Region, Beam, SBC | Unassigned | Rejected
216411 | #216374 | Feature | List Users Impacted by EMI | Unassigned | Rejected
216410 | #216367 | Feature | Develop Plans to Restore Comms | Unassigned | Rejected
216409 | #216374 | Feature | Format EMI Reports Similar to Format of JSMPS | Unassigned | Rejected
216408 | #216374 | Feature | Perform Geolocation Tasks | Unassigned | Rejected
216407 | #216374 | Feature | RTWP Distribution Across SBCs | Unassigned | Rejected
216406 | #216374 | Feature | Monitor Impacts of EMI | Unassigned | Rejected
216405 | #216374 | Feature | Generate UE Composite Mask Reports | Unassigned | Rejected
216404 | #216374 | Feature | Monitor Trends in Notching Profiles by SBC | Unassigned | Rejected
216403 | #217630 | Feature | Display SBC Planned to Actual: CSSE | Unassigned | Rejected
216402 | #217630 | Feature | Display SBC Planned to Actual: Comms Manager | Unassigned | Rejected
216401 | #217630 | Feature | Displays Trends in Planned to Actual Data | Unassigned | Rejected
216400 | #217630 | Feature | List of Groups Exceeding their Planned Resource Usage | Unassigned | Rejected
216399 | #217630 | Feature | Compare Bandwidth Utilization Planned Vs Actual | Unassigned | Rejected
216398 | #219692 | Feature | Filter Usage Reports by Group ID/Name | Unassigned | Rejected
216397 | #219692 | Feature | Display/Generate Report of Traffic by Radio Service Type | Unassigned | Rejected
216396 | #219692 | Feature | Monitor and Display Types of Service | Unassigned | Rejected
216395 | #219692 | Feature | Trend Usage by Service Type | Unassigned | Rejected
216394 | #219692 | Feature | Trend Cell State Over Time | Unassigned | Rejected
216393 | #219692 | Feature | Generate Report of Bandwidth Over Time | Unassigned | Rejected
216392 | #219692 | Feature | Generate Report Resources Over Time | Unassigned | Rejected
216391 | #216367 | Feature | Compare Terminal Presets with NMS Profile Data | Unassigned | Rejected
216389 | #217588 | Feature | Operational Status and Throughput of External Interfaces | Unassigned | Rejected
216388 | #219681 | Feature | Add Ruthless Preemption to the WCDMA Congestion Screens | Unassigned | Draft
216387 | #217635 | Feature | Provisioning Status Alert | Unassigned | Rejected
216386 | #217635 | Feature | Provisioning Status Drill Downs | Unassigned | Rejected
216384 | #219681 | Feature | Generate Pre-Built Report of Congestion Log/History | Unassigned | Rejected
216383 | #217577 | Feature | Status of HLR/AuCs | Unassigned | Rejected
216382 | #216422 | Feature | Fixed Gain Mode Indication for Each Satellite Down-Converter | Unassigned | Rejected
216381 | #219592 | Feature | Incorporate Faults/Alarms into Feederlink Status | Unassigned | Rejected
216380 | #217570 | Feature | Context Specific Help (Bridge Gap from SA to IETM) | Unassigned | Draft
216379 | #219598 | Feature | Intersite Link Performance Monitoring | Unassigned | Rejected
216378 | #219598 | Feature | Intersite Link Plain-text Network Congestion | Unassigned | Rejected
216377 | #219598 | Feature | Intersite Link Plain-Text Errors Increasing | Unassigned | Rejected
216376 | #219598 | Feature | Intersite Link Traffic History | Unassigned | Draft
216372 | #219670 | Feature | Organize Failures by Beam, RBS, Etc. to Isolate Cause | Unassigned | Rejected
216371 | #219592 | Feature | Beacon Status for Each ETISP | Unassigned | Rejected
216370 | #219692 | Feature | Compare Resource Usage to AARM thresholds | Unassigned | Rejected
216369 | #219692 | Feature | Throughput by SBC Heatmap | Unassigned | Rejected
216368 | #219692 | Feature | B2U Transmit Power Distribution Across SBCs | Unassigned | Rejected
216365 | #216363 | Feature | ARSTRAT Coordinate with NMF on Re-key Events | Unassigned | Rejected
216361 | #219670 | Feature | P2P Call Completion Metrics (Dashboard/Report) | Unassigned | Rejected
216360 |  | Feature | CRL Web Server Security Patching | Unassigned | Rejected
216359 | #216422 | Feature | Loss of Total Satellite B2U USSPA | Unassigned | Rejected
216358 | #219692 | Feature | SBC Throughput Over Time | Unassigned | Rejected
216357 | #217577 | Feature | Healthy UE Authentications at a RAF- SGSN Counters | Unassigned | Rejected
216356 | #217577 | Feature | Healthy UE c0 and c1 Registration at a RAF- SGSN Counters | Unassigned | Rejected
216354 | #219670 | Feature | Research- Display Degraded Operational Capability for Each SBC | Unassigned | Rejected
216348 | #219592 | Feature | Detect Bad Range Rate Tables | Unassigned | Rejected
216346 | #217577 | Feature | Detect Zombie Networks | Unassigned | Rejected
216344 | #219670 | Feature | Implement- Display Degraded Operational Capability for Each SBC | Unassigned | Rejected
216157 | #216554 | Story | Evaluate Call Failure with DCS Core | Unassigned | Invalid | 0
215106 |  | Story | Evaluate Packets lost RLC to RLC on AM | Unassigned | Invalid | 0
214997 | #225178 | Story | Evaluate Unable to approve SAR | Unassigned | Invalid | 0
214616 |  | Story | Duplicate | Unassigned | Invalid | 0
214615 |  | Story | Duplicate | Unassigned | Invalid | 0
214614 |  | Story | Duplicate | Unassigned | Invalid | 0
214613 |  | Story | Duplicate | Unassigned | Invalid | 0
214612 |  | Story | Duplicate | Unassigned | Invalid | 0
214611 |  | Story | Duplicate | Unassigned | Invalid | 0
214610 |  | Story | Duplicate | Unassigned | Invalid | 0
214608 |  | Story | Duplicate | Unassigned | Invalid | 0
214607 |  | Story | Duplicate | Unassigned | Invalid | 0
214606 | #216934 | Story | As a Developer, I want to make IETM and drawing updates as part of my software development, so that I can complete a full work unit (SW, IETM, Documentation) | Unassigned | Invalid | 0
214600 |  | Story | Duplicate | Unassigned | Invalid | 0
214595 |  | Story | Duplicate | Unassigned | Invalid | 0
214593 |  | Story | As a Developer, I want to see what changes (Files/PCRs) others have delivered that I need to pull into my workspace, so that I can rebase my work knowing what changed ahead of time - delete | Unassigned | Invalid | 0
214590 |  | Story | As a Tester, I want to easily pull and apply an individual binary patch from a particular CI/Build, so that I can test a change with a minimum amount of overhead - delete | Unassigned | Invalid | 0
214589 |  | Story | As a Tester, I want an easily queried delta between two builds listing in terms of both source files and PCRs, so that I can figure out what to test or what change caused a problem - delete | Unassigned | Invalid | 0
214588 |  | Story | As a Tester, I want to see what PCRs/CIs came in between two dates, so that I can see what to test - delete | Unassigned | Invalid | 0
214584 |  | Story | 0_TOOLS complete SVD mapping and buildforge settings for delivery/build/muosrel icm release/etc | Unassigned | Invalid | 0
214580 | #261091 | Story | As a RAN tools owner, I want to setup and test the new RAN servers so that I can provide a better environment for the developers | Unassigned | Invalid | 0
214567 |  | Story | Nick EA 3.1 Tool Support | Unassigned | Invalid | 0
214467 | #216558 | Story | Evaluate UE receives control TFCIs when transferring data | Unassigned | Invalid | 0
213803 | #262146 | Story | KADEMOD RF drawer, SN 106, needs to be tested in the lab by the ETISP team to determine root cause of the hardware failure - duplicate of (266974)? | Unassigned | Invalid | 0
213598 | #1020735 | Feature | Fix Issues with Multiple Group SARs (Design) | PI 17 | Draft
212152 | #220243 | Story | Investigate rncId misassignment | Unassigned | Invalid | 0
212083 | #216598 | Story | Test changes to add additional granularity to error codes between RCG and RNC | Unassigned | Invalid | 0
212080 | #216568 | Story | Implement changes to add additional granularity to error codes between RCG and RNC | Unassigned | Invalid | 0
210214 | #210174 | Task | Review current Problem work item information and make any updates or request EAS for MUOS specific updates | Unassigned | Invalid
210213 |  | Story | Completed Story | Unassigned | Invalid | 0
210211 |  | Task | Complete Task Test | Unassigned | Invalid
209155 |  | Task | Test Task with progress | Unassigned | Invalid
205409 |  | Story | Identify specific other programs that we need access to and request access from PMW-146 and ARSTRAT | Unassigned | Invalid | 0
205364 | #221698 | Story | Document and Train team on path forward | Unassigned | Invalid | 0
204327 | #216566 | Story | Script and install/test newly obtained IAVA VID software/patches | Unassigned | New | 5
204326 | #216566 | Story | Obtain outstanding IAVA VID software/patches that we currently do not own or have in possession | Unassigned | New | 5
204312 | #231643 | Story | Investigate the Addition of System Wide Group QBR and Partial Network Status (PCR308336)[Submitted] | Unassigned | Invalid | 0
202230 |  | Feature | Reject: WF - Frequency Profiles not included in Bootstrap OTA-FT OtapUpdateReq | Unassigned | Rejected
202223 |  | Feature | Reject: WF Memory Access Error After Frequency Profile Deletion | Unassigned | Rejected