## Task_Table
ID | Active | Task Mode | Name | Duration | PlannedFor | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes |  | 1005820: Implement - PWI 387434 | 8 | EA 15.3
2 |  |  | 1008508: Document Initial capability specification and detailed design to start Implement | 3 | PI 16
3 |  |  | 1008509: Create STCD and review with stakeholders | 3 | PI 16
4 |  |  | 1008510: Provide Deployment Notes and Operator Impact Inputs - final | 1 | PI 16
5 |  |  | 1008511: Perform Iterative Implementation, Integration, development Testing including upd | 3 | PI 16
6 |  |  | 1008512: MFR 1 – Dev Team Performs Cybersecurity Assessment | 1 | PI 16
7 |  |  | 1008513: Develop IETMs and Perform Development Testing | 3 | PI 16
8 |  |  | 1008514: UX Research and Design Support (Change back to UX Team) | 3 | PI 16
9 |  |  | 1008515: ILS Incorporation of IETM updates and integration support (Change back to Falcon | 1 | PI 16
10 |  |  | 1008516: Provide Development inputs to common documents | 3 | PI 16
11 |  |  | 1008517: Execute STCD Feature Integration and testing including STCD updates identified | 3 | PI 16
12 |  |  | 1008518: Review the Site Functional Test Plan within STCD and get customer stakeholder ap | 2 | PI 16
13 |  |  | 1008519: Prep and Perform Feature Demo – Customer Demo Event | 1 | PI 16
14 |  |  | 1008520: Initiate CM PDO Processing for all CI's | 1 | EA 16.5
15 |  |  | 1014336: Write Troubleshooting Procedure 1 - Recover from windows universal forwarders go | 5 | EA 15.2
16 |  |  | 1014337: Write Troubleshooting procedure 2 - Recover from solaris universal forwarders go | 5 | EA 15.3
17 |  |  | 1014340: Write Troubleshooting procedure 3 - Recover from Decoder going down | 5 | EA 15.4
18 |  |  | 1014341: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 2 - | 3 | EA 15.3
19 |  |  | 1014342: Write Troubleshooting procedure 5 - Recover from Forwarder <-> Indexer lost com | 5 | PI 16
20 |  |  | 1014343: Write Troubleshooting procedure 6 - Recover from Indexer <-> Search Head lost c | 5 | PI 16
21 |  |  | 1014344: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster | 3 | PI 16
22 |  |  | 1014345: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search | 2 | EA 15.1
23 |  |  | 1014346: Write Troubleshooting procedure 9 - Recover from Cluster Master <-> Indexer Clu | 5 | EA 15.4
24 |  |  | 1014347: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master | 3 | EA 15.3
25 |  |  | 1014348: Write Troubleshooting procedure 11- Recover from UF/HF Forwarders <-> Deploymen | 5 | EA 15.3
26 |  |  | 1014349: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store | 3 | EA 15.2
27 |  |  | 1015751: Resolve Problem 332002: "IETM Procedure update from DTA-4 Finding: Action to Res | 1 | EA 15.1
28 |  |  | 1017340: UX Support for HA Splunk - Recovery Procedures only (Part 1 of 3) | 1 | EA 15.1
29 |  |  | 1017341: UX Support for HA Splunk - Nutanix Procedures (Part 2 of 3) | 5 | PI 16
30 |  |  | 1017342: UX Support for HA Splunk - Nutanix Procedures (Part 3 of 3) | 5 | PI 16
31 |  |  | 1017449: Write recovery Procedure 6- Decoder recovery procedure for lost heartbeat alarm | 3 | EA 15.1
32 |  |  | 1017450: Create and support review of Splunk HA recovery procedures | 2 | EA 15.2
33 |  |  | 1017451: Sprint 15.3 Support review of Splunk HA recovery procedures (leader) | 3 | EA 15.3
34 |  |  | 1017452: Sprint 15.4 Support review of Splunk HA recovery procedures (leader) | 3 | EA 15.4
35 |  |  | 1017456: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 1) | 1 | EA 15.2
36 |  |  | 1017458: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 2) | 1 | EA 15.3
37 |  |  | 1017463: Developer perform recovery procedure dry-runs (Part 2) | 1 | EA 15.3
38 |  |  | 1017465: Developer perform recovery procedure dry-runs (Part 1) | 1 | EA 15.2
39 |  |  | 1017471: Developer perform troubleshooting procedure dry-runs (Part 1) | 2 | PI 16
40 |  |  | 1017472: Developer perform troubleshooting procedure dry-runs (Part 2) | 2 | PI 16
41 |  |  | 1017474: Developer perform troubleshooting procedure dry-runs (Part 3) | 2 | PI 16
42 |  |  | 1017475: Write Troubleshooting procedure 13 - Troubleshooting procedure for Search Factor | 5 | PI 16
43 |  |  | 1017476: Write Troubleshooting procedure 14 - Troubleshooting procedure for Replication F | 5 | PI 16
44 |  |  | 1017477: Write Troubleshooting procedure 15 - Troubleshooting procedure to fix dbconnect | 5 | PI 16
45 |  |  | 1017478: Write Troubleshooting procedure 16 - Troubleshooting when search head member can | 2 | EA 15.1
46 |  |  | 1017480: Write Troubleshooting procedure 17 - Data rebalancing for indexers new or offlin | 5 | PI 16
47 |  |  | 1017482: Developer perform troubleshooting procedure dry-runs (Part 4) | 3 | PI 16
48 |  |  | 1017484: Interim Demo for Feature - Feature 1008506 | 1 | EA 15.5
49 |  |  | 1017491: Perform dry-run of STCD for interim demo | 1 | EA 15.4
50 |  |  | 1017492: Splunk HA recovery procedures - Create and review STCD for interim demo | 2 | EA 15.3
51 |  |  | 1017494: Recovery procedures for Splunk HA - SME support for interim demo | 1 | EA 15.5
52 |  |  | 1017496: Implement - Problem 1010039 | 2 | EA 15.4
53 |  |  | 1017497: Implement - Problem 1010043 | 2 | EA 15.4
54 |  |  | 1017512: Sprint 15.3 UX support review of Splunk HA recovery procedures | 1 | EA 15.3
55 |  |  | 1017513: Sprint 15.4 UX support review of Splunk HA recovery procedures | 1 | EA 15.4
56 |  |  | 1017526: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master | 2 | EA 15.2
57 |  |  | 1018078: ILS support - Review of Splunk HA recovery procedures | 1 | EA 15.4
58 |  |  | 1018319: Provide Deployment Notes and Operator Impact Inputs - interim | 1 | EA 15.4
59 |  |  | 1019150: Create template for Splunk Troubleshooting procedures | 1 | EA 15.1
60 |  |  | 1019307: Write Troubleshooting procedure 16 - Troubleshooting when search head member can | 3 | EA 15.3
61 |  |  | 1019308: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search | 3 | EA 15.4
62 |  |  | 1019489: Insure redlines of AMP are incorporated into final release. | 1 | PI 16
63 |  |  | 1019490: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store (Investigatio | 2 | EA 15.2
64 |  |  | 1019717: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster | 2 | EA 15.4
65 |  |  | 1020233: Perform Dry Run to test: Problem 332002: "IETM Procedure update from DTA-4 Findi | 1 | EA 15.2
66 |  |  | 1020329: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 1 - | 2 | EA 15.2
67
68
69
70
71
72
73
74
75
76
77
78

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units