## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | PI 15 | 50 days | 2020 April 09 8:00 AM | 2020 June 17 5:00 PM |  | 1
2 | Yes | Manually Scheduled | EA 15.1 | 2 wks | 2020 April 09 8:00 AM | 2020 April 22 5:00 PM |  | 2
3 | Yes | Manually Scheduled | EA 15.2 | 2 wks | 2020 April 23 8:00 AM | 2020 May 06 5:00 PM | 2 | 2
4 | Yes | Manually Scheduled | EA 15.3 | 2 wks | 2020 May 07 8:00 AM | 2020 May 20 5:00 PM | 3 | 2
5 | Yes | Manually Scheduled | EA 15.4 | 2 wks | 2020 May 21 8:00 AM | 2020 June 03 5:00 PM | 4 | 2
6 | Yes | Manually Scheduled | EA 15.5 | 2 wks | 2020 June 04 8:00 AM | 2020 June 17 5:00 PM | 5 | 2
7 | Yes | Manually Scheduled | PI 16 | 10 wks | 2020 June 18 8:00 AM | 2020 August 26 5:00 PM | 1 | 1
8 | Yes | Auto Scheduled | Write Recovery Procedures | 12 days | 2020 April 09 8:00 AM | 2020 April 24 5:00 PM |  | 1
9 | Yes | Auto Scheduled | 1017449: Write recovery Procedure 6- Decoder recovery procedure for lost heartbeat alarm | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
10 | Yes | Auto Scheduled | 1017492: Splunk HA recovery procedures - Create and review STCD for interim demo | 2 days | 2020 April 23 8:00 AM | 2020 April 24 5:00 PM | 9 | 2
11 | Yes | Auto Scheduled | Review Recovery Procedures | 8 days | 2020 April 27 8:00 AM | 2020 May 06 5:00 PM | 8 | 1
12 | Yes | Auto Scheduled | 1017340: UX Support for HA Splunk - Recovery Procedures only (Part 1 of 3) | 1 day | 2020 April 27 8:00 AM | 2020 April 27 5:00 PM |  | 2
13 | Yes | Auto Scheduled | 1017450: Create and support review of Splunk HA recovery procedures | 2 days | 2020 April 27 8:00 AM | 2020 April 28 5:00 PM |  | 2
14 | Yes | Auto Scheduled | 1017451: Sprint 15.3 Support review of Splunk HA recovery procedures (leader) | 3 days | 2020 April 29 8:00 AM | 2020 May 01 5:00 PM | 13 | 2
15 | Yes | Auto Scheduled | 1017512: Sprint 15.3 UX support review of Splunk HA recovery procedures | 1 day | 2020 April 27 8:00 AM | 2020 April 27 5:00 PM |  | 2
16 | Yes | Auto Scheduled | 1018078: ILS support - Review of Splunk HA recovery procedures | 1 day | 2020 April 27 8:00 AM | 2020 April 27 5:00 PM |  | 2
17 | Yes | Auto Scheduled | 1017452: Sprint 15.4 Support review of Splunk HA recovery procedures (leader) | 3 days | 2020 May 04 8:00 AM | 2020 May 06 5:00 PM | 14 | 2
18 | Yes | Auto Scheduled | 1017513: Sprint 15.4 UX support review of Splunk HA recovery procedures | 1 day | 2020 April 27 8:00 AM | 2020 April 27 5:00 PM |  | 2
19 | Yes | Auto Scheduled | Dry Run Recovery Procedures | 2 days | 2020 May 07 8:00 AM | 2020 May 08 5:00 PM | 11 | 1
20 | Yes | Auto Scheduled | 1017465: Developer perform recovery procedure dry-runs (Part 1) | 1 day | 2020 May 07 8:00 AM | 2020 May 07 5:00 PM |  | 2
21 | Yes | Auto Scheduled | 1017456: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 1) | 1 day | 2020 May 07 8:00 AM | 2020 May 07 5:00 PM |  | 2
22 | Yes | Auto Scheduled | 1017463: Developer perform recovery procedure dry-runs (Part 2) | 1 day | 2020 May 08 8:00 AM | 2020 May 08 5:00 PM | 20 | 2
23 | Yes | Auto Scheduled | 1017458: UX Dry Run Support for HA Splunk - Recovery Procedures only (Part 2) | 1 day | 2020 May 07 8:00 AM | 2020 May 07 5:00 PM |  | 2
24 | Yes | Auto Scheduled | 1017494: Recovery procedures for Splunk HA - SME support for interim demo | 1 day | 2020 May 07 8:00 AM | 2020 May 07 5:00 PM |  | 2
25 | Yes | Auto Scheduled | Write PI 15 Troubleshooting Procedures | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 1
26 | Yes | Auto Scheduled | 1019150: Create template for Splunk Troubleshooting procedures | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
27 | Yes | Auto Scheduled | 1017478: Write Troubleshooting procedure 16 - Troubleshooting when search head member can | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
28 | Yes | Auto Scheduled | 1014345: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
29 | Yes | Auto Scheduled | 1014336: Write Troubleshooting Procedure 1 - Recover from windows universal forwarders go | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
30 | Yes | Auto Scheduled | 1017526: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
31 | Yes | Auto Scheduled | 1014349: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
32 | Yes | Auto Scheduled | 1019490: Write Troubleshooting procedure 12 - Troubleshoot/Recover KV Store (Investigatio | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
33 | Yes | Auto Scheduled | 1020329: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 1 - | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
34 | Yes | Auto Scheduled | 1014347: Write Troubleshooting procedure 10 - Recover from All Nodes <-> License Master | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
35 | Yes | Auto Scheduled | 1014348: Write Troubleshooting procedure 11- Recover from UF/HF Forwarders <-> Deploymen | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
36 | Yes | Auto Scheduled | 1019307: Write Troubleshooting procedure 16 - Troubleshooting when search head member can | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
37 | Yes | Auto Scheduled | 1014337: Write Troubleshooting procedure 2 - Recover from solaris universal forwarders go | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
38 | Yes | Auto Scheduled | 1014341: Write Troubleshooting procedure 4- Recover from DB Connect going down (Part 2 - | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
39 | Yes | Auto Scheduled | 1014340: Write Troubleshooting procedure 3 - Recover from Decoder going down | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
40 | Yes | Auto Scheduled | 1019717: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
41 | Yes | Auto Scheduled | 1019308: Write Troubleshooting procedure 8 - Recover from Search Head Cluster <-> Search | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
42 | Yes | Auto Scheduled | 1014346: Write Troubleshooting procedure 9 - Recover from Cluster Master <-> Indexer Clu | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
43 | Yes | Auto Scheduled | Write PI 16 Troubleshooting Procedures | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 1
44 | Yes | Auto Scheduled | 1008511: Perform Iterative Implementation, Integration, development Testing including upd | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
45 | Yes | Auto Scheduled | 1008514: UX Research and Design Support (Change back to UX Team) | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
46 | Yes | Auto Scheduled | 1017341: UX Support for HA Splunk - Nutanix Procedures (Part 2 of 3) | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
47 | Yes | Auto Scheduled | 1008508: Document Initial capability specification and detailed design to start Implement | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
48 | Yes | Auto Scheduled | 1017475: Write Troubleshooting procedure 13 - Troubleshooting procedure for Search Factor | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
49 | Yes | Auto Scheduled | 1017476: Write Troubleshooting procedure 14 - Troubleshooting procedure for Replication F | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
50 | Yes | Auto Scheduled | 1017477: Write Troubleshooting procedure 15 - Troubleshooting procedure to fix dbconnect | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
51 | Yes | Auto Scheduled | 1017480: Write Troubleshooting procedure 17 - Data rebalancing for indexers new or offlin | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
52 | Yes | Auto Scheduled | 1014342: Write Troubleshooting procedure 5 - Recover from Forwarder <-> Indexer lost com | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
53 | Yes | Auto Scheduled | 1014343: Write Troubleshooting procedure 6 - Recover from Indexer <-> Search Head lost c | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
54 | Yes | Auto Scheduled | 1014344: Write Troubleshooting procedure 7- Recover from Search Head Cluster <-> Cluster | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
55 | Yes | Auto Scheduled | 1008509: Create STCD and review with stakeholders | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
56 | Yes | Auto Scheduled | Review Troubleshooting Procedures | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 1
57 | Yes | Auto Scheduled | 1017342: UX Support for HA Splunk - Nutanix Procedures (Part 3 of 3) | 5 days | 2020 April 09 8:00 AM | 2020 April 15 5:00 PM |  | 2
58 | Yes | Auto Scheduled | 1008518: Review the Site Functional Test Plan within STCD and get customer stakeholder ap | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
59 | Yes | Auto Scheduled | Dry Run PI 15 Troubleshooting Procedures | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 1
60 | Yes | Auto Scheduled | 1017471: Developer perform troubleshooting procedure dry-runs (Part 1) | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
61 | Yes | Auto Scheduled | 1017472: Developer perform troubleshooting procedure dry-runs (Part 2) | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
62 | Yes | Auto Scheduled | 1017474: Developer perform troubleshooting procedure dry-runs (Part 3) | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
63 | Yes | Auto Scheduled | Dry Run PI 16 Troubleshooting Procedures | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 1
64 | Yes | Auto Scheduled | 1017482: Developer perform troubleshooting procedure dry-runs (Part 4) | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
65 | Yes | Auto Scheduled | Perform Interim Demo for PI 15 Troubleshooting Procedures | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 1
66 | Yes | Auto Scheduled | 1017491: Perform dry-run of STCD for interim demo | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
67 | Yes | Auto Scheduled | 1017484: Interim Demo for Feature - Feature 1008506 | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
68 | Yes | Auto Scheduled | Work PWIs | 8 days | 2020 April 09 8:00 AM | 2020 April 20 5:00 PM |  | 1
69 | Yes | Auto Scheduled | 1015751: Resolve Problem 332002: "IETM Procedure update from DTA-4 Finding: Action to Res | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
70 | Yes | Auto Scheduled | 1005820: Implement - PWI 387434 | 8 days | 2020 April 09 8:00 AM | 2020 April 20 5:00 PM |  | 2
71 | Yes | Auto Scheduled | 1017496: Implement - Problem 1010039 | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
72 | Yes | Auto Scheduled | 1017497: Implement - Problem 1010043 | 2 days | 2020 April 09 8:00 AM | 2020 April 10 5:00 PM |  | 2
73 | Yes | Auto Scheduled | 1020233: Perform Dry Run to test: Problem 332002: "IETM Procedure update from DTA-4 Findi | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
74 | Yes | Auto Scheduled | Feature Closeout | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 1
75 | Yes | Auto Scheduled | 1018319: Provide Deployment Notes and Operator Impact Inputs - interim | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
76 | Yes | Auto Scheduled | 1008512: MFR 1 – Dev Team Performs Cybersecurity Assessment | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
77 | Yes | Auto Scheduled | 1008515: ILS Incorporation of IETM updates and integration support (Change back to Falcon | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
78 | Yes | Auto Scheduled | 1019489: Insure redlines of AMP are incorporated into final release. | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
79 | Yes | Auto Scheduled | 1008510: Provide Deployment Notes and Operator Impact Inputs - final | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
80 | Yes | Auto Scheduled | 1008516: Provide Development inputs to common documents | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
81 | Yes | Auto Scheduled | 1008513: Develop IETMs and Perform Development Testing | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
82 | Yes | Auto Scheduled | 1008520: Initiate CM PDO Processing for all CI's | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2
83 | Yes | Auto Scheduled | 1008517: Execute STCD Feature Integration and testing including STCD updates identified | 3 days | 2020 April 09 8:00 AM | 2020 April 13 5:00 PM |  | 2
84 | Yes | Auto Scheduled | 1008519: Prep and Perform Feature Demo – Customer Demo Event | 1 day | 2020 April 09 8:00 AM | 2020 April 09 5:00 PM |  | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Katie | K | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Ken | K | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Joel | J | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Art | A | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
EA 15.2 | Katie | 0 | 80h | 100%
EA 15.3 | Ken | 0 | 80h | 100%
EA 15.4 | Joel | 0 | 80h | 100%
EA 15.5 | Art | 0 | 80h | 100%
1017340: UX Support for HA Splunk - Recovery Procedures only (Part 1 of 3) | Joel | 0 | 8h | 100%
1017450: Create and support review of Splunk HA recovery procedures | Art | 0 | 16h | 100%